## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Date | Closed | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | E2UB - S Program Management Timing | 715 days | November 17, 2017 5:00 PM | August 17, 2020 8:00 AM | 2020-08-17 | 0 |  | 1
2 | Yes | Auto Scheduled | GM Milestones MY21 EU2B | 715 days | November 17, 2017 5:00 PM | August 17, 2020 8:00 AM | 2020-08-17 | 0 |  | 2
3 | Yes | Auto Scheduled | Styling Freeze (SF) | 0 days | November 17, 2017 5:00 PM | November 17, 2017 5:00 PM | 2017-11-17 | 1 |  | 3
4 | Yes | Auto Scheduled | IDR (Initial Data Release) | 0 days | January 26, 2018 5:00 PM | January 26, 2018 5:00 PM | 2018-01-26 | 1 |  | 3 | Internal to GM
5 | Yes | Auto Scheduled | Integration Bench MRD/P-Release | 0 days | July 9, 2018 8:00 AM | July 9, 2018 8:00 AM | 2018-07-09 | 1 |  | 3
6 | Yes | Auto Scheduled | Verified Data Release (VDR) | 0 days | July 6, 2018 8:00 AM | July 6, 2018 8:00 AM | 2018-07-06 | 1 |  | 3
7 | Yes | Auto Scheduled | Electrical A-Frame MRD | 0 days | September 24, 2018 8:00 AM | September 24, 2018 8:00 AM | 2018-09-24 | 1 |  | 3
8 | Yes | Auto Scheduled | IVER MRD (E2UB-S) | 0 days | November 5, 2018 8:00 AM | November 5, 2018 8:00 AM | 2018-11-05 | 1 |  | 3
9 | Yes | Auto Scheduled | IVER MRD (E2UB-N) | 0 days | December 3, 2018 8:00 AM | December 3, 2018 8:00 AM | 2018-12-03 | 1 |  | 3
10 | Yes | Auto Scheduled | 65% Buyoff Ride | 0 days | April 5, 2019 8:00 AM | April 5, 2019 8:00 AM | 2019-04-05 | 1 |  | 3
11 | Yes | Auto Scheduled | 80% Buyoff Ride | 0 days | September 13, 2019 8:00 AM | September 13, 2019 8:00 AM | 2019-09-13 | 0 |  | 3
12 | Yes | Auto Scheduled | 100% Buyoff Ride | 0 days | February 21, 2020 8:00 AM | February 21, 2020 8:00 AM | 2020-02-21 | 0 |  | 3
13 | No | Auto Scheduled | Matching 1 MRD | 0 days | August 19, 2019 8:00 AM | August 19, 2019 8:00 AM | 2019-08-19 | 1 |  | 3
14 | Yes | Auto Scheduled | NCT / OTS GM MRD | 0 days | September 6, 2019 8:00 AM | September 6, 2019 8:00 AM | 2019-09-06 | 0 |  | 3
15 | Yes | Auto Scheduled | PPV MRD | 0 days | November 15, 2019 8:00 AM | November 15, 2019 8:00 AM | 2019-11-15 | 0 |  | 3
16 | Yes | Auto Scheduled | Matching 2 MRD | 0 days | November 15, 2019 8:00 AM | November 15, 2019 8:00 AM | 2019-11-15 | 0 |  | 3
17 | Yes | Auto Scheduled | PPAP NS | 0 days | September 2, 2019 8:00 AM | September 2, 2019 8:00 AM | 2019-09-02 | 0 |  | 3
18 | Yes | Auto Scheduled | MVB-NS MRD | 0 days | February 28, 2020 8:00 AM | February 28, 2020 8:00 AM | 2020-02-28 | 0 |  | 3
19 | Yes | Auto Scheduled | MRD (Validation Testing Complete) | 0 days | February 28, 2020 8:00 AM | February 28, 2020 8:00 AM | 2020-02-28 | 0 |  | 3
20 | Yes | Auto Scheduled | PPAP Gate Final | 0 days | April 24, 2020 8:00 AM | April 24, 2020 8:00 AM | 2020-04-24 | 0 |  | 3
21 | Yes | Auto Scheduled | Validation Documentation Complete (VDC) | 0 days | April 10, 2020 8:00 AM | April 10, 2020 8:00 AM | 2020-04-10 | 0 |  | 3
22 | Yes | Auto Scheduled | MVB-S (ManVal Saleable) MRD | 0 days | May 8, 2020 8:00 AM | May 8, 2020 8:00 AM | 2020-05-08 | 0 |  | 3
23 | Yes | Auto Scheduled | SORP | 0 days | August 17, 2020 8:00 AM | August 17, 2020 8:00 AM | 2020-08-17 | 0 |  | 3
24 | Yes | Auto Scheduled | GM Bench Delivery Development | 149 | December 5, 2017 8:00 AM | July 2, 2018 8:00 AM | 2018-07-02 | 1 |  | 2
25 | Yes | Auto Scheduled | Define BOM for Bench Sample (Mecha) | 1 | December 5, 2017 8:00 AM | December 5, 2017 5:00 PM | 2017-12-05 | 1 |  | 3
26 | Yes | Auto Scheduled | Order C1UB board for bench | 14.5 | January 1, 2018 8:00 AM | April 6, 2018 5:00 PM | 2018-04-06 | 1 |  | 3 | C1UB board was ordered to be converted.
27 | Yes | Auto Scheduled | Build bench sample | 13,5 | June 11, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 |  | 3
28 | Yes | Auto Scheduled | Bench Sample MRD | 0 days | July 2, 2018 8:00 AM | July 2, 2018 8:00 AM | 2018-07-02 | 1 |  | 3
29 | Yes | Auto Scheduled | Quality Gate Reviews | 561 days | January 5, 2018 8:00 AM | February 28, 2020 5:00 PM | 2020-02-28 | 0 |  | 1
30 | Yes | Auto Scheduled | QG2 - Concept Design Review | 1 day | January 5, 2018 8:00 AM | January 5, 2018 5:00 PM | 2018-01-05 | 1 |  | 2
31 | Yes | Auto Scheduled | QG3 - Prototype Design Review | 1 day | May 14, 2018 8:00 AM | May 14, 2018 5:00 PM | 2018-05-14 | 1 |  | 2
32 | Yes | Auto Scheduled | QG4 - DV Test Readiness Review | 1 day | September 13, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 2
33 | Yes | Auto Scheduled | QG5 - Production Design Review | 1 day | July 11, 2019 8:00 AM | July 11, 2019 5:00 PM | 2019-07-11 | 1 |  | 2
34 | Yes | Auto Scheduled | QG6 - PV Test Readiness Review | 1 day | September 2, 2019 8:00 AM | September 2, 2019 5:00 PM | 2019-09-02 | 0 |  | 2
35 | Yes | Auto Scheduled | QG7 - Production Launch Review | 1 day | February 28, 2020 8:00 AM | February 28, 2020 5:00 PM | 2020-02-28 | 0 |  | 2
36 | Yes | Auto Scheduled | Recurring Meetings/Activities | 747 days | October 5, 2017 8:00 AM | August 17, 2020 5:00 PM | 2020-08-17 | 0 |  | 1
37 | Yes | Auto Scheduled | Internal PDT meeting | 446 days | December 3, 2018 8:00 AM | August 17, 2020 5:00 PM | 2020-08-17 | 0 |  | 2
38 | Yes | Auto Scheduled | Internal PDT meeting 1 | 1 day | December 3, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 3
39 | Yes | Auto Scheduled | Internal PDT meeting 2 | 1 day | December 10, 2018 8:00 AM | December 10, 2018 5:00 PM | 2018-12-10 | 1 |  | 3
40 | Yes | Auto Scheduled | Internal PDT meeting 3 | 1 day | December 17, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 |  | 3
41 | No | Auto Scheduled | Internal PDT meeting 4 | 1 day | January 4, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 3
42 | No | Auto Scheduled | Internal PDT meeting 5 | 1 day | January 4, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 3
43 | No | Auto Scheduled | Internal PDT meeting 6 | 1 day | January 7, 2019 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 3
44 | Yes | Auto Scheduled | Internal PDT meeting 7 | 1 day | January 14, 2019 8:00 AM | January 14, 2019 5:00 PM | 2019-01-14 | 1 |  | 3
45 | No | Auto Scheduled | Internal PDT meeting 8 | 1 day | January 21, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 |  | 3 | Holiday
46 | No | Auto Scheduled | Internal PDT meeting 9 | 1 day | January 28, 2019 8:00 AM | January 28, 2019 5:00 PM | 2019-01-28 | 1 |  | 3
47 | Yes | Auto Scheduled | Internal PDT meeting 10 | 1 day | February 4, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 |  | 3
48 | Yes | Auto Scheduled | Internal PDT meeting 11 | 1 day | February 11, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 |  | 3
49 | Yes | Auto Scheduled | Internal PDT meeting 12 | 1 day | February 18, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 |  | 3
50 | Yes | Auto Scheduled | Internal PDT meeting 13 | 1 day | February 25, 2019 8:00 AM | February 25, 2019 5:00 PM | 2019-02-25 | 1 |  | 3
51 | Yes | Auto Scheduled | Internal PDT meeting 14 | 1 day | March 4, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 |  | 3
52 | Yes | Auto Scheduled | Internal PDT meeting 15 | 1 day | March 11, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 3
53 | Yes | Auto Scheduled | Internal PDT meeting 16 | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
54 | Yes | Auto Scheduled | Internal PDT meeting 17 | 1 day | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 3
55 | Yes | Auto Scheduled | Internal PDT meeting 18 | 1 day | April 1, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 |  | 3
56 | Yes | Auto Scheduled | Internal PDT meeting 19 | 1 day | April 8, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 |  | 3
57 | No | Auto Scheduled | Internal PDT meeting 20 | 1 day | April 15, 2019 8:00 AM | April 15, 2019 5:00 PM | 2019-04-15 | 1 |  | 3
58 | Yes | Auto Scheduled | Internal PDT meeting 21 | 1 day | April 22, 2019 8:00 AM | April 22, 2019 5:00 PM | 2019-04-22 | 1 |  | 3
59 | Yes | Auto Scheduled | Internal PDT meeting 22 | 1 day | April 29, 2019 8:00 AM | April 29, 2019 5:00 PM | 2019-04-29 | 1 |  | 3
60 | Yes | Auto Scheduled | Internal PDT meeting 23 | 1 day | May 6, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 3
61 | Yes | Auto Scheduled | Internal PDT meeting 24 | 1 day | May 13, 2019 8:00 AM | May 13, 2019 5:00 PM | 2019-05-13 | 1 |  | 3
62 | No | Auto Scheduled | Internal PDT meeting 25 | 1 day | May 20, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 |  | 3
63 | Yes | Auto Scheduled | Internal PDT meeting 26 | 1 day | May 27, 2019 8:00 AM | May 27, 2019 5:00 PM | 2019-05-27 | 1 |  | 3
64 | Yes | Auto Scheduled | Internal PDT meeting 27 | 1 day | June 3, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 3
65 | Yes | Auto Scheduled | Internal PDT meeting 28 | 1 day | June 10, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 3
66 | Yes | Auto Scheduled | Internal PDT meeting 29 | 1 day | June 17, 2019 8:00 AM | June 17, 2019 5:00 PM | 2019-06-17 | 1 |  | 3
67 | Yes | Auto Scheduled | Internal PDT meeting 30 | 1 day | June 24, 2019 8:00 AM | June 24, 2019 5:00 PM | 2019-06-24 | 1 |  | 3
68 | Yes | Auto Scheduled | Internal PDT meeting 31 | 1 day | July 1, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 3
69 | Yes | Auto Scheduled | Internal PDT meeting 32 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
70 | Yes | Auto Scheduled | Internal PDT meeting 33 | 1 day | July 15, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 3
71 | Yes | Auto Scheduled | Internal PDT meeting 34 | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 |  | 3
72 | Yes | Auto Scheduled | Internal PDT meeting 35 | 1 day | July 29, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 |  | 3
73 | Yes | Auto Scheduled | Internal PDT meeting 36 | 1 day | August 5, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 |  | 3
74 | Yes | Auto Scheduled | Internal PDT meeting 37 | 1 day | August 12, 2019 8:00 AM | August 12, 2019 5:00 PM | 2019-08-12 | 1 |  | 3
75 | Yes | Auto Scheduled | Internal PDT meeting 38 | 1 day | August 19, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 |  | 3
76 | Yes | Auto Scheduled | Internal PDT meeting 39 | 1 day | August 26, 2019 8:00 AM | August 26, 2019 5:00 PM | 2019-08-26 | 1 |  | 3
77 | Yes | Auto Scheduled | Internal PDT meeting 40 | 1 day | September 2, 2019 8:00 AM | September 2, 2019 5:00 PM | 2019-09-02 | 0 |  | 3
78 | Yes | Auto Scheduled | Internal PDT meeting 41 | 1 day | September 9, 2019 8:00 AM | September 9, 2019 5:00 PM | 2019-09-09 | 0 |  | 3
79 | Yes | Auto Scheduled | Internal PDT meeting 42 | 1 day | September 16, 2019 8:00 AM | September 16, 2019 5:00 PM | 2019-09-16 | 0 |  | 3
80 | Yes | Auto Scheduled | Internal PDT meeting 43 | 1 day | September 23, 2019 8:00 AM | September 23, 2019 5:00 PM | 2019-09-23 | 0 |  | 3
81 | Yes | Auto Scheduled | Internal PDT meeting 44 | 1 day | September 30, 2019 8:00 AM | September 30, 2019 5:00 PM | 2019-09-30 | 0 |  | 3
82 | Yes | Auto Scheduled | Internal PDT meeting 45 | 1 day | October 7, 2019 8:00 AM | October 7, 2019 5:00 PM | 2019-10-07 | 0 |  | 3
83 | Yes | Auto Scheduled | Internal PDT meeting 46 | 1 day | October 14, 2019 8:00 AM | October 14, 2019 5:00 PM | 2019-10-14 | 0 |  | 3
84 | Yes | Auto Scheduled | Internal PDT meeting 47 | 1 day | October 21, 2019 8:00 AM | October 21, 2019 5:00 PM | 2019-10-21 | 0 |  | 3
85 | Yes | Auto Scheduled | Internal PDT meeting 48 | 1 day | October 28, 2019 8:00 AM | October 28, 2019 5:00 PM | 2019-10-28 | 0 |  | 3
86 | Yes | Auto Scheduled | Internal PDT meeting 49 | 1 day | November 4, 2019 8:00 AM | November 4, 2019 5:00 PM | 2019-11-04 | 0 |  | 3
87 | Yes | Auto Scheduled | Internal PDT meeting 50 | 1 day | November 11, 2019 8:00 AM | November 11, 2019 5:00 PM | 2019-11-11 | 0 |  | 3
88 | Yes | Auto Scheduled | Internal PDT meeting 51 | 1 day | November 18, 2019 8:00 AM | November 18, 2019 5:00 PM | 2019-11-18 | 0 |  | 3
89 | Yes | Auto Scheduled | Internal PDT meeting 52 | 1 day | November 25, 2019 8:00 AM | November 25, 2019 5:00 PM | 2019-11-25 | 0 |  | 3
90 | Yes | Auto Scheduled | Internal PDT meeting 53 | 1 day | December 2, 2019 8:00 AM | December 2, 2019 5:00 PM | 2019-12-02 | 0 |  | 3
91 | Yes | Auto Scheduled | Internal PDT meeting 54 | 1 day | December 9, 2019 8:00 AM | December 9, 2019 5:00 PM | 2019-12-09 | 0 |  | 3
92 | Yes | Auto Scheduled | Internal PDT meeting 55 | 1 day | December 16, 2019 8:00 AM | December 16, 2019 5:00 PM | 2019-12-16 | 0 |  | 3
93 | Yes | Auto Scheduled | Internal PDT meeting 56 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
94 | Yes | Auto Scheduled | Internal PDT meeting 57 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
95 | Yes | Auto Scheduled | Internal PDT meeting 58 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
96 | Yes | Auto Scheduled | Internal PDT meeting 59 | 1 day | January 13, 2020 8:00 AM | January 13, 2020 5:00 PM | 2020-01-13 | 0 |  | 3
97 | Yes | Auto Scheduled | Internal PDT meeting 60 | 1 day | January 20, 2020 8:00 AM | January 20, 2020 5:00 PM | 2020-01-20 | 0 |  | 3
98 | Yes | Auto Scheduled | Internal PDT meeting 61 | 1 day | January 27, 2020 8:00 AM | January 27, 2020 5:00 PM | 2020-01-27 | 0 |  | 3
99 | Yes | Auto Scheduled | Internal PDT meeting 62 | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 2020-02-03 | 0 |  | 3
100 | Yes | Auto Scheduled | Internal PDT meeting 63 | 1 day | February 10, 2020 8:00 AM | February 10, 2020 5:00 PM | 2020-02-10 | 0 |  | 3
101 | Yes | Auto Scheduled | Internal PDT meeting 64 | 1 day | February 17, 2020 8:00 AM | February 17, 2020 5:00 PM | 2020-02-17 | 0 |  | 3
102 | Yes | Auto Scheduled | Internal PDT meeting 65 | 1 day | February 24, 2020 8:00 AM | February 24, 2020 5:00 PM | 2020-02-24 | 0 |  | 3
103 | Yes | Auto Scheduled | Internal PDT meeting 66 | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 3
104 | Yes | Auto Scheduled | Internal PDT meeting 67 | 1 day | March 9, 2020 8:00 AM | March 9, 2020 5:00 PM | 2020-03-09 | 0 |  | 3
105 | Yes | Auto Scheduled | Internal PDT meeting 68 | 1 day | March 16, 2020 8:00 AM | March 16, 2020 5:00 PM | 2020-03-16 | 0 |  | 3
106 | Yes | Auto Scheduled | Internal PDT meeting 69 | 1 day | March 23, 2020 8:00 AM | March 23, 2020 5:00 PM | 2020-03-23 | 0 |  | 3
107 | Yes | Auto Scheduled | Internal PDT meeting 70 | 1 day | March 30, 2020 8:00 AM | March 30, 2020 5:00 PM | 2020-03-30 | 0 |  | 3
108 | Yes | Auto Scheduled | Internal PDT meeting 71 | 1 day | April 6, 2020 8:00 AM | April 6, 2020 5:00 PM | 2020-04-06 | 0 |  | 3
109 | Yes | Auto Scheduled | Internal PDT meeting 72 | 1 day | April 13, 2020 8:00 AM | April 13, 2020 5:00 PM | 2020-04-13 | 0 |  | 3
110 | Yes | Auto Scheduled | Internal PDT meeting 73 | 1 day | April 20, 2020 8:00 AM | April 20, 2020 5:00 PM | 2020-04-20 | 0 |  | 3
111 | Yes | Auto Scheduled | Internal PDT meeting 74 | 1 day | April 27, 2020 8:00 AM | April 27, 2020 5:00 PM | 2020-04-27 | 0 |  | 3
112 | Yes | Auto Scheduled | Internal PDT meeting 75 | 1 day | May 4, 2020 8:00 AM | May 4, 2020 5:00 PM | 2020-05-04 | 0 |  | 3
113 | Yes | Auto Scheduled | Internal PDT meeting 76 | 1 day | May 11, 2020 8:00 AM | May 11, 2020 5:00 PM | 2020-05-11 | 0 |  | 3
114 | Yes | Auto Scheduled | Internal PDT meeting 77 | 1 day | May 18, 2020 8:00 AM | May 18, 2020 5:00 PM | 2020-05-18 | 0 |  | 3
115 | Yes | Auto Scheduled | Internal PDT meeting 78 | 1 day | May 25, 2020 8:00 AM | May 25, 2020 5:00 PM | 2020-05-25 | 0 |  | 3
116 | Yes | Auto Scheduled | Internal PDT meeting 79 | 1 day | June 1, 2020 8:00 AM | June 1, 2020 5:00 PM | 2020-06-01 | 0 |  | 3
117 | Yes | Auto Scheduled | Internal PDT meeting 80 | 1 day | June 8, 2020 8:00 AM | June 8, 2020 5:00 PM | 2020-06-08 | 0 |  | 3
118 | Yes | Auto Scheduled | Internal PDT meeting 81 | 1 day | June 15, 2020 8:00 AM | June 15, 2020 5:00 PM | 2020-06-15 | 0 |  | 3
119 | Yes | Auto Scheduled | Internal PDT meeting 82 | 1 day | June 22, 2020 8:00 AM | June 22, 2020 5:00 PM | 2020-06-22 | 0 |  | 3
120 | Yes | Auto Scheduled | Internal PDT meeting 83 | 1 day | June 29, 2020 8:00 AM | June 29, 2020 5:00 PM | 2020-06-29 | 0 |  | 3
121 | Yes | Auto Scheduled | Internal PDT meeting 84 | 1 day | July 6, 2020 8:00 AM | July 6, 2020 5:00 PM | 2020-07-06 | 0 |  | 3
122 | Yes | Auto Scheduled | Internal PDT meeting 85 | 1 day | July 13, 2020 8:00 AM | July 13, 2020 5:00 PM | 2020-07-13 | 0 |  | 3
123 | Yes | Auto Scheduled | Internal PDT meeting 86 | 1 day | July 20, 2020 8:00 AM | July 20, 2020 5:00 PM | 2020-07-20 | 0 |  | 3
124 | Yes | Auto Scheduled | Internal PDT meeting 87 | 1 day | July 27, 2020 8:00 AM | July 27, 2020 5:00 PM | 2020-07-27 | 0 |  | 3
125 | Yes | Auto Scheduled | Internal PDT meeting 88 | 1 day | August 3, 2020 8:00 AM | August 3, 2020 5:00 PM | 2020-08-03 | 0 |  | 3
126 | Yes | Auto Scheduled | Internal PDT meeting 89 | 1 day | August 10, 2020 8:00 AM | August 10, 2020 5:00 PM | 2020-08-10 | 0 |  | 3
127 | Yes | Auto Scheduled | Internal PDT meeting 90 | 1 day | August 17, 2020 8:00 AM | August 17, 2020 5:00 PM | 2020-08-17 | 0 |  | 3
128 | Yes | Auto Scheduled | Internal RAID meeting | 436 days | December 14, 2018 8:00 AM | August 14, 2020 5:00 PM | 2020-08-14 | 0 |  | 2
129 | Yes | Auto Scheduled | Internal RAID meeting 1 | 1 day | December 14, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 |  | 3
130 | No | Auto Scheduled | Internal RAID meeting 2 | 1 day | January 4, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 3
131 | No | Auto Scheduled | Internal RAID meeting 3 | 1 day | January 4, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 3
132 | No | Auto Scheduled | Internal RAID meeting 4 | 1 day | January 4, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 3
133 | Yes | Auto Scheduled | Internal RAID meeting 5 | 1 day | January 11, 2019 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 |  | 3
134 | Yes | Auto Scheduled | Internal RAID meeting 6 | 1 day | January 18, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 3
135 | Yes | Auto Scheduled | Internal RAID meeting 7 | 1 day | January 25, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 |  | 3
136 | Yes | Auto Scheduled | Internal RAID meeting 8 | 1 day | February 1, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 3
137 | Yes | Auto Scheduled | Internal RAID meeting 9 | 1 day | February 8, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 |  | 3
138 | Yes | Auto Scheduled | Internal RAID meeting 10 | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 3
139 | Yes | Auto Scheduled | Internal RAID meeting 11 | 1 day | February 22, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3
140 | Yes | Auto Scheduled | Internal RAID meeting 12 | 1 day | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 |  | 3
141 | Yes | Auto Scheduled | Internal RAID meeting 13 | 1 day | March 8, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 3
142 | Yes | Auto Scheduled | Internal RAID meeting 14 | 1 day | March 15, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 3
143 | Yes | Auto Scheduled | Internal RAID meeting 15 | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
144 | No | Auto Scheduled | Internal RAID meeting 16 | 1 day | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 3
145 | Yes | Auto Scheduled | Internal RAID meeting 17 | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 |  | 3
146 | No | Auto Scheduled | Internal RAID meeting 18 | 1 day | April 12, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 3
147 | No | Auto Scheduled | Internal RAID meeting 19 | 1 day | April 19, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 |  | 3
148 | No | Auto Scheduled | Internal RAID meeting 20 | 1 day | April 26, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 3
149 | Yes | Auto Scheduled | Internal RAID meeting 21 | 1 day | May 3, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 3
150 | Yes | Auto Scheduled | Internal RAID meeting 22 | 1 day | May 10, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 3
151 | Yes | Auto Scheduled | Internal RAID meeting 23 | 1 day | May 17, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 |  | 3
152 | Yes | Auto Scheduled | Internal RAID meeting 24 | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 |  | 3
153 | Yes | Auto Scheduled | Internal RAID meeting 25 | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 3
154 | Yes | Auto Scheduled | Internal RAID meeting 26 | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
155 | Yes | Auto Scheduled | Internal RAID meeting 27 | 1 day | June 14, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 3
156 | No | Auto Scheduled | Internal RAID meeting 28 | 1 day | June 21, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 3
157 | No | Auto Scheduled | Internal RAID meeting 29 | 1 day | June 28, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 3
158 | Yes | Auto Scheduled | Internal RAID meeting 30 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
159 | Yes | Auto Scheduled | Internal RAID meeting 31 | 1 day | July 12, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 |  | 3
160 | Yes | Auto Scheduled | Internal RAID meeting 32 | 1 day | July 19, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 3
161 | Yes | Auto Scheduled | Internal RAID meeting 33 | 1 day | July 26, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 3
162 | Yes | Auto Scheduled | Internal RAID meeting 34 | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
163 | Yes | Auto Scheduled | Internal RAID meeting 35 | 1 day | August 9, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 3
164 | Yes | Auto Scheduled | Internal RAID meeting 36 | 1 day | August 16, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
165 | Yes | Auto Scheduled | Internal RAID meeting 37 | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 |  | 3
166 | Yes | Auto Scheduled | Internal RAID meeting 38 | 1 day | August 30, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 |  | 3
167 | Yes | Auto Scheduled | Internal RAID meeting 39 | 1 day | September 6, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 |  | 3
168 | Yes | Auto Scheduled | Internal RAID meeting 40 | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM | 2019-09-13 | 0 |  | 3
169 | Yes | Auto Scheduled | Internal RAID meeting 41 | 1 day | September 20, 2019 8:00 AM | September 20, 2019 5:00 PM | 2019-09-20 | 0 |  | 3
170 | Yes | Auto Scheduled | Internal RAID meeting 42 | 1 day | September 27, 2019 8:00 AM | September 27, 2019 5:00 PM | 2019-09-27 | 0 |  | 3
171 | Yes | Auto Scheduled | Internal RAID meeting 43 | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 2019-10-04 | 0 |  | 3
172 | Yes | Auto Scheduled | Internal RAID meeting 44 | 1 day | October 11, 2019 8:00 AM | October 11, 2019 5:00 PM | 2019-10-11 | 0 |  | 3
173 | Yes | Auto Scheduled | Internal RAID meeting 45 | 1 day | October 18, 2019 8:00 AM | October 18, 2019 5:00 PM | 2019-10-18 | 0 |  | 3
174 | Yes | Auto Scheduled | Internal RAID meeting 46 | 1 day | October 25, 2019 8:00 AM | October 25, 2019 5:00 PM | 2019-10-25 | 0 |  | 3
175 | Yes | Auto Scheduled | Internal RAID meeting 47 | 1 day | November 1, 2019 8:00 AM | November 1, 2019 5:00 PM | 2019-11-01 | 0 |  | 3
176 | Yes | Auto Scheduled | Internal RAID meeting 48 | 1 day | November 8, 2019 8:00 AM | November 8, 2019 5:00 PM | 2019-11-08 | 0 |  | 3
177 | Yes | Auto Scheduled | Internal RAID meeting 49 | 1 day | November 15, 2019 8:00 AM | November 15, 2019 5:00 PM | 2019-11-15 | 0 |  | 3
178 | Yes | Auto Scheduled | Internal RAID meeting 50 | 1 day | November 22, 2019 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 3
179 | Yes | Auto Scheduled | Internal RAID meeting 51 | 1 day | December 2, 2019 8:00 AM | December 2, 2019 5:00 PM | 2019-12-02 | 0 |  | 3
180 | Yes | Auto Scheduled | Internal RAID meeting 52 | 1 day | December 6, 2019 8:00 AM | December 6, 2019 5:00 PM | 2019-12-06 | 0 |  | 3
181 | Yes | Auto Scheduled | Internal RAID meeting 53 | 1 day | December 13, 2019 8:00 AM | December 13, 2019 5:00 PM | 2019-12-13 | 0 |  | 3
182 | Yes | Auto Scheduled | Internal RAID meeting 54 | 1 day | December 20, 2019 8:00 AM | December 20, 2019 5:00 PM | 2019-12-20 | 0 |  | 3
183 | Yes | Auto Scheduled | Internal RAID meeting 55 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
184 | Yes | Auto Scheduled | Internal RAID meeting 56 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
185 | Yes | Auto Scheduled | Internal RAID meeting 57 | 1 day | January 10, 2020 8:00 AM | January 10, 2020 5:00 PM | 2020-01-10 | 0 |  | 3
186 | Yes | Auto Scheduled | Internal RAID meeting 58 | 1 day | January 17, 2020 8:00 AM | January 17, 2020 5:00 PM | 2020-01-17 | 0 |  | 3
187 | Yes | Auto Scheduled | Internal RAID meeting 59 | 1 day | January 24, 2020 8:00 AM | January 24, 2020 5:00 PM | 2020-01-24 | 0 |  | 3
188 | Yes | Auto Scheduled | Internal RAID meeting 60 | 1 day | January 31, 2020 8:00 AM | January 31, 2020 5:00 PM | 2020-01-31 | 0 |  | 3
189 | Yes | Auto Scheduled | Internal RAID meeting 61 | 1 day | February 7, 2020 8:00 AM | February 7, 2020 5:00 PM | 2020-02-07 | 0 |  | 3
190 | Yes | Auto Scheduled | Internal RAID meeting 62 | 1 day | February 14, 2020 8:00 AM | February 14, 2020 5:00 PM | 2020-02-14 | 0 |  | 3
191 | Yes | Auto Scheduled | Internal RAID meeting 63 | 1 day | February 21, 2020 8:00 AM | February 21, 2020 5:00 PM | 2020-02-21 | 0 |  | 3
192 | Yes | Auto Scheduled | Internal RAID meeting 64 | 1 day | February 28, 2020 8:00 AM | February 28, 2020 5:00 PM | 2020-02-28 | 0 |  | 3
193 | Yes | Auto Scheduled | Internal RAID meeting 65 | 1 day | March 6, 2020 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 3
194 | Yes | Auto Scheduled | Internal RAID meeting 66 | 1 day | March 13, 2020 8:00 AM | March 13, 2020 5:00 PM | 2020-03-13 | 0 |  | 3
195 | Yes | Auto Scheduled | Internal RAID meeting 67 | 1 day | March 20, 2020 8:00 AM | March 20, 2020 5:00 PM | 2020-03-20 | 0 |  | 3
196 | Yes | Auto Scheduled | Internal RAID meeting 68 | 1 day | March 27, 2020 8:00 AM | March 27, 2020 5:00 PM | 2020-03-27 | 0 |  | 3
197 | Yes | Auto Scheduled | Internal RAID meeting 69 | 1 day | April 3, 2020 8:00 AM | April 3, 2020 5:00 PM | 2020-04-03 | 0 |  | 3
198 | Yes | Auto Scheduled | Internal RAID meeting 70 | 1 day | April 10, 2020 8:00 AM | April 10, 2020 5:00 PM | 2020-04-10 | 0 |  | 3
199 | Yes | Auto Scheduled | Internal RAID meeting 71 | 1 day | April 17, 2020 8:00 AM | April 17, 2020 5:00 PM | 2020-04-17 | 0 |  | 3
200 | Yes | Auto Scheduled | Internal RAID meeting 72 | 1 day | April 24, 2020 8:00 AM | April 24, 2020 5:00 PM | 2020-04-24 | 0 |  | 3
201 | Yes | Auto Scheduled | Internal RAID meeting 73 | 1 day | May 1, 2020 8:00 AM | May 1, 2020 5:00 PM | 2020-05-01 | 0 |  | 3
202 | Yes | Auto Scheduled | Internal RAID meeting 74 | 1 day | May 8, 2020 8:00 AM | May 8, 2020 5:00 PM | 2020-05-08 | 0 |  | 3
203 | Yes | Auto Scheduled | Internal RAID meeting 75 | 1 day | May 15, 2020 8:00 AM | May 15, 2020 5:00 PM | 2020-05-15 | 0 |  | 3
204 | Yes | Auto Scheduled | Internal RAID meeting 76 | 1 day | May 22, 2020 8:00 AM | May 22, 2020 5:00 PM | 2020-05-22 | 0 |  | 3
205 | Yes | Auto Scheduled | Internal RAID meeting 77 | 1 day | May 29, 2020 8:00 AM | May 29, 2020 5:00 PM | 2020-05-29 | 0 |  | 3
206 | Yes | Auto Scheduled | Internal RAID meeting 78 | 1 day | June 5, 2020 8:00 AM | June 5, 2020 5:00 PM | 2020-06-05 | 0 |  | 3
207 | Yes | Auto Scheduled | Internal RAID meeting 79 | 1 day | June 12, 2020 8:00 AM | June 12, 2020 5:00 PM | 2020-06-12 | 0 |  | 3
208 | Yes | Auto Scheduled | Internal RAID meeting 80 | 1 day | June 19, 2020 8:00 AM | June 19, 2020 5:00 PM | 2020-06-19 | 0 |  | 3
209 | Yes | Auto Scheduled | Internal RAID meeting 81 | 1 day | June 26, 2020 8:00 AM | June 26, 2020 5:00 PM | 2020-06-26 | 0 |  | 3
210 | Yes | Auto Scheduled | Internal RAID meeting 82 | 1 day | July 6, 2020 8:00 AM | July 6, 2020 5:00 PM | 2020-07-06 | 0 |  | 3
211 | Yes | Auto Scheduled | Internal RAID meeting 83 | 1 day | July 10, 2020 8:00 AM | July 10, 2020 5:00 PM | 2020-07-10 | 0 |  | 3
212 | Yes | Auto Scheduled | Internal RAID meeting 84 | 1 day | July 17, 2020 8:00 AM | July 17, 2020 5:00 PM | 2020-07-17 | 0 |  | 3
213 | Yes | Auto Scheduled | Internal RAID meeting 85 | 1 day | July 24, 2020 8:00 AM | July 24, 2020 5:00 PM | 2020-07-24 | 0 |  | 3
214 | Yes | Auto Scheduled | Internal RAID meeting 86 | 1 day | July 31, 2020 8:00 AM | July 31, 2020 5:00 PM | 2020-07-31 | 0 |  | 3
215 | Yes | Auto Scheduled | Internal RAID meeting 87 | 1 day | August 7, 2020 8:00 AM | August 7, 2020 5:00 PM | 2020-08-07 | 0 |  | 3
216 | Yes | Auto Scheduled | Internal RAID meeting 88 | 1 day | August 14, 2020 8:00 AM | August 14, 2020 5:00 PM | 2020-08-14 | 0 |  | 3
217 | Yes | Auto Scheduled | NC Reporting and Closure | 336 days | December 14, 2018 8:00 AM | March 27, 2020 5:00 PM | 2020-03-27 | 0 |  | 2
218 | No | Auto Scheduled | NC Reporting and Closure 1 | 1 day | November 2, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 |  | 3
219 | No | Auto Scheduled | NC Reporting and Closure 2 | 1 day | November 9, 2018 8:00 AM | November 9, 2018 5:00 PM | 2018-11-09 | 1 |  | 3
220 | No | Auto Scheduled | NC Reporting and Closure 3 | 1 day | November 16, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 3
221 | No | Auto Scheduled | NC Reporting and Closure 4 | 1 day | November 26, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 |  | 3
222 | No | Auto Scheduled | NC Reporting and Closure 5 | 1 day | November 30, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 |  | 3
223 | No | Auto Scheduled | NC Reporting and Closure 6 | 1 day | December 7, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 3
224 | Yes | Auto Scheduled | NC Reporting and Closure 7 | 1 day | December 14, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 |  | 3
225 | Yes | Auto Scheduled | NC Reporting and Closure 8 | 0 days | December 21, 2018 8:00 AM | December 21, 2018 5:00 PM | 2018-12-21 | 1 |  | 3
226 | Yes | Auto Scheduled | NC Reporting and Closure 9 | 1 day | January 8, 2019 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 |  | 3
227 | Yes | Auto Scheduled | NC Reporting and Closure 11 | 1 day | January 15, 2019 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 |  | 3
228 | Yes | Auto Scheduled | NC Reporting and Closure 12 | 1 day | January 22, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 |  | 3
229 | Yes | Auto Scheduled | NC Reporting and Closure 13 | 3 days | January 25, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 3
230 | Yes | Auto Scheduled | NC Reporting and Closure 14 | 3 days | February 1, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 |  | 3
231 | Yes | Auto Scheduled | NC Reporting and Closure 15 | 1 day | February 5, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 |  | 3
232 | Yes | Auto Scheduled | NC Reporting and Closure 16 | 1 day | February 12, 2019 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 |  | 3
233 | Yes | Auto Scheduled | NC Reporting and Closure 17 | 1 day | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 3
234 | Yes | Auto Scheduled | NC Reporting and Closure 18 | 1 day | February 26, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 |  | 3
235 | Yes | Auto Scheduled | NC Reporting and Closure 19 | 1 day | March 5, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 |  | 3
236 | Yes | Auto Scheduled | NC Reporting and Closure 20 | 1 day | March 12, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 3
237 | Yes | Auto Scheduled | NC Reporting and Closure 21 | 1 day | March 20, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 3
238 | Yes | Auto Scheduled | NC Reporting and Closure 22 | 1 day | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 3
239 | Yes | Auto Scheduled | NC Reporting and Closure 23 | 1 day | April 4, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 |  | 3
240 | Yes | Auto Scheduled | NC Reporting and Closure 24 | 1 day | April 12, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 3
241 | Yes | Auto Scheduled | NC Reporting and Closure 25 | 1 day | April 19, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 |  | 3
242 | Yes | Auto Scheduled | NC Reporting and Closure 26 | 1 day | April 26, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 3
243 | Yes | Auto Scheduled | NC Reporting and Closure 27 | 1 day | May 3, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 3
244 | Yes | Auto Scheduled | NC Reporting and Closure 28 | 1 day | May 10, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 3
245 | Yes | Auto Scheduled | NC Reporting and Closure 29 | 1 day | May 17, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 |  | 3
246 | Yes | Auto Scheduled | NC Reporting and Closure 30 | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 |  | 3
247 | Yes | Auto Scheduled | NC Reporting and Closure 31 | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 3
248 | Yes | Auto Scheduled | NC Reporting and Closure 32 | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
249 | Yes | Auto Scheduled | NC Reporting and Closure 33 | 1 day | June 14, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 3
250 | Yes | Auto Scheduled | NC Reporting and Closure 34 | 1 day | June 21, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 3
251 | Yes | Auto Scheduled | NC Reporting and Closure 35 | 1 day | June 28, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 3
252 | Yes | Auto Scheduled | NC Reporting and Closure 36 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
253 | Yes | Auto Scheduled | NC Reporting and Closure 37 | 1 day | July 12, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 |  | 3
254 | Yes | Auto Scheduled | NC Reporting and Closure 38 | 1 day | July 19, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 3
255 | Yes | Auto Scheduled | NC Reporting and Closure 39 | 1 day | July 26, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 3
256 | Yes | Auto Scheduled | NC Reporting and Closure 40 | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
257 | Yes | Auto Scheduled | NC Reporting and Closure 41 | 1 day | August 9, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 3
258 | Yes | Auto Scheduled | NC Reporting and Closure 42 | 1 day | August 16, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
259 | Yes | Auto Scheduled | NC Reporting and Closure 43 | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 |  | 3
260 | Yes | Auto Scheduled | NC Reporting and Closure 44 | 1 day | August 30, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 |  | 3
261 | Yes | Auto Scheduled | NC Reporting and Closure 45 | 1 day | September 6, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 |  | 3
262 | Yes | Auto Scheduled | NC Reporting and Closure 46 | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM | 2019-09-13 | 0 |  | 3
263 | Yes | Auto Scheduled | NC Reporting and Closure 47 | 1 day | September 20, 2019 8:00 AM | September 20, 2019 5:00 PM | 2019-09-20 | 0 |  | 3
264 | Yes | Auto Scheduled | NC Reporting and Closure 48 | 1 day | September 27, 2019 8:00 AM | September 27, 2019 5:00 PM | 2019-09-27 | 0 |  | 3
265 | Yes | Auto Scheduled | NC Reporting and Closure 49 | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 2019-10-04 | 0 |  | 3
266 | Yes | Auto Scheduled | NC Reporting and Closure 50 | 1 day | October 11, 2019 8:00 AM | October 11, 2019 5:00 PM | 2019-10-11 | 0 |  | 3
267 | Yes | Auto Scheduled | NC Reporting and Closure 51 | 1 day | October 18, 2019 8:00 AM | October 18, 2019 5:00 PM | 2019-10-18 | 0 |  | 3
268 | Yes | Auto Scheduled | NC Reporting and Closure 52 | 1 day | October 25, 2019 8:00 AM | October 25, 2019 5:00 PM | 2019-10-25 | 0 |  | 3
269 | Yes | Auto Scheduled | NC Reporting and Closure 53 | 1 day | November 1, 2019 8:00 AM | November 1, 2019 5:00 PM | 2019-11-01 | 0 |  | 3
270 | Yes | Auto Scheduled | NC Reporting and Closure 54 | 1 day | November 8, 2019 8:00 AM | November 8, 2019 5:00 PM | 2019-11-08 | 0 |  | 3
271 | Yes | Auto Scheduled | NC Reporting and Closure 55 | 1 day | November 15, 2019 8:00 AM | November 15, 2019 5:00 PM | 2019-11-15 | 0 |  | 3
272 | Yes | Auto Scheduled | NC Reporting and Closure 56 | 1 day | November 22, 2019 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 3
273 | Yes | Auto Scheduled | NC Reporting and Closure 57 | 1 day | December 2, 2019 8:00 AM | December 2, 2019 5:00 PM | 2019-12-02 | 0 |  | 3
274 | Yes | Auto Scheduled | NC Reporting and Closure 58 | 1 day | December 6, 2019 8:00 AM | December 6, 2019 5:00 PM | 2019-12-06 | 0 |  | 3
275 | Yes | Auto Scheduled | NC Reporting and Closure 59 | 1 day | December 13, 2019 8:00 AM | December 13, 2019 5:00 PM | 2019-12-13 | 0 |  | 3
276 | Yes | Auto Scheduled | NC Reporting and Closure 60 | 1 day | December 20, 2019 8:00 AM | December 20, 2019 5:00 PM | 2019-12-20 | 0 |  | 3
277 | Yes | Auto Scheduled | NC Reporting and Closure 61 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
278 | Yes | Auto Scheduled | NC Reporting and Closure 62 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
279 | Yes | Auto Scheduled | NC Reporting and Closure 63 | 1 day | January 10, 2020 8:00 AM | January 10, 2020 5:00 PM | 2020-01-10 | 0 |  | 3
280 | Yes | Auto Scheduled | NC Reporting and Closure 64 | 1 day | January 17, 2020 8:00 AM | January 17, 2020 5:00 PM | 2020-01-17 | 0 |  | 3
281 | Yes | Auto Scheduled | NC Reporting and Closure 65 | 1 day | January 24, 2020 8:00 AM | January 24, 2020 5:00 PM | 2020-01-24 | 0 |  | 3
282 | Yes | Auto Scheduled | NC Reporting and Closure 66 | 1 day | January 31, 2020 8:00 AM | January 31, 2020 5:00 PM | 2020-01-31 | 0 |  | 3
283 | Yes | Auto Scheduled | NC Reporting and Closure 67 | 1 day | February 7, 2020 8:00 AM | February 7, 2020 5:00 PM | 2020-02-07 | 0 |  | 3
284 | Yes | Auto Scheduled | NC Reporting and Closure 68 | 1 day | February 14, 2020 8:00 AM | February 14, 2020 5:00 PM | 2020-02-14 | 0 |  | 3
285 | Yes | Auto Scheduled | NC Reporting and Closure 69 | 1 day | February 21, 2020 8:00 AM | February 21, 2020 5:00 PM | 2020-02-21 | 0 |  | 3
286 | Yes | Auto Scheduled | NC Reporting and Closure 70 | 1 day | February 28, 2020 8:00 AM | February 28, 2020 5:00 PM | 2020-02-28 | 0 |  | 3
287 | Yes | Auto Scheduled | NC Reporting and Closure 71 | 1 day | March 6, 2020 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 3
288 | Yes | Auto Scheduled | NC Reporting and Closure 72 | 1 day | March 13, 2020 8:00 AM | March 13, 2020 5:00 PM | 2020-03-13 | 0 |  | 3
289 | Yes | Auto Scheduled | NC Reporting and Closure 73 | 1 day | March 20, 2020 8:00 AM | March 20, 2020 5:00 PM | 2020-03-20 | 0 |  | 3
290 | Yes | Auto Scheduled | NC Reporting and Closure 74 | 1 day | March 27, 2020 8:00 AM | March 27, 2020 5:00 PM | 2020-03-27 | 0 |  | 3
291 | Yes | Auto Scheduled | QA Status Reporting | 251 days | January 4, 2019 8:00 AM | December 20, 2019 5:00 PM | 2019-12-20 | 0 |  | 2
292 | Yes | Auto Scheduled | QA Status Reporting 1 | 2 days | January 4, 2019 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 3
293 | Yes | Auto Scheduled | QA Status Reporting 2 | 1 day | January 11, 2019 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 |  | 3
294 | Yes | Auto Scheduled | QA Status Reporting 5 | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 3
295 | Yes | Auto Scheduled | QA Status Reporting 6 | 3 days | January 25, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 3
296 | Yes | Auto Scheduled | QA Status Reporting 7 | 1 day | February 7, 2019 8:00 AM | February 7, 2019 5:00 PM | 2019-02-07 | 1 |  | 3
297 | Yes | Auto Scheduled | QA Status Reporting 8 | 1 day | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 3
298 | Yes | Auto Scheduled | QA Status Reporting 9 | 1 day | February 21, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 3
299 | Yes | Auto Scheduled | QA Status Reporting 10 | 1 day | February 28, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 |  | 3
300 | Yes | Auto Scheduled | QA Status Reporting 11 | 1 day | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 3
301 | Yes | Auto Scheduled | QA Status Reporting 12 | 1 day | March 14, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 3
302 | Yes | Auto Scheduled | QA Status Reporting 13 | 1 day | March 21, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 3
303 | Yes | Auto Scheduled | QA Status Reporting 14 | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
304 | Yes | Auto Scheduled | QA Status Reporting 15 | 1 day | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 3
305 | Yes | Auto Scheduled | QA Status Reporting 16 | 0 days | April 4, 2019 5:00 PM | April 4, 2019 5:00 PM | 2019-04-04 | 1 |  | 3
306 | Yes | Auto Scheduled | QA Status Reporting 17 | 1 day | April 12, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 3
307 | Yes | Auto Scheduled | QA Status Reporting 18 | 1 day | April 19, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 |  | 3
308 | Yes | Auto Scheduled | QA Status Reporting 19 | 1 day | April 26, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 3
309 | Yes | Auto Scheduled | QA Status Reporting 20 | 1 day | May 3, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 3
310 | Yes | Auto Scheduled | QA Status Reporting 21 | 1 day | May 10, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 3
311 | Yes | Auto Scheduled | QA Status Reporting 22 | 1 day | May 17, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 |  | 3
312 | Yes | Auto Scheduled | QA Status Reporting 23 | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 |  | 3
313 | Yes | Auto Scheduled | QA Status Reporting 24 | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 3
314 | Yes | Auto Scheduled | QA Status Reporting 25 | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
315 | Yes | Auto Scheduled | QA Status Reporting 26 | 1 day | June 14, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 3
316 | Yes | Auto Scheduled | QA Status Reporting 27 | 1 day | June 21, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 3
317 | Yes | Auto Scheduled | QA Status Reporting 28 | 1 day | June 28, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 3
318 | Yes | Auto Scheduled | QA Status Reporting 29 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
319 | Yes | Auto Scheduled | QA Status Reporting 30 | 1 day | July 12, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 |  | 3
320 | Yes | Auto Scheduled | QA Status Reporting 31 | 1 day | July 19, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 3
321 | Yes | Auto Scheduled | QA Status Reporting 32 | 1 day | July 26, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 3
322 | Yes | Auto Scheduled | QA Status Reporting 33 | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
323 | Yes | Auto Scheduled | QA Status Reporting 34 | 1 day | August 9, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 3
324 | Yes | Auto Scheduled | QA Status Reporting 35 | 1 day | August 16, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
325 | Yes | Auto Scheduled | QA Status Reporting 36 | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 |  | 3
326 | Yes | Auto Scheduled | QA Status Reporting 37 | 1 day | August 30, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 |  | 3
327 | Yes | Auto Scheduled | QA Status Reporting 38 | 1 day | September 6, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 |  | 3
328 | Yes | Auto Scheduled | QA Status Reporting 39 | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM | 2019-09-13 | 0 |  | 3
329 | Yes | Auto Scheduled | QA Status Reporting 40 | 1 day | September 20, 2019 8:00 AM | September 20, 2019 5:00 PM | 2019-09-20 | 0 |  | 3
330 | Yes | Auto Scheduled | QA Status Reporting 41 | 1 day | September 27, 2019 8:00 AM | September 27, 2019 5:00 PM | 2019-09-27 | 0 |  | 3
331 | Yes | Auto Scheduled | QA Status Reporting 42 | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 2019-10-04 | 0 |  | 3
332 | Yes | Auto Scheduled | QA Status Reporting 43 | 1 day | October 11, 2019 8:00 AM | October 11, 2019 5:00 PM | 2019-10-11 | 0 |  | 3
333 | Yes | Auto Scheduled | QA Status Reporting 44 | 1 day | October 18, 2019 8:00 AM | October 18, 2019 5:00 PM | 2019-10-18 | 0 |  | 3
334 | Yes | Auto Scheduled | QA Status Reporting 45 | 1 day | October 25, 2019 8:00 AM | October 25, 2019 5:00 PM | 2019-10-25 | 0 |  | 3
335 | Yes | Auto Scheduled | QA Status Reporting 46 | 1 day | November 1, 2019 8:00 AM | November 1, 2019 5:00 PM | 2019-11-01 | 0 |  | 3
336 | Yes | Auto Scheduled | QA Status Reporting 47 | 1 day | November 8, 2019 8:00 AM | November 8, 2019 5:00 PM | 2019-11-08 | 0 |  | 3
337 | Yes | Auto Scheduled | QA Status Reporting 48 | 1 day | November 15, 2019 8:00 AM | November 15, 2019 5:00 PM | 2019-11-15 | 0 |  | 3
338 | Yes | Auto Scheduled | QA Status Reporting 49 | 1 day | November 22, 2019 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 3
339 | Yes | Auto Scheduled | QA Status Reporting 50 | 1 day | December 2, 2019 8:00 AM | December 2, 2019 5:00 PM | 2019-12-02 | 0 |  | 3
340 | Yes | Auto Scheduled | QA Status Reporting 51 | 1 day | December 6, 2019 8:00 AM | December 6, 2019 5:00 PM | 2019-12-06 | 0 |  | 3
341 | Yes | Auto Scheduled | QA Status Reporting 52 | 1 day | December 13, 2019 8:00 AM | December 13, 2019 5:00 PM | 2019-12-13 | 0 |  | 3
342 | Yes | Auto Scheduled | QA Status Reporting 53 | 1 day | December 20, 2019 8:00 AM | December 20, 2019 5:00 PM | 2019-12-20 | 0 |  | 3
343 | Yes | Auto Scheduled | QA Compliance Audit TPL | 345 days | November 6, 2018 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
344 | Yes | Auto Scheduled | QA Compliance Audit TPL 1 | 1 day | November 6, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 3
345 | Yes | Auto Scheduled | QA Compliance Audit TPL 2 | 1 day | December 4, 2018 8:00 AM | December 4, 2018 5:00 PM | 2018-12-04 | 1 |  | 3
346 | Yes | Auto Scheduled | QA Compliance Audit TPL 3 | 9 days | January 11, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 |  | 3
347 | Yes | Auto Scheduled | QA Compliance Audit TPL 4 | 1 day | February 22, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3
348 | Yes | Auto Scheduled | QA Compliance Audit TPL 5 | 1 day | March 19, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 3
349 | Yes | Auto Scheduled | QA Compliance Audit TPL 6 | 1 day | April 1, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 |  | 3
350 | Yes | Auto Scheduled | QA Compliance Audit TPL 7 | 1 day | May 6, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 3
351 | Yes | Auto Scheduled | QA Compliance Audit TPL 8 | 1 day | June 3, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 3
352 | Yes | Auto Scheduled | QA Compliance Audit TPL 9 | 1 day | July 1, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 3
353 | Yes | Auto Scheduled | QA Compliance Audit TPL 10 | 1 day | August 5, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 |  | 3
354 | Yes | Auto Scheduled | QA Compliance Audit TPL 11 | 1 day | September 2, 2019 8:00 AM | September 2, 2019 5:00 PM | 2019-09-02 | 0 |  | 3
355 | Yes | Auto Scheduled | QA Compliance Audit TPL 12 | 1 day | October 7, 2019 8:00 AM | October 7, 2019 5:00 PM | 2019-10-07 | 0 |  | 3
356 | Yes | Auto Scheduled | QA Compliance Audit TPL 13 | 1 day | November 4, 2019 8:00 AM | November 4, 2019 5:00 PM | 2019-11-04 | 0 |  | 3
357 | Yes | Auto Scheduled | QA Compliance Audit TPL 14 | 1 day | December 2, 2019 8:00 AM | December 2, 2019 5:00 PM | 2019-12-02 | 0 |  | 3
358 | Yes | Auto Scheduled | QA Compliance Audit TPL 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
359 | Yes | Auto Scheduled | QA Compliance Audit TPL 16 | 1 day | February 3, 2020 8:00 AM | February 3, 2020 5:00 PM | 2020-02-03 | 0 |  | 3
360 | Yes | Auto Scheduled | QA Compliance Audit TPL 17 | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 3
361 | Yes | Auto Scheduled | QA Compliance Audit SPL | 331 days | November 28, 2018 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 2
362 | Yes | Auto Scheduled | QA Compliance Audit SPL 1 | 1 day | November 28, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 |  | 3
363 | Yes | Auto Scheduled | QA Compliance Audit SPL 2 | 1 day | December 18, 2018 8:00 AM | December 18, 2018 5:00 PM | 2018-12-18 | 1 |  | 3
364 | Yes | Auto Scheduled | QA Compliance Audit SPL 3 | 1 day | January 31, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 |  | 3
365 | Yes | Auto Scheduled | QA Compliance Audit SPL 4 | 1 day | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 |  | 3
366 | Yes | Auto Scheduled | QA Compliance Audit SPL 5 | 1 day | March 6, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 |  | 3
367 | Yes | Auto Scheduled | QA Compliance Audit SPL 6 | 1 day | April 3, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 3
368 | Yes | Auto Scheduled | QA Compliance Audit SPL 7 | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 |  | 3
369 | Yes | Auto Scheduled | QA Compliance Audit SPL 8 | 1 day | June 5, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 |  | 3
370 | Yes | Auto Scheduled | QA Compliance Audit SPL 9 | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 3
371 | Yes | Auto Scheduled | QA Compliance Audit SPL 10 | 1 day | August 7, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 3
372 | Yes | Auto Scheduled | QA Compliance Audit SPL 11 | 1 day | September 4, 2019 8:00 AM | September 4, 2019 5:00 PM | 2019-09-04 | 0 |  | 3
373 | Yes | Auto Scheduled | QA Compliance Audit SPL 12 | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM | 2019-10-02 | 0 |  | 3
374 | Yes | Auto Scheduled | QA Compliance Audit SPL 13 | 1 day | November 6, 2019 8:00 AM | November 6, 2019 5:00 PM | 2019-11-06 | 0 |  | 3
375 | Yes | Auto Scheduled | QA Compliance Audit SPL 14 | 1 day | December 4, 2019 8:00 AM | December 4, 2019 5:00 PM | 2019-12-04 | 0 |  | 3
376 | Yes | Auto Scheduled | QA Compliance Audit SPL 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
377 | Yes | Auto Scheduled | QA Compliance Audit SPL 16 | 1 day | February 5, 2020 8:00 AM | February 5, 2020 5:00 PM | 2020-02-05 | 0 |  | 3
378 | Yes | Auto Scheduled | QA Compliance Audit SPL 17 | 1 day | March 4, 2020 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 3
379 | Yes | Auto Scheduled | QA Compliance Audit Systems | 346 days | November 6, 2018 8:00 AM | March 3, 2020 5:00 PM | 2020-03-03 | 0 |  | 2
380 | Yes | Auto Scheduled | QA Compliance Audit Systems 1 | 1 day | November 6, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 3
381 | Yes | Auto Scheduled | QA Compliance Audit Systems 2 | 1 day | December 4, 2018 8:00 AM | December 4, 2018 5:00 PM | 2018-12-04 | 1 |  | 3
382 | Yes | Auto Scheduled | QA Compliance Audit Systems 3 | 1 day | January 30, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 3
383 | Yes | Auto Scheduled | QA Compliance Audit Systems 4 | 1 day | February 26, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 |  | 3
384 | Yes | Auto Scheduled | QA Compliance Audit Systems 5 | 1 day | March 21, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 3
385 | Yes | Auto Scheduled | QA Compliance Audit Systems 6 | 1 day | April 2, 2019 8:00 AM | April 2, 2019 5:00 PM | 2019-04-02 | 1 |  | 3
386 | Yes | Auto Scheduled | QA Compliance Audit Systems 7 | 1 day | May 7, 2019 8:00 AM | May 7, 2019 5:00 PM | 2019-05-07 | 1 |  | 3
387 | Yes | Auto Scheduled | QA Compliance Audit Systems 8 | 1 day | June 4, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 |  | 3
388 | Yes | Auto Scheduled | QA Compliance Audit Systems 9 | 1 day | July 2, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 |  | 3
389 | Yes | Auto Scheduled | QA Compliance Audit Systems 10 | 1 day | August 6, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 |  | 3
390 | Yes | Auto Scheduled | QA Compliance Audit Systems 11 | 1 day | September 3, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 |  | 3
391 | Yes | Auto Scheduled | QA Compliance Audit Systems 12 | 1 day | October 1, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 3
392 | Yes | Auto Scheduled | QA Compliance Audit Systems 13 | 1 day | November 5, 2019 8:00 AM | November 5, 2019 5:00 PM | 2019-11-05 | 0 |  | 3
393 | Yes | Auto Scheduled | QA Compliance Audit Systems 14 | 1 day | December 3, 2019 8:00 AM | December 3, 2019 5:00 PM | 2019-12-03 | 0 |  | 3
394 | Yes | Auto Scheduled | QA Compliance Audit Systems 15 | 1 day | January 7, 2020 8:00 AM | January 7, 2020 5:00 PM | 2020-01-07 | 0 |  | 3
395 | Yes | Auto Scheduled | QA Compliance Audit Systems 16 | 1 day | February 4, 2020 8:00 AM | February 4, 2020 5:00 PM | 2020-02-04 | 0 |  | 3
396 | Yes | Auto Scheduled | QA Compliance Audit Systems 17 | 1 day | March 3, 2020 8:00 AM | March 3, 2020 5:00 PM | 2020-03-03 | 0 |  | 3
397 | Yes | Auto Scheduled | QA Compliance Audit SW System | 317 days | December 17, 2018 8:00 AM | March 3, 2020 5:00 PM | 2020-03-03 | 0 |  | 2
398 | Yes | Auto Scheduled | QA Compliance Audit SW System 1 | 0 days | December 27, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 |  | 3
399 | Yes | Auto Scheduled | QA Compliance Audit SW System 2 | 1 day | December 17, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 |  | 3
400 | Yes | Auto Scheduled | QA Compliance Audit SW System 3 | 1 day | January 30, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 3
401 | Yes | Auto Scheduled | QA Compliance Audit SW System 4 | 1 day | February 28, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 |  | 3
402 | Yes | Auto Scheduled | QA Compliance Audit SW System 5 | 1 day | March 5, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 |  | 3
403 | Yes | Auto Scheduled | QA Compliance Audit SW System 6 | 1 day | April 2, 2019 8:00 AM | April 2, 2019 5:00 PM | 2019-04-02 | 1 |  | 3
404 | Yes | Auto Scheduled | QA Compliance Audit SW System 7 | 1 day | May 7, 2019 8:00 AM | May 7, 2019 5:00 PM | 2019-05-07 | 1 |  | 3
405 | Yes | Auto Scheduled | QA Compliance Audit SW System 8 | 1 day | June 4, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 |  | 3
406 | Yes | Auto Scheduled | QA Compliance Audit SW System 9 | 1 day | July 2, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 |  | 3
407 | Yes | Auto Scheduled | QA Compliance Audit SW System 10 | 1 day | August 6, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 |  | 3
408 | Yes | Auto Scheduled | QA Compliance Audit SW System 11 | 1 day | September 3, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 |  | 3
409 | Yes | Auto Scheduled | QA Compliance Audit SW System 12 | 1 day | October 1, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 3
410 | Yes | Auto Scheduled | QA Compliance Audit SW System 13 | 1 day | November 5, 2019 8:00 AM | November 5, 2019 5:00 PM | 2019-11-05 | 0 |  | 3
411 | Yes | Auto Scheduled | QA Compliance Audit SW System 14 | 1 day | December 3, 2019 8:00 AM | December 3, 2019 5:00 PM | 2019-12-03 | 0 |  | 3
412 | Yes | Auto Scheduled | QA Compliance Audit SW System 15 | 1 day | January 7, 2020 8:00 AM | January 7, 2020 5:00 PM | 2020-01-07 | 0 |  | 3
413 | Yes | Auto Scheduled | QA Compliance Audit SW System 16 | 1 day | February 4, 2020 8:00 AM | February 4, 2020 5:00 PM | 2020-02-04 | 0 |  | 3
414 | Yes | Auto Scheduled | QA Compliance Audit SW System 17 | 1 day | March 3, 2020 8:00 AM | March 3, 2020 5:00 PM | 2020-03-03 | 0 |  | 3
415 | Yes | Auto Scheduled | QA Compliance Audit SW Design | 331 days | November 28, 2018 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 2
416 | Yes | Auto Scheduled | QA Compliance Audit SW Design 1 | 17 days | November 28, 2018 8:00 AM | December 28, 2018 5:00 PM | 2018-12-28 | 1 |  | 3
417 | Yes | Auto Scheduled | QA Compliance Audit SW Design 2 | 1 day | December 10, 2018 8:00 AM | December 10, 2018 5:00 PM | 2018-12-10 | 1 |  | 3
418 | Yes | Auto Scheduled | QA Compliance Audit SW Design 3 | 1 day | January 31, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 |  | 3
419 | Yes | Auto Scheduled | QA Compliance Audit SW Design 4 | 1 day | February 28, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 |  | 3
420 | Yes | Auto Scheduled | QA Compliance Audit SW Design 5 | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
421 | Yes | Auto Scheduled | QA Compliance Audit SW Design 6 | 1 day | April 3, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 3
422 | Yes | Auto Scheduled | QA Compliance Audit SW Design 7 | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 |  | 3
423 | Yes | Auto Scheduled | QA Compliance Audit SW Design 8 | 1 day | June 5, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 |  | 3
424 | Yes | Auto Scheduled | QA Compliance Audit SW Design 9 | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 3
425 | Yes | Auto Scheduled | QA Compliance Audit SW Design 10 | 1 day | August 7, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 3
426 | Yes | Auto Scheduled | QA Compliance Audit SW Design 11 | 1 day | September 4, 2019 8:00 AM | September 4, 2019 5:00 PM | 2019-09-04 | 0 |  | 3
427 | Yes | Auto Scheduled | QA Compliance Audit SW Design 12 | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM | 2019-10-02 | 0 |  | 3
428 | Yes | Auto Scheduled | QA Compliance Audit SW Design 13 | 1 day | November 6, 2019 8:00 AM | November 6, 2019 5:00 PM | 2019-11-06 | 0 |  | 3
429 | Yes | Auto Scheduled | QA Compliance Audit SW Design 14 | 1 day | December 4, 2019 8:00 AM | December 4, 2019 5:00 PM | 2019-12-04 | 0 |  | 3
430 | Yes | Auto Scheduled | QA Compliance Audit SW Design 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
431 | Yes | Auto Scheduled | QA Compliance Audit SW Design 16 | 1 day | February 5, 2020 8:00 AM | February 5, 2020 5:00 PM | 2020-02-05 | 0 |  | 3
432 | Yes | Auto Scheduled | QA Compliance Audit SW Design 17 | 1 day | March 4, 2020 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 3
433 | Yes | Auto Scheduled | QA Compliance Audit SW Validation | 330 days | November 29, 2018 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 2
434 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 1 | 1 day | November 29, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 |  | 3
435 | No | Auto Scheduled | QA Compliance Audit SW Validation 2 | 1 day | December 5, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 |  | 3
436 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 3 | 1 day | January 30, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 3
437 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 4 | 1 day | March 6, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 |  | 3
438 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 5 | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
439 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 6 | 1 day | April 3, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 3
440 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 7 | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 |  | 3
441 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 8 | 1 day | June 5, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 |  | 3
442 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 9 | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 3
443 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 10 | 1 day | August 7, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 3
444 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 11 | 1 day | September 4, 2019 8:00 AM | September 4, 2019 5:00 PM | 2019-09-04 | 0 |  | 3
445 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 12 | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM | 2019-10-02 | 0 |  | 3
446 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 13 | 1 day | November 6, 2019 8:00 AM | November 6, 2019 5:00 PM | 2019-11-06 | 0 |  | 3
447 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 14 | 1 day | December 4, 2019 8:00 AM | December 4, 2019 5:00 PM | 2019-12-04 | 0 |  | 3
448 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
449 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 16 | 1 day | February 5, 2020 8:00 AM | February 5, 2020 5:00 PM | 2020-02-05 | 0 |  | 3
450 | Yes | Auto Scheduled | QA Compliance Audit SW Validation 17 | 1 day | March 4, 2020 8:00 AM | March 4, 2020 5:00 PM | 2020-03-04 | 0 |  | 3
451 | Yes | Auto Scheduled | QA Compliance Audit Hardware | 329 days | December 3, 2018 8:00 AM | March 5, 2020 5:00 PM | 2020-03-05 | 0 |  | 2
452 | No | Auto Scheduled | QA Compliance Audit Hardware 1 | 1 day | November 1, 2018 8:00 AM | November 1, 2018 5:00 PM | 2018-11-01 | 1 |  | 3
453 | Yes | Auto Scheduled | QA Compliance Audit Hardware 2 | 1 day | December 3, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 3
454 | Yes | Auto Scheduled | QA Compliance Audit Hardware 3 | 1 day | February 4, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 |  | 3
455 | Yes | Auto Scheduled | QA Compliance Audit Hardware 4 | 1 day | March 6, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 |  | 3
456 | Yes | Auto Scheduled | QA Compliance Audit Hardware 5 | 1 day | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 3
457 | Yes | Auto Scheduled | QA Compliance Audit Hardware 6 | 1 day | April 4, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 |  | 3
458 | Yes | Auto Scheduled | QA Compliance Audit Hardware 7 | 1 day | May 2, 2019 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 3
459 | Yes | Auto Scheduled | QA Compliance Audit Hardware 8 | 1 day | June 6, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
460 | Yes | Auto Scheduled | QA Compliance Audit Hardware 9 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
461 | Yes | Auto Scheduled | QA Compliance Audit Hardware 10 | 1 day | August 1, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 |  | 3
462 | Yes | Auto Scheduled | QA Compliance Audit Hardware 11 | 1 day | September 5, 2019 8:00 AM | September 5, 2019 5:00 PM | 2019-09-05 | 0 |  | 3
463 | Yes | Auto Scheduled | QA Compliance Audit Hardware 12 | 1 day | October 3, 2019 8:00 AM | October 3, 2019 5:00 PM | 2019-10-03 | 0 |  | 3
464 | Yes | Auto Scheduled | QA Compliance Audit Hardware 13 | 1 day | November 7, 2019 8:00 AM | November 7, 2019 5:00 PM | 2019-11-07 | 0 |  | 3
465 | Yes | Auto Scheduled | QA Compliance Audit Hardware 14 | 1 day | December 5, 2019 8:00 AM | December 5, 2019 5:00 PM | 2019-12-05 | 0 |  | 3
466 | Yes | Auto Scheduled | QA Compliance Audit Hardware 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
467 | Yes | Auto Scheduled | QA Compliance Audit Hardware 16 | 1 day | February 6, 2020 8:00 AM | February 6, 2020 5:00 PM | 2020-02-06 | 0 |  | 3
468 | Yes | Auto Scheduled | QA Compliance Audit Hardware 17 | 1 day | March 5, 2020 8:00 AM | March 5, 2020 5:00 PM | 2020-03-05 | 0 |  | 3
469 | Yes | Auto Scheduled | QA Compliance Audit Mechanical | 331 days | November 29, 2018 8:00 AM | March 5, 2020 5:00 PM | 2020-03-05 | 0 |  | 2
470 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 1 | 1 day | November 29, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 |  | 3
471 | No | Auto Scheduled | QA Compliance Audit Mechanical 2 | 1 day | December 6, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 3
472 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 3 | 1 day | February 1, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 3
473 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 4 | 1 day | March 14, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 3
474 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 5 | 1 day | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 3
475 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 6 | 1 day | April 4, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 |  | 3
476 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 7 | 1 day | May 2, 2019 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 3
477 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 8 | 1 day | June 6, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
478 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 9 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
479 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 10 | 1 day | August 1, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 |  | 3
480 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 11 | 1 day | September 5, 2019 8:00 AM | September 5, 2019 5:00 PM | 2019-09-05 | 0 |  | 3
481 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 12 | 1 day | October 3, 2019 8:00 AM | October 3, 2019 5:00 PM | 2019-10-03 | 0 |  | 3
482 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 13 | 1 day | November 7, 2019 8:00 AM | November 7, 2019 5:00 PM | 2019-11-07 | 0 |  | 3
483 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 14 | 1 day | December 5, 2019 8:00 AM | December 5, 2019 5:00 PM | 2019-12-05 | 0 |  | 3
484 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
485 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 16 | 1 day | February 6, 2020 8:00 AM | February 6, 2020 5:00 PM | 2020-02-06 | 0 |  | 3
486 | Yes | Auto Scheduled | QA Compliance Audit Mechanical 17 | 1 day | March 5, 2020 8:00 AM | March 5, 2020 5:00 PM | 2020-03-05 | 0 |  | 3
487 | Yes | Auto Scheduled | QA Compliance Audit CM | 331 days | November 30, 2018 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 2
488 | Yes | Auto Scheduled | QA Compliance Audit CM 1 | 1 day | November 30, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 |  | 3
489 | Yes | Auto Scheduled | QA Compliance Audit CM 2 | 1 day | December 12, 2018 8:00 AM | December 12, 2018 5:00 PM | 2018-12-12 | 1 |  | 3
490 | Yes | Auto Scheduled | QA Compliance Audit CM 3 | 1 day | January 30, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 3
491 | Yes | Auto Scheduled | QA Compliance Audit CM 4 | 1 day | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 3
492 | Yes | Auto Scheduled | QA Compliance Audit CM 5 | 1 day | March 15, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 3
493 | Yes | Auto Scheduled | QA Compliance Audit CM 6 | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 |  | 3
494 | Yes | Auto Scheduled | QA Compliance Audit CM 7 | 1 day | May 3, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 3
495 | Yes | Auto Scheduled | QA Compliance Audit CM 8 | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
496 | Yes | Auto Scheduled | QA Compliance Audit CM 9 | 3 days | July 5, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 3
497 | Yes | Auto Scheduled | QA Compliance Audit CM 10 | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
498 | Yes | Auto Scheduled | QA Compliance Audit CM 11 | 1 day | September 6, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 |  | 3
499 | Yes | Auto Scheduled | QA Compliance Audit CM 12 | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 2019-10-04 | 0 |  | 3
500 | Yes | Auto Scheduled | QA Compliance Audit CM 13 | 1 day | November 1, 2019 8:00 AM | November 1, 2019 5:00 PM | 2019-11-01 | 0 |  | 3
501 | Yes | Auto Scheduled | QA Compliance Audit CM 14 | 1 day | December 6, 2019 8:00 AM | December 6, 2019 5:00 PM | 2019-12-06 | 0 |  | 3
502 | Yes | Auto Scheduled | QA Compliance Audit CM 15 | 3 days | January 3, 2020 8:00 AM | January 7, 2020 5:00 PM | 2020-01-07 | 0 |  | 3
503 | Yes | Auto Scheduled | QA Compliance Audit CM 16 | 1 day | February 7, 2020 8:00 AM | February 7, 2020 5:00 PM | 2020-02-07 | 0 |  | 3
504 | Yes | Auto Scheduled | QA Compliance Audit CM 17 | 1 day | March 6, 2020 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 3
505 | Yes | Auto Scheduled | QA Compliance Audit EQA | 328 days | December 5, 2018 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 2
506 | Yes | Auto Scheduled | QA Compliance Audit EQA 1 | 1 day | December 5, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 |  | 3
507 | Yes | Auto Scheduled | QA Compliance Audit EQA 2 | 1 day | December 20, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 |  | 3
508 | Yes | Auto Scheduled | QA Compliance Audit EQA 3 | 1 day | February 4, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 |  | 3
509 | Yes | Auto Scheduled | QA Compliance Audit EQA 4 | 1 day | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 |  | 3
510 | Yes | Auto Scheduled | QA Compliance Audit EQA 5 | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
511 | Yes | Auto Scheduled | QA Compliance Audit EQA 6 | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 |  | 3
512 | Yes | Auto Scheduled | QA Compliance Audit EQA 7 | 1 day | May 3, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 3
513 | Yes | Auto Scheduled | QA Compliance Audit EQA 8 | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
514 | Yes | Auto Scheduled | QA Compliance Audit EQA 9 | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
515 | Yes | Auto Scheduled | QA Compliance Audit EQA 10 | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
516 | Yes | Auto Scheduled | QA Compliance Audit EQA 11 | 1 day | September 6, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 |  | 3
517 | Yes | Auto Scheduled | QA Compliance Audit EQA 12 | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 2019-10-04 | 0 |  | 3
518 | Yes | Auto Scheduled | QA Compliance Audit EQA 13 | 1 day | November 1, 2019 8:00 AM | November 1, 2019 5:00 PM | 2019-11-01 | 0 |  | 3
519 | Yes | Auto Scheduled | QA Compliance Audit EQA 14 | 1 day | December 6, 2019 8:00 AM | December 6, 2019 5:00 PM | 2019-12-06 | 0 |  | 3
520 | Yes | Auto Scheduled | QA Compliance Audit EQA 15 | 1 day | January 6, 2020 8:00 AM | January 6, 2020 5:00 PM | 2020-01-06 | 0 |  | 3
521 | Yes | Auto Scheduled | QA Compliance Audit EQA 16 | 1 day | February 7, 2020 8:00 AM | February 7, 2020 5:00 PM | 2020-02-07 | 0 |  | 3
522 | Yes | Auto Scheduled | QA Compliance Audit EQA 17 | 1 day | March 6, 2020 8:00 AM | March 6, 2020 5:00 PM | 2020-03-06 | 0 |  | 3
523 | Yes | Auto Scheduled | CM Weekly/Monthly Reviews | 645 days | October 5, 2017 8:00 AM | March 26, 2020 5:00 PM | 2020-03-26 | 0 |  | 2
524 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review | 645 days | October 5, 2017 8:00 AM | March 26, 2020 5:00 PM | 2020-03-26 | 0 |  | 3
525 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 1 | 1 day | October 5, 2017 8:00 AM | October 5, 2017 5:00 PM | 2017-10-05 | 1 |  | 4
526 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 2 | 1 day | October 12, 2017 8:00 AM | October 12, 2017 5:00 PM | 2017-10-12 | 1 |  | 4
527 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 3 | 1 day | October 19, 2017 8:00 AM | October 19, 2017 5:00 PM | 2017-10-19 | 1 |  | 4
528 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 4 | 1 day | October 26, 2017 8:00 AM | October 26, 2017 5:00 PM | 2017-10-26 | 1 |  | 4
529 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 5 | 1 day | November 2, 2017 8:00 AM | November 2, 2017 5:00 PM | 2017-11-02 | 1 |  | 4
530 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 6 | 1 day | November 9, 2017 8:00 AM | November 9, 2017 5:00 PM | 2017-11-09 | 1 |  | 4
531 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 7 | 1 day | November 16, 2017 8:00 AM | November 16, 2017 5:00 PM | 2017-11-16 | 1 |  | 4
532 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 8 | 1 day | November 23, 2017 8:00 AM | November 23, 2017 5:00 PM | 2017-11-23 | 1 |  | 4
533 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 9 | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 2017-11-30 | 1 |  | 4
534 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 10 | 1 day | December 7, 2017 8:00 AM | December 7, 2017 5:00 PM | 2017-12-07 | 1 |  | 4
535 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 11 | 1 day | December 14, 2017 8:00 AM | December 14, 2017 5:00 PM | 2017-12-14 | 1 |  | 4
536 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 12 | 1 day | December 21, 2017 8:00 AM | December 21, 2017 5:00 PM | 2017-12-21 | 1 |  | 4
537 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 13 | 1 day | December 28, 2017 8:00 AM | December 28, 2017 5:00 PM | 2017-12-28 | 1 |  | 4
538 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 14 | 1 day | January 4, 2018 8:00 AM | January 4, 2018 5:00 PM | 2018-01-04 | 1 |  | 4
539 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 15 | 1 day | January 11, 2018 8:00 AM | January 11, 2018 5:00 PM | 2018-01-11 | 1 |  | 4
540 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 16 | 1 day | January 18, 2018 8:00 AM | January 18, 2018 5:00 PM | 2018-01-18 | 1 |  | 4
541 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 17 | 1 day | January 25, 2018 8:00 AM | January 25, 2018 5:00 PM | 2018-01-25 | 1 |  | 4
542 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 18 | 1 day | February 1, 2018 8:00 AM | February 1, 2018 5:00 PM | 2018-02-01 | 1 |  | 4
543 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 19 | 1 day | February 8, 2018 8:00 AM | February 8, 2018 5:00 PM | 2018-02-08 | 1 |  | 4
544 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 20 | 1 day | February 15, 2018 8:00 AM | February 15, 2018 5:00 PM | 2018-02-15 | 1 |  | 4
545 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 21 | 1 day | February 22, 2018 8:00 AM | February 22, 2018 5:00 PM | 2018-02-22 | 1 |  | 4
546 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 22 | 1 day | March 1, 2018 8:00 AM | March 1, 2018 5:00 PM | 2018-03-01 | 1 |  | 4
547 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 23 | 1 day | March 8, 2018 8:00 AM | March 8, 2018 5:00 PM | 2018-03-08 | 1 |  | 4
548 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 24 | 1 day | March 15, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 |  | 4
549 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 25 | 1 day | March 22, 2018 8:00 AM | March 22, 2018 5:00 PM | 2018-03-22 | 1 |  | 4
550 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 26 | 1 day | March 29, 2018 8:00 AM | March 29, 2018 5:00 PM | 2018-03-29 | 1 |  | 4
551 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 27 | 1 day | April 5, 2018 8:00 AM | April 5, 2018 5:00 PM | 2018-04-05 | 1 |  | 4
552 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 28 | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 2018-04-12 | 1 |  | 4
553 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 29 | 1 day | April 19, 2018 8:00 AM | April 19, 2018 5:00 PM | 2018-04-19 | 1 |  | 4
554 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 30 | 1 day | April 26, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 |  | 4
555 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 31 | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 4
556 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 32 | 1 day | May 10, 2018 8:00 AM | May 10, 2018 5:00 PM | 2018-05-10 | 1 |  | 4
557 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 33 | 1 day | May 17, 2018 8:00 AM | May 17, 2018 5:00 PM | 2018-05-17 | 1 |  | 4
558 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 34 | 1 day | May 24, 2018 8:00 AM | May 24, 2018 5:00 PM | 2018-05-24 | 1 |  | 4
559 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 35 | 1 day | May 31, 2018 8:00 AM | May 31, 2018 5:00 PM | 2018-05-31 | 1 |  | 4
560 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 36 | 1 day | June 7, 2018 8:00 AM | June 7, 2018 5:00 PM | 2018-06-07 | 1 |  | 4
561 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 37 | 1 day | June 14, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 4
562 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 38 | 1 day | June 21, 2018 8:00 AM | June 21, 2018 5:00 PM | 2018-06-21 | 1 |  | 4
563 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 39 | 1 day | June 28, 2018 8:00 AM | June 28, 2018 5:00 PM | 2018-06-28 | 1 |  | 4
564 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 40 | 1 day | July 5, 2018 8:00 AM | July 5, 2018 5:00 PM | 2018-07-05 | 1 |  | 4
565 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 41 | 1 day | July 12, 2018 8:00 AM | July 12, 2018 5:00 PM | 2018-07-12 | 1 |  | 4
566 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 42 | 1 day | July 19, 2018 8:00 AM | July 19, 2018 5:00 PM | 2018-07-19 | 1 |  | 4
567 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 43 | 1 day | July 26, 2018 8:00 AM | July 26, 2018 5:00 PM | 2018-07-26 | 1 |  | 4
568 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 44 | 1 day | August 2, 2018 8:00 AM | August 2, 2018 5:00 PM | 2018-08-02 | 1 |  | 4
569 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 45 | 1 day | August 9, 2018 8:00 AM | August 9, 2018 5:00 PM | 2018-08-09 | 1 |  | 4
570 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 46 | 1 day | August 16, 2018 8:00 AM | August 16, 2018 5:00 PM | 2018-08-16 | 1 |  | 4
571 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 47 | 1 day | August 23, 2018 8:00 AM | August 23, 2018 5:00 PM | 2018-08-23 | 1 |  | 4
572 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 48 | 1 day | August 30, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 |  | 4
573 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 49 | 1 day | September 6, 2018 8:00 AM | September 6, 2018 5:00 PM | 2018-09-06 | 1 |  | 4
574 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 50 | 1 day | September 13, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 4
575 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 51 | 1 day | September 20, 2018 8:00 AM | September 20, 2018 5:00 PM | 2018-09-20 | 1 |  | 4
576 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 52 | 1 day | September 27, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 4
577 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 53 | 1 day | October 4, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 |  | 4
578 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 54 | 1 day | October 11, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 |  | 4
579 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 55 | 1 day | October 18, 2018 8:00 AM | October 18, 2018 5:00 PM | 2018-10-18 | 1 |  | 4
580 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 56 | 1 day | October 25, 2018 8:00 AM | October 25, 2018 5:00 PM | 2018-10-25 | 1 |  | 4
581 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 57 | 1 day | November 1, 2018 8:00 AM | November 1, 2018 5:00 PM | 2018-11-01 | 1 |  | 4
582 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 58 | 1 day | November 8, 2018 8:00 AM | November 8, 2018 5:00 PM | 2018-11-08 | 1 |  | 4
583 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 59 | 1 day | November 15, 2018 8:00 AM | November 15, 2018 5:00 PM | 2018-11-15 | 1 |  | 4
584 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 60 | 1 day | November 22, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 |  | 4
585 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 61 | 1 day | November 29, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 |  | 4
586 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 62 | 1 day | December 6, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 4
587 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 63 | 1 day | December 13, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
588 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 64 | 1 day | December 20, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 |  | 4
589 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 65 | 1 day | December 27, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 |  | 4
590 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 66 | 1 day | January 3, 2019 8:00 AM | January 3, 2019 5:00 PM | 2019-01-03 | 1 |  | 4
591 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 67 | 1 day | January 10, 2019 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 4
592 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 68 | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 4
593 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 69 | 1 day | January 24, 2019 8:00 AM | January 24, 2019 5:00 PM | 2019-01-24 | 1 |  | 4
594 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 70 | 1 day | January 31, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 |  | 4
595 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 71 | 1 day | February 7, 2019 8:00 AM | February 7, 2019 5:00 PM | 2019-02-07 | 1 |  | 4
596 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 72 | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 4
597 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 73 | 1 day | February 22, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 4
598 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 74 | 1 day | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 |  | 4
599 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 75 | 1 day | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 4
600 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 76 | 1 day | March 14, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
601 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 77 | 1 day | March 21, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 4
602 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 78 | 1 day | March 28, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 |  | 4
603 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 79 | 1 day | April 4, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 |  | 4
604 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 80 | 1 day | April 11, 2019 8:00 AM | April 11, 2019 5:00 PM | 2019-04-11 | 1 |  | 4
605 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 81 | 1 day | April 18, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 |  | 4
606 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 82 | 1 day | April 25, 2019 8:00 AM | April 25, 2019 5:00 PM | 2019-04-25 | 1 |  | 4
607 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 83 | 1 day | May 2, 2019 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 4
608 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 84 | 1 day | May 9, 2019 8:00 AM | May 9, 2019 5:00 PM | 2019-05-09 | 1 |  | 4
609 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 85 | 1 day | May 16, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 |  | 4
610 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 86 | 1 day | May 23, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 |  | 4
611 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 87 | 1 day | May 30, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 |  | 4
612 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 88 | 1 day | June 6, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
613 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 89 | 1 day | June 13, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
614 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 90 | 1 day | June 20, 2019 8:00 AM | June 20, 2019 5:00 PM | 2019-06-20 | 1 |  | 4
615 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 91 | 1 day | June 27, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 |  | 4
616 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 92 | 1 day | July 4, 2019 8:00 AM | July 4, 2019 5:00 PM | 2019-07-04 | 1 |  | 4
617 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 93 | 1 day | July 11, 2019 8:00 AM | July 11, 2019 5:00 PM | 2019-07-11 | 1 |  | 4
618 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 94 | 1 day | July 18, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 |  | 4
619 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 95 | 1 day | July 25, 2019 8:00 AM | July 25, 2019 5:00 PM | 2019-07-25 | 1 |  | 4
620 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 96 | 1 day | August 1, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 |  | 4
621 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 97 | 1 day | August 8, 2019 8:00 AM | August 8, 2019 5:00 PM | 2019-08-08 | 1 |  | 4
622 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 98 | 1 day | August 15, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 |  | 4
623 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 99 | 1 day | August 22, 2019 8:00 AM | August 22, 2019 5:00 PM | 2019-08-22 | 1 |  | 4
624 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 100 | 1 day | August 29, 2019 8:00 AM | August 29, 2019 5:00 PM | 2019-08-29 | 0 |  | 4
625 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 101 | 1 day | September 5, 2019 8:00 AM | September 5, 2019 5:00 PM | 2019-09-05 | 0 |  | 4
626 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 102 | 1 day | September 12, 2019 8:00 AM | September 12, 2019 5:00 PM | 2019-09-12 | 0 |  | 4
627 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 103 | 1 day | September 19, 2019 8:00 AM | September 19, 2019 5:00 PM | 2019-09-19 | 0 |  | 4
628 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 104 | 1 day | September 26, 2019 8:00 AM | September 26, 2019 5:00 PM | 2019-09-26 | 0 |  | 4
629 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 105 | 1 day | October 3, 2019 8:00 AM | October 3, 2019 5:00 PM | 2019-10-03 | 0 |  | 4
630 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 106 | 1 day | October 10, 2019 8:00 AM | October 10, 2019 5:00 PM | 2019-10-10 | 0 |  | 4
631 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 107 | 1 day | October 17, 2019 8:00 AM | October 17, 2019 5:00 PM | 2019-10-17 | 0 |  | 4
632 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 108 | 1 day | October 24, 2019 8:00 AM | October 24, 2019 5:00 PM | 2019-10-24 | 0 |  | 4
633 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 109 | 1 day | October 31, 2019 8:00 AM | October 31, 2019 5:00 PM | 2019-10-31 | 0 |  | 4
634 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 110 | 1 day | November 7, 2019 8:00 AM | November 7, 2019 5:00 PM | 2019-11-07 | 0 |  | 4
635 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 111 | 1 day | November 14, 2019 8:00 AM | November 14, 2019 5:00 PM | 2019-11-14 | 0 |  | 4
636 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 112 | 1 day | November 21, 2019 8:00 AM | November 21, 2019 5:00 PM | 2019-11-21 | 0 |  | 4
637 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 113 | 1 day | November 28, 2019 8:00 AM | November 28, 2019 5:00 PM | 2019-11-28 | 0 |  | 4
638 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 114 | 1 day | December 5, 2019 8:00 AM | December 5, 2019 5:00 PM | 2019-12-05 | 0 |  | 4
639 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 115 | 1 day | December 12, 2019 8:00 AM | December 12, 2019 5:00 PM | 2019-12-12 | 0 |  | 4
640 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 116 | 1 day | December 19, 2019 8:00 AM | December 19, 2019 5:00 PM | 2019-12-19 | 0 |  | 4
641 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 117 | 1 day | December 26, 2019 8:00 AM | December 26, 2019 5:00 PM | 2019-12-26 | 0 |  | 4
642 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 118 | 1 day | January 2, 2020 8:00 AM | January 2, 2020 5:00 PM | 2020-01-02 | 0 |  | 4
643 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 119 | 1 day | January 9, 2020 8:00 AM | January 9, 2020 5:00 PM | 2020-01-09 | 0 |  | 4
644 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 120 | 1 day | January 16, 2020 8:00 AM | January 16, 2020 5:00 PM | 2020-01-16 | 0 |  | 4
645 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 121 | 1 day | January 23, 2020 8:00 AM | January 23, 2020 5:00 PM | 2020-01-23 | 0 |  | 4
646 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 122 | 1 day | January 30, 2020 8:00 AM | January 30, 2020 5:00 PM | 2020-01-30 | 0 |  | 4
647 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 123 | 1 day | February 6, 2020 8:00 AM | February 6, 2020 5:00 PM | 2020-02-06 | 0 |  | 4
648 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 124 | 1 day | February 13, 2020 8:00 AM | February 13, 2020 5:00 PM | 2020-02-13 | 0 |  | 4
649 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 125 | 1 day | February 20, 2020 8:00 AM | February 20, 2020 5:00 PM | 2020-02-20 | 0 |  | 4
650 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 126 | 1 day | February 27, 2020 8:00 AM | February 27, 2020 5:00 PM | 2020-02-27 | 0 |  | 4
651 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 127 | 1 day | March 5, 2020 8:00 AM | March 5, 2020 5:00 PM | 2020-03-05 | 0 |  | 4
652 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 128 | 1 day | March 12, 2020 8:00 AM | March 12, 2020 5:00 PM | 2020-03-12 | 0 |  | 4
653 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 129 | 1 day | March 19, 2020 8:00 AM | March 19, 2020 5:00 PM | 2020-03-19 | 0 |  | 4
654 | Yes | Auto Scheduled | SharePoint, DOORS and Document Approval Status Review 130 | 1 day | March 26, 2020 8:00 AM | March 26, 2020 5:00 PM | 2020-03-26 | 0 |  | 4
655 | Yes | Auto Scheduled | CM Audit and NC Closure | 586 days | December 20, 2017 8:00 AM | March 18, 2020 5:00 PM | 2020-03-18 | 0 |  | 3
656 | Yes | Auto Scheduled | CM Audit and NC Closure 1 | 1 day | December 20, 2017 8:00 AM | December 20, 2017 5:00 PM | 2017-12-20 | 1 |  | 4
657 | Yes | Auto Scheduled | CM Audit and NC Closure 2 | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM | 2018-01-17 | 1 |  | 4
658 | Yes | Auto Scheduled | CM Audit and NC Closure 3 | 1 day | February 21, 2018 8:00 AM | February 21, 2018 5:00 PM | 2018-02-21 | 1 |  | 4
659 | Yes | Auto Scheduled | CM Audit and NC Closure 4 | 1 day | March 21, 2018 8:00 AM | March 21, 2018 5:00 PM | 2018-03-21 | 1 |  | 4
660 | Yes | Auto Scheduled | CM Audit and NC Closure 5 | 1 day | April 18, 2018 8:00 AM | April 18, 2018 5:00 PM | 2018-04-18 | 1 |  | 4
661 | Yes | Auto Scheduled | CM Audit and NC Closure 6 | 1 day | May 16, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 |  | 4
662 | Yes | Auto Scheduled | CM Audit and NC Closure 7 | 1 day | June 20, 2018 8:00 AM | June 20, 2018 5:00 PM | 2018-06-20 | 1 |  | 4
663 | Yes | Auto Scheduled | CM Audit and NC Closure 8 | 1 day | July 18, 2018 8:00 AM | July 18, 2018 5:00 PM | 2018-07-18 | 1 |  | 4
664 | Yes | Auto Scheduled | CM Audit and NC Closure 9 | 1 day | August 15, 2018 8:00 AM | August 15, 2018 5:00 PM | 2018-08-15 | 1 |  | 4
665 | Yes | Auto Scheduled | CM Audit and NC Closure 10 | 1 day | September 19, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 |  | 4
666 | Yes | Auto Scheduled | CM Audit and NC Closure 11 | 1 day | October 17, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 |  | 4
667 | Yes | Auto Scheduled | CM Audit and NC Closure 12 | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 |  | 4
668 | Yes | Auto Scheduled | CM Audit and NC Closure 13 | 1 day | December 19, 2018 8:00 AM | December 19, 2018 5:00 PM | 2018-12-19 | 1 |  | 4
669 | Yes | Auto Scheduled | CM Audit and NC Closure 14 | 1 day | January 16, 2019 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 |  | 4
670 | Yes | Auto Scheduled | CM Audit and NC Closure 15 | 1 day | February 28, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 |  | 4
671 | Yes | Auto Scheduled | CM Audit and NC Closure 16 | 1 day | March 20, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 4
672 | Yes | Auto Scheduled | CM Audit and NC Closure 17 | 1 day | April 17, 2019 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 |  | 4
673 | Yes | Auto Scheduled | CM Audit and NC Closure 18 | 1 day | May 15, 2019 8:00 AM | May 15, 2019 5:00 PM | 2019-05-15 | 1 |  | 4
674 | Yes | Auto Scheduled | CM Audit and NC Closure 19 | 1 day | June 19, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 |  | 4
675 | Yes | Auto Scheduled | CM Audit and NC Closure 20 | 1 day | July 17, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
676 | Yes | Auto Scheduled | CM Audit and NC Closure 21 | 1 day | August 21, 2019 8:00 AM | August 21, 2019 5:00 PM | 2019-08-21 | 1 |  | 4
677 | Yes | Auto Scheduled | CM Audit and NC Closure 22 | 1 day | September 18, 2019 8:00 AM | September 18, 2019 5:00 PM | 2019-09-18 | 0 |  | 4
678 | Yes | Auto Scheduled | CM Audit and NC Closure 23 | 1 day | October 16, 2019 8:00 AM | October 16, 2019 5:00 PM | 2019-10-16 | 0 |  | 4
679 | Yes | Auto Scheduled | CM Audit and NC Closure 24 | 1 day | November 20, 2019 8:00 AM | November 20, 2019 5:00 PM | 2019-11-20 | 0 |  | 4
680 | Yes | Auto Scheduled | CM Audit and NC Closure 25 | 1 day | December 18, 2019 8:00 AM | December 18, 2019 5:00 PM | 2019-12-18 | 0 |  | 4
681 | Yes | Auto Scheduled | CM Audit and NC Closure 26 | 1 day | January 15, 2020 8:00 AM | January 15, 2020 5:00 PM | 2020-01-15 | 0 |  | 4
682 | Yes | Auto Scheduled | CM Audit and NC Closure 27 | 1 day | February 19, 2020 8:00 AM | February 19, 2020 5:00 PM | 2020-02-19 | 0 |  | 4
683 | Yes | Auto Scheduled | CM Audit and NC Closure 28 | 1 day | March 18, 2020 8:00 AM | March 18, 2020 5:00 PM | 2020-03-18 | 0 |  | 4
684 | Yes | Auto Scheduled | CI list, Work Product (CM Review) & Baseline Review | 147 days | January 1, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 |  | 3
685 | Yes | Auto Scheduled | Release 21.21.142.01 | 44 days | January 1, 2019 8:00 AM | March 3, 2019 5:00 PM | 2019-03-03 | 1 |  | 4
686 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 44 days | January 1, 2019 8:00 AM | March 3, 2019 5:00 PM | 2019-03-03 | 1 |  | 5
687 | Yes | Auto Scheduled | Work Product Review (CM) | 39 days | January 1, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 5
688 | Yes | Auto Scheduled | SharePoint Baseline Library Management activity | 6 days | February 22, 2019 8:00 AM | March 3, 2019 5:00 PM | 2019-03-03 | 1 |  | 5
689 | Yes | Auto Scheduled | Release 21.21.144 | 21 days | February 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 4
690 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 20 days | February 25, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 5
691 | Yes | Auto Scheduled | Work Product Review (CM) | 20 days | February 25, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 5
692 | Yes | Auto Scheduled | SharePoint Baseline Library Management activity | 2 days | March 22, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 5
693 | Yes | Auto Scheduled | Release 21.21.144.1 | 4 days | April 5, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 |  | 4
694 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 |  | 5
695 | Yes | Auto Scheduled | Work Product Review (CM) | 1 day | April 10, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 694 | 5
696 | Yes | Auto Scheduled | SharePoint Baseline Library Management activity | 1 day | April 10, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 694 | 5
697 | Yes | Auto Scheduled | Release 21.21.145 | 54 days | March 25, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
698 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 35 days | March 25, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 5
699 | Yes | Auto Scheduled | Work Product Review (CM) | 1 day | May 10, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 5
700 | Yes | Auto Scheduled | SharePoint Baseline Library Management activity | 2 days | June 5, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 5
701 | Yes | Auto Scheduled | Release 21.21.145.01 | 16 days | June 7, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 4
702 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 1 day | June 27, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 |  | 5
703 | Yes | Auto Scheduled | Work Product Review (CM) | 3 days | June 26, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 5
704 | Yes | Auto Scheduled | SharePoint Baseline Library Management activity | 2 days | June 7, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 5
705 | Yes | Auto Scheduled | Release 21.21.145.02 | 21 days | June 26, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 |  | 4
706 | Yes | Auto Scheduled | CI list Updation - Baseline applicability & Version | 19 days | June 26, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 |  | 5
707 | Yes | Auto Scheduled | Work Product Review (CM) | 2 days | July 23, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 706 | 5
708 | Yes | Auto Scheduled | Process Documentation | 743 days | January 17, 2017 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 1
709 | Yes | Auto Scheduled | Develop Project Management Plan (PMP) | 661 days | January 17, 2017 8:00 AM | July 31, 2019 5:00 PM | 2019-07-31 | 1 |  | 2
710 | Yes | Auto Scheduled | First Version of PMP | 280 days | January 17, 2017 8:00 AM | February 13, 2018 5:00 PM | 2018-02-13 | 1 |  | 3
711 | Yes | Auto Scheduled | Create PMP | 15 days | January 17, 2017 8:00 AM | February 6, 2017 5:00 PM | 2017-02-06 | 1 |  | 4
712 | Yes | Auto Scheduled | Reviewed by QA | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 4
713 | Yes | Auto Scheduled | PMP Updated | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 4
714 | Yes | Auto Scheduled | PMP Peer Reviewed | 1 day | February 5, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 | 713,750 | 4
715 | Yes | Auto Scheduled | Approved by Managers | 6 days | February 6, 2018 8:00 AM | February 13, 2018 5:00 PM | 2018-02-13 | 1 | 714 | 4
716 | Yes | Auto Scheduled | PMP Review Checklist | 2 days | February 5, 2018 8:00 AM | February 6, 2018 5:00 PM | 2018-02-06 | 1 | 714 | 4
717 | Yes | Auto Scheduled | Second Version of PMP | 123 days | April 16, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 3
718 | Yes | Auto Scheduled | PMP Update | 70 days | April 16, 2018 8:00 AM | July 20, 2018 5:00 PM | 2018-07-20 | 1 |  | 4
719 | Yes | Auto Scheduled | Reviewed by QA | 35 days | July 23, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 718 | 4
720 | Yes | Auto Scheduled | PMP Update | 15 days | September 10, 2018 8:00 AM | September 28, 2018 5:00 PM | 2018-09-28 | 1 | 719 | 4
721 | Yes | Auto Scheduled | PMP release | 3 days | October 1, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 720 | 4
722 | Yes | Auto Scheduled | PMP update | 84 days | November 28, 2018 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 3
723 | Yes | Auto Scheduled | Scope update | 7 days | November 28, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 4
724 | Yes | Auto Scheduled | Life cycle update | 18 days | December 7, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 723 | 4
725 | Yes | Auto Scheduled | Trainign Plan update | 3 days | December 14, 2018 8:00 AM | January 16, 2019 4:12 PM | 2019-01-16 | 1 | 724 | 4
726 | Yes | Auto Scheduled | Project governance update | 0 days | January 9, 2019 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 | 725 | 4
727 | Yes | Auto Scheduled | Redmine life cycle update | 2 days | January 14, 2019 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 726 | 4
728 | Yes | Auto Scheduled | PMP review/feedback | 1 wk | January 16, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 727 | 4
729 | Yes | Auto Scheduled | PMP update based on feedback | 11 days | January 22, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 | 728 | 4
730 | Yes | Auto Scheduled | PMP check list review | 29 days | February 6, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 | 729 | 4
731 | Yes | Auto Scheduled | PMP update based on feedback | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 730 | 4
732 | Yes | Auto Scheduled | PMP Approval | 0 days | March 25, 2019 5:00 PM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 731 | 4
733 | Yes | Auto Scheduled | PMP update | 13 days | July 15, 2019 8:00 AM | July 31, 2019 5:00 PM | 2019-07-31 | 1 |  | 3
734 | Yes | Auto Scheduled | Review of current PMP | 1 day | July 15, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 4
735 | Yes | Auto Scheduled | Update PMP | 1 day | July 16, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 734 | 4
736 | Yes | Auto Scheduled | PMP review/feedback | 2 days | July 17, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 | 735 | 4
737 | Yes | Auto Scheduled | PMP update based on feedback | 1 day | July 19, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 736 | 4
738 | Yes | Auto Scheduled | PMP check list review | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 737 | 4
739 | Yes | Auto Scheduled | PMP update based on feedback | 2 days | July 23, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 738 | 4
740 | Yes | Auto Scheduled | PMP Approval | 5 days | July 25, 2019 8:00 AM | July 31, 2019 5:00 PM | 2019-07-31 | 1 | 739 | 4
741 | Yes | Auto Scheduled | Quality Assurance Plan | 112 days | December 6, 2018 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 2
742 | Yes | Auto Scheduled | Develop Quality Assurance Plan | 24 days | December 6, 2018 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 |  | 3
743 | Yes | Auto Scheduled | Review and Update of the QA Plan | 0 days | January 22, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 742 | 3
744 | Yes | Auto Scheduled | Review and Update of the QA Plan | 17 days | February 28, 2019 8:00 AM | March 24, 2019 5:00 PM | 2019-03-24 | 1 |  | 3
745 | Yes | Auto Scheduled | Review and Update of the QA Plan | 10 days | April 29, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 744 | 3
746 | Yes | Auto Scheduled | Develop PRMP | 394 days | February 2, 2018 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 2
747 | Yes | Auto Scheduled | Create PRMP | 7 days | February 2, 2018 8:00 AM | February 12, 2018 5:00 PM | 2018-02-12 | 1 |  | 3
748 | Yes | Auto Scheduled | PRMP Peer Review | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 4
749 | Yes | Auto Scheduled | Reviewed by QA | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 4
750 | Yes | Auto Scheduled | PRMP Updated | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 4
751 | Yes | Auto Scheduled | Approved by Managers | 5 days | February 6, 2018 8:00 AM | February 12, 2018 5:00 PM | 2018-02-12 | 1 | 750 | 4
752 | Yes | Auto Scheduled | PRMP Review Checklist | 2 days | February 14, 2018 8:00 AM | February 15, 2018 5:00 PM | 2018-02-15 | 1 |  | 3
753 | Yes | Auto Scheduled | PRMP Update | 61 days | January 25, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 |  | 3
754 | Yes | Auto Scheduled | PRMP update | 4 days | January 25, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 4
755 | Yes | Auto Scheduled | Review/Feedback via TPL workproduct list | 3 days | January 31, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 | 754 | 4
756 | Yes | Auto Scheduled | PRMP update based on feedback | 1 day | February 5, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 | 755 | 4
757 | Yes | Auto Scheduled | PRMP review Checklist | 31 days | February 6, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 756 | 4
758 | Yes | Auto Scheduled | PRMP update based on feedback | 3 days | March 21, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 757 | 4
759 | Yes | Auto Scheduled | PRMP approval | 19 days | March 26, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 758 | 4 | Pending with Slavko
760 | Yes | Auto Scheduled | PRMP Update | 13 days | July 22, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 3
761 | Yes | Auto Scheduled | PRMP update | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 |  | 4
762 | Yes | Auto Scheduled | Review/Feedback via TPL workproduct list | 2 days | July 23, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 761 | 4
763 | Yes | Auto Scheduled | PRMP update based on feedback | 1 day | July 25, 2019 8:00 AM | July 25, 2019 5:00 PM | 2019-07-25 | 1 | 762 | 4
764 | Yes | Auto Scheduled | PRMP review Checklist | 1 day | July 26, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 763 | 4
765 | Yes | Auto Scheduled | PRMP update based on feedback | 3 days | July 29, 2019 8:00 AM | July 31, 2019 5:00 PM | 2019-07-31 | 1 | 764 | 4
766 | Yes | Auto Scheduled | PRMP approval | 5 days | August 1, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 | 765 | 4 | Pending with Slavko
767 | Yes | Auto Scheduled | Health Report | 1 day | January 17, 2018 8:00 AM | January 17, 2018 5:00 PM | 2018-01-17 | 1 |  | 2 | living document
768 | Yes | Auto Scheduled | Update RAID Log and clean file | 30 days | December 15, 2017 8:00 AM | January 25, 2018 5:00 PM | 2018-01-25 | 1 |  | 2
769 | Yes | Auto Scheduled | Develop Change Management Plan | 403 days | February 2, 2018 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 |  | 2
770 | Yes | Auto Scheduled | CHMP initial version | 142 days | February 2, 2018 8:00 AM | August 20, 2018 5:00 PM | 2018-08-20 | 1 |  | 3
771 | Yes | Auto Scheduled | Update Change Management Plan | 15 days | February 17, 2018 8:00 AM | March 9, 2018 5:00 PM | 2018-03-09 | 1 |  | 4
772 | Yes | Auto Scheduled | Reviewed by QA | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 | 771 | 4
773 | Yes | Auto Scheduled | CMP Updated | 2 days | February 2, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 | 772 | 4
774 | Yes | Auto Scheduled | CMP Peer Reviewed | 1 day | February 5, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 | 773 | 4
775 | Yes | Auto Scheduled | Approved by Managers | 6 days | February 6, 2018 8:00 AM | February 13, 2018 5:00 PM | 2018-02-13 | 1 | 774 | 4
776 | Yes | Auto Scheduled | CMP Review Checklist | 132 days | February 14, 2018 8:00 AM | August 20, 2018 5:00 PM | 2018-08-20 | 1 | 775 | 4
777 | Yes | Auto Scheduled | CHMP Update | 86 days | April 19, 2018 8:00 AM | August 16, 2018 5:00 PM | 2018-08-16 | 1 |  | 3
778 | Yes | Auto Scheduled | Update CMP | 86 days | April 19, 2018 8:00 AM | August 16, 2018 5:00 PM | 2018-08-16 | 1 |  | 4 | Need to provide new completion date
779 | Yes | Auto Scheduled | Reviewed by QA | 0 days | August 16, 2018 5:00 PM | August 16, 2018 5:00 PM | 2018-08-16 | 1 | 778 | 4 | Need to provide new completion date
780 | Yes | Auto Scheduled | CMP Updated | 0 days | August 16, 2018 5:00 PM | August 16, 2018 5:00 PM | 2018-08-16 | 1 | 779 | 4 | Need to provide new completion date
781 | Yes | Auto Scheduled | CHMP Update | 27 days | February 20, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 |  | 3
782 | Yes | Auto Scheduled | CHMP update | 2 days | February 20, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 4
783 | Yes | Auto Scheduled | Review/Feedback via TPL workproduct list | 5 days | February 22, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 782 | 4
784 | Yes | Auto Scheduled | CHMP update based on feedback | 5 days | March 1, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 | 783 | 4
785 | Yes | Auto Scheduled | CHMP check list review | 8 days | March 8, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 784 | 4
786 | Yes | Auto Scheduled | CHMP update based on feedback | 4 days | March 20, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 785 | 4
787 | Yes | Auto Scheduled | CHMP approval | 3 days | March 26, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 786 | 4
788 | Yes | Auto Scheduled | CHMP Update | 17 days | July 29, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 |  | 3
789 | Yes | Auto Scheduled | CHMP update | 2 days | July 29, 2019 8:00 AM | July 30, 2019 5:00 PM | 2019-07-30 | 1 |  | 4
790 | Yes | Auto Scheduled | Review/Feedback via TPL workproduct list | 5 days | July 31, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 789 | 4
791 | Yes | Auto Scheduled | CHMP update based on feedback | 1 day | August 7, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 | 790 | 4
792 | Yes | Auto Scheduled | CHMP check list review | 1 day | August 7, 2019 5:00 PM | August 8, 2019 5:00 PM | 2019-08-08 | 1 | 791 | 4
793 | Yes | Auto Scheduled | CHMP update based on feedback | 3 days | August 9, 2019 8:00 AM | August 13, 2019 5:00 PM | 2019-08-13 | 1 | 792 | 4
794 | Yes | Auto Scheduled | CHMP approval | 5 days | August 14, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 | 793 | 4
795 | Yes | Auto Scheduled | Configuration Management Plan | 394 days | September 11, 2017 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 2
796 | Yes | Auto Scheduled | Update CMP - First Version | 20 days | September 11, 2017 8:00 AM | October 6, 2017 5:00 PM | 2017-10-06 | 1 |  | 3
797 | Yes | Auto Scheduled | Review & Approval of CM Plan - First Version | 10 days | October 9, 2017 8:00 AM | October 20, 2017 5:00 PM | 2017-10-20 | 1 | 796 | 3
798 | Yes | Auto Scheduled | Update CMP - Second Version | 55 days | December 3, 2018 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 797 | 3
799 | Yes | Auto Scheduled | Review of CM Plan - Second Version | 13 days | February 18, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 | 798 | 3
800 | Yes | Auto Scheduled | Approval of CM Plan - Second Version | 7 days | March 7, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 799 | 3
801 | Yes | Auto Scheduled | Systems Integration Test Strategy | 209 days | June 11, 2018 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 |  | 2
802 | Yes | Auto Scheduled | Systems Integration Test Strategy | 40 days | June 11, 2018 8:00 AM | September 24, 2018 12:00 PM | 2018-09-24 | 1 | 950 | 3
803 | Yes | Auto Scheduled | System Integration Test Strategy Review Checklist | 4.5 days | September 24, 2018 1:00 PM | September 28, 2018 5:00 PM | 2018-09-28 | 1 | 802 | 3
804 | Yes | Auto Scheduled | System Integration Test Strategy Approval | 6 days | September 24, 2018 1:00 PM | October 2, 2018 12:00 PM | 2018-10-02 | 1 | 802 | 3
805 | Yes | Auto Scheduled | Systems Integration Test Strategy update | 11 days | March 4, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
806 | Yes | Auto Scheduled | Systems Integration Test Strategy Review | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 805 | 3
807 | Yes | Auto Scheduled | Systems Integration Test Strategy Appoval | 3 days | March 26, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 806 | 3
808 | Yes | Auto Scheduled | Systems Qualification Test Strategy | 205 days | June 15, 2018 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 |  | 2
809 | Yes | Auto Scheduled | System Qualification Test Strategy | 80 days | June 15, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 916 | 3
810 | Yes | Auto Scheduled | Systems Validation Strategy Review Checklist | 5.8 days | July 9, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 809 | 3
811 | Yes | Auto Scheduled | System Validation Test Strategy Approval | 1 day | October 5, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 809 | 3
812 | Yes | Auto Scheduled | System Qualification Test Strategy | 13 days | March 4, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 811 | 3
813 | Yes | Auto Scheduled | Systems Validation Strategy Review Checklist | 2 days | March 21, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 812 | 3
814 | Yes | Auto Scheduled | System Validation Test Strategy Approval | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 813 | 3
815 | Yes | Auto Scheduled | TPL Project Tracker | 10 days | February 15, 2018 8:00 AM | February 28, 2018 5:00 PM | 2018-02-28 | 1 |  | 2
816 | Yes | Auto Scheduled | Develop Project Tracker document | 2 days | February 15, 2018 8:00 AM | February 16, 2018 5:00 PM | 2018-02-16 | 1 |  | 3
817 | Yes | Auto Scheduled | Reviewed by QA | 3 days | February 19, 2018 8:00 AM | February 21, 2018 5:00 PM | 2018-02-21 | 1 | 816 | 3
818 | Yes | Auto Scheduled | Project Tracker Updated Updated | 5 days | February 22, 2018 8:00 AM | February 28, 2018 5:00 PM | 2018-02-28 | 1 | 817 | 3
819 | Yes | Auto Scheduled | Engineering Timing Plan Creation | 233 days | January 22, 2018 8:00 AM | December 12, 2018 5:00 PM | 2018-12-12 | 1 |  | 2
820 | Yes | Auto Scheduled | First Version created | 0 days | December 12, 2018 8:00 AM | December 12, 2018 8:00 AM | 2018-12-12 | 1 |  | 3
821 | Yes | Auto Scheduled | Reviewed and approved by HW Team | 0.9 days | January 22, 2018 8:00 AM | January 22, 2018 4:12 PM | 2018-01-22 | 1 | 820 | 3
822 | Yes | Auto Scheduled | Reviewed and approved by ME Team | 15 days | January 22, 2018 8:00 AM | February 9, 2018 5:00 PM | 2018-02-09 | 1 | 820 | 3
823 | Yes | Auto Scheduled | Reviewed and approved by SW Team | 0.9 days | January 22, 2018 8:00 AM | January 22, 2018 4:12 PM | 2018-01-22 | 1 | 820 | 3
824 | Yes | Auto Scheduled | Reviewed and approved by PM Team | 1 day | January 23, 2018 5:00 PM | December 12, 2018 5:00 PM | 2018-12-12 | 1 | 820 | 3
825 | Yes | Auto Scheduled | Reviewed and approved by SW Validation Team | 1 day | January 23, 2018 5:00 PM | December 12, 2018 5:00 PM | 2018-12-12 | 1 | 820 | 3
826 | Yes | Auto Scheduled | Approved by Managers | 5 days | February 14, 2018 8:00 AM | February 20, 2018 5:00 PM | 2018-02-20 | 1 |  | 3
827 | Yes | Auto Scheduled | Training Schedule | 291 days | October 26, 2017 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 2
828 | Yes | Auto Scheduled | Tools Training | 52 days | September 26, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 3
829 | Yes | Auto Scheduled | Sharepoint | 1 day | December 6, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 4
830 | Yes | Auto Scheduled | DOORS | 1 day | December 6, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 4
831 | No | Auto Scheduled | Redmine | 1 day | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
832 | Yes | Auto Scheduled | Vector CAST session 1 | 1 day | September 26, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 |  | 4
833 | Yes | Auto Scheduled | Vector CAST session 2 | 1 day | September 27, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 4
834 | Yes | Auto Scheduled | Functional Safety session 1 | 1 day | October 26, 2017 8:00 AM | October 26, 2017 5:00 PM | 2017-10-26 | 1 |  | 3
835 | Yes | Auto Scheduled | Functional Safety session 2 | 1 day | May 16, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 |  | 3
836 | Yes | Auto Scheduled | ASPICE | 1 day | March 26, 2018 8:00 AM | March 26, 2018 5:00 PM | 2018-03-26 | 1 |  | 3
837 | Yes | Auto Scheduled | Cyber Security | 1 day | June 13, 2018 8:00 AM | June 13, 2018 5:00 PM | 2018-06-13 | 1 |  | 3
838 | Yes | Auto Scheduled | GM Questionnaires and Procedure | 743 days | January 17, 2017 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 2
839 | Yes | Auto Scheduled | HSCAN Questionnaire - CG4090 | 139 days | January 23, 2018 8:00 AM | August 3, 2018 5:00 PM | 2018-08-03 | 1 |  | 3 | Submit to Supply Power is missing
840 | Yes | Auto Scheduled | HSCAN Questionnaire - CG4090 GM Approval | 1 wk | August 6, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 839 | 3
841 | Yes | Auto Scheduled | HSCAN Questionnaire Update | 2 days | September 24, 2018 8:00 AM | September 25, 2018 5:00 PM | 2018-09-25 | 1 |  | 3
842 | Yes | Auto Scheduled | HSCAN Questionnaire Approval | 12 days | September 26, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 | 841 | 3
843 | Yes | Auto Scheduled | LIN Questionnaire - CG4080 | 0 days | December 15, 2017 8:00 AM | December 15, 2017 8:00 AM | 2017-12-15 | 1 |  | 3 | Submit to Supply Power is missing
844 | Yes | Auto Scheduled | LIN Questionnaire - CG4080 GM Approval | 2 wks | August 10, 2018 8:00 AM | August 23, 2018 5:00 PM | 2018-08-23 | 1 | 843 | 3
845 | Yes | Auto Scheduled | Ethernet Questionnaire - CG4077 | 19 days | January 23, 2018 8:00 AM | February 16, 2018 5:00 PM | 2018-02-16 | 1 |  | 3
846 | Yes | Auto Scheduled | Ethernet Questionnaire - CG4077 GM Approval | 1.2 wks | August 16, 2018 8:00 AM | August 23, 2018 5:00 PM | 2018-08-23 | 1 | 845 | 3
847 | Yes | Auto Scheduled | Diagnostic validation Questionnaire –CG4422 | 5 days | January 17, 2017 8:00 AM | January 23, 2017 5:00 PM | 2017-01-23 | 1 |  | 3
848 | Yes | Auto Scheduled | OTA Questionnaire - CG4879 | 5 days | January 17, 2018 8:00 AM | January 23, 2018 5:00 PM | 2018-01-23 | 1 |  | 3
849 | Yes | Auto Scheduled | FUSA (DIA)---CG2694 | 88 days | January 17, 2018 8:00 AM | May 18, 2018 5:00 PM | 2018-05-18 | 1 |  | 3
850 | Yes | Auto Scheduled | Flash Bootloader Test Procedure -----CG3687 | 5 days | March 19, 2018 8:00 AM | March 23, 2018 5:00 PM | 2018-03-23 | 1 |  | 3
851 | Yes | Auto Scheduled | CG4879 Test Procedure | 79 days | May 21, 2018 8:00 AM | September 6, 2018 5:00 PM | 2018-09-06 | 1 |  | 3 | Update Actual Start date to 5/21 once baselined
852 | Yes | Auto Scheduled | CG4748 Test Plan | 5 days | April 19, 2018 8:00 AM | April 25, 2018 5:00 PM | 2018-04-25 | 1 |  | 3
853 | Yes | Auto Scheduled | CG4111 - Global B Serial Data and Diagnostics Test Plan | 57 days | September 24, 2018 8:00 AM | December 11, 2018 5:00 PM | 2018-12-11 | 1 |  | 3
854 | Yes | Auto Scheduled | CG4111 Approval from GM | 3 days | December 12, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 | 853 | 3 | CG4111 has to be added to every software testing for CAN compliance
855 | Yes | Auto Scheduled | CG4073 Diagnostics Questionnaire | 18 days | December 5, 2018 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 |  | 3
856 | Yes | Auto Scheduled | CG4073 Diagnostics Questionnaire GM feedback | 5 days | January 14, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 | 855 | 3
857 | Yes | Auto Scheduled | CG4073 Dianostics Questionnaire Update | 29 days | January 21, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 856 | 3
858 | Yes | Auto Scheduled | CG4073 Diagsnostics Questionnaire GM Feedback | 10 days | March 1, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 857 | 3
859 | Yes | Auto Scheduled | CG4073 Diagnostics Questionnaire Update | 10 days | May 20, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 858 | 3
860 | Yes | Auto Scheduled | CG4073 CG4073 Diagsnostics Questionnaire GM Approval | 10 days | June 3, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 | 859 | 3
861 | Yes | Auto Scheduled | Indicator Alerts | 0 days | March 19, 2018 8:00 AM | March 19, 2018 8:00 AM | 2018-03-19 | 1 |  | 3
862 | Yes | Auto Scheduled | GMW17219 Open Source Document Process (IVER) | 0 days | July 17, 2018 8:00 AM | July 17, 2018 8:00 AM | 2018-07-17 | 1 |  | 3 | Supplier to provide an updated OSS BoM with any changes to OSS. If no changes have been made, the supplier simply needs to re-sign and re-date the OSS BoM, and send it back to us for another approval.
863 | Yes | Auto Scheduled | CGXXX VCRI | 10 days | May 27, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 3
864 | Yes | Auto Scheduled | Cyber Security | 427 days | November 1, 2017 8:00 AM | June 20, 2019 5:00 PM | 2019-06-20 | 1 |  | 3
865 | Yes | Auto Scheduled | DIA Complete | 36.4 wks | May 8, 2018 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 |  | 4
866 | Yes | Auto Scheduled | CG3532 Hardening requirement tracing | 170 days | January 8, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 |  | 4 | One pending item to be tested with sw140
867 | Yes | Auto Scheduled | GM Vehicle Cybersecurity Questionnaire - Supplier Cryptographic Library Usage | 60 days | November 1, 2017 8:00 AM | January 23, 2018 5:00 PM | 2018-01-23 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
868 | Yes | Auto Scheduled | Cybersecurity Capability Assessment Questionnaire | 1 day | July 17, 2018 8:00 AM | July 17, 2018 5:00 PM | 2018-07-17 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
869 | Yes | Auto Scheduled | SAQ | 1 day | July 17, 2018 8:00 AM | July 17, 2018 5:00 PM | 2018-07-17 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
870 | Yes | Auto Scheduled | GM Service Programming System Non-Disclose Agreement | 1 day | July 17, 2018 8:00 AM | July 17, 2018 5:00 PM | 2018-07-17 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
871 | Yes | Auto Scheduled | Supplier Provisioning Portal Access Request Form | 76 days | November 1, 2017 8:00 AM | February 14, 2018 5:00 PM | 2018-02-14 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
872 | Yes | Auto Scheduled | GB IECS NDA Questionnaire | 16 days | November 1, 2017 8:00 AM | November 22, 2017 5:00 PM | 2017-11-22 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
873 | Yes | Auto Scheduled | Security Peripheral Review Template | 10 days | November 1, 2017 8:00 AM | November 14, 2017 5:00 PM | 2017-11-14 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
874 | Yes | Auto Scheduled | Message Authentication Design Review Template | 357 days | November 1, 2017 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
875 | Yes | Auto Scheduled | Complete Review Templeate | 259 days | November 1, 2017 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 |  | 5
876 | Yes | Auto Scheduled | GM Review | 20 days | October 30, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 875 | 5
877 | Yes | Auto Scheduled | Update Template based on the feedback from GM Phase 1 (3 items) | 5 days | February 11, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 876 | 5
878 | Yes | Auto Scheduled | Update Template based on the feedback from GM Phase 2 (4 items) | 9 days | February 18, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 877 | 5
879 | Yes | Auto Scheduled | GM Review and Approval | 10 days | March 1, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 878 | 5 | No feedback from GM has been provided. Tracked in CySe meeting with GM by Cacho
880 | Yes | Auto Scheduled | Cyber-Security Design Review | 59 days | March 21, 2018 8:00 AM | June 11, 2018 5:00 PM | 2018-06-11 | 1 |  | 4 | Timing will be confirmed with ETAS on 7/19
881 | Yes | Auto Scheduled | Cyber Security Final Validation Review and Final RAT | 37 days | May 1, 2019 8:00 AM | June 20, 2019 5:00 PM | 2019-06-20 | 1 |  | 4
882 | Yes | Auto Scheduled | Cyber Security Final Validation Review and Final RAT (initial) | 12 days | May 1, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 |  | 5
883 | Yes | Auto Scheduled | GM review and Approval | 10 days | May 17, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 | 882 | 5
884 | Yes | Auto Scheduled | Update from NSI | 5 days | May 31, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 883 | 5
885 | Yes | Auto Scheduled | Final Review and approval from GM | 10 days | June 7, 2019 8:00 AM | June 20, 2019 5:00 PM | 2019-06-20 | 1 | 884 | 5
886 | Yes | Auto Scheduled | GMW17219 Open Source Document Process (VTC) | 5 days | November 18, 2019 8:00 AM | November 22, 2019 5:00 PM | 2019-11-22 | 0 |  | 3 | Supplier to provide a final updated OSS BoM with any changes to OSS. If no changes have been made, the supplier simply needs to re-sign and re-date the OSS BoM, and send it back to us for the final approval
887 | Yes | Auto Scheduled | Requirement Analysis | 303 days | November 22, 2017 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 1
888 | Yes | Auto Scheduled | Requirement Gathering and Analysis | 303 days | November 22, 2017 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 2
889 | Yes | Auto Scheduled | Gathering Customer Requirements | 30 days | November 20, 2018 8:00 AM | December 31, 2018 5:00 PM | 2018-12-31 | 1 |  | 3
890 | Yes | Auto Scheduled | Allocating Customer Requirements to Competencies | 15 days | January 1, 2018 8:00 AM | January 2, 2019 12:00 PM | 2019-01-02 | 1 | 889 | 3
891 | Yes | Auto Scheduled | Requirement Analysis on RFQ and PWR SUPP packages | 45 days | November 22, 2017 8:00 AM | February 6, 2018 5:00 PM | 2018-02-06 | 1 |  | 3
892 | Yes | Auto Scheduled | CTRS update and competency allocation | 5 days | January 30, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 |  | 3
893 | Yes | Auto Scheduled | Query Log Completion for RFQ and Supp Power | 61 days | January 20, 2018 8:00 AM | April 16, 2018 5:00 PM | 2018-04-16 | 1 |  | 3
894 | Yes | Auto Scheduled | Create Requirement Analysis Plan for CTRS reference Documents | 31 days | January 29, 2018 8:00 AM | March 12, 2018 5:00 PM | 2018-03-12 | 1 |  | 3
895 | Yes | Manually Scheduled | Perform Requirement Analysis on CTRS references | 55 days | February 2, 2018 8:00 AM | April 19, 2018 5:00 PM | 2018-04-19 | 1 |  | 3
896 | Yes | Auto Scheduled | EE Analysis | 41 days | February 2, 2018 8:00 AM | March 30, 2018 5:00 PM | 2018-03-30 | 1 |  | 4
897 | Yes | Auto Scheduled | ME Analysis | 19 days | February 2, 2018 8:00 AM | February 28, 2018 5:00 PM | 2018-02-28 | 1 |  | 4
898 | Yes | Auto Scheduled | SW Analysis | 52 days | February 2, 2018 8:00 AM | April 16, 2018 5:00 PM | 2018-04-16 | 1 |  | 4
899 | Yes | Auto Scheduled | TPL Analysis | 52 days | February 2, 2018 8:00 AM | April 16, 2018 5:00 PM | 2018-04-16 | 1 |  | 4
900 | Yes | Auto Scheduled | Review Resuls from Req Analysis | 24.4 days | March 16, 2018 8:00 AM | April 19, 2018 11:12 AM | 2018-04-19 | 1 | 896,897,898,899 | 4
901 | Yes | Auto Scheduled | Query Log Completion for CTRS reference document | 66.6 days | April 19, 2018 11:12 AM | July 24, 2018 5:00 PM | 2018-07-24 | 1 | 900 | 3 | GM has cancelled reviews to wait for CTRS139
902 | Yes | Auto Scheduled | Software CTRS analysis | 24 days | April 23, 2018 8:00 AM | May 24, 2018 5:00 PM | 2018-05-24 | 1 |  | 3
903 | Yes | Auto Scheduled | Develop System Requirements Specifications | 254 days | January 30, 2018 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 3
904 | Yes | Auto Scheduled | Create First Version of Systems Req. Spec | 17 days | February 2, 2018 8:00 AM | February 26, 2018 5:00 PM | 2018-02-26 | 1 |  | 4
905 | Yes | Auto Scheduled | Create TSR | 10 days | February 2, 2018 8:00 AM | February 15, 2018 5:00 PM | 2018-02-15 | 1 |  | 5
906 | Yes | Auto Scheduled | Release for Review | 2 days | February 16, 2018 8:00 AM | February 19, 2018 5:00 PM | 2018-02-19 | 1 | 905 | 5
907 | Yes | Auto Scheduled | Reviewed by QA | 5 days | February 16, 2018 8:00 AM | February 22, 2018 5:00 PM | 2018-02-22 | 1 | 905 | 5
908 | Yes | Auto Scheduled | Update based on feedback | 5 days | February 20, 2018 8:00 AM | February 26, 2018 5:00 PM | 2018-02-26 | 1 | 906 | 5
909 | Yes | Auto Scheduled | Create Second Version of Systems Requirement Spec | 12 days | May 14, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 |  | 4
910 | Yes | Auto Scheduled | Release for Review | 2 days | May 14, 2018 8:00 AM | May 15, 2018 5:00 PM | 2018-05-15 | 1 | 908 | 5
911 | Yes | Auto Scheduled | Reviewed by QA and Team | 5 days | May 16, 2018 8:00 AM | May 22, 2018 5:00 PM | 2018-05-22 | 1 | 910 | 5
912 | Yes | Auto Scheduled | Update based on feedback | 5 days | May 23, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 | 911 | 5
913 | Yes | Auto Scheduled | Create Third Version of Systems Requirement Spec | 12 days | May 30, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 4
914 | Yes | Auto Scheduled | Release for Review | 2 days | May 30, 2018 8:00 AM | May 31, 2018 5:00 PM | 2018-05-31 | 1 | 912 | 5
915 | Yes | Auto Scheduled | Reviewed by QA and team | 5 days | June 1, 2018 8:00 AM | June 7, 2018 5:00 PM | 2018-06-07 | 1 | 914 | 5
916 | Yes | Auto Scheduled | Update based on feedback | 5 days | June 8, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 | 915 | 5
917 | Yes | Auto Scheduled | Create Forth Version of Systems Requirement Spec | 16 days | June 1, 2018 8:00 AM | June 22, 2018 5:00 PM | 2018-06-22 | 1 |  | 4
918 | Yes | Auto Scheduled | Release for review | 6 days | June 1, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 | 914 | 5
919 | Yes | Auto Scheduled | Reviewed by QA and Team | 5 days | June 11, 2018 8:00 AM | June 15, 2018 5:00 PM | 2018-06-15 | 1 | 918 | 5
920 | Yes | Auto Scheduled | Update based on feedback | 5 days | June 18, 2018 8:00 AM | June 22, 2018 5:00 PM | 2018-06-22 | 1 | 919 | 5
921 | Yes | Auto Scheduled | Create Fifth Version of systems Requirement Spec | 10 days | June 11, 2018 8:00 AM | June 22, 2018 5:00 PM | 2018-06-22 | 1 |  | 4
922 | Yes | Auto Scheduled | Release for review | 10 days | June 11, 2018 8:00 AM | June 22, 2018 5:00 PM | 2018-06-22 | 1 | 918 | 5
923 | No | Auto Scheduled | Reviewed by QA and Team | 35 days | June 25, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 922 | 5
924 | No | Auto Scheduled | Update based on feedback | 5 days | August 13, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 | 923 | 5
925 | Yes | Auto Scheduled | Create Sixth Version of systems Requirement Spec | 74 days | June 25, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 |  | 4 | Include PCE 026
926 | Yes | Auto Scheduled | Release for review | 21 days | June 25, 2018 8:00 AM | July 23, 2018 5:00 PM | 2018-07-23 | 1 | 922 | 5
927 | Yes | Auto Scheduled | Review by SYS5 of SRS 5.0 and SRS 6.0 | 25 days | June 29, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 |  | 5
928 | Yes | Auto Scheduled | Review by Software SYS of SRS 5.0 and SRS 6.0 | 60 days | June 29, 2018 8:00 AM | September 24, 2018 5:00 PM | 2018-09-24 | 1 |  | 5 | Tracked in RAID issue 41. Reschedule is needed after updating issue with Mauro Lopez
929 | Yes | Auto Scheduled | Review by HW team of SRS 5.0 and SRS 6.0 | 30 days | June 29, 2018 8:00 AM | August 9, 2018 5:00 PM | 2018-08-09 | 1 |  | 5
930 | Yes | Auto Scheduled | Review by ME team of SRS 5.0 and SRS 6.0 | 30 days | June 29, 2018 8:00 AM | August 13, 2018 5:00 PM | 2018-08-13 | 1 |  | 5
931 | Yes | Auto Scheduled | Update based on feedback | 25 days | August 27, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 927,928,929,930 | 5
932 | Yes | Auto Scheduled | Reviewed by QA of SRS 5.0 and SRS 6.0 | 3 days | October 2, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 931 | 5
933 | No | Auto Scheduled | Create Seventh Version of Systems Requirements Spec | 21 days | October 5, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 |  | 4 | Tasks are now tracked as part of each software cadence starting on 21.21.143
934 | No | Auto Scheduled | Release for review | 1 day | October 5, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 932 | 5
935 | No | Auto Scheduled | Review by HW team of SRS 7.0 | 20 days | October 8, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 | 934 | 5
936 | Yes | Auto Scheduled | Requirements Clarification | 40 days | November 12, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 4
937 | Yes | Auto Scheduled | Compliance Specs (CAN, LIN, Ethernet, Bootloader) | 40 days | November 12, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 5
938 | Yes | Auto Scheduled | Bootloader | 5 days | November 12, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 6
939 | Yes | Auto Scheduled | CAN | 28 days | November 12, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 6
940 | Yes | Auto Scheduled | LIN | 11 days | November 12, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 |  | 6
941 | Yes | Auto Scheduled | Ethernet | 1.5 days | November 29, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 | 940,939,938 | 6
942 | Yes | Auto Scheduled | Systems Requirements Spec | 40 days | November 12, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 |  | 5
943 | Yes | Auto Scheduled | GB Specs from May | 10 days | November 12, 2018 8:00 AM | November 27, 2018 5:00 PM | 2018-11-27 | 1 |  | 6
944 | Yes | Auto Scheduled | CTRS | 12 days | November 28, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 | 943 | 6
945 | Yes | Auto Scheduled | Close rejections from SRS | 6 days | December 14, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 | 944 | 6
946 | Yes | Auto Scheduled | Traceability | 166 days | June 1, 2018 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 4
947 | Yes | Auto Scheduled | CTRS to SRS | 40 days | June 1, 2018 8:00 AM | July 26, 2018 5:00 PM | 2018-07-26 | 1 |  | 5
948 | Yes | Auto Scheduled | SRS to SFS | 50 days | July 27, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 947 | 5 | Pending to determine the progress based on links
949 | Yes | Auto Scheduled | SRS to SYS5 Test Cases | 45 days | November 19, 2018 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 5 | Progress updated. Need to determine based on links
950 | Yes | Auto Scheduled | System Architecture document | 147 days | January 30, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 912 | 4
951 | Yes | Auto Scheduled | PCEs | 400 days | January 22, 2018 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 1
952 | Yes | Auto Scheduled | PCE 0E3 Implement Global B ASIL B requirements | 24 days | January 22, 2018 8:00 AM | February 22, 2018 5:00 PM | 2018-02-22 | 1 |  | 2
953 | Yes | Auto Scheduled | Create PCE | 3 days | January 22, 2018 8:00 AM | January 24, 2018 5:00 PM | 2018-01-24 | 1 |  | 3
954 | Yes | Auto Scheduled | Analysis and approval | 21 days | January 25, 2018 8:00 AM | February 22, 2018 5:00 PM | 2018-02-22 | 1 |  | 3
955 | Yes | Auto Scheduled | Software | 20 days | January 25, 2018 8:00 AM | February 21, 2018 5:00 PM | 2018-02-21 | 1 | 953 | 4
956 | Yes | Auto Scheduled | Software Systems | 21 days | January 25, 2018 8:00 AM | February 22, 2018 5:00 PM | 2018-02-22 | 1 | 953 | 4
957 | Yes | Auto Scheduled | PCE 004 - Remove or modify the added LIN circuitry | 25 days | February 12, 2018 8:00 AM | March 16, 2018 5:00 PM | 2018-03-16 | 1 |  | 2
958 | Yes | Auto Scheduled | Create PCE | 22 days | February 12, 2018 8:00 AM | March 13, 2018 5:00 PM | 2018-03-13 | 1 |  | 3
959 | Yes | Auto Scheduled | Analysis and approval | 3 days | March 14, 2018 8:00 AM | March 16, 2018 5:00 PM | 2018-03-16 | 1 |  | 3
960 | Yes | Auto Scheduled | Hardware | 3 days | March 14, 2018 8:00 AM | March 16, 2018 5:00 PM | 2018-03-16 | 1 | 958 | 4
961 | Yes | Auto Scheduled | PCE 012 - MY22 E2YB Fuel Door Arrow | 100 days | January 18, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 2
962 | Yes | Auto Scheduled | Create PCE | 1 day | January 18, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 3
963 | Yes | Auto Scheduled | Analysis and approval | 99 days | January 21, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
964 | Yes | Auto Scheduled | Hardware | 19 days | January 21, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 962 | 4
965 | Yes | Auto Scheduled | Mechanical | 12 days | January 21, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 | 962 | 4
966 | Yes | Auto Scheduled | Software | 99 days | January 21, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 962 | 4
967 | Yes | Auto Scheduled | TPL/Systems | 49 days | January 21, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 962 | 4
968 | Yes | Auto Scheduled | PCE 019 - Production backlight LED change Internal (march 2018) | 81 days | March 1, 2018 8:00 AM | June 21, 2018 5:00 PM | 2018-06-21 | 1 |  | 2
969 | Yes | Auto Scheduled | Create PCE | 1 day | March 1, 2018 8:00 AM | March 1, 2018 5:00 PM | 2018-03-01 | 1 |  | 3
970 | Yes | Auto Scheduled | Analysis and approval | 80 days | March 2, 2018 8:00 AM | June 21, 2018 5:00 PM | 2018-06-21 | 1 |  | 3
971 | Yes | Auto Scheduled | Hardware | 80 days | March 2, 2018 8:00 AM | June 21, 2018 5:00 PM | 2018-06-21 | 1 | 969 | 4
972 | Yes | Auto Scheduled | Mechanical | 4 days | March 2, 2018 8:00 AM | March 7, 2018 5:00 PM | 2018-03-07 | 1 | 969 | 4
973 | Yes | Auto Scheduled | PCE 020 - Inner case on production tooling | 6 days | March 8, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 |  | 2
974 | Yes | Auto Scheduled | Create PCE | 1 day | March 8, 2018 8:00 AM | March 8, 2018 5:00 PM | 2018-03-08 | 1 |  | 3
975 | Yes | Auto Scheduled | Analysis and approval | 5 days | March 9, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 |  | 3
976 | Yes | Auto Scheduled | Mechanical | 5 days | March 9, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 | 974 | 4
977 | Yes | Auto Scheduled | PCE 021 - Add mountain rail to housing (march 2018) | 2 days | March 8, 2018 8:00 AM | March 9, 2018 5:00 PM | 2018-03-09 | 1 |  | 2
978 | Yes | Auto Scheduled | Create PCE | 1 day | March 8, 2018 8:00 AM | March 8, 2018 5:00 PM | 2018-03-08 | 1 |  | 3
979 | Yes | Auto Scheduled | Analysis and approval | 1 day | March 9, 2018 8:00 AM | March 9, 2018 5:00 PM | 2018-03-09 | 1 |  | 3
980 | Yes | Auto Scheduled | Mechanical | 1 day | March 9, 2018 8:00 AM | March 9, 2018 5:00 PM | 2018-03-09 | 1 | 978 | 4
981 | Yes | Auto Scheduled | PCE 022 - Redline change (Cancelled) | 64 days | April 11, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 |  | 2 | PCE is now combined with PCE 028. PCE applicable for PV. Timing will be updated for PV after DV testing is completed.
982 | Yes | Auto Scheduled | Create PCE | 1 day | April 11, 2018 8:00 AM | April 11, 2018 5:00 PM | 2018-04-11 | 1 |  | 3
983 | Yes | Auto Scheduled | Analysis and approval | 63 days | April 12, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 |  | 3
984 | Yes | Auto Scheduled | Hardware | 63 days | April 12, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 | 982 | 4
985 | Yes | Auto Scheduled | Mechanical | 10 days | April 12, 2018 8:00 AM | April 25, 2018 5:00 PM | 2018-04-25 | 1 | 982 | 4
986 | Yes | Auto Scheduled | Software | 25 days | April 12, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 | 982 | 4
987 | Yes | Auto Scheduled | PCE 023 - FUSA changes May 2018 | 46 days | May 7, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 |  | 2
988 | Yes | Auto Scheduled | Create PCE | 1 day | May 7, 2018 8:00 AM | May 7, 2018 5:00 PM | 2018-05-07 | 1 |  | 3
989 | Yes | Auto Scheduled | Analysis and approval | 45 days | May 8, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 |  | 3
990 | Yes | Auto Scheduled | Hardware | 45 days | May 8, 2018 8:00 AM | July 9, 2018 5:00 PM | 2018-07-09 | 1 | 988 | 4
991 | Yes | Auto Scheduled | PCE 024 - Matt Finish Jelcon internal | 3 days | June 12, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 2
992 | Yes | Auto Scheduled | Create PCE | 1 day | June 12, 2018 8:00 AM | June 12, 2018 5:00 PM | 2018-06-12 | 1 |  | 3
993 | Yes | Auto Scheduled | Analysis and approval | 2 days | June 13, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 3
994 | Yes | Auto Scheduled | Mechanical | 2 days | June 13, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 | 992 | 4
995 | No | Auto Scheduled | PCE 025 - Packing foam change for production internal (cancelled) | 6 days | June 12, 2018 8:00 AM | June 19, 2018 5:00 PM | 2018-06-19 | 1 |  | 2 | PCE Cancelled
996 | No | Auto Scheduled | Analysis | 5 days | June 12, 2018 8:00 AM | June 18, 2018 5:00 PM | 2018-06-18 | 1 |  | 3
997 | No | Auto Scheduled | Mechanical | 1 wk | June 12, 2018 8:00 AM | June 18, 2018 5:00 PM | 2018-06-18 | 1 |  | 4
998 | No | Auto Scheduled | Approval | 1 day | June 19, 2018 8:00 AM | June 19, 2018 5:00 PM | 2018-06-19 | 1 | 997 | 3
999 | Yes | Auto Scheduled | PCE 026 - New GB specs May 2018 | 54 days | July 2, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 2
1000 | Yes | Auto Scheduled | Create PCE | 1 day | July 2, 2018 8:00 AM | July 2, 2018 5:00 PM | 2018-07-02 | 1 |  | 3
1001 | Yes | Auto Scheduled | Analysis and approval | 53 days | July 3, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 3
1002 | Yes | Auto Scheduled | Software Design | 52 days | July 3, 2018 8:00 AM | September 12, 2018 5:00 PM | 2018-09-12 | 1 | 1000 | 4
1003 | Yes | Auto Scheduled | Software Systems | 42 days | July 3, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 1000 | 4
1004 | Yes | Auto Scheduled | Software Verification | 53 days | July 3, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 | 1000 | 4
1005 | Yes | Auto Scheduled | PCE 027 - MY22 9BYG | 11 days | July 13, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 2 | PCE for new variation
1006 | Yes | Auto Scheduled | Create PCE | 1 day | July 13, 2018 8:00 AM | July 13, 2018 5:00 PM | 2018-07-13 | 1 |  | 3
1007 | Yes | Auto Scheduled | Analysis and approval | 10 days | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 3
1008 | Yes | Auto Scheduled | TPL/Systems | 10 days | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1006 | 4
1009 | Yes | Auto Scheduled | Software Design | 10 days | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1006 | 4
1010 | Yes | Auto Scheduled | Software Systems | 10 days | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1006 | 4
1011 | Yes | Auto Scheduled | Software Verification | 10 days | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1006 | 4
1012 | Yes | Auto Scheduled | Hardware | 9 days | July 16, 2018 8:00 AM | July 26, 2018 5:00 PM | 2018-07-26 | 1 | 1006 | 4
1013 | Yes | Auto Scheduled | Mechanical | 4 days | July 16, 2018 8:00 AM | July 19, 2018 5:00 PM | 2018-07-19 | 1 | 1006 | 4
1014 | Yes | Auto Scheduled | PCE 028 - New applique math | 32 days | August 15, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 2 | PCE applicable for PV. Timing will be updated for PV after DV testing is completed.
1015 | Yes | Auto Scheduled | Create PCE | 1 day | August 15, 2018 8:00 AM | August 15, 2018 5:00 PM | 2018-08-15 | 1 |  | 3
1016 | Yes | Auto Scheduled | Analysis and approval | 4 days | August 16, 2018 8:00 AM | August 21, 2018 5:00 PM | 2018-08-21 | 1 |  | 3
1017 | Yes | Auto Scheduled | Mechanical | 1 day | August 16, 2018 8:00 AM | August 16, 2018 5:00 PM | 2018-08-16 | 1 | 1015 | 4
1018 | Yes | Auto Scheduled | Hardware | 3 days | August 16, 2018 8:00 AM | August 20, 2018 5:00 PM | 2018-08-20 | 1 | 1015 | 4
1019 | Yes | Auto Scheduled | Software Development | 4 days | August 16, 2018 8:00 AM | August 21, 2018 5:00 PM | 2018-08-21 | 1 | 1015 | 4
1020 | Yes | Auto Scheduled | Software SYS | 4 days | August 16, 2018 8:00 AM | August 21, 2018 5:00 PM | 2018-08-21 | 1 | 1015 | 4
1021 | Yes | Auto Scheduled | Software Verification | 1 day | August 16, 2018 8:00 AM | August 16, 2018 5:00 PM | 2018-08-16 | 1 | 1015 | 4
1022 | Yes | Auto Scheduled | TPL | 2 days | August 16, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 | 1015 | 4
1023 | Yes | Auto Scheduled | JPN feeback | 5 days | August 20, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1022 | 3
1024 | Yes | Auto Scheduled | Customer EWO | 15 days | August 27, 2018 8:00 AM | September 14, 2018 5:00 PM | 2018-09-14 | 1 | 1023 | 3
1025 | Yes | Auto Scheduled | EWO approval at NSI | 8 days | September 17, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 1024 | 3
1026 | Yes | Auto Scheduled | EWO release from GM to NSI | 1 day | September 27, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 | 1025 | 3
1027 | Yes | Auto Scheduled | PCE 029 - MY22 9BYG 2D Flat Applique | 53 days | October 2, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 2
1028 | Yes | Auto Scheduled | Create PCE | 1 day | October 2, 2018 8:00 AM | October 2, 2018 5:00 PM | 2018-10-02 | 1 |  | 3
1029 | Yes | Auto Scheduled | Analysis and approval | 52 days | October 3, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 3
1030 | Yes | Auto Scheduled | Mechanical | 50 days | October 3, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 | 1028 | 4
1031 | Yes | Auto Scheduled | PCE 030 - GWM3172 April 2018 | 179 days | November 13, 2018 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 2
1032 | Yes | Auto Scheduled | Create PCE | 1 day | November 13, 2018 8:00 AM | November 13, 2018 5:00 PM | 2018-11-13 | 1 |  | 3
1033 | Yes | Auto Scheduled | Analysis and approval | 178 days | November 14, 2018 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 3
1034 | Yes | Auto Scheduled | Hardware | 11 days | November 14, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 1032 | 4 | Pending with GM to confirm swtich that can be used
1035 | No | Auto Scheduled | Mechanical | 5 days | July 15, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 1032 | 4
1036 | No | Auto Scheduled | Software | 5 days | July 15, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 1032 | 4
1037 | No | Auto Scheduled | TPL/Systems | 5 days | July 15, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 1032 | 4
1038 | Yes | Auto Scheduled | Test Labs | 5 days | July 15, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 1032 | 4
1039 | Yes | Auto Scheduled | PCE 031 - New GB Specs Sep 2018 | 59 days | March 18, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 2
1040 | Yes | Auto Scheduled | Create PCE | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
1041 | Yes | Auto Scheduled | Analysis and approval | 58 days | March 19, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
1042 | Yes | Auto Scheduled | Software | 58 days | March 19, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 1040 | 4
1043 | Yes | Auto Scheduled | TPL/Systems | 7 days | March 19, 2019 8:00 AM | March 27, 2019 5:00 PM | 2019-03-27 | 1 | 1040 | 4
1044 | Yes | Auto Scheduled | PCE 032 - MY21-MY22 E2UB-E2YB Applique Change Jan 2019 | 9 days | February 1, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 |  | 2
1045 | Yes | Auto Scheduled | Create PCE | 1 day | February 1, 2019 8:00 AM | February 2, 2019 5:00 PM | 2019-02-02 | 1 |  | 3
1046 | Yes | Auto Scheduled | Analysis and approval | 8 days | February 4, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 |  | 3
1047 | Yes | Auto Scheduled | Mechanical | 8 days | February 4, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 1045 | 4
1048 | Yes | Auto Scheduled | TPL/Systems | 8 days | February 4, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 1045 | 4
1049 | Yes | Auto Scheduled | PCE 033 - MY21-MY22 E2UB-E2YB WOW Change Jan2019 | 126 days | February 1, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 2
1050 | Yes | Auto Scheduled | Create PCE | 1 day | February 1, 2019 8:00 AM | February 2, 2019 5:00 PM | 2019-02-02 | 1 |  | 3
1051 | Yes | Auto Scheduled | Analysis and approval | 125 days | February 4, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 3
1052 | Yes | Auto Scheduled | Software | 123 days | February 4, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 1050 | 4
1053 | Yes | Auto Scheduled | TPL/Systems | 22 days | February 4, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 1050 | 4
1054 | Yes | Auto Scheduled | PCE 034 - Mounting Tab ribs add | 6 days | March 18, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 2
1055 | Yes | Auto Scheduled | Create PCE | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
1056 | Yes | Auto Scheduled | Analysis and approval | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 3
1057 | Yes | Auto Scheduled | Mechanical | 2 days | March 19, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 1055 | 4
1058 | Yes | Auto Scheduled | TPL / Systems | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 1055 | 4
1059 | Yes | Auto Scheduled | PCE 035 - Bumper Pad desing change | 6 days | March 18, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 2
1060 | Yes | Auto Scheduled | Create PCE | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
1061 | Yes | Auto Scheduled | Analysis and approval | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 3
1062 | Yes | Auto Scheduled | Mechanical | 2 days | March 19, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 1060 | 4
1063 | Yes | Auto Scheduled | TPL / Systems | 5 days | March 19, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 1060 | 4
1064 | Yes | Auto Scheduled | PCE 036 - Low Level Fuel LED change | 100 days | March 18, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 2
1065 | Yes | Auto Scheduled | Create PCE | 1 day | March 18, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
1066 | Yes | Auto Scheduled | Analysis and approval | 99 days | March 19, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
1067 | Yes | Auto Scheduled | Mechanical | 2 days | March 19, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 1065 | 4
1068 | Yes | Auto Scheduled | TPL / Systems | 59 days | March 19, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 1065 | 4
1069 | Yes | Auto Scheduled | Hardware | 97 days | March 19, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 1065 | 4 | HW manager approval pending only
1070 | Yes | Auto Scheduled | Mechanical | 1 day | March 20, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 1065 | 4
1071 | Yes | Auto Scheduled | Software | 87 days | March 19, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 1065 | 4 | Manager approval only
1072 | Yes | Auto Scheduled | Five Phases | 283 days | June 22, 2018 8:00 AM | July 23, 2019 5:00 PM | 2019-07-23 | 1 |  | 1
1073 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase_001 Comm Issue with Customer | 68 days | June 22, 2018 8:00 AM | September 25, 2018 5:00 PM | 2018-09-25 | 1 |  | 2
1074 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 002 ENV Test Plan 5 Phases | 62 days | July 12, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 |  | 2
1075 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 003 Ethernet Disconnection | 9 days | January 25, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 |  | 2
1076 | Yes | Auto Scheduled | Reopen 5 Phases | 1 day | January 25, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 |  | 3
1077 | Yes | Auto Scheduled | Update document with new information | 4 days | January 28, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1076 | 3
1078 | Yes | Auto Scheduled | Review with GM | 1 day | February 1, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1077 | 3
1079 | Yes | Auto Scheduled | Update 5 phases | 3 days | February 4, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 | 1078 | 3
1080 | No | Auto Scheduled | Review with NSI management and agreement on Action Plan | 1 day | February 11, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 | 1079 | 3
1081 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 004 Key Slot 12 Reset Issue | 4 days | September 10, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 2
1082 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 005 DIT failure sw21.21.140.2 | 6 days | October 3, 2018 8:00 AM | October 10, 2018 5:00 PM | 2018-10-10 | 1 |  | 2
1083 | Yes | Auto Scheduled | Create 5 phase with issue description | 1 day | October 3, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 3
1084 | Yes | Auto Scheduled | Reproduce issue | 1 day | October 4, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 1083 | 3
1085 | Yes | Auto Scheduled | Root cause analysis | 2 days | October 5, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 1084 | 3
1086 | Yes | Auto Scheduled | Software implemantation | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 | 1085 | 3
1087 | Yes | Auto Scheduled | Demo with DPS at NSI | 1 day | October 10, 2018 8:00 AM | October 10, 2018 5:00 PM | 2018-10-10 | 1 | 1086 | 3
1088 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 006 Key Slot Multiple Provisioning Issue | 116 days | September 14, 2018 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 2
1089 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | October 3, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 3
1090 | Yes | Auto Scheduled | Issue analysis to identify watchdog trigger | 7 days | September 14, 2018 8:00 AM | September 24, 2018 5:00 PM | 2018-09-24 | 1 |  | 3
1091 | Yes | Auto Scheduled | Take measurements of all task execution timing | 7 days | September 25, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 1090 | 3
1092 | Yes | Auto Scheduled | Identify module causing the watch dog reset | 1 day | October 4, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 1091 | 3
1093 | Yes | Auto Scheduled | Gather timing measurement for SHE module processing and Work with Cypress on further root cause | 1 day | October 5, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 1092 | 3
1094 | Yes | Auto Scheduled | Validate DPS testing with RID 200 | 1.4 wks | December 12, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 2278 | 3
1095 | Yes | Auto Scheduled | Revalidate with SW 21.21.142.1 | 16 days | February 1, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2499 | 3 | Validation pending with sw 21.21.142.1 due to delya in sw release
1096 | No | Auto Scheduled | Provide Impact Analysis on other solutions to GM | 12 days | January 16, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 |  | 3
1097 | Yes | Auto Scheduled | 21E3_E2Ux 5 007 Phase DV Software IPC shuts down | 115 days | October 1, 2018 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 2
1098 | Yes | Auto Scheduled | Create 5 Phase with issue description | 1 day | October 1, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 3
1099 | Yes | Auto Scheduled | Issue Debugging | 9 days | October 2, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 1098 | 3
1100 | Yes | Auto Scheduled | Implementation for Power resume handle shifting from CAN Error message for DID to CAN busload | 3 days | October 15, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 | 1099 | 3
1101 | Yes | Auto Scheduled | Verification of Fix | 28 days | October 18, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 1100 | 3
1102 | Yes | Auto Scheduled | Update 5 Phase with respective test results | 9 days | November 27, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 | 1101 | 3
1103 | Yes | Auto Scheduled | Release new CANoe tool. | 28 days | January 16, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3 | DV SW release is delayed
1104 | Yes | Auto Scheduled | Retest with new CANoe tool | 10 days | February 25, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1103 | 3
1105 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 008 DV Software LIN bus issue | 109 days | October 9, 2018 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 2
1106 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 |  | 3
1107 | Yes | Auto Scheduled | Reproduce issue with current DV software | 10 days | October 10, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 1106 | 3
1108 | Yes | Auto Scheduled | Retest issue with updated CANoe panel | 20 days | October 24, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 | 1107 | 3
1109 | Yes | Auto Scheduled | Reproduce issue with IVER software (21.21.140.4) | 2 days | November 21, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 1108 | 3
1110 | Yes | Auto Scheduled | Contact GM TCI about the issue | 10 days | November 27, 2018 8:00 AM | December 10, 2018 5:00 PM | 2018-12-10 | 1 | 1109 | 3
1111 | Yes | Auto Scheduled | Reproduct the issue at GM TCI | 5 days | November 29, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1110 | 3
1112 | Yes | Auto Scheduled | Determine if root cause is in application code | 2 days | December 6, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 | 1111 | 3
1113 | No | Auto Scheduled | Release new application code | 10 days | December 10, 2018 8:00 AM | December 21, 2018 5:00 PM | 2018-12-21 | 1 | 1112 | 3
1114 | Yes | Auto Scheduled | Integrate test code | 5 days | December 10, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 | 1113 | 3
1115 | Yes | Auto Scheduled | Verify the fix at NSI | 40 days | December 17, 2018 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1114 | 3
1116 | Yes | Auto Scheduled | Run test with new DV software | 10 days | February 25, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1115 | 3
1117 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 009 DV Software Tacho | 109 days | October 9, 2018 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 2
1118 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 |  | 3
1119 | Yes | Auto Scheduled | Issue Debugging | 3 days | October 10, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 1118 | 3
1120 | Yes | Auto Scheduled | Implementation for Gauge Configuration | 2 days | October 15, 2018 8:00 AM | October 16, 2018 5:00 PM | 2018-10-16 | 1 | 1119 | 3
1121 | Yes | Auto Scheduled | Verification of Fix | 3 days | October 17, 2018 8:00 AM | October 19, 2018 5:00 PM | 2018-10-19 | 1 | 1120 | 3
1122 | Yes | Auto Scheduled | Update 5 Phase with respective results | 16 days | October 22, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 1121 | 3
1123 | Yes | Auto Scheduled | Release new software version | 28 days | January 16, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3 | DV SW release is delayed
1124 | Yes | Auto Scheduled | Re-test with releases software version. | 5 days | March 4, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1123 | 3
1125 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 010 ECU Unlock Issue | 18 days | October 12, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 2
1126 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 011 OTA Reflash | 196 days | October 9, 2018 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 2
1127 | Yes | Auto Scheduled | Create 5 phase with description | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 |  | 3
1128 | Yes | Auto Scheduled | Fix ERR Correction Issue | 4 days | October 10, 2018 8:00 AM | October 15, 2018 5:00 PM | 2018-10-15 | 1 | 1127 | 3
1129 | Yes | Auto Scheduled | Perform White Box testing to validate the fix | 9 days | October 16, 2018 8:00 AM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 1128 | 3
1130 | Yes | Auto Scheduled | Release the Software for Validation Team to test the fix | 0 days | October 26, 2018 5:00 PM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 1129 | 3
1131 | Yes | Auto Scheduled | Provide Feedback to SW team if need/SW Team to fix the issue if need | 1 day | October 29, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 | 1130 | 3
1132 | Yes | Auto Scheduled | Investigate why tool is sending reset request | 5 days | October 30, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 | 1131 | 3
1133 | Yes | Auto Scheduled | Re-run test with new tool 2.3.5 and software to generate separate log files to be able to analyze. | 17 days | November 6, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 1132 | 3
1134 | Yes | Auto Scheduled | Analyze logs to determine if OTA tool or IPC software is the issue. | 12 days | December 3, 2018 8:00 AM | December 18, 2018 5:00 PM | 2018-12-18 | 1 | 1133 | 3
1135 | Yes | Auto Scheduled | Provoide Delta packages to SWE6 | 11 days | December 19, 2018 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 1134 | 3 | Delayed due to 5 Phase 21 / Pending approval from GM to be CAT 4 and start testing
1136 | Yes | Auto Scheduled | Re-evaluate timeline for OTA Reliability and get Plan approved with GM | 7 days | January 17, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1135 | 3
1137 | No | Auto Scheduled | Run 10000 cycles | 40 days | January 28, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 1136 | 3
1138 | Yes | Auto Scheduled | Root cause "memory fault" | 10 days | May 28, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 3
1139 | Yes | Auto Scheduled | Root cause "pending fault" issue | 4 days | May 20, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 |  | 3
1140 | Yes | Auto Scheduled | Run test at CGM bench | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 | 1139 | 3
1141 | Yes | Auto Scheduled | Root cause reponses on HSCAN instead of Ethernet | 3 days | May 27, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 1140 | 3
1142 | Yes | Auto Scheduled | Release new sw21.21.145 | 1 day | May 30, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 | 1141 | 3
1143 | Yes | Auto Scheduled | Run test at CGM bench | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 1142 | 3
1144 | Yes | Auto Scheduled | Run 10000 cycles | 25 days | June 3, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 1143 | 3
1145 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 012 DV_SnR_Failure | 107 days | October 16, 2018 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 |  | 2
1146 | Yes | Auto Scheduled | Create 5 phase with issue description | 1 day | October 16, 2018 8:00 AM | October 16, 2018 5:00 PM | 2018-10-16 | 1 |  | 3
1147 | Yes | Auto Scheduled | Root cause analysis at Sibina | 3 days | October 17, 2018 8:00 AM | October 19, 2018 5:00 PM | 2018-10-19 | 1 | 1146 | 3
1148 | Yes | Auto Scheduled | Run DoE with new pointer | 10 days | October 22, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 | 1147 | 3
1149 | Yes | Auto Scheduled | Tear down failed parts | 9 days | October 17, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 | 1146 | 3
1150 | Yes | Auto Scheduled | New pointer assembly with supplier | 1 day | November 26, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 |  | 3
1151 | Yes | Auto Scheduled | Review new pointers with GM | 2 days | November 27, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 | 1150 | 3
1152 | Yes | Auto Scheduled | DOE BSR with new pointers | 5 days | November 29, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1151 | 3
1153 | Yes | Auto Scheduled | New pointer jig fabrication | 12 days | January 2, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 3
1154 | Yes | Auto Scheduled | Build C1UB pointer samples off process | 14 days | January 18, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 | 1153 | 3
1155 | Yes | Auto Scheduled | Retest with C1UB PV testing updated pointers | 25 days | February 7, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 1154 | 3
1156 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 013 DV_MTG TAB_Failure | 96 days | October 18, 2018 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 |  | 2
1157 | Yes | Auto Scheduled | Create 5 phase with issue description | 1 day | October 18, 2018 8:00 AM | October 18, 2018 5:00 PM | 2018-10-18 | 1 |  | 3
1158 | Yes | Auto Scheduled | CAE Static Analysis | 6 days | October 19, 2018 8:00 AM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 1157 | 3
1159 | Yes | Auto Scheduled | CAE Dynamic Analysis | 15 days | October 29, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 | 1158 | 3
1160 | Yes | Auto Scheduled | Review with GM on root cause | 1 day | November 19, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 1159 | 3
1161 | Yes | Auto Scheduled | Customer drawing and data release to Team Center | 1 day | November 14, 2018 8:00 AM | November 14, 2018 5:00 PM | 2018-11-14 | 1 |  | 3
1162 | No | Auto Scheduled | Issue EWO | 3 wks | November 15, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1161 | 3
1163 | Yes | Auto Scheduled | ENV Test Plan for DV03 | 4.2 wks | November 28, 2018 8:00 AM | January 9, 2019 5:00 PM | 2019-01-09 | 1 |  | 3
1164 | Yes | Auto Scheduled | ENV Test PlanDV03 Review and internal approval | 10 days | January 10, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1163 | 3
1165 | Yes | Auto Scheduled | ENV Test Plan for DV03 GM Approval | 1.4 wks | January 24, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1164 | 3
1166 | Yes | Auto Scheduled | Test Request Sheet | 2 days | January 15, 2019 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 |  | 3
1167 | Yes | Auto Scheduled | Math data to Team Center | 12 days | December 13, 2018 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 |  | 3
1168 | Yes | Auto Scheduled | Kick off tooling | 1 day | December 17, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 |  | 3
1169 | Yes | Auto Scheduled | Tooling Modification (Visor & Outercase) | 15 days | December 18, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 | 1168 | 3
1170 | Yes | Auto Scheduled | Mold in color parts | 1.4 wks | January 8, 2019 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 1169 | 3
1171 | Yes | Auto Scheduled | Ship to Branson | 1 wk | January 17, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1170 | 3
1172 | Yes | Auto Scheduled | Laser welding for new desing | 1 wk | February 4, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 |  | 3
1173 | Yes | Auto Scheduled | Ship to new Sabina | 0.6 wks | February 11, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 1172 | 3
1174 | Yes | Auto Scheduled | Build IPCs | 1 day | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 1173 | 3
1175 | Yes | Auto Scheduled | Retest countermeasure (DV03 Testing) | 2 wks | February 15, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 1174 | 3
1176 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 014 DV Software TFT Blue Lines | 81 days | November 2, 2018 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 2
1177 | Yes | Auto Scheduled | Create 5 phase with issue description | 1 day | November 2, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 |  | 3
1178 | Yes | Auto Scheduled | Open redmine for software team. | 0 days | November 2, 2018 8:00 AM | November 2, 2018 8:00 AM | 2018-11-02 | 1 | 1177 | 3
1179 | Yes | Auto Scheduled | Test previous software version to confirm if the issue is present. | 4 days | November 5, 2018 8:00 AM | November 8, 2018 5:00 PM | 2018-11-08 | 1 | 1178 | 3
1180 | Yes | Auto Scheduled | Update 5 Phase with results of previous software (add pictures) | 1 day | November 9, 2018 8:00 AM | November 9, 2018 5:00 PM | 2018-11-09 | 1 | 1179 | 3
1181 | Yes | Auto Scheduled | Root cause analysis – identify changes between the 2 software versions | 2 days | November 12, 2018 8:00 AM | November 13, 2018 5:00 PM | 2018-11-13 | 1 | 1180 | 3
1182 | No | Auto Scheduled | Root cause analysis – identify the changes for IVER (port configs) | 6 days | November 14, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 1181 | 3
1183 | Yes | Auto Scheduled | Fix software | 5 days | November 22, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 | 1182 | 3
1184 | Yes | Auto Scheduled | Test new software and update results in 5 Phase | 2 days | November 29, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 1183 | 3 | DV SW release is delayed
1185 | Yes | Auto Scheduled | Release new software version | 50 days | December 3, 2018 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1184 | 3
1186 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 015 DV Software EMC 3.5.2 CI Nominal 12v Lines | 188 days | November 2, 2018 8:00 AM | July 23, 2019 5:00 PM | 2019-07-23 | 1 |  | 2
1187 | Yes | Auto Scheduled | Create 5 Phase with description | 0 days | November 2, 2018 8:00 AM | November 2, 2018 8:00 AM | 2018-11-02 | 1 |  | 3
1188 | Yes | Auto Scheduled | Open redmine for software team. | 1 day | November 2, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 | 1187 | 3
1189 | Yes | Auto Scheduled | Analyze CANoe panel to confirm issue is in the tool | 7 days | November 5, 2018 8:00 AM | November 13, 2018 5:00 PM | 2018-11-13 | 1 | 1188 | 3
1190 | Yes | Auto Scheduled | Reproduce issue at EMC lab | 7 days | November 5, 2018 8:00 AM | November 13, 2018 5:00 PM | 2018-11-13 | 1 | 1188 | 3
1191 | Yes | Auto Scheduled | Test updated CANoe configuration | 4 days | November 14, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 1190 | 3
1192 | Yes | Auto Scheduled | Release new CANoe tool. | 27 days | January 17, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3 | DV SW release is delayed
1193 | Yes | Auto Scheduled | Retest with new CANoe tool | 10 days | February 25, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1192 | 3
1194 | Yes | Auto Scheduled | HW review and investigation | 10 days | March 11, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 1193 | 3 | Pending to review with Antonio Jimenez, who is in PTO
1195 | Yes | Auto Scheduled | SW review and investigation | 55 days | March 25, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 1194 | 3
1196 | Yes | Auto Scheduled | Test DV code at test lab | 9 days | June 10, 2019 8:00 AM | June 20, 2019 5:00 PM | 2019-06-20 | 1 | 1195 | 3
1197 | Yes | Auto Scheduled | 5 Phase update | 16 days | June 21, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 1196 | 3
1198 | Yes | Auto Scheduled | 5 Phase review and approval by management | 4 days | July 17, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 1197 | 3
1199 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 23, 2019 8:00 AM | July 23, 2019 5:00 PM | 2019-07-23 | 1 | 1198 | 3
1200 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 016 OTA timing | 184 days | November 2, 2018 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 2
1201 | Yes | Auto Scheduled | Create 5 Phase with issue description | 0 days | November 2, 2018 8:00 AM | November 2, 2018 8:00 AM | 2018-11-02 | 1 |  | 3
1202 | Yes | Auto Scheduled | Investigate the issue behavior through DPS | 22 days | November 2, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1201 | 3
1203 | Yes | Auto Scheduled | Investigate the issue behavior through Vflash | 22 days | November 2, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1201 | 3
1204 | Yes | Auto Scheduled | Conduct a Design analysis to improve performance | 22 days | November 2, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1201 | 3 | Delayed due to 5 Phase 21
1205 | Yes | Auto Scheduled | Perform changes to implement the design change | 7 days | December 6, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 | 1202;1203;1204 | 3
1206 | Yes | Auto Scheduled | Validate the Change through Integration testing | 13 days | December 17, 2018 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 1205 | 3
1207 | Yes | Auto Scheduled | Perform testing at CGM Bench | 13 days | December 17, 2018 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 1205 | 3
1208 | Yes | Auto Scheduled | Validate the improvement through OTA Tool | 11 days | January 17, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1207 | 3
1209 | Yes | Auto Scheduled | Improve SW flashing time | 10 days | April 22, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 | 1208 | 3
1210 | Yes | Auto Scheduled | Test at GM bench | 7 days | May 6, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 1209 | 3
1211 | Yes | Auto Scheduled | Implement Pending Response | 7 days | May 15, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 | 1210 | 3
1212 | Yes | Auto Scheduled | Test at GM bench | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 | 1211 | 3
1213 | Yes | Auto Scheduled | Root cause issue with HSCAN response | 3 days | May 27, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 1212 | 3
1214 | Yes | Auto Scheduled | Release new software version | 1 day | May 30, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 | 1213 | 3
1215 | Yes | Auto Scheduled | Test at GM bench | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 1214 | 3
1216 | Yes | Auto Scheduled | Run test with 21.21.145 Official version | 10 days | June 3, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 | 1215 | 3
1217 | Yes | Auto Scheduled | Run test with sw21.21.145.01 official version | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 1216 | 3
1218 | Yes | Auto Scheduled | 5 Phase update | 1 day | July 15, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 1217 | 3
1219 | Yes | Auto Scheduled | 5 Phase review and approval by management | 1 day | July 16, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 1218 | 3
1220 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 17, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 1219 | 3
1221 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_017_Sleep failure sw21.21.140.4.pptx | 96 days | October 26, 2018 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 2
1222 | Yes | Auto Scheduled | Create 5 Phase with issue description | 0 days | October 26, 2018 8:00 AM | October 26, 2018 8:00 AM | 2018-10-26 | 1 |  | 3
1223 | Yes | Auto Scheduled | Reproduce issue manually (40 Cycles) | 1 day | October 26, 2018 8:00 AM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 1222 | 3
1224 | Yes | Auto Scheduled | Reproduce issue automatically (>200 Cycles) | 1 day | October 26, 2018 8:00 AM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 1222 | 3
1225 | Yes | Auto Scheduled | Trace back the DET through GHS debugger and call stack | 3 days | October 29, 2018 8:00 AM | October 31, 2018 5:00 PM | 2018-10-31 | 1 | 1224 | 3
1226 | Yes | Auto Scheduled | Identify block causing issue | 3 days | October 29, 2018 8:00 AM | October 31, 2018 5:00 PM | 2018-10-31 | 1 | 1224 | 3
1227 | Yes | Auto Scheduled | RAM Buffer update | 1 day | November 1, 2018 8:00 AM | November 1, 2018 5:00 PM | 2018-11-01 | 1 | 1226 | 3
1228 | Yes | Auto Scheduled | Temporary fix | 1 day | November 1, 2018 8:00 AM | November 1, 2018 5:00 PM | 2018-11-01 | 1 | 1226 | 3
1229 | No | Auto Scheduled | Test temporary fix with automated script | 1 day | November 2, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 | 1228 | 3
1230 | No | Auto Scheduled | Software validation testing | 7 days | November 2, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 1228 | 3
1231 | Yes | Auto Scheduled | Permanent solution with Vector | 6 days | November 2, 2018 8:00 AM | November 9, 2018 5:00 PM | 2018-11-09 | 1 | 1228 | 3
1232 | Yes | Auto Scheduled | Analyze AUTOSAR requirements for Write Verify | 2 days | November 2, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 | 1228 | 3
1233 | Yes | Auto Scheduled | Analyze Vector Techcnical reference manual for NVM/FEE | 2 days | November 2, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 | 1228 | 3
1234 | Yes | Auto Scheduled | Analyze Task Priority | 2 days | November 2, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 | 1228 | 3
1235 | Yes | Auto Scheduled | Check with Vector if any NVM block can create the issue | 6 days | November 2, 2018 8:00 AM | November 9, 2018 5:00 PM | 2018-11-09 | 1 | 1228 | 3
1236 | Yes | Auto Scheduled | Run 1000 cycles to confirm the issue is fixed | 3 days | February 25, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 3
1237 | Yes | Auto Scheduled | Implement permanent fix with sw21.21.144 | 7 days | February 28, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1236 | 3
1238 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 018 DV Bumper Pad Break Failure | 75 days | November 2, 2018 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 2 | Implement for production only, not for prototype.
1239 | Yes | Auto Scheduled | Create 5 Phase with issue description | 0 days | November 2, 2018 8:00 AM | November 2, 2018 8:00 AM | 2018-11-02 | 1 |  | 3
1240 | Yes | Auto Scheduled | Review failed cluster | 1 day | November 2, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 | 1239 | 3
1241 | Yes | Auto Scheduled | Study potential root cause and alternate solutions | 6 days | November 5, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 1240 | 3
1242 | Yes | Auto Scheduled | Root cause confirmation through CAE | 6 days | November 5, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 1240 | 3
1243 | Yes | Auto Scheduled | Feasibility confirmation of alternate design from GM IPC Eng | 18 days | November 13, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 | 1242 | 3
1244 | Yes | Auto Scheduled | Alternate fix: Add rib to front of bumper pad | 12 days | November 13, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 1242 | 3 | Requested by Alex Debek during meeting
1245 | Yes | Auto Scheduled | Feasibility confirmation of alternate design from molding | 5 days | November 13, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 1242 | 3
1246 | Yes | Auto Scheduled | Feasibility confirmation of alternate design from welding | 5 days | November 13, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 1242 | 3
1247 | Yes | Auto Scheduled | Provide updated design for visor change to GM | 1 day | December 7, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 | 124312451246 | 3 | Need to create a radious as much as tool allows
1248 | Yes | Auto Scheduled | GM to review updated design provided by NSI | 39 days | December 10, 2018 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1247 | 3
1249 | Yes | Auto Scheduled | Implementation | 10 days | February 1, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 1243,1245,1246,1248 | 3
1250 | No | Auto Scheduled | PV testing | 10 days | September 9, 2019 8:00 AM | September 20, 2019 5:00 PM | 2019-09-20 | 0 | 1249 | 3 | Task is part of PV testing
1251 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 019 DID 272 NRC issue (problem tracked in 5 phase 026 with all the CG4117 issues) | 9 days | November 5, 2018 8:00 AM | November 15, 2018 5:00 PM | 2018-11-15 | 1 |  | 2
1252 | Yes | Auto Scheduled | Create 5 Phase with issue description | 1 day | November 5, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 |  | 3
1253 | Yes | Auto Scheduled | Investigate Time out and NRC issue | 8 days | November 6, 2018 8:00 AM | November 15, 2018 5:00 PM | 2018-11-15 | 1 | 1252 | 3
1254 | No | Auto Scheduled | Design a solution to solve the issue | 32 days | November 16, 2018 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 1253 | 3
1255 | No | Auto Scheduled | Perform White Box Testing to validate the fix | 11 days | January 17, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1254 | 3
1256 | No | Auto Scheduled | Perform validation testing to confirm the fix | 12 days | February 1, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1255 | 3
1257 | No | Auto Scheduled | Release the software to GMTCI for their testing | 10 days | February 19, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 1256 | 3
1258 | Yes | Auto Scheduled | 21E3_E2Ux 5 Phase 020 DV Software Intermittent Short Circuit Failure | 166 days | November 14, 2018 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 2
1259 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | November 16, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 3
1260 | Yes | Auto Scheduled | Reproduce issue | 1 day | November 14, 2018 8:00 AM | November 14, 2018 5:00 PM | 2018-11-14 | 1 |  | 3
1261 | Yes | Auto Scheduled | Test with ADC Calibration updated (suggested by Cypress) | 1 day | November 14, 2018 8:00 AM | November 14, 2018 5:00 PM | 2018-11-14 | 1 |  | 3
1262 | Yes | Auto Scheduled | Determine if issue is due to software implementation | 3 days | November 15, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 1260,1261 | 3
1263 | Yes | Auto Scheduled | Test with IVER software 21.21.140.4 | 8 days | November 28, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 | 1262 | 3
1264 | Yes | Auto Scheduled | Review solution with GM | 5 days | January 28, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1263 | 3 | Pending confirmation from GM validation team
1265 | Yes | Auto Scheduled | Approval of change by GM | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 1264 | 3 | Under review with GM and HW team. Rescheduled due to delay with GM
1266 | No | Auto Scheduled | System Design Sheet update with new hysteresis values | 4 days | April 1, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 1265 | 3 | Under review with GM and HW team
1267 | No | Auto Scheduled | Approve System Design Sheet | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 1266 | 3
1268 | No | Auto Scheduled | Software update and release | 5 days | April 10, 2019 8:00 AM | April 16, 2019 5:00 PM | 2019-04-16 | 1 | 1267 | 3
1269 | No | Auto Scheduled | Test and confirm issue is fixed | 5 days | April 17, 2019 8:00 AM | April 23, 2019 5:00 PM | 2019-04-23 | 1 | 1268 | 3
1270 | Yes | Auto Scheduled | Update Test Plan | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 3
1271 | Yes | Auto Scheduled | Review and approve test plan | 10 days | April 15, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 | 1270 | 3
1272 | Yes | Auto Scheduled | Test Plan approval in CEMENT | 16 days | April 29, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 1271 | 3
1273 | Yes | Auto Scheduled | Build DV04 parts | 20 days | April 15, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 1270 | 3
1274 | Yes | Auto Scheduled | DV04 Test Execution | 25 days | May 23, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 |  | 3
1275 | Yes | Auto Scheduled | Intermittent Short Circuit | 9 days | May 23, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 1272,1273 | 4
1276 | Yes | Auto Scheduled | Continues Short Circuit | 3 days | June 5, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 1275 | 4
1277 | Yes | Auto Scheduled | CEMENT GM Approval | 13 days | June 10, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 | 1276 | 4
1278 | Yes | Auto Scheduled | 5 Phase update | 2 days | June 27, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 1277 | 3
1279 | Yes | Auto Scheduled | 5 Phase review and approval by management | 2 days | July 1, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 | 1278 | 3
1280 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 1279 | 3
1281 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_021_ECU goes to Sleep after reflash (sw21.21.142.1) | 19 days | January 29, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 2 | Acitivities related to 65% BOR
1282 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | January 29, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 3 | Acitivities related to 65% BOR
1283 | Yes | Auto Scheduled | Add details to the 5 phase | 2 days | January 30, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1282 | 3 | Acitivities related to 65% BOR
1284 | Yes | Auto Scheduled | Review with GM | 1 day | February 1, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1283 | 3 | Acitivities related to 65% BOR
1285 | Yes | Auto Scheduled | Fix Programming Session to do software reset | 1 day | February 4, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 | 1284 | 3 | Acitivities related to 65% BOR
1286 | Yes | Auto Scheduled | Fix Network Management Issue | 7 days | February 5, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 1285 | 3 | Acitivities related to 65% BOR
1287 | Yes | Auto Scheduled | Integration Testing (partial) | 1 eday | February 13, 2019 5:00 PM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 1286 | 3 | Acitivities related to 65% BOR
1288 | Yes | Auto Scheduled | sw21.21.142.1 software internal release | 0 days | February 14, 2019 5:00 PM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 1287 | 3 | Acitivities related to 65% BOR
1289 | Yes | Auto Scheduled | Internal Validation (partial) (sw21.21.142.1) | 6 days | February 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 3 | Acitivities related to 65% BOR
1290 | Yes | Auto Scheduled | Redmine testing | 4 days | February 18, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 1288 | 4 | Acitivities related to 65% BOR
1291 | Yes | Auto Scheduled | Release rediness test | 2 days | February 15, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1288 | 4 | Acitivities related to 65% BOR
1292 | Yes | Auto Scheduled | CG3388 Bootloader Tests | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 1288 | 4 | Acitivities related to 65% BOR
1293 | Yes | Auto Scheduled | CG4879 OTA testing | 2 days | February 18, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 1292 | 4 | Acitivities related to 65% BOR
1294 | Yes | Auto Scheduled | Bootloader test | 5 days | February 15, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 1288 | 4 | Acitivities related to 65% BOR
1295 | Yes | Auto Scheduled | Test Report Review | 1 day | February 22, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1294,1293,1292 | 4 | Acitivities related to 65% BOR
1296 | Yes | Auto Scheduled | Update 5 Phases based on the feedback | 5 days | February 4, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 | 1284 | 3 | Acitivities related to 65% BOR
1297 | Yes | Auto Scheduled | Review with managers | 1 day | February 11, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 | 1296 | 3 | Acitivities related to 65% BOR
1298 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_022_Reset During Bootup | 1 day | January 29, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 2
1299 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | January 29, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 3
1300 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_023_Reset after some ING cycles | 45 days | January 19, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 2
1301 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | January 29, 2019 8:00 AM | January 29, 2019 5:00 PM | 2019-01-29 | 1 |  | 3
1302 | Yes | Auto Scheduled | Temporary solution | 10 days | January 19, 2019 5:00 PM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 3
1303 | Yes | Auto Scheduled | Reproduce issue | 0 days | January 19, 2019 5:00 PM | January 19, 2019 5:00 PM | 2019-01-19 | 1 | 1301 | 4
1304 | Yes | Auto Scheduled | Disable alive monitoring | 2 days | January 21, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 1303 | 4
1305 | Yes | Auto Scheduled | Temporary solution verification | 1 day | January 23, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1304 | 4
1306 | Yes | Auto Scheduled | Release sw21.21.142.1 with alive monitoring diabled | 6 days | January 24, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 1305 | 4
1307 | Yes | Auto Scheduled | Re Test software | 1 day | February 1, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1306 | 4
1308 | Yes | Auto Scheduled | Permanent solution | 35 days | February 4, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
1309 | Yes | Auto Scheduled | Identify permanent solution | 9 days | February 4, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 4
1310 | Yes | Auto Scheduled | Implement permanent solution | 11 days | February 15, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 1309 | 4
1311 | Yes | Auto Scheduled | Release with Alive Monitoring enabled sw21.21.144 | 8 days | March 4, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 1310 | 4
1312 | Yes | Auto Scheduled | Retest | 7 days | March 14, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 1311 | 4
1313 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_024_RHMI Disconnection | 30 days | February 11, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 2
1314 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | February 11, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 |  | 3
1315 | Yes | Auto Scheduled | Root cause analyis | 10 days | February 12, 2019 8:00 AM | February 25, 2019 5:00 PM | 2019-02-25 | 1 | 1314 | 3
1316 | Yes | Auto Scheduled | Permanent solution | 9 days | February 26, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1315 | 3
1317 | Yes | Auto Scheduled | Internal SW release | 3 days | March 11, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 1316 | 3
1318 | Yes | Auto Scheduled | Internal sw testing | 7 days | March 14, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 1317 | 3
1319 | Yes | Auto Scheduled | Confirmation at GM Bench | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 1318 | 3
1320 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_025_IPC Stuck in boot and part 2 OTA fail | 1 day | March 15, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 2
1321 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | March 15, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 3
1322 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_026_CG4117 Issues | 76 days | March 26, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 2
1323 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | March 26, 2019 8:00 AM | March 26, 2019 5:00 PM | 2019-03-26 | 1 |  | 3
1324 | Yes | Auto Scheduled | Impact analysis for NVM change review | 4 days | March 27, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 1323 | 3
1325 | Yes | Auto Scheduled | Implement Cypress Fee in Beta Software 21.145 | 6 days | April 10, 2019 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 | 1323 | 3
1326 | Yes | Auto Scheduled | Perform Stress Testing with MAC tester with Beta Software | 2 days | April 18, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 1325 | 3
1327 | Yes | Auto Scheduled | Release beta software to GMTCI | 2 days | April 22, 2019 8:00 AM | April 23, 2019 5:00 PM | 2019-04-23 | 1 | 1326 | 3
1328 | Yes | Auto Scheduled | GMTCI validation on beta software | 2 days | April 24, 2019 8:00 AM | April 25, 2019 5:00 PM | 2019-04-25 | 1 | 1327 | 3
1329 | Yes | Auto Scheduled | Release sw21.21.145 | 6 days | May 28, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 1328 | 3
1330 | Yes | Auto Scheduled | GMTCI validation (use sw21.21.145.01) | 5 days | June 26, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 | 1329 | 3
1331 | Yes | Auto Scheduled | 5 Phase update | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 1330 | 3
1332 | Yes | Auto Scheduled | 5 Phase review and approval by management | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 1331 | 3
1333 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 9, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 1332 | 3
1334 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_027_Sticky Pointer | 27 days | June 3, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 2
1335 | Yes | Auto Scheduled | Implement priority change in sw21.21.145.01 | 10 days | June 3, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 3
1336 | Yes | Auto Scheduled | Demo fix to GM | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 1335 | 3
1337 | Yes | Auto Scheduled | 5 Phase update | 9 days | June 24, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 1336 | 3
1338 | Yes | Auto Scheduled | 5 Phase review and approval by management | 1 day | July 9, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 1337 | 3
1339 | Yes | Auto Scheduled | Share 5 phase with GM | 0 days | July 9, 2019 5:00 PM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 1338 | 3
1340 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_028_CAL flashing Missed Requirement | 1 day | May 6, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 2
1341 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_029_DIC Service Instrument Cluster | 9 days | June 26, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 2
1342 | Yes | Auto Scheduled | 5 Phase update | 4 days | June 26, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 3
1343 | Yes | Auto Scheduled | 5 Phase review and approval by management | 2 days | July 2, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 1342 | 3
1344 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 1343 | 3
1345 | Yes | Auto Scheduled | 21E3_E2Ux_5 Phase_030_FUSA_Telltales_Open_Fault | 30 days | May 23, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 2
1346 | Yes | Auto Scheduled | Create 5 Phase with description | 1 day | May 23, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 |  | 3
1347 | Yes | Auto Scheduled | Update 5 phase with details from issue | 4 days | May 24, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 1346 | 3
1348 | Yes | Auto Scheduled | Perform Intensity Measurements | 2 days | May 24, 2019 8:00 AM | May 27, 2019 5:00 PM | 2019-05-27 | 1 | 1346 | 3
1349 | Yes | Auto Scheduled | Run HW test with updated software and hardware | 8 days | May 24, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 1346 | 3
1350 | Yes | Auto Scheduled | Run SW test with updated software and hardware | 8 days | May 24, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 1346 | 3
1351 | Yes | Auto Scheduled | Update 5 whys | 5 days | June 19, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 |  | 3
1352 | Yes | Auto Scheduled | 5 Phase update | 3 days | June 26, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 1351 | 3
1353 | Yes | Auto Scheduled | 5 Phase review and approval by management | 2 days | July 1, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 | 1352 | 3
1354 | Yes | Auto Scheduled | Share 5 phase with GM | 1 day | July 3, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 1353 | 3
1355 | Yes | Auto Scheduled | Functional Safety | 518 days | January 15, 2018 8:00 AM | January 8, 2020 5:00 PM | 2020-01-08 | 0 |  | 1 | Functional Safety Implementation from PCE 0E3
1356 | Yes | Auto Scheduled | DIA Agreement | 7 days | April 20, 2018 8:00 AM | April 30, 2018 5:00 PM | 2018-04-30 | 1 |  | 2
1357 | Yes | Manually Scheduled | DIA completion | 2 days | April 25, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 |  | 3
1358 | Yes | Manually Scheduled | System Safety Program Plan agreement | 4 days | April 25, 2018 8:00 AM | April 30, 2018 5:00 PM | 2018-04-30 | 1 | 1357 | 3 | System safety prgoram plan is present in the sharePoint
1359 | Yes | Manually Scheduled | DIA agreement with GM | 5 days | April 20, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 |  | 3 | update completed
1360 | Yes | Auto Scheduled | Concept Phase | 88 days | January 15, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 |  | 2 | This is a summary task. Use summary tasks to help organize your project into sections.
1361 | Yes | Manually Scheduled | Basic System Architecture | 1 day | January 15, 2018 8:00 AM | January 15, 2018 5:00 PM | 2018-01-15 | 1 |  | 3
1362 | Yes | Auto Scheduled | System FTA SG01 - Discrete Indicators (Tell Tales) | 59 days | February 5, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1361 | 3
1363 | Yes | Manually Scheduled | Draft FTA design Sketch | 1 day | February 5, 2018 8:00 AM | February 5, 2018 5:00 PM | 2018-02-05 | 1 | 1361 | 4
1364 | Yes | Manually Scheduled | FTA (in Medini) | 9 days | March 5, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 | 1363 | 4
1365 | Yes | Manually Scheduled | FTA Review | 1 day | March 16, 2018 8:00 AM | March 16, 2018 5:00 PM | 2018-03-16 | 1 | 1364 | 4
1366 | Yes | Manually Scheduled | FTA Finalization | 5 days | April 20, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1365 | 4 | Document approval completed
1367 | Yes | Manually Scheduled | Cut Set Generation | 6 days | April 16, 2018 8:00 AM | April 23, 2018 5:00 PM | 2018-04-23 | 1 | 1365 | 4 | Document approval completed
1368 | Yes | Manually Scheduled | Quantitative Analysis | 5 days | April 16, 2018 8:00 AM | April 20, 2018 5:00 PM | 2018-04-20 | 1 | 1367 | 4
1369 | Yes | Auto Scheduled | System FTA SG02 - Rendered Indicators (Display) | 59 days | February 5, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1361 | 3
1370 | Yes | Manually Scheduled | Draft FTA design Sketch | 18 days | February 5, 2018 8:00 AM | February 28, 2018 5:00 PM | 2018-02-28 | 1 | 1361 | 4
1371 | Yes | Manually Scheduled | FTA (in Medini) | 9 days | March 5, 2018 8:00 AM | March 15, 2018 5:00 PM | 2018-03-15 | 1 | 1370 | 4
1372 | Yes | Manually Scheduled | FTA Review | 0 days | March 16, 2018 8:00 AM | March 16, 2018 8:00 AM | 2018-03-16 | 1 | 1371 | 4
1373 | Yes | Manually Scheduled | FTA Finalization | 5 days | April 20, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1372 | 4 | Document approval completed
1374 | Yes | Manually Scheduled | Cut Set Generation | 5 days | April 16, 2018 8:00 AM | April 20, 2018 5:00 PM | 2018-04-20 | 1 | 1365 | 4
1375 | Yes | Manually Scheduled | Quantitative Analysis | 5 days | April 16, 2018 8:00 AM | April 20, 2018 5:00 PM | 2018-04-20 | 1 | 1367 | 4 | quantitative Analysis completed
1376 | Yes | Manually Scheduled | Concept HW SEFA (SCS-050) | 10 days | April 6, 2018 8:00 AM | April 19, 2018 5:00 PM | 2018-04-19 | 1 | 1361 | 3 | This is a milestone task. Set a task to 0d duration to mark an event in your project.
1377 | Yes | Manually Scheduled | Cut-Set Analysis Template (SCS-053) | 6 days | April 19, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1361 | 3 | Document approval completed
1378 | Yes | Auto Scheduled | System Safety Concept (SCS-015) | 27 days | March 26, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 | 1361 | 3
1379 | Yes | Manually Scheduled | Fault Categorization | 1 day | April 2, 2018 8:00 AM | April 2, 2018 5:00 PM | 2018-04-02 | 1 |  | 4
1380 | Yes | Manually Scheduled | System Degradation Strategy | 1 day | April 5, 2018 8:00 AM | April 5, 2018 5:00 PM | 2018-04-05 | 1 | 1379 | 4
1381 | Yes | Manually Scheduled | Hardware Integrity Strategy | 6 days | March 26, 2018 8:00 AM | April 10, 2018 5:00 PM | 2018-04-10 | 1 | 1361 | 4
1382 | Yes | Manually Scheduled | Review of Safety Concept | 4 days | April 26, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 | 1381 | 4 | KPIT review completed
1383 | Yes | Manually Scheduled | Finalization of System Safety Concept (SCS-015) | 4 days | April 26, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 |  | 4 | Document is completed
1384 | Yes | Manually Scheduled | Best Practices Evaulation (SCS-094) Concept Phase | 5 days | April 23, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 |  | 3 | Minor updates to be done, document will be completed today
1385 | Yes | Manually Scheduled | Concept Review Presentation (SCS-057) Preperation | 2 days | May 2, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 | 1384 | 3 | Alejandro to review and upload the PPT in SharePoint
1386 | Yes | Manually Scheduled | Send SCS-015 to GM for review | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 3
1387 | Yes | Manually Scheduled | Concept Review Presentation with GM Peer Review Board | 1 day | May 16, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 | 1385 | 3
1388 | Yes | Auto Scheduled | Requirement Analysis Phase | 114 days | April 1, 2018 8:00 AM | September 6, 2018 5:00 PM | 2018-09-06 | 1 | 1385 | 2
1389 | Yes | Manually Scheduled | System Functional Interface Analysis (SCS-016) | 3 days | April 4, 2018 8:00 AM | April 6, 2018 5:00 PM | 2018-04-06 | 1 | 1378 | 3
1390 | Yes | Manually Scheduled | Translation of Hazard Metric (SCS-052) | 5 days | April 23, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 |  | 3 | This can be updated as an assumption in SCS015
1391 | Yes | Auto Scheduled | Functional Safety Requirement Specifications | 22 days | April 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 | 1389 | 3
1392 | Yes | Manually Scheduled | System Safety Requirements (TSR) | 2 days | April 26, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 | 1390 | 4 | Current version would be taken for GM review, traceability part is still in discussion
1393 | Yes | Manually Scheduled | Hardware Safety Requirements (HSR) | 1 day | April 26, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1392 | 4 | Current version would be taken for GM review, traceability part is still in discussion
1394 | Yes | Manually Scheduled | Software Safety Requirements (SSR) | 23 days | April 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 |  | 4 | Current version would be taken for GM review, traceability part is still in discussion
1395 | Yes | Manually Scheduled | System Safety Requirements Traceability Matrix (SCS-083) | 99 days | April 23, 2018 8:00 AM | September 6, 2018 5:00 PM | 2018-09-06 | 1 | 1391 | 3 | DOORS traceability to be discussed with GM during the meeting
1396 | Yes | Manually Scheduled | Safety Verification / Validation Plan (SCS-017) | 6 days | April 25, 2018 8:00 AM | May 2, 2018 5:00 PM | 2018-05-02 | 1 |  | 3 | Document approval to be done
1397 | Yes | Manually Scheduled | Best Practices Evaulation (SCS-094) Requirement Analysis Phase | 5 days | April 23, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 |  | 3 | Minor updates to be done, document will be completed today
1398 | Yes | Manually Scheduled | Requirement Analysis Review Presentation (SCS-058) Preperation | 2 days | May 2, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 3 | Alejandro to review and upload the PPT in SharePoint
1399 | Yes | Manually Scheduled | Send Requirements Documents to GM for review | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 3
1400 | Yes | Auto Scheduled | Requirement Analysis Review Presentation (SCS-058) | 1 day | May 16, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 | 1398 | 3 | Tasks with the pushpin next to them are manually scheduled tasks. Use them when you don't want Project to move the task. Also, you can enter freeform text in the duration, start and finish fields or leave them blank if you don't have all the information y
1401 | Yes | Auto Scheduled | Design Phase | 86 days | February 5, 2018 8:00 AM | June 4, 2018 5:00 PM | 2018-06-04 | 1 | 1398 | 2
1402 | Yes | Auto Scheduled | System FMEA | 36 days | April 16, 2018 8:00 AM | June 4, 2018 5:00 PM | 2018-06-04 | 1 |  | 3
1403 | Yes | Manually Scheduled | System FMEA Draft | 5 days | April 16, 2018 8:00 AM | April 20, 2018 5:00 PM | 2018-04-20 | 1 |  | 4
1404 | Yes | Manually Scheduled | System FMEA Review | 1 day | April 20, 2018 8:00 AM | April 20, 2018 5:00 PM | 2018-04-20 | 1 | 1403 | 4
1405 | Yes | Manually Scheduled | System FMEA Finalization | 3 days | April 20, 2018 8:00 AM | April 24, 2018 5:00 PM | 2018-04-24 | 1 | 1404 | 4
1406 | Yes | Manually Scheduled | System FMEA Report (SCS-055) Updated by SW | 2 days | April 25, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 |  | 4 | Alejandro is working on the updates
1407 | Yes | Manually Scheduled | System FMEA Report (SCS-055) Updated by HW | 3 days | April 25, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 | 1417 | 4 | HW part completed
1408 | Yes | Manually Scheduled | System FMEA Report (SCS-055) Finalization | 29 days | April 25, 2018 8:00 AM | June 4, 2018 5:00 PM | 2018-06-04 | 1 | 1406 | 4 | HW part completed
1409 | Yes | Auto Scheduled | SW FMEA | 5 days | April 24, 2018 8:00 AM | April 30, 2018 5:00 PM | 2018-04-30 | 1 |  | 3
1410 | Yes | Manually Scheduled | Software System DFMEA Template (SCS-064) | 5 days | April 24, 2018 8:00 AM | April 30, 2018 5:00 PM | 2018-04-30 | 1 |  | 4 | KPIT review completed, approval done
1411 | Yes | Manually Scheduled | Software Safety Analysis Report (SCS-063) | 5 days | April 24, 2018 8:00 AM | April 30, 2018 5:00 PM | 2018-04-30 | 1 |  | 4 | KPIT review completed, approval done
1412 | Yes | Auto Scheduled | HW FMEDA | 59 days | February 5, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 |  | 3
1413 | Yes | Manually Scheduled | Draft FMEDA (Excel Sheet) | 10 days | February 5, 2018 8:00 AM | February 16, 2018 5:00 PM | 2018-02-16 | 1 |  | 4
1414 | Yes | Manually Scheduled | Draft FMEDA (in Medini) | 5 days | February 19, 2018 8:00 AM | February 23, 2018 5:00 PM | 2018-02-23 | 1 | 1413 | 4
1415 | Yes | Manually Scheduled | Review of FMEDA | 4 days | April 11, 2018 8:00 AM | April 16, 2018 5:00 PM | 2018-04-16 | 1 | 1414 | 4
1416 | Yes | Manually Scheduled | Final review by HW Team | 1 day | April 16, 2018 8:00 AM | April 16, 2018 5:00 PM | 2018-04-16 | 1 | 1415 | 4 | NSI to confirm
1417 | Yes | Manually Scheduled | FMEDA Finalization | 3 days | April 24, 2018 8:00 AM | April 26, 2018 5:00 PM | 2018-04-26 | 1 | 1416 | 4 | Internal review update completed and updated into share point
1418 | Yes | Manually Scheduled | Common Cause Analysis (CCA) | 1 day | April 23, 2018 8:00 AM | April 23, 2018 5:00 PM | 2018-04-23 | 1 | 1417 | 3
1419 | Yes | Manually Scheduled | System Safety Concept (SCS-015 Update) | 4 days | April 16, 2018 8:00 AM | April 19, 2018 5:00 PM | 2018-04-19 | 1 | 1418 | 3
1420 | Yes | Manually Scheduled | SW Coding Guideline Review (SCS-047) | 5 days | April 28, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 3 | Document approval in progress
1421 | Yes | Manually Scheduled | Safety V&V Plan (SCS-017) Update | 6 days | April 25, 2018 8:00 AM | May 2, 2018 5:00 PM | 2018-05-02 | 1 |  | 3 | Document approval is pending
1422 | Yes | Manually Scheduled | Best Practices Evaulation (SCS-094) Design Phase | 5 days | April 23, 2018 8:00 AM | April 27, 2018 5:00 PM | 2018-04-27 | 1 |  | 3 | Minor updates to be done, document will be completed today
1423 | Yes | Manually Scheduled | Send Design Documentation to GM for review | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 2018-05-01 | 1 |  | 3
1424 | Yes | Manually Scheduled | Safety Design Solution Review Presentation (SCS-059) Preperation | 2 days | May 2, 2018 8:00 AM | May 3, 2018 5:00 PM | 2018-05-03 | 1 |  | 3 | 4th May: Alejandro to review and upload the PPT in SharePoint
1425 | Yes | Manually Scheduled | Safety Design Solution Review Presentation (SCS-059) | 1 day | May 16, 2018 8:00 AM | May 16, 2018 5:00 PM | 2018-05-16 | 1 | 1424 | 3
1426 | Yes | Manually Scheduled | Diagnostics Coverage (SCS-054) | 21 days | April 13, 2018 8:00 AM | May 11, 2018 5:00 PM | 2018-05-11 | 1 |  | 3
1427 | Yes | Auto Scheduled | Update documentation from GM Review 1 according to MOM | 16 days | May 17, 2018 8:00 AM | June 7, 2018 5:00 PM | 2018-06-07 | 1 | 1387,1400,1425 | 2
1428 | Yes | Auto Scheduled | Share Concept, Requirement Analysis and Design updated presentations to GM | 1 day | June 8, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 | 1427 | 2
1429 | Yes | Auto Scheduled | Concept, Requirement Analysis and Design peer review 2 with GM | 1 day | June 27, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 |  | 2
1430 | Yes | Auto Scheduled | Update documentation from GM Review 2 according to MOM | 6 wks | June 28, 2018 8:00 AM | August 8, 2018 5:00 PM | 2018-08-08 | 1 | 1429 | 2
1431 | Yes | Auto Scheduled | Share Concept, Requirement Analysis and Design updated presentations to GM | 1 day | August 9, 2018 8:00 AM | August 9, 2018 5:00 PM | 2018-08-09 | 1 | 1430 | 2
1432 | Yes | Auto Scheduled | Concept, Requirement Analysis and Design peer review 3 with GM | 1 day | August 22, 2018 8:00 AM | August 22, 2018 5:00 PM | 2018-08-22 | 1 |  | 2
1433 | Yes | Auto Scheduled | Safety Implementation Phase | 242 days | May 15, 2018 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 |  | 2
1434 | Yes | Auto Scheduled | Functional Safety Implementation | 238 days | May 21, 2018 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 |  | 3
1435 | Yes | Auto Scheduled | Serial Data Integrity (sw21.21.140) | 70 days | May 21, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 |  | 4
1436 | Yes | Auto Scheduled | Telltale Error Diagnostics (sw21.21.142.1) | 180 days | May 21, 2018 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 |  | 4
1437 | Yes | Auto Scheduled | Error Display and Reporting (sw21.21.140) | 70 days | May 21, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 |  | 5
1438 | Yes | Auto Scheduled | SPI Diagnostics (NSI) (sw21.21.142.1) | 32 days | December 3, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 |  | 5
1439 | Yes | Auto Scheduled | SSRs rework | 8 days | December 3, 2018 8:00 AM | December 12, 2018 5:00 PM | 2018-12-12 | 1 |  | 6
1440 | Yes | Auto Scheduled | SSRs reviews / update | 4 days | December 13, 2018 8:00 AM | December 18, 2018 5:00 PM | 2018-12-18 | 1 | 1439 | 6
1441 | Yes | Auto Scheduled | Architechture Design | 6 days | December 13, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 1439 | 6
1442 | Yes | Auto Scheduled | Architechture Design Review | 2 days | December 21, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 | 1441 | 6
1443 | Yes | Auto Scheduled | Unit Design | 6 days | December 13, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 1439 | 6
1444 | Yes | Auto Scheduled | Unit Design Review | 3 days | December 21, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 | 1443 | 6
1445 | Yes | Auto Scheduled | Design Implementation | 6 days | January 8, 2019 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 1444,1442 | 6
1446 | Yes | Auto Scheduled | Final Integration | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1437,1445 | 5
1447 | Yes | Auto Scheduled | HW Diagnostics (Built In Selft Test) | 64 days | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 4 | Altia has not confirmed a release date, but they it will be available for sw142
1448 | Yes | Auto Scheduled | Telltale SPI BIST (sw21.21.142.1) | 33 days | November 30, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 |  | 5
1449 | Yes | Auto Scheduled | CAN Transceiver SPI BIST (sw21.21.145) | 64 days | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 5
1450 | Yes | Auto Scheduled | Design Implementation | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1451 | Yes | Auto Scheduled | SSRs rework | 10 days | January 2, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 6
1452 | Yes | Auto Scheduled | SSRs reviews / update | 5 days | February 4, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 | 1451 | 6
1453 | Yes | Auto Scheduled | Architechture Design | 6 days | February 11, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1452 | 6
1454 | Yes | Auto Scheduled | Architechture Design Review | 2 days | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1453 | 6
1455 | Yes | Auto Scheduled | Unit Design | 6 days | February 11, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1452 | 6
1456 | Yes | Auto Scheduled | Unit Design Review | 2 days | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1455 | 6
1457 | Yes | Auto Scheduled | Design Implementation | 5 days | February 21, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 1454,1456 | 6
1458 | Yes | Auto Scheduled | TFT BIST (sw21.21.144) | 64 days | November 30, 2018 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 5
1459 | Yes | Auto Scheduled | Design Implementation | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1460 | Yes | Auto Scheduled | SSRs rework | 10 days | January 2, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 6
1461 | Yes | Auto Scheduled | SSRs reviews / update | 5 days | February 4, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 | 1460 | 6
1462 | Yes | Auto Scheduled | Architechture Design | 6 days | February 11, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1461 | 6
1463 | Yes | Auto Scheduled | Architechture Design Review | 2 days | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1462 | 6
1464 | Yes | Auto Scheduled | Unit Design | 6 days | February 11, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1461 | 6
1465 | Yes | Auto Scheduled | Unit Design Review | 2 days | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1464 | 6
1466 | Yes | Auto Scheduled | Design Implementation | 5 days | February 21, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 1463,1465 | 6
1467 | Yes | Auto Scheduled | Flash Test (sw21.21.142.1) | 40 days | November 30, 2018 8:00 AM | January 24, 2019 5:00 PM | 2019-01-24 | 1 |  | 5
1468 | Yes | Auto Scheduled | Design Implementation | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1469 | Yes | Auto Scheduled | SSRs rework | 0 days | January 7, 2019 5:00 PM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 6
1470 | Yes | Auto Scheduled | SSRs reviews / update | 0 days | January 7, 2019 5:00 PM | January 7, 2019 5:00 PM | 2019-01-07 | 1 | 1469 | 6
1471 | Yes | Auto Scheduled | Architechture Design | 6 days | January 8, 2019 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 1470 | 6
1472 | Yes | Auto Scheduled | Architechture Design Review | 2 days | January 16, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 | 1471 | 6
1473 | Yes | Auto Scheduled | Unit Design | 6 days | January 8, 2019 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 1470 | 6
1474 | Yes | Auto Scheduled | Unit Design Review | 2 days | January 16, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 | 1473 | 6
1475 | Yes | Auto Scheduled | Design Implementation | 5 days | January 18, 2019 8:00 AM | January 24, 2019 5:00 PM | 2019-01-24 | 1 | 1472,1474 | 6
1476 | Yes | Auto Scheduled | RAM ECC BIST (sw21.21.142.1) | 46 days | November 30, 2018 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 5 | Pradeep needs to confirm if this task is needed
1477 | Yes | Auto Scheduled | Design Implementation | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1478 | Yes | Auto Scheduled | SSRs rework | 10 days | January 2, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 6
1479 | Yes | Auto Scheduled | SSRs reviews / update | 1 day | January 18, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 | 1478 | 6
1480 | Yes | Auto Scheduled | Architechture Design | 3 days | January 21, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1479 | 6
1481 | Yes | Auto Scheduled | Architechture Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1480 | 6
1482 | Yes | Auto Scheduled | Unit Design | 3 days | January 21, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1479 | 6
1483 | Yes | Auto Scheduled | Unit Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1482 | 6
1484 | Yes | Auto Scheduled | Design Implementation | 5 days | January 28, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1481,1483 | 6
1485 | Yes | Auto Scheduled | Core Test BIST (sw.21.21.142.1) | 46 days | November 30, 2018 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 5
1486 | Yes | Auto Scheduled | Design Implementation | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1487 | Yes | Auto Scheduled | SSRs rework | 10 days | January 2, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 6
1488 | Yes | Auto Scheduled | SSRs reviews / update | 2 days | January 18, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 | 1487 | 6
1489 | Yes | Auto Scheduled | Architechture Design | 2 days | January 22, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1488 | 6
1490 | Yes | Auto Scheduled | Architechture Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1489 | 6
1491 | Yes | Auto Scheduled | Unit Design | 2 days | January 22, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1488 | 6
1492 | Yes | Auto Scheduled | Unit Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1491 | 6
1493 | Yes | Auto Scheduled | Design Implementation | 5 days | January 28, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1490,1492 | 6
1494 | Yes | Auto Scheduled | Display Error Diagnostics (sw21.21.145) | 95 days | November 30, 2018 8:00 AM | April 11, 2019 5:00 PM | 2019-04-11 | 1 |  | 4
1495 | Yes | Auto Scheduled | Cypress implementation (included in RC-1 for sw21.21.144) | 33 days | November 30, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 |  | 5 | PCE 0E3
1496 | Yes | Auto Scheduled | RAMP/Altia implementation (include in RC2) | 10 days | March 18, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5 | PCE 0E3 / GM TCI facing integration issues
1497 | Yes | Auto Scheduled | Error Display and Reporting (include in RC2) | 10 days | March 18, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5 | PCE 0E3 / GM TCI facing integration issues
1498 | Yes | Auto Scheduled | NSI Final Integration (Altia with Driver at BSP Level) | 19 days | March 18, 2019 8:00 AM | April 11, 2019 5:00 PM | 2019-04-11 | 1 |  | 5 | PCE 0E3
1499 | Yes | Auto Scheduled | SSRs rework | 7 days | March 18, 2019 8:00 AM | March 26, 2019 5:00 PM | 2019-03-26 | 1 |  | 6
1500 | Yes | Auto Scheduled | SSRs reviews / update | 3 days | March 26, 2019 5:00 PM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 1499 | 6
1501 | Yes | Auto Scheduled | Architechture Design | 2 days | April 1, 2019 8:00 AM | April 2, 2019 5:00 PM | 2019-04-02 | 1 | 1500 | 6
1502 | Yes | Auto Scheduled | Architechture Design Review | 2 days | April 3, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 1501 | 6
1503 | Yes | Auto Scheduled | Unit Design | 2 days | April 1, 2019 8:00 AM | April 2, 2019 5:00 PM | 2019-04-02 | 1 | 1500 | 6
1504 | Yes | Auto Scheduled | Unit Design Review | 2 days | April 3, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 1503 | 6
1505 | Yes | Auto Scheduled | Design Implementation | 5 days | April 5, 2019 8:00 AM | April 11, 2019 5:00 PM | 2019-04-11 | 1 | 1502,1504 | 6
1506 | Yes | Auto Scheduled | Memory Fault Implementation (sw21.21.142.1) | 21 days | January 4, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 4
1507 | Yes | Auto Scheduled | SSRs rework | 10 days | January 4, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 5
1508 | Yes | Auto Scheduled | SSRs reviews / update | 2 days | January 18, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 | 1507 | 5
1509 | Yes | Auto Scheduled | Architechture Design | 2 days | January 22, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1508 | 5
1510 | Yes | Auto Scheduled | Architechture Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1509 | 5
1511 | Yes | Auto Scheduled | Unit Design | 2 days | January 22, 2019 8:00 AM | January 23, 2019 5:00 PM | 2019-01-23 | 1 | 1508 | 5
1512 | Yes | Auto Scheduled | Unit Design Review | 2 days | January 24, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 1511 | 5
1513 | Yes | Auto Scheduled | Design Implementation | 5 days | January 28, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 1510,1512 | 5
1514 | Yes | Auto Scheduled | Watchdog (sw21.21.144) | 20 days | February 13, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 4
1515 | Yes | Auto Scheduled | Basic Monitoring (sw21.21.144) | 16 days | February 15, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 5
1516 | Yes | Auto Scheduled | SSRs rework | 2 days | February 15, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1524 | 6
1517 | Yes | Auto Scheduled | SSRs reviews / update | 4 days | February 19, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1516 | 6
1518 | Yes | Auto Scheduled | Architechture Design | 6 days | February 19, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 | 1516 | 6
1519 | Yes | Auto Scheduled | Architechture Design Review | 3 days | February 27, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 1518 | 6
1520 | Yes | Auto Scheduled | Unit Design | 6 days | February 19, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 | 1516 | 6
1521 | Yes | Auto Scheduled | Unit Design Review | 3 days | February 27, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 1520 | 6
1522 | Yes | Auto Scheduled | Design Implementation | 5 days | March 4, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1519,1521 | 6
1523 | Yes | Auto Scheduled | Alive Monitoring (sw21.21.144) | 16 days | February 13, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 |  | 5
1524 | Yes | Auto Scheduled | SSRs rework | 2 days | February 13, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 6
1525 | Yes | Auto Scheduled | SSRs reviews / update | 4 days | February 15, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1524 | 6
1526 | Yes | Auto Scheduled | Architechture Design | 6 days | February 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1524 | 6
1527 | Yes | Auto Scheduled | Architechture Design Review | 3 days | February 25, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 1526 | 6
1528 | Yes | Auto Scheduled | Unit Design | 6 days | February 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1524 | 6
1529 | Yes | Auto Scheduled | Unit Design Review | 3 days | February 25, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 1528 | 6
1530 | Yes | Auto Scheduled | Design Implementation | 5 days | February 28, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 | 1527,1529 | 6
1531 | Yes | Auto Scheduled | Code Flow Monitoring (sw21.21.144) | 16 days | February 19, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 5
1532 | Yes | Auto Scheduled | SSRs rework | 2 days | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1516 | 6
1533 | Yes | Auto Scheduled | SSRs reviews / update | 4 days | February 21, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 | 1532 | 6
1534 | Yes | Auto Scheduled | Architechture Design | 6 days | February 21, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 1532 | 6
1535 | Yes | Auto Scheduled | Architechture Design Review | 3 days | March 1, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 1534 | 6
1536 | Yes | Auto Scheduled | Unit Design | 6 days | February 21, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 1532 | 6
1537 | Yes | Auto Scheduled | Unit Design Review | 3 days | March 1, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 1536 | 6
1538 | Yes | Auto Scheduled | Design Implementation | 5 days | March 6, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 1535,1537 | 6
1539 | Yes | Auto Scheduled | Memory Partition (sw21.21.144) | 76 days | November 30, 2018 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 4
1540 | Yes | Auto Scheduled | Application SW-C | 74 days | November 30, 2018 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 |  | 5
1541 | Yes | Auto Scheduled | Design Implementation (sw21.21.142.beta) | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1542 | Yes | Auto Scheduled | SSRs rework | 2 days | February 21, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 1532 | 6
1543 | Yes | Auto Scheduled | SSRs reviews / update | 5 days | February 25, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 1542 | 6
1544 | Yes | Auto Scheduled | Architechture Design | 3 days | March 4, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 | 1543 | 6
1545 | Yes | Auto Scheduled | Architechture Design Review | 2 days | March 7, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1544 | 6
1546 | Yes | Auto Scheduled | Unit Design | 3 days | March 4, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 | 1543 | 6
1547 | Yes | Auto Scheduled | Unit Design Review | 2 days | March 7, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1546 | 6
1548 | Yes | Auto Scheduled | Design Implementation | 3 days | March 11, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 1547,1545 | 6
1549 | Yes | Auto Scheduled | BSP / BSW | 76 days | November 30, 2018 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 5
1550 | Yes | Auto Scheduled | Design Implementation (sw21.21.142.beta) | 10 days | November 30, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6 | Based on SSRs initial development
1551 | Yes | Auto Scheduled | SSRs rework | 2 days | February 25, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 | 1542 | 6
1552 | Yes | Auto Scheduled | SSRs reviews / update | 5 days | February 27, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 1551 | 6
1553 | Yes | Auto Scheduled | Architechture Design | 3 days | March 6, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1552 | 6
1554 | Yes | Auto Scheduled | Architechture Design Review | 2 days | March 11, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 1553 | 6
1555 | Yes | Auto Scheduled | Unit Design | 3 days | March 6, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1552 | 6
1556 | Yes | Auto Scheduled | Unit Design Review | 2 days | March 11, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 1555 | 6
1557 | Yes | Auto Scheduled | Design Implementation | 3 days | March 13, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 1556,1554 | 6
1558 | Yes | Auto Scheduled | Trusted/Non Trusted & Priviledge Levels (sw21.21.145) | 23 days | March 18, 2019 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 |  | 4
1559 | Yes | Auto Scheduled | SSRs rework | 7 days | March 18, 2019 8:00 AM | March 26, 2019 5:00 PM | 2019-03-26 | 1 |  | 5
1560 | Yes | Auto Scheduled | SSRs reviews / update | 3 days | March 27, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 1559 | 5
1561 | Yes | Auto Scheduled | Architechture Design | 6 days | April 1, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 | 1560 | 5
1562 | Yes | Auto Scheduled | Architechture Design Review | 2 days | April 9, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 1561 | 5
1563 | Yes | Auto Scheduled | Unit Design | 6 days | April 1, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 | 1560 | 5
1564 | Yes | Auto Scheduled | Unit Design Review | 2 days | April 9, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 1563 | 5
1565 | Yes | Auto Scheduled | Design Implementation | 5 days | April 11, 2019 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 | 1562,1564 | 5
1566 | Yes | Auto Scheduled | Hardware | 173 days | May 15, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 3
1567 | Yes | Auto Scheduled | Creation of Tester Drawings | 0 days | May 15, 2018 8:00 AM | May 15, 2018 8:00 AM | 2018-05-15 | 1 |  | 4
1568 | Yes | Auto Scheduled | BOM Creation | 2 days | June 13, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 | 1567 | 4
1569 | Yes | Auto Scheduled | Parts ordering | 1 day | June 15, 2018 8:00 AM | June 15, 2018 5:00 PM | 2018-06-15 | 1 | 1568 | 4
1570 | Yes | Auto Scheduled | IPCs with new artwork | 1 wk | July 30, 2018 8:00 AM | August 3, 2018 5:00 PM | 2018-08-03 | 1 |  | 4
1571 | Yes | Auto Scheduled | Tester build proto 1 | 18 days | June 21, 2018 8:00 AM | July 16, 2018 5:00 PM | 2018-07-16 | 1 |  | 4
1572 | Yes | Auto Scheduled | Integration with IPC | 3 wks | August 6, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1569FS+3d,1570 | 4
1573 | Yes | Auto Scheduled | Tester build (2 parts) | 44 days | November 12, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 | 1571 | 4
1574 | Yes | Auto Scheduled | Tester 2 (SYS) | 5 days | November 12, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 5
1575 | Yes | Auto Scheduled | Tester 3 (SW) | 22 days | November 19, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 1574 | 5
1576 | Yes | Auto Scheduled | Integration with IPC | 1 wk | January 4, 2019 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 | 1575 | 5 | On hold due to missing D&D parts from TPL
1577 | Yes | Auto Scheduled | Creation of HSR Test cases | 21 days | May 21, 2018 8:00 AM | June 18, 2018 5:00 PM | 2018-06-18 | 1 |  | 4
1578 | Yes | Auto Scheduled | Update SW FMEA (SCS 063) - sw21.21.145.04 | 5 days | August 21, 2019 8:00 AM | August 27, 2019 5:00 PM | 2019-08-27 | 0 |  | 2
1579 | Yes | Auto Scheduled | Update SW FMEA (SCS 063) - sw21.21.145.05 | 5 days | October 7, 2019 8:00 AM | October 11, 2019 5:00 PM | 2019-10-11 | 0 |  | 2
1580 | Yes | Auto Scheduled | Update System FTA (SCS 061) - sw21.21.145.05 | 5 days | October 14, 2019 8:00 AM | October 18, 2019 5:00 PM | 2019-10-18 | 0 | 1579 | 2
1581 | Yes | Auto Scheduled | Update Common Mode / Common Cause Analysis - sw21.21.145.04 | 3 days | October 21, 2019 8:00 AM | October 23, 2019 5:00 PM | 2019-10-23 | 0 | 1580 | 2
1582 | Yes | Auto Scheduled | Update System Safety Verification / Validation Planning (SCS 017) - sw21.21.145.04 | 5 days | August 1, 2019 8:00 AM | August 7, 2019 5:00 PM | 2019-08-07 | 1 |  | 2
1583 | Yes | Auto Scheduled | Update Safety Implementation Review presentation | 95 days | August 1, 2019 8:00 AM | December 12, 2019 8:00 AM | 2019-12-12 | 0 |  | 2
1584 | Yes | Auto Scheduled | Safety Process and GM Vehicle Milestone Timing | 1 day | August 1, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 |  | 3
1585 | Yes | Auto Scheduled | NSI GM IPC V&V RASIC Functional Safety | 1 day | August 2, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 1584 | 3
1586 | Yes | Auto Scheduled | Technical Safety Requirements | 2 days | August 5, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 1585 | 3
1587 | Yes | Auto Scheduled | Hardware Safety Requirements | 2 days | August 7, 2019 8:00 AM | August 8, 2019 5:00 PM | 2019-08-08 | 1 | 1586 | 3
1588 | Yes | Auto Scheduled | Software Safety Requirements | 5 days | August 9, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 1587 | 3
1589 | Yes | Auto Scheduled | Safety Concept Report (SCS-015) | 2 days | August 16, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 1588 | 3
1590 | Yes | Auto Scheduled | Common Mode/Common Cause Analysis Report | 0 days | August 19, 2019 5:00 PM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 1589 | 3
1591 | Yes | Auto Scheduled | FTA Report (SCS_061) | 0 days | August 19, 2019 5:00 PM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 1589 | 3
1592 | Yes | Auto Scheduled | FMEDA Report (SCS_055) | 0 days | August 19, 2019 5:00 PM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 1589 | 3
1593 | Yes | Auto Scheduled | SW FMEA Report (SCS_063) | 0 days | August 19, 2019 5:00 PM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 1589 | 3
1594 | Yes | Auto Scheduled | Presentation Internal review | 1 day | December 6, 2019 8:00 AM | December 9, 2019 8:00 AM | 2019-12-09 | 0 | 1595SF-1d | 3
1595 | Yes | Auto Scheduled | Update presentation | 2 days | December 10, 2019 8:00 AM | December 12, 2019 8:00 AM | 2019-12-12 | 0 | 1596SF-2d,1697SF-2d | 3
1596 | Yes | Auto Scheduled | Share with GM Update Safety Implementation Review presentation | 0 days | November 13, 2019 8:00 AM | November 13, 2019 8:00 AM | 2019-11-13 | 0 | 1597SF | 2
1597 | Yes | Auto Scheduled | Update safety Implementation review presentation after GM review | 7 days | November 13, 2019 8:00 AM | November 22, 2019 8:00 AM | 2019-11-22 | 0 | 1598SF | 2
1598 | Yes | Auto Scheduled | Share safety Implementation review presentation with GM after review comment fix | 0 days | November 22, 2019 8:00 AM | November 22, 2019 8:00 AM | 2019-11-22 | 0 | 1599SF-3d | 2
1599 | Yes | Auto Scheduled | Safety Implementation Review with GM | 1 day | November 27, 2019 8:00 AM | November 27, 2019 5:00 PM | 2019-11-27 | 0 |  | 2
1600 | Yes | Auto Scheduled | Safety Verification Phase | 359 days | August 24, 2018 8:00 AM | January 8, 2020 5:00 PM | 2020-01-08 | 0 |  | 2
1601 | Yes | Auto Scheduled | Hardware | 10 days | February 5, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 |  | 3
1602 | Yes | Auto Scheduled | HSR Test execution phase 1 (HW releated test cases only sw21.21.142.1) | 2 wks | February 5, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 1577,1570,1576,2499 | 4
1603 | No | Auto Scheduled | HSR Test execution phase 2 (pending for new sw to fix redmine) | 2 wks | March 15, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2703 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1604 | No | Auto Scheduled | Test Report creation | 5 days | March 29, 2019 8:00 AM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 1603 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1605 | No | Auto Scheduled | Test Report review with hardware team | 5 days | April 5, 2019 8:00 AM | April 11, 2019 5:00 PM | 2019-04-11 | 1 | 1604 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1606 | No | Auto Scheduled | Test Report review with FuSa team | 5 days | April 12, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 | 1605 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1607 | No | Auto Scheduled | Test Report approval | 1 day | April 19, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 1606 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1608 | No | Auto Scheduled | Test Results upload to DOORS | 5 days | April 22, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 | 1607 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1609 | No | Auto Scheduled | Create Traceability to Test Results | 5 days | April 29, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 | 1608 | 4 | Tasks replanned for sw21.21.145, tasks added in sw21.21.145 cadence
1610 | Yes | Auto Scheduled | Software unit verification | 0 days | June 6, 2019 8:00 AM | June 6, 2019 8:00 AM | 2019-06-06 | 1 |  | 3
1611 | Yes | Auto Scheduled | Code inspection | 0 days | June 6, 2019 8:00 AM | June 6, 2019 8:00 AM | 2019-06-06 | 1 | 2499 | 4
1612 | Yes | Auto Scheduled | Static code analysis | 0 days | June 6, 2019 8:00 AM | June 6, 2019 8:00 AM | 2019-06-06 | 1 | 2499 | 4
1613 | Yes | Auto Scheduled | Unit Level Test Phase (SWE4) | 1 day | June 6, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
1614 | Yes | Auto Scheduled | Unit Test case preparation | 1 day | June 6, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1615 | Yes | Auto Scheduled | Analysis of requirements | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1616 | Yes | Auto Scheduled | Equivalence classes generation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1617 | Yes | Auto Scheduled | Boundary Classes | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1618 | Yes | Auto Scheduled | Requirements based | 0 days | June 6, 2019 8:00 AM | June 6, 2019 8:00 AM | 2019-06-06 | 1 | 2499 | 5
1619 | Yes | Auto Scheduled | Statement Coverage/Branch Coverage | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1620 | Yes | Auto Scheduled | Unit Level Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1621 | Yes | Auto Scheduled | Requirements based Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1622 | Yes | Auto Scheduled | Fault Injection | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1623 | Yes | Auto Scheduled | Software Integration Level Test Phase (SWE5) | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
1624 | Yes | Auto Scheduled | Software Integration Test case preparation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1625 | Yes | Auto Scheduled | Analysis of requirements | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1626 | Yes | Auto Scheduled | Equivalence classes generation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1627 | Yes | Auto Scheduled | Boundary Classes | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1628 | Yes | Auto Scheduled | Requirements based | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1629 | Yes | Auto Scheduled | Software Integration Level Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1630 | Yes | Auto Scheduled | Interface Test | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1631 | Yes | Auto Scheduled | Requirements based Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1632 | Yes | Auto Scheduled | Fault Injection | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1633 | Yes | Auto Scheduled | Software Safety Requirements Verification (SWE6) | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
1634 | Yes | Auto Scheduled | Software Safety Requirement Test case preparation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1635 | Yes | Auto Scheduled | Analysis of requirements | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1636 | Yes | Auto Scheduled | Equivalence classes generation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1637 | Yes | Auto Scheduled | Boundary Classes | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1638 | Yes | Auto Scheduled | Requirements based | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1639 | Yes | Auto Scheduled | Software Safety Requirement Verification | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1640 | Yes | Auto Scheduled | Interface Test | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1641 | Yes | Auto Scheduled | Requirements based Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1642 | Yes | Auto Scheduled | Fault Injection | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1643 | Yes | Auto Scheduled | System/Item Test Phase (SYS4 / SYS5) | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 3
1644 | Yes | Auto Scheduled | System/Item Level test case preparation | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1645 | Yes | Auto Scheduled | Environmental conditions analysis, Internal, External Interfaces | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1646 | Yes | Auto Scheduled | Test of interaction and communication | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1647 | Yes | Auto Scheduled | System/Item Testing | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 |  | 4
1648 | Yes | Auto Scheduled | Fault Injection | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1649 | Yes | Auto Scheduled | Requirement based | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1650 | Yes | Auto Scheduled | Resource Usage test | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1651 | Yes | Auto Scheduled | Performance Test | 0 days | June 6, 2019 5:00 PM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2499 | 5
1652 | Yes | Auto Scheduled | Vehicle level testing | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
1653 | Yes | Auto Scheduled | Requirement based | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2821,3001,3139,3252,3411 | 4 | Pending to define after meeting with Mahesh
1654 | Yes | Auto Scheduled | Fault Injection | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2821,3001,3139,3252,3411 | 4
1655 | Yes | Auto Scheduled | Long-Term test | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2821,3001,3139,3252,3411 | 4
1656 | Yes | Auto Scheduled | User test under real life scenarios | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2821,3001,3139,3252,3411 | 4
1657 | Yes | Auto Scheduled | Performance Test | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2821,3001,3139,3252,3411 | 4
1658 | Yes | Auto Scheduled | 3.5 Compliance Testing | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 3
1659 | Yes | Auto Scheduled | 3.2.8 Verification of Software Unit Test Case Completeness | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1660 | Yes | Auto Scheduled | DOORS with Rational Quality Manager (RQM) can be used (Optional) | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1661 | Yes | Auto Scheduled | 3.6 Compliance of Test Plan to Requirements | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 3
1662 | Yes | Auto Scheduled | DOORS with Rational Quality Manager (RQM) can be used (Optional) | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1663 | Yes | Auto Scheduled | Verification review | 210 days | August 24, 2018 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 3
1664 | Yes | Auto Scheduled | Safety plan | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4
1665 | Yes | Auto Scheduled | Technical safety requirements | 5 days | August 24, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 |  | 4
1666 | Yes | Auto Scheduled | Technical architecture | 5 days | August 24, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 |  | 4
1667 | Yes | Auto Scheduled | Technical safety concept | 5 days | August 24, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 |  | 4
1668 | Yes | Auto Scheduled | System design | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 | 1672 | 4
1669 | Yes | Auto Scheduled | Hardware-software integration and testing. | 5 days | June 7, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 1651 | 4
1670 | Yes | Auto Scheduled | Item integration and testing.(System integration and testing) | 1 day | June 7, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 1651 | 4
1671 | Yes | Auto Scheduled | Hardware safety requirements | 3 days | August 24, 2018 8:00 AM | August 28, 2018 5:00 PM | 2018-08-28 | 1 |  | 4
1672 | Yes | Auto Scheduled | Hardware architectural design | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1673 | Yes | Auto Scheduled | Safety analyses(See Part 8 section 12 Annexure 12) Hardware | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1674 | Yes | Auto Scheduled | Hardware detailed design | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1675 | Yes | Auto Scheduled | Diagnostics requirements | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1676 | Yes | Auto Scheduled | Diagnostics Coverage Implementation | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1677 | Yes | Auto Scheduled | hardware architectural metrics(SPF, LFM, PMHF, FTA) | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1678 | Yes | Auto Scheduled | Random hardware failures | 0 days | December 13, 2018 8:00 AM | December 13, 2018 8:00 AM | 2018-12-13 | 1 |  | 4 | Pradeep needs to confirm if these are needed
1679 | Yes | Auto Scheduled | Review of Hardware test case, test procedure and test results(boardlevel and integration testing) | 5 days | September 24, 2018 8:00 AM | September 28, 2018 5:00 PM | 2018-09-28 | 1 |  | 4
1680 | Yes | Auto Scheduled | Software safety requirements 1st review | 8 days | October 3, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 |  | 4
1681 | Yes | Auto Scheduled | Software architectural design 1st review | 4 days | October 24, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 |  | 4
1682 | Yes | Auto Scheduled | Software unit design and implementation | 40 days | February 1, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2499 | 4
1683 | Yes | Auto Scheduled | Review of MISRA coding guidelines. | 3 days | October 31, 2018 8:00 AM | November 2, 2018 5:00 PM | 2018-11-02 | 1 |  | 4
1684 | Yes | Auto Scheduled | Software unit testing (safety requirements) | 40 days | January 18, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
1685 | Yes | Auto Scheduled | Software integration and testing (safety requirements) | 40 days | January 18, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
1686 | Yes | Auto Scheduled | Software qualification testing (end to end) | 40 days | January 18, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
1687 | Yes | Auto Scheduled | SYS4 and SYS5 Tese Cases review | 24 days | November 5, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 4
1688 | Yes | Auto Scheduled | Software component qualification report | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1689 | Yes | Auto Scheduled | Hardware component qualification report | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1690 | Yes | Auto Scheduled | Freedom from Inteference | 0 days | December 13, 2018 5:00 PM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 4
1691 | Yes | Auto Scheduled | Safety case | 77 days | December 13, 2018 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 4
1692 | Yes | Auto Scheduled | Confirmation measures | 5 days | April 1, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 1691 | 4
1693 | Yes | Auto Scheduled | Functional safety audit | 5 days | April 8, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 1692 | 4
1694 | Yes | Auto Scheduled | Functional safety assessment | 5 days | April 15, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 1693 | 4
1695 | Yes | Auto Scheduled | Safety V&V Presentation | 28 days | December 2, 2019 8:00 AM | January 8, 2020 5:00 PM | 2020-01-08 | 0 |  | 3
1696 | Yes | Auto Scheduled | Update Safety V&V Presentation | 10 days | December 2, 2019 8:00 AM | December 13, 2019 5:00 PM | 2019-12-13 | 0 |  | 4
1697 | Yes | Auto Scheduled | Share with GM Update Safety V&V Review presentation | 0 days | December 13, 2019 5:00 PM | December 13, 2019 5:00 PM | 2019-12-13 | 0 | 1696 | 4
1698 | Yes | Auto Scheduled | Update safety V&V review presentation after GM review | 7 days | December 16, 2019 8:00 AM | January 7, 2020 5:00 PM | 2020-01-07 | 0 | 1697 | 4
1699 | Yes | Auto Scheduled | Share safety V&V review presentation with GM after review comment fix | 0 days | January 7, 2020 5:00 PM | January 7, 2020 5:00 PM | 2020-01-07 | 0 | 1698 | 4
1700 | Yes | Auto Scheduled | Safety V&V Review with GM | 1 day | January 8, 2020 8:00 AM | January 8, 2020 5:00 PM | 2020-01-08 | 0 | 1699 | 4
1701 | Yes | Auto Scheduled | Bench MRD | 436 days | January 17, 2017 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 |  | 1
1702 | Yes | Auto Scheduled | Process Documentation | 9 days | January 26, 2018 8:00 AM | February 7, 2018 5:00 PM | 2018-02-07 | 1 |  | 2
1703 | Yes | Auto Scheduled | Collect order quantity needed for pre IVER samples (bench, DV01,NSNADC samples, TCI) | 1 wk | January 26, 2018 8:00 AM | February 1, 2018 5:00 PM | 2018-02-01 | 1 |  | 3
1704 | Yes | Auto Scheduled | Create RFP for bench, DV01 and other pre IVER samples (mod C1UC parts) | 4 days | February 2, 2018 8:00 AM | February 7, 2018 5:00 PM | 2018-02-07 | 1 |  | 3
1705 | Yes | Auto Scheduled | Build samples (27 PCBs new artwork) | 46 days | June 1, 2018 8:00 AM | August 3, 2018 5:00 PM | 2018-08-03 | 1 |  | 2
1706 | Yes | Auto Scheduled | Build PCBs | 41 days | June 1, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 3
1707 | Yes | Auto Scheduled | Ship to NSI | 5 days | July 30, 2018 8:00 AM | August 3, 2018 5:00 PM | 2018-08-03 | 1 | 1706 | 3
1708 | No | Auto Scheduled | Rework IPCs with new PCB | 5 days | August 6, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1707 | 3
1709 | Yes | Auto Scheduled | Software Development | 436 days | January 17, 2017 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 |  | 2
1710 | Yes | Auto Scheduled | Define Reflash plan and tools for Bench and IVER parts | 42 days | May 2, 2018 8:00 AM | June 28, 2018 5:00 PM | 2018-06-28 | 1 |  | 3
1711 | Yes | Auto Scheduled | Develop SW Validation Test Plan (strategy) | 143 days | March 5, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 |  | 3 | Approval is missing
1712 | Yes | Auto Scheduled | 20.20.136 Release | 61 days | February 9, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 3
1713 | Yes | Auto Scheduled | Internal SW release | 2 days | February 9, 2018 8:00 AM | February 12, 2018 5:00 PM | 2018-02-12 | 1 |  | 4
1714 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 5 days | February 12, 2018 8:00 AM | February 16, 2018 5:00 PM | 2018-02-16 | 1 | 1713 | 4
1715 | Yes | Auto Scheduled | SW Validation Testing | 15 days | February 14, 2018 8:00 AM | March 6, 2018 5:00 PM | 2018-03-06 | 1 | 1713 | 4
1716 | Yes | Auto Scheduled | SW Validation Test Report | 43 days | March 7, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 | 1715 | 4
1717 | Yes | Auto Scheduled | 20.20.136.1 Release | 48 days | March 23, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 |  | 3 | per GM request 137 was changed to 136.1
1718 | Yes | Auto Scheduled | Internal SW Release | 2 days | March 23, 2018 8:00 AM | March 26, 2018 5:00 PM | 2018-03-26 | 1 |  | 4
1719 | Yes | Auto Scheduled | SW issues report and status of the SW | 2 days | March 28, 2018 8:00 AM | March 29, 2018 5:00 PM | 2018-03-29 | 1 | 1718 | 4
1720 | Yes | Auto Scheduled | Memory and Cal Release for testing (both variants) | 6 days | March 28, 2018 8:00 AM | April 4, 2018 5:00 PM | 2018-04-04 | 1 | 1718 | 4
1721 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 8 days | March 29, 2018 8:00 AM | April 9, 2018 5:00 PM | 2018-04-09 | 1 | 1718 | 4
1722 | Yes | Auto Scheduled | SW Validation Testing | 37.3 days | March 30, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 | 1721 | 4 | Need to update actual finish after baseline to 5/29
1723 | Yes | Auto Scheduled | SW Validation Test Report | 1 day | May 21, 2018 8:00 AM | May 21, 2018 5:00 PM | 2018-05-21 | 1 | 1722 | 4
1724 | Yes | Auto Scheduled | SW Release | 2 days | April 16, 2018 8:00 AM | April 17, 2018 5:00 PM | 2018-04-17 | 1 |  | 4
1725 | Yes | Auto Scheduled | 20.20.138 Release | 408 days | January 17, 2017 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 |  | 3
1726 | Yes | Auto Scheduled | Develop SW Validation Test Specification | 21 days | January 17, 2017 8:00 AM | February 14, 2017 5:00 PM | 2017-02-14 | 1 |  | 4
1727 | Yes | Auto Scheduled | SWE6 Test Case Creation | 51 days | May 7, 2018 8:00 AM | July 16, 2018 5:00 PM | 2018-07-16 | 1 |  | 4
1728 | Yes | Auto Scheduled | Internal SW release | 2 days | May 26, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 |  | 4
1729 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 3 days | May 21, 2018 8:00 AM | May 23, 2018 5:00 PM | 2018-05-23 | 1 | 1728 | 4
1730 | Yes | Auto Scheduled | SWE4 Integration Testing | 36 days | May 21, 2018 8:00 AM | July 11, 2018 5:00 PM | 2018-07-11 | 1 | 1728 | 4 | Deviation as only test cases available were tested
1731 | Yes | Auto Scheduled | SWE6 Verification Testing | 26 days | May 21, 2018 8:00 AM | June 25, 2018 5:00 PM | 2018-06-25 | 1 | 1728 | 4
1732 | Yes | Auto Scheduled | SWE6 Verification Test Report | 34 days | June 26, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1731 | 4 | Approval is missing
1733 | Yes | Auto Scheduled | SYS4 Validation Testing | 26 days | May 29, 2018 8:00 AM | July 3, 2018 5:00 PM | 2018-07-03 | 1 | 1728 | 4
1734 | Yes | Auto Scheduled | SYS5 Validation Testing | 26 days | May 29, 2018 8:00 AM | July 3, 2018 5:00 PM | 2018-07-03 | 1 | 1728 | 4
1735 | Yes | Auto Scheduled | SYS Validation Test Report | 28 days | July 4, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1733,1734 | 4 | Approval is missing
1736 | Yes | Auto Scheduled | SW Release to GM (138.0) | 0 days | May 31, 2018 8:00 AM | May 31, 2018 8:00 AM | 2018-05-31 | 1 | 1729 | 4
1737 | Yes | Auto Scheduled | Internal SW release (W3) | 1 day | June 25, 2018 8:00 AM | June 25, 2018 5:00 PM | 2018-06-25 | 1 |  | 4
1738 | Yes | Auto Scheduled | TWN (W3) | 12 days | June 26, 2018 8:00 AM | July 11, 2018 5:00 PM | 2018-07-11 | 1 |  | 4
1739 | Yes | Auto Scheduled | Master TWN | 1 day | June 26, 2018 8:00 AM | June 26, 2018 5:00 PM | 2018-06-26 | 1 |  | 5
1740 | Yes | Auto Scheduled | TWN to JPN | 2 wks | June 28, 2018 8:00 AM | July 11, 2018 5:00 PM | 2018-07-11 | 1 | 1739 | 5
1741 | Yes | Auto Scheduled | 20.20.139 Release | 143 days | March 5, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 |  | 3 | Refer to risk and issues for process deviations
1742 | Yes | Auto Scheduled | Integration Test Cases creation | 90 days | March 5, 2018 8:00 AM | July 10, 2018 5:00 PM | 2018-07-10 | 1 |  | 4
1743 | Yes | Auto Scheduled | Internal SW release | 8 days | July 24, 2018 8:00 AM | August 2, 2018 5:00 PM | 2018-08-02 | 1 |  | 4
1744 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 1 day | July 27, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 4
1745 | Yes | Auto Scheduled | SWE4 Validation Testing | 20 days | July 30, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1744 | 4
1746 | Yes | Auto Scheduled | SWE6 Verification Testing | 41 days | June 27, 2018 8:00 AM | August 22, 2018 5:00 PM | 2018-08-22 | 1 |  | 4
1747 | Yes | Auto Scheduled | SWE6 Test Case Creation and Updates | 15 days | June 27, 2018 8:00 AM | July 17, 2018 5:00 PM | 2018-07-17 | 1 |  | 5 | HCL has provided the test cases, but Oscar needs to complete the review and approve
1748 | Yes | Auto Scheduled | Test Execution | 18 days | July 30, 2018 8:00 AM | August 22, 2018 5:00 PM | 2018-08-22 | 1 | 1744 | 5
1749 | Yes | Auto Scheduled | SW Validation Test Report | 2 days | August 23, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1746 | 4
1750 | Yes | Auto Scheduled | SYS4 Validation Testing | 65 days | May 10, 2018 8:00 AM | August 8, 2018 5:00 PM | 2018-08-08 | 1 |  | 4
1751 | Yes | Auto Scheduled | Requirement analysis and Test Case creation | 35 days | May 10, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 |  | 5
1752 | Yes | Auto Scheduled | Power Mode | 15 days | May 10, 2018 8:00 AM | May 30, 2018 5:00 PM | 2018-05-30 | 1 |  | 6
1753 | Yes | Auto Scheduled | CAN | 13 days | May 14, 2018 8:00 AM | May 30, 2018 5:00 PM | 2018-05-30 | 1 |  | 6
1754 | Yes | Auto Scheduled | LIN | 19 days | May 17, 2018 8:00 AM | June 12, 2018 5:00 PM | 2018-06-12 | 1 |  | 6
1755 | Yes | Auto Scheduled | TFT | 20 days | May 14, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 |  | 6
1756 | Yes | Auto Scheduled | Telltales | 15 days | May 10, 2018 8:00 AM | May 30, 2018 5:00 PM | 2018-05-30 | 1 |  | 6
1757 | Yes | Auto Scheduled | Ethernet | 17 days | June 5, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 |  | 6
1758 | Yes | Auto Scheduled | Gages | 8 days | June 5, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 6
1759 | Yes | Auto Scheduled | IOs | 7 days | May 28, 2018 8:00 AM | June 5, 2018 5:00 PM | 2018-06-05 | 1 |  | 6
1760 | Yes | Auto Scheduled | Illumination | 8 days | June 5, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 6
1761 | Yes | Auto Scheduled | Memory | 7 days | June 19, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 |  | 6
1762 | Yes | Auto Scheduled | Segment Display | 8 days | June 4, 2018 8:00 AM | June 13, 2018 5:00 PM | 2018-06-13 | 1 |  | 6
1763 | Yes | Auto Scheduled | Bootloader | 5 days | June 19, 2018 8:00 AM | June 25, 2018 5:00 PM | 2018-06-25 | 1 |  | 6
1764 | Yes | Auto Scheduled | Test Execution | 8 days | July 28, 2018 8:00 AM | August 8, 2018 5:00 PM | 2018-08-08 | 1 | 1743,1751 | 5
1765 | Yes | Auto Scheduled | Bootloader | 2 days | July 28, 2018 8:00 AM | July 29, 2018 3:00 PM | 2018-07-29 | 1 |  | 6
1766 | Yes | Auto Scheduled | Telltales | 4 days | July 28, 2018 8:00 AM | July 31, 2018 3:00 PM | 2018-07-31 | 1 |  | 6
1767 | Yes | Auto Scheduled | Illumination | 3 days | July 28, 2018 8:00 AM | July 30, 2018 3:00 PM | 2018-07-30 | 1 |  | 6
1768 | Yes | Auto Scheduled | Power Mode | 2 days | July 30, 2018 8:00 AM | July 31, 2018 5:00 PM | 2018-07-31 | 1 |  | 6
1769 | Yes | Auto Scheduled | CAN | 3 days | August 6, 2018 8:00 AM | August 8, 2018 5:00 PM | 2018-08-08 | 1 |  | 6
1770 | Yes | Auto Scheduled | LIN | 2 days | August 6, 2018 8:00 AM | August 7, 2018 5:00 PM | 2018-08-07 | 1 |  | 6
1771 | Yes | Auto Scheduled | TFT | 2 days | July 30, 2018 8:00 AM | July 31, 2018 5:00 PM | 2018-07-31 | 1 |  | 6
1772 | Yes | Auto Scheduled | Ethernet | 2 days | July 30, 2018 8:00 AM | July 31, 2018 5:00 PM | 2018-07-31 | 1 |  | 6
1773 | Yes | Auto Scheduled | Gages | 2 days | July 30, 2018 8:00 AM | July 31, 2018 5:00 PM | 2018-07-31 | 1 |  | 6
1774 | Yes | Auto Scheduled | HWIOs | 2 days | August 6, 2018 8:00 AM | August 7, 2018 5:00 PM | 2018-08-07 | 1 |  | 6
1775 | Yes | Auto Scheduled | Memory | 2 days | August 6, 2018 8:00 AM | August 7, 2018 5:00 PM | 2018-08-07 | 1 |  | 6
1776 | Yes | Auto Scheduled | Segment Display | 2 days | July 30, 2018 8:00 AM | July 31, 2018 5:00 PM | 2018-07-31 | 1 |  | 6
1777 | Yes | Auto Scheduled | SYS5 Validation Testing | 92 days | May 14, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 |  | 4
1778 | Yes | Auto Scheduled | Requirements analysis and Test Case creation (SRS v3.0) | 55 days | May 14, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 5
1779 | Yes | Auto Scheduled | Bootloader | 10 days | May 14, 2018 8:00 AM | May 25, 2018 5:00 PM | 2018-05-25 | 1 |  | 6
1780 | Yes | Auto Scheduled | Power Moding | 12 days | May 14, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 |  | 6
1781 | Yes | Auto Scheduled | Line Test | 12 days | May 14, 2018 8:00 AM | May 29, 2018 5:00 PM | 2018-05-29 | 1 |  | 6
1782 | Yes | Auto Scheduled | CAN | 14 days | May 14, 2018 8:00 AM | May 31, 2018 5:00 PM | 2018-05-31 | 1 |  | 6
1783 | Yes | Auto Scheduled | Gauges | 14 days | May 14, 2018 8:00 AM | May 31, 2018 5:00 PM | 2018-05-31 | 1 |  | 6
1784 | Yes | Auto Scheduled | LIN | 8 days | May 30, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 |  | 6
1785 | Yes | Auto Scheduled | Cyber Security | 6 days | May 30, 2018 8:00 AM | June 6, 2018 5:00 PM | 2018-06-06 | 1 |  | 6
1786 | Yes | Auto Scheduled | Ethernet | 6 days | June 15, 2018 8:00 AM | June 22, 2018 5:00 PM | 2018-06-22 | 1 |  | 6
1787 | Yes | Auto Scheduled | Telltales | 6 days | June 1, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 |  | 6
1788 | Yes | Auto Scheduled | Illumination | 6 days | June 1, 2018 8:00 AM | June 8, 2018 5:00 PM | 2018-06-08 | 1 |  | 6
1789 | Yes | Auto Scheduled | TFT | 7 days | May 28, 2018 8:00 AM | June 5, 2018 5:00 PM | 2018-06-05 | 1 |  | 6
1790 | Yes | Auto Scheduled | NVM | 7 days | June 11, 2018 8:00 AM | June 19, 2018 5:00 PM | 2018-06-19 | 1 |  | 6
1791 | Yes | Auto Scheduled | Functional Safety | 6 days | June 7, 2018 8:00 AM | June 14, 2018 5:00 PM | 2018-06-14 | 1 |  | 6
1792 | Yes | Auto Scheduled | Software Stress Test Case creation | 3 wks | July 9, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 |  | 6
1793 | Yes | Auto Scheduled | Fuzz Test CG4579 Test Case creation | 7 days | August 6, 2018 8:00 AM | August 14, 2018 5:00 PM | 2018-08-14 | 1 |  | 5
1794 | Yes | Auto Scheduled | Test Execution | 37 days | July 28, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 | 1743 | 5
1795 | Yes | Auto Scheduled | Features | 17 days | July 28, 2018 8:00 AM | August 21, 2018 5:00 PM | 2018-08-21 | 1 |  | 6
1796 | Yes | Auto Scheduled | Bootloader | 2 days | July 28, 2018 8:00 AM | July 29, 2018 3:00 PM | 2018-07-29 | 1 |  | 7
1797 | Yes | Auto Scheduled | Telltales | 3 days | July 28, 2018 8:00 AM | July 30, 2018 3:00 PM | 2018-07-30 | 1 |  | 7
1798 | Yes | Auto Scheduled | TFT | 2 days | July 28, 2018 8:00 AM | July 29, 2018 3:00 PM | 2018-07-29 | 1 |  | 7
1799 | Yes | Auto Scheduled | Illumination | 4 days | July 30, 2018 8:00 AM | August 2, 2018 5:00 PM | 2018-08-02 | 1 |  | 7
1800 | Yes | Auto Scheduled | Power Moding | 3 days | July 30, 2018 8:00 AM | August 1, 2018 5:00 PM | 2018-08-01 | 1 |  | 7
1801 | Yes | Auto Scheduled | Gauges | 2 days | July 31, 2018 8:00 AM | August 1, 2018 5:00 PM | 2018-08-01 | 1 |  | 7
1802 | Yes | Auto Scheduled | Ethernet | 3 days | August 17, 2018 8:00 AM | August 21, 2018 5:00 PM | 2018-08-21 | 1 |  | 7
1803 | Yes | Auto Scheduled | Stress Testing | 7 days | August 2, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 |  | 7
1804 | Yes | Auto Scheduled | Line Test | 3 days | August 8, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 |  | 7
1805 | Yes | Auto Scheduled | CAN | 7 days | August 2, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 |  | 7
1806 | Yes | Auto Scheduled | LIN | 4 days | August 8, 2018 8:00 AM | August 13, 2018 5:00 PM | 2018-08-13 | 1 |  | 7
1807 | Yes | Auto Scheduled | Cyber Security | 6 days | August 6, 2018 8:00 AM | August 13, 2018 5:00 PM | 2018-08-13 | 1 |  | 7
1808 | Yes | Auto Scheduled | NVM | 7 days | August 6, 2018 8:00 AM | August 14, 2018 5:00 PM | 2018-08-14 | 1 |  | 7
1809 | Yes | Auto Scheduled | Functional Safety | 2 days | August 6, 2018 8:00 AM | August 7, 2018 5:00 PM | 2018-08-07 | 1 |  | 7
1810 | Yes | Auto Scheduled | Compliance Testing | 27 days | August 13, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 |  | 6
1811 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance | 20 days | August 13, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 1743 | 7
1812 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming | 25 days | August 13, 2018 8:00 AM | September 14, 2018 5:00 PM | 2018-09-14 | 1 | 1743 | 7
1813 | Yes | Auto Scheduled | CG3877 - CAN Physical Layer Test | 27 days | August 13, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 | 1743 | 7
1814 | No | Auto Scheduled | CG3689 - Ethernet AVB Device Test | 19 days | September 17, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 | 1743 | 7 | Confirm testing duration
1815 | No | Auto Scheduled | CG4111 - Global B Serial Data and Diagnostics Test | 18 days | September 24, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 |  | 7
1816 | No | Auto Scheduled | Fuzz Test Execution | 25 days | August 15, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 | 1793 | 6
1817 | Yes | Auto Scheduled | SYS Validation Test Report | 1 day | September 19, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1750,1777 | 4
1818 | No | Auto Scheduled | CG3001 Release | 1 day | June 29, 2018 8:00 AM | June 29, 2018 5:00 PM | 2018-06-29 | 1 |  | 4 | GM confirmed it is not needed
1819 | Yes | Auto Scheduled | TWN | 11 days | July 30, 2018 8:00 AM | August 13, 2018 5:00 PM | 2018-08-13 | 1 |  | 4
1820 | Yes | Auto Scheduled | Master TWN | 1 day | July 30, 2018 8:00 AM | July 30, 2018 5:00 PM | 2018-07-30 | 1 | 1743 | 5
1821 | Yes | Auto Scheduled | TWN to JPN | 2 wks | July 31, 2018 8:00 AM | August 13, 2018 5:00 PM | 2018-08-13 | 1 | 1820 | 5
1822 | Yes | Auto Scheduled | CSV&V Release to customer (CG2999) Initial | 12 days | June 11, 2018 8:00 AM | June 26, 2018 5:00 PM | 2018-06-26 | 1 |  | 4
1823 | Yes | Auto Scheduled | CG4422 (Form for CG2999) | 12 days | June 11, 2018 8:00 AM | June 26, 2018 5:00 PM | 2018-06-26 | 1 |  | 5
1824 | Yes | Auto Scheduled | CSV&V Release to customer (CG2999) Final | 10 days | August 6, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 |  | 4
1825 | Yes | Auto Scheduled | CG4422 (Form for CG2999) | 10 days | August 6, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 |  | 5
1826 | Yes | Auto Scheduled | SW release to GM | 0 days | August 3, 2018 8:00 AM | August 3, 2018 8:00 AM | 2018-08-03 | 1 |  | 4
1827 | Yes | Auto Scheduled | Functional Safety (Concept, Requirements and Design phase) | 11 days | April 30, 2018 8:00 AM | May 15, 2018 8:00 AM | 2018-05-15 | 1 |  | 2
1828 | Yes | Auto Scheduled | System Safety Concept | 5 days | April 30, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 3
1829 | Yes | Auto Scheduled | SCS-057 Safety Concept Review Presentation | 5 days | April 30, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 4
1830 | Yes | Auto Scheduled | SCS-058 Safety Requirement Review Presentation | 5 days | April 30, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 4
1831 | Yes | Auto Scheduled | SCS-059 Safety Design Review Presentation | 5 days | April 30, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 4
1832 | Yes | Auto Scheduled | System Safety Requirements | 1 day | May 14, 2018 8:00 AM | May 14, 2018 5:00 PM | 2018-05-14 | 1 |  | 3
1833 | Yes | Auto Scheduled | System Safety Design | 1 day | May 14, 2018 8:00 AM | May 14, 2018 5:00 PM | 2018-05-14 | 1 |  | 3
1834 | Yes | Auto Scheduled | Concept, Design & Requirements Phase Review with GM | 0 days | May 15, 2018 8:00 AM | May 15, 2018 8:00 AM | 2018-05-15 | 1 | 1828,1832,1833 | 3
1835 | Yes | Auto Scheduled | Design Validation - DV | 746 days | May 6, 2016 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 1
1836 | Yes | Auto Scheduled | Mechanical Development - DV | 176 days | November 17, 2017 8:00 AM | July 20, 2018 5:00 PM | 2018-07-20 | 1 |  | 2
1837 | Yes | Auto Scheduled | Mechanical Design | 14 wks | November 17, 2017 8:00 AM | March 8, 2018 5:00 PM | 2018-03-08 | 1 |  | 3
1838 | Yes | Auto Scheduled | Draft LED Management Sheet | 3 wks | November 17, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3 | 12/4/2017: on track
1839 | Yes | Auto Scheduled | Draft PCB Interface DWG | 3 wks | November 17, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1840 | Yes | Auto Scheduled | Variation List - First 3 pages | 3 wks | November 17, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1841 | Yes | Auto Scheduled | Final LED Management Sheet | 3 wks | November 17, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1842 | Yes | Auto Scheduled | Final PCB Interface DWG | 3 wks | November 17, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1843 | Yes | Auto Scheduled | DFMEA | 0 days | November 17, 2017 5:00 PM | November 17, 2017 5:00 PM | 2017-11-17 | 1 |  | 3 | we are missing some documents from Opel
1844 | Yes | Auto Scheduled | Graphic freeze from GM | 0 days | November 17, 2017 5:00 PM | November 17, 2017 5:00 PM | 2017-11-17 | 1 |  | 3 | there are some small changes on the graphics received today 12/4
1845 | Yes | Auto Scheduled | Graphic Check | 1 wk | November 17, 2017 8:00 AM | November 27, 2017 5:00 PM | 2017-11-27 | 1 |  | 3 | we are still missing the final drawings from GM
1846 | Yes | Auto Scheduled | NS Review of graphics | 2 wks | November 28, 2017 8:00 AM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3 | Anshuman to review graphics and if everything is OK, he will send them to Japan for review
1847 | Yes | Auto Scheduled | Supplier Selection and Drawing Release | 150 days | December 22, 2017 5:00 PM | July 20, 2018 5:00 PM | 2018-07-20 | 1 |  | 3
1848 | Yes | Auto Scheduled | Advanced drawing for tooling quotes | 1 day | January 16, 2018 8:00 AM | January 16, 2018 5:00 PM | 2018-01-16 | 1 |  | 4
1849 | Yes | Auto Scheduled | Advanced BOM released for Quoting DV02 and IVER | 1 day | January 16, 2018 8:00 AM | January 16, 2018 5:00 PM | 2018-01-16 | 1 |  | 4
1850 | Yes | Auto Scheduled | Advanced BOM for DV01 Parts (Modified C1UB) | 0 days | December 22, 2017 5:00 PM | December 22, 2017 5:00 PM | 2017-12-22 | 1 |  | 4
1851 | Yes | Auto Scheduled | Final Supplier selection | 2 wks | January 12, 2018 8:00 AM | January 25, 2018 5:00 PM | 2018-01-25 | 1 |  | 4
1852 | Yes | Auto Scheduled | Tooling Design Review | 14.6 wks | January 26, 2018 8:00 AM | May 8, 2018 5:00 PM | 2018-05-08 | 1 |  | 4
1853 | Yes | Auto Scheduled | Applique final drawing release | 1 day | February 23, 2018 8:00 AM | February 23, 2018 5:00 PM | 2018-02-23 | 1 |  | 4 | Include PCE 024 activities
1854 | Yes | Auto Scheduled | Kick off lens & Visor 3D & 2D | 1 day | May 15, 2018 8:00 AM | May 15, 2018 5:00 PM | 2018-05-15 | 1 | 1902 | 4
1855 | Yes | Auto Scheduled | OK to tool Drawing from Customer | 0 days | May 14, 2018 8:00 AM | May 14, 2018 8:00 AM | 2018-05-14 | 1 |  | 4 | Include PCE 021 activities. No impact on release time.
1856 | Yes | Auto Scheduled | Plastic Outer case and Chrome ring Drawing Release | 0 days | May 14, 2018 5:00 PM | May 14, 2018 5:00 PM | 2018-05-14 | 1 | 1902 | 4
1857 | Yes | Auto Scheduled | Final IVER BOM | 9 days | May 8, 2018 8:00 AM | May 18, 2018 5:00 PM | 2018-05-18 | 1 |  | 4 | Include PCE 020 activities. No impact on release time.
1858 | Yes | Auto Scheduled | Final Variation List | 29 days | June 8, 2018 8:00 AM | July 20, 2018 5:00 PM | 2018-07-20 | 1 | 1857 | 4
1859 | Yes | Auto Scheduled | Hardware Development - DV | 746 days | May 6, 2016 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 2
1860 | Yes | Auto Scheduled | Final LED Management Sheet Received | 0 days | December 11, 2017 5:00 PM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1861 | Yes | Auto Scheduled | Final PCB Interface DWG Received | 0 days | December 11, 2017 5:00 PM | December 11, 2017 5:00 PM | 2017-12-11 | 1 |  | 3
1862 | Yes | Auto Scheduled | DV and IVER PCB BOM Release | 14.2 wks | January 26, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 3 | Include PCE 004, 018, 019, 023 activities. No impact on release time.
1863 | Yes | Auto Scheduled | DV and IVER PCB BOM Release | 56.4 days | January 26, 2018 8:00 AM | May 4, 2018 5:00 PM | 2018-05-04 | 1 |  | 3 | Include PCE 004, 018, 019, 023 activities. No impact on release time.
1864 | Yes | Auto Scheduled | PCB prototype check template | 12.4 wks | January 26, 2018 8:00 AM | April 23, 2018 5:00 PM | 2018-04-23 | 1 |  | 3
1865 | Yes | Auto Scheduled | NS PCB Blank | 4 wks | June 11, 2018 8:00 AM | July 6, 2018 5:00 PM | 2018-07-06 | 1 | 1863,1864,1902 | 3
1866 | Yes | Auto Scheduled | Deliver Line Test to NS | 270 days | February 15, 2018 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 3
1867 | Yes | Auto Scheduled | NS PCB Assy& testing | 5 wks | July 9, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1865 | 3
1868 | Yes | Auto Scheduled | NS Ship PCB to NSII | 1 wk | August 13, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 | 1867 | 3
1869 | Yes | Auto Scheduled | System examination meeting(0) | 0 days | May 6, 2016 8:00 AM | May 6, 2016 8:00 AM | 2016-05-06 | 1 |  | 3
1870 | Yes | Auto Scheduled | Sys / SW to decide Micro Strategy, Architecture, & Type | 0 days | May 6, 2016 8:00 AM | May 6, 2016 8:00 AM | 2016-05-06 | 1 |  | 4
1871 | Yes | Auto Scheduled | SW/SYS: Decide External or Emulated EEPROM & Capacity | 0 days | May 6, 2016 8:00 AM | May 6, 2016 8:00 AM | 2016-05-06 | 1 |  | 4
1872 | Yes | Auto Scheduled | System examination meeting(1) | 317 days | January 16, 2017 8:00 AM | April 4, 2018 5:00 PM | 2018-04-04 | 1 |  | 3
1873 | Yes | Auto Scheduled | HW: Complete Block Diagram | 0 days | November 21, 2017 8:00 AM | November 21, 2017 8:00 AM | 2017-11-21 | 1 |  | 4
1874 | Yes | Auto Scheduled | MECHA: Provide Stepper Motor Movement Type, Pointer Inertial Moment all per variation | 5 days | January 25, 2018 8:00 AM | January 31, 2018 5:00 PM | 2018-01-31 | 1 |  | 4
1875 | Yes | Auto Scheduled | SW/SYS: Stepper Motor Drive Duty (Normal Operation & Initial Response) | 10 days | January 25, 2018 8:00 AM | February 7, 2018 5:00 PM | 2018-02-07 | 1 |  | 4
1876 | Yes | Auto Scheduled | SW/SYS: Decide Strategy for Linetest Communication | 50 days | January 25, 2018 8:00 AM | April 4, 2018 5:00 PM | 2018-04-04 | 1 |  | 4
1877 | Yes | Auto Scheduled | SW/SYS: Strategy for data Re-writing for all ROM | 50 days | January 25, 2018 8:00 AM | April 4, 2018 5:00 PM | 2018-04-04 | 1 |  | 4
1878 | Yes | Auto Scheduled | SW/SYS: Requirements for Switchbox | 0 days | January 16, 2017 8:00 AM | January 16, 2017 8:00 AM | 2017-01-16 | 1 |  | 4
1879 | Yes | Auto Scheduled | SW/SYS: HW based functions implementation schedule & All Clocks | 0 days | January 30, 2017 8:00 AM | January 30, 2017 8:00 AM | 2017-01-30 | 1 |  | 4
1880 | Yes | Auto Scheduled | System examination meeting(2) | 206 days | January 9, 2017 8:00 AM | October 25, 2017 8:00 AM | 2017-10-25 | 1 |  | 3
1881 | Yes | Auto Scheduled | HW: Port Function Definition & HW Settings | 0 days | October 25, 2017 8:00 AM | October 25, 2017 8:00 AM | 2017-10-25 | 1 |  | 4
1882 | Yes | Auto Scheduled | HW: Provide Initial Proposal for System Frequencies | 0 days | January 9, 2017 8:00 AM | January 9, 2017 8:00 AM | 2017-01-09 | 1 |  | 4
1883 | Yes | Auto Scheduled | SW/SYS: Provide and Set Full System Clock Tree | 0 days | January 16, 2017 8:00 AM | January 16, 2017 8:00 AM | 2017-01-16 | 1 |  | 4
1884 | Yes | Auto Scheduled | HW: Review Clock tree and Provide Feedback on selected Frequencies | 0 days | January 23, 2017 8:00 AM | January 23, 2017 8:00 AM | 2017-01-23 | 1 |  | 4
1885 | Yes | Auto Scheduled | System examination meeting(3) | 10 days | January 25, 2018 8:00 AM | February 7, 2018 5:00 PM | 2018-02-07 | 1 |  | 3
1886 | Yes | Auto Scheduled | HW: Create HW Power Sequence Spec | 5 days | January 25, 2018 8:00 AM | January 31, 2018 5:00 PM | 2018-01-31 | 1 |  | 4
1887 | Yes | Auto Scheduled | SW/SYS: Create SW Power Sequence Spec | 10 days | January 25, 2018 8:00 AM | February 7, 2018 5:00 PM | 2018-02-07 | 1 |  | 4
1888 | Yes | Auto Scheduled | Software Development - DV | 173.5 days | January 15, 2018 8:00 AM | September 13, 2018 12:00 PM | 2018-09-13 | 1 |  | 2
1889 | Yes | Auto Scheduled | DV EMC & ENV Software | 173.5 days | January 15, 2018 8:00 AM | September 13, 2018 12:00 PM | 2018-09-13 | 1 |  | 3
1890 | Yes | Auto Scheduled | EMC SW/Canoe Panel Draft | 50 days | January 15, 2018 8:00 AM | March 23, 2018 5:00 PM | 2018-03-23 | 1 |  | 4 | 2/12/2018 SW will create the panels by April 2018
1891 | Yes | Auto Scheduled | EMC DV Spec | 58 days | April 3, 2018 8:00 AM | June 21, 2018 5:00 PM | 2018-06-21 | 1 |  | 4 | Update actual Start date to 5/21 once baselined
1892 | Yes | Auto Scheduled | EMC DV Test software released | 141 days | February 19, 2018 8:00 AM | September 5, 2018 5:00 PM | 2018-09-05 | 1 | 1891 | 4
1893 | Yes | Auto Scheduled | EMC SW/CANoe panel Final | 93 days | February 19, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 | 1890 | 4
1894 | Yes | Auto Scheduled | EMC & DV SW | 40 days | June 28, 2018 8:00 AM | August 22, 2018 5:00 PM | 2018-08-22 | 1 | 1893 | 4
1895 | Yes | Auto Scheduled | DV CANoe Panel | 8 days | July 26, 2018 8:00 AM | August 29, 2018 12:00 PM | 2018-08-29 | 1 | 1894 | 4
1896 | Yes | Auto Scheduled | TWN for Sabina | 2 days | August 29, 2018 1:00 PM | August 31, 2018 12:00 PM | 2018-08-31 | 1 |  | 4
1897 | Yes | Auto Scheduled | Master TWN | 1 day | August 29, 2018 1:00 PM | August 30, 2018 12:00 PM | 2018-08-30 | 1 | 1895 | 5
1898 | Yes | Auto Scheduled | TWN to Sabina | 1 day | August 30, 2018 1:00 PM | August 31, 2018 12:00 PM | 2018-08-31 | 1 | 1897 | 5
1899 | Yes | Auto Scheduled | ENV DV test software validated by Sabina with Galaxy | 11 days | August 29, 2018 1:00 PM | September 13, 2018 12:00 PM | 2018-09-13 | 1 | 1895 | 4
1900 | Yes | Auto Scheduled | Tooling Timing - DV | 179 days | January 2, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 |  | 2
1901 | Yes | Auto Scheduled | Receive Tooling PO from GM | 0 days | May 4, 2018 8:00 AM | May 4, 2018 8:00 AM | 2018-05-04 | 1 |  | 3
1902 | Yes | Auto Scheduled | NSI PO to suppliers | 14 days | May 4, 2018 8:00 AM | May 23, 2018 5:00 PM | 2018-05-23 | 1 | 1901 | 3
1903 | Yes | Auto Scheduled | Lens Tooling | 50 days | May 24, 2018 8:00 AM | August 1, 2018 5:00 PM | 2018-08-01 | 1 |  | 3
1904 | Yes | Auto Scheduled | Tooling lead time | 5 wks | May 24, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 | 1854,1902 | 4
1905 | Yes | Auto Scheduled | T0 part including measurement data / shipping | 2 wks | June 28, 2018 8:00 AM | July 11, 2018 5:00 PM | 2018-07-11 | 1 | 1904 | 4
1906 | Yes | Auto Scheduled | T1 part including measurement data / shipping | 1 wk | July 12, 2018 8:00 AM | July 18, 2018 5:00 PM | 2018-07-18 | 1 | 1905 | 4
1907 | Yes | Auto Scheduled | Mold Lens DV/IVER parts | 1 wk | July 19, 2018 8:00 AM | July 25, 2018 5:00 PM | 2018-07-25 | 1 | 1906 | 4
1908 | Yes | Auto Scheduled | Ship to welder | 1 wk | July 26, 2018 8:00 AM | August 1, 2018 5:00 PM | 2018-08-01 | 1 | 1907 | 4
1909 | Yes | Auto Scheduled | Visor Tooling | 63.5 days | May 24, 2018 8:00 AM | August 21, 2018 12:00 PM | 2018-08-21 | 1 |  | 3
1910 | Yes | Auto Scheduled | Tooling lead time | 5.5 wks | May 24, 2018 8:00 AM | July 2, 2018 12:00 PM | 2018-07-02 | 1 | 1854,1902 | 4
1911 | Yes | Auto Scheduled | T1 part including measurement data / shipping | 2 wks | July 2, 2018 1:00 PM | July 16, 2018 12:00 PM | 2018-07-16 | 1 | 1910 | 4
1912 | Yes | Auto Scheduled | T2 part including measurement data / shipping | 1 wk | July 16, 2018 1:00 PM | July 23, 2018 12:00 PM | 2018-07-23 | 1 | 1911 | 4
1913 | Yes | Auto Scheduled | Mold Visor weilding trail parts | 2 days | July 16, 2018 1:00 PM | July 18, 2018 12:00 PM | 2018-07-18 | 1 | 1911 | 4
1914 | Yes | Auto Scheduled | Ship Visor to welder | 1 wk | July 18, 2018 1:00 PM | July 25, 2018 12:00 PM | 2018-07-25 | 1 | 1913 | 4
1915 | Yes | Auto Scheduled | Graining | 24 days | July 18, 2018 1:00 PM | August 21, 2018 12:00 PM | 2018-08-21 | 1 |  | 4
1916 | Yes | Auto Scheduled | Round trip & graining | 17 days | July 18, 2018 1:00 PM | August 10, 2018 12:00 PM | 2018-08-10 | 1 | 1913 | 5
1917 | Yes | Auto Scheduled | Mold grain visors | 3 days | August 10, 2018 1:00 PM | August 15, 2018 12:00 PM | 2018-08-15 | 1 | 1916 | 5
1918 | Yes | Auto Scheduled | Ship grained visor to welder | 4 days | August 15, 2018 1:00 PM | August 21, 2018 12:00 PM | 2018-08-21 | 1 | 1917 | 5
1919 | Yes | Auto Scheduled | Back Cover Tooling (Outer Case) | 72 days | May 24, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 |  | 3
1920 | Yes | Auto Scheduled | Tooling lead time | 7 wks | May 24, 2018 8:00 AM | July 13, 2018 5:00 PM | 2018-07-13 | 1 | 1856,1902 | 4
1921 | Yes | Auto Scheduled | T0 part including measurement data / shipping | 2 wks | July 16, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1920 | 4
1922 | Yes | Auto Scheduled | T1 part including measurement data / shipping | 2 wks | July 30, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1921 | 4
1923 | Yes | Auto Scheduled | Mold Back Cover DV/IVER parts | 2 wks | August 13, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1922 | 4
1924 | Yes | Auto Scheduled | Ship Back cover to NSII | 1 wk | August 27, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 1923 | 4
1925 | Yes | Auto Scheduled | Decorative Ring | 67 days | May 24, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 |  | 3
1926 | Yes | Auto Scheduled | Tooling lead time | 11 wks | May 24, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1856,1902 | 4
1927 | Yes | Auto Scheduled | Mold Decorative DV/IVER parts | 1 wk | August 13, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 | 1926 | 4
1928 | Yes | Auto Scheduled | Ship Decorative ring to NSII for heat staking | 1 wk | August 20, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 1927 | 4
1929 | Yes | Auto Scheduled | Applique Tooling | 147 days | January 2, 2018 8:00 AM | July 25, 2018 5:00 PM | 2018-07-25 | 1 |  | 3
1930 | Yes | Auto Scheduled | Film& Drawing Preparation | 2 wks | January 2, 2018 8:00 AM | January 15, 2018 5:00 PM | 2018-01-15 | 1 |  | 4
1931 | Yes | Auto Scheduled | Screen preparation and printing | 2 wks | January 8, 2018 8:00 AM | January 19, 2018 5:00 PM | 2018-01-19 | 1 |  | 4
1932 | Yes | Auto Scheduled | Forming and applique blank tooling lead time | 5 wks | May 24, 2018 8:00 AM | June 27, 2018 5:00 PM | 2018-06-27 | 1 | 1902 | 4
1933 | Yes | Auto Scheduled | forming and punching | 2 wks | June 28, 2018 8:00 AM | July 13, 2018 5:00 PM | 2018-07-13 | 1 | 1932 | 4
1934 | Yes | Auto Scheduled | applique - shipping to OB supplier | 3 days | July 16, 2018 8:00 AM | July 18, 2018 5:00 PM | 2018-07-18 | 1 | 1933 | 4
1935 | Yes | Auto Scheduled | Applique shipping to NSII for LEG2 and LEG6 - no OB required | 1 wk | July 19, 2018 8:00 AM | July 25, 2018 5:00 PM | 2018-07-25 | 1 | 1934 | 4
1936 | Yes | Auto Scheduled | Optical Bonding | 37 days | July 19, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 |  | 3
1937 | Yes | Auto Scheduled | TFT to NS | 1 wk | July 19, 2018 8:00 AM | July 25, 2018 5:00 PM | 2018-07-25 | 1 | 1938SF | 4
1938 | Yes | Auto Scheduled | Receive applique | 2 days | July 26, 2018 8:00 AM | July 27, 2018 5:00 PM | 2018-07-27 | 1 | 1935,3583 | 4
1939 | Yes | Auto Scheduled | Optical bonding process | 5 wks | July 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 1938 | 4
1940 | Yes | Auto Scheduled | Ship OB assembly to NSII for heat staking | 1 wk | September 3, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 1939 | 4
1941 | Yes | Auto Scheduled | Laser Welding (Lens+Visor) | 68.5 days | May 24, 2018 8:00 AM | August 28, 2018 12:00 PM | 2018-08-28 | 1 |  | 3
1942 | Yes | Auto Scheduled | Laser Weld tooling lead time | 11 wks | May 24, 2018 8:00 AM | August 10, 2018 5:00 PM | 2018-08-10 | 1 | 1854,1902 | 4
1943 | Yes | Auto Scheduled | Tune Weld fix | 3 days | August 13, 2018 8:00 AM | August 15, 2018 5:00 PM | 2018-08-15 | 1 | 1942,1908,1914 | 4
1944 | Yes | Auto Scheduled | Weld samples | 3 days | August 21, 2018 1:00 PM | August 24, 2018 12:00 PM | 2018-08-24 | 1 | 1943,1908,1918 | 4
1945 | Yes | Auto Scheduled | Ship lens+Visor assembly to NSII | 2 days | August 24, 2018 1:00 PM | August 28, 2018 12:00 PM | 2018-08-28 | 1 | 1944 | 4
1946 | Yes | Auto Scheduled | DV Testing | 312 days | December 8, 2017 5:00 PM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 2
1947 | Yes | Auto Scheduled | DV Test Plan | 209 days | December 8, 2017 5:00 PM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 3
1948 | Yes | Auto Scheduled | EMC Test Plan | 75 days | December 8, 2017 5:00 PM | March 23, 2018 5:00 PM | 2018-03-23 | 1 |  | 4
1949 | Yes | Auto Scheduled | Draft EMC test plan | 0 days | December 8, 2017 5:00 PM | December 8, 2017 5:00 PM | 2017-12-08 | 1 |  | 5
1950 | Yes | Auto Scheduled | Final EMC test plan | 20 days | February 12, 2018 8:00 AM | March 9, 2018 5:00 PM | 2018-03-09 | 1 |  | 5
1951 | Yes | Auto Scheduled | EMC test plan negotiation with Richard Grunow | 11 days | March 9, 2018 8:00 AM | March 23, 2018 5:00 PM | 2018-03-23 | 1 |  | 5 | 2/12/2018 the plan is to have a meeting with Pat next week
1952 | Yes | Auto Scheduled | EMC DV test plan approval | 0 days | March 23, 2018 8:00 AM | March 23, 2018 8:00 AM | 2018-03-23 | 1 | 1951 | 5
1953 | Yes | Auto Scheduled | ENV Test Plan | 182 days | January 17, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 4
1954 | Yes | Auto Scheduled | Environmental Test Plan Creation | 5 days | January 17, 2018 8:00 AM | January 23, 2018 5:00 PM | 2018-01-23 | 1 |  | 5
1955 | Yes | Auto Scheduled | Environmental Test Plan update | 12 wks | May 1, 2018 8:00 AM | July 23, 2018 5:00 PM | 2018-07-23 | 1 |  | 5
1956 | Yes | Auto Scheduled | ENV Test Plan Submission to Customer and Negotiation | 1 wk | July 24, 2018 8:00 AM | July 30, 2018 5:00 PM | 2018-07-30 | 1 | 1955 | 5
1957 | Yes | Auto Scheduled | Update ENV Test Plan | 1 wk | July 31, 2018 8:00 AM | August 6, 2018 5:00 PM | 2018-08-06 | 1 | 1956 | 5
1958 | Yes | Auto Scheduled | ENV Tests Plan approval (DV01) | 18 days | August 7, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 | 1957 | 5
1959 | Yes | Auto Scheduled | ENV Test Plan Update (DV01) - Resubmit for Vibration Fixture deviation | 15 days | August 31, 2018 8:00 AM | September 20, 2018 5:00 PM | 2018-09-20 | 1 | 1958 | 5
1960 | Yes | Auto Scheduled | ENV Test Plan approval (DV01) - Resubmit for Vibration Fixture deviation | 5 days | September 21, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 | 1959 | 5
1961 | Yes | Auto Scheduled | ENV Tests Plan approval (DV02) | 32 days | August 7, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1957 | 5
1962 | Yes | Auto Scheduled | DV Part Fab/testing | 24 days | August 16, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 |  | 3
1963 | Yes | Auto Scheduled | DV Parts build | 24 days | August 16, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 |  | 4
1964 | Yes | Auto Scheduled | Test request / test specimen sheet format | 2 days | August 21, 2018 8:00 AM | August 22, 2018 5:00 PM | 2018-08-22 | 1 | 1958 | 5
1965 | Yes | Auto Scheduled | Receive PCB board | 2 days | August 16, 2018 8:00 AM | August 17, 2018 5:00 PM | 2018-08-17 | 1 |  | 5
1966 | Yes | Auto Scheduled | Flash PCB baords with DV test SW | 2 days | August 31, 2018 1:00 PM | September 4, 2018 12:00 PM | 2018-09-04 | 1 | 1965,1898 | 5
1967 | Yes | Auto Scheduled | Receive ME components | 2 days | September 6, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 1945 | 5
1968 | Yes | Auto Scheduled | Trial Assembly | 1 day | September 5, 2018 8:00 AM | September 5, 2018 5:00 PM | 2018-09-05 | 1 | 1966 | 5
1969 | Yes | Auto Scheduled | Build clusters | 1 wk | September 10, 2018 8:00 AM | September 14, 2018 5:00 PM | 2018-09-14 | 1 | 1968,1967 | 5
1970 | Yes | Auto Scheduled | DV samples delivery | 2 days | September 17, 2018 8:00 AM | September 18, 2018 5:00 PM | 2018-09-18 | 1 | 1969 | 5
1971 | Yes | Auto Scheduled | DV01 (main DV) | 112 days | September 17, 2018 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 3
1972 | Yes | Auto Scheduled | DV Test Execution | 58 days | September 17, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 |  | 4
1973 | Yes | Auto Scheduled | Leg 0a and 0b | 21 days | September 19, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 |  | 5
1974 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR (Leg 0a) | 1 day | October 4, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 1970 | 6
1975 | Yes | Auto Scheduled | Cross Section and Inspection | 3 days | October 15, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 | 1974 | 6
1976 | Yes | Auto Scheduled | Thermal Cycle Profile Development | 8 days | September 19, 2018 8:00 AM | September 28, 2018 5:00 PM | 2018-09-28 | 1 | 1970 | 6
1977 | Yes | Auto Scheduled | Vibration Transmissibility Demonstration | 10 days | September 25, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 1970 | 6
1978 | Yes | Auto Scheduled | Leg 1 | 58 days | September 17, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 |  | 5
1979 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 1 day | September 17, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1970 | 6
1980 | Yes | Auto Scheduled | Low Temperature Wakeup | 2 days | September 19, 2018 8:00 AM | September 20, 2018 5:00 PM | 2018-09-20 | 1 | 1979 | 6
1981 | Yes | Auto Scheduled | High Temperature Degradation | 5.38 edays | September 21, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 1980 | 6
1982 | Yes | Auto Scheduled | Mechanical Shock Pothole | 1 day | October 8, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 1981 | 6
1983 | Yes | Auto Scheduled | Vibration with Thermal Cycling | 7 days | October 8, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 | 1982 | 6
1984 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 2 days | October 22, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 1983 | 6
1985 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 5 days | October 31, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 1984 | 6
1986 | Yes | Auto Scheduled | Cross Section and Inspection | 4 days | November 30, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 1985 | 6
1987 | Yes | Auto Scheduled | Leg 2a | 37 days | September 17, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 5
1988 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 1 day | September 17, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1970 | 6
1989 | Yes | Auto Scheduled | Low Temperature Wakeup | 1 day | September 19, 2018 8:00 AM | September 20, 2018 5:00 PM | 2018-09-20 | 1 | 1988 | 6
1990 | Yes | Auto Scheduled | Humid Heat Cyclic | 10.38 edays | September 21, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 6
1991 | Yes | Auto Scheduled | Humid Heat Constant | 10.38 edays | September 21, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 6
1992 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 2 days | October 3, 2018 8:00 AM | October 4, 2018 5:00 PM | 2018-10-04 | 1 | 1991 | 6
1993 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 5 days | October 31, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 1018 | 6
1994 | Yes | Auto Scheduled | Leg 2b | 31 days | September 17, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 |  | 5
1995 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 1 day | September 17, 2018 8:00 AM | September 17, 2018 5:00 PM | 2018-09-17 | 1 | 1970 | 6
1996 | Yes | Auto Scheduled | Low Temperature Wakeup | 2 days | September 20, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 1995 | 6
1997 | Yes | Auto Scheduled | Thermal Shock Air to Air (100 cycles) | 7 days | September 28, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 1996 | 6
1998 | Yes | Auto Scheduled | Power Temperature Cycle (100 cycles) | 8 days | October 18, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 | 1997 | 6
1999 | Yes | Auto Scheduled | 1 point functional/parametric check | 1 day | October 29, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 | 1998 | 6
2000 | Yes | Auto Scheduled | Leg 3 | 37 days | September 17, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 5
2001 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 3 days | September 17, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1970 | 6
2002 | Yes | Auto Scheduled | Low Temperature Wakeup | 2 days | September 20, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 2001 | 6
2003 | Yes | Auto Scheduled | Dust | 2 days | September 28, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2002 | 6
2004 | Yes | Auto Scheduled | Water | 1 day | October 2, 2018 8:00 AM | October 2, 2018 5:00 PM | 2018-10-02 | 1 | 2003 | 6
2005 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 1 day | October 3, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2004 | 6
2006 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 5 days | October 31, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 2005 | 6
2007 | Yes | Auto Scheduled | Leg 6a | 23 days | September 19, 2018 8:00 AM | October 19, 2018 5:00 PM | 2018-10-19 | 1 |  | 5
2008 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 2 days | September 19, 2018 8:00 AM | September 20, 2018 5:00 PM | 2018-09-20 | 1 | 1970 | 6
2009 | Yes | Auto Scheduled | Low Temperature Wakeup | 1 day | September 20, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 2008 | 6
2010 | Yes | Auto Scheduled | Jump Start | 5 days | September 27, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2009FS+3d | 6
2011 | Yes | Auto Scheduled | Reverse Polarity | 5 days | September 27, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2010 | 6
2012 | Yes | Auto Scheduled | Over Voltage | 5 days | September 27, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2011 | 6
2013 | Yes | Auto Scheduled | State Change Waveform Characterization | 3 days | October 9, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 | 2012 | 6
2014 | Yes | Auto Scheduled | Ground Path Inductive Sensitivity | 0 days | October 11, 2018 8:00 AM | October 11, 2018 8:00 AM | 2018-10-11 | 1 | 2013 | 6
2015 | Yes | Auto Scheduled | Parasitic Current | 1 day | October 12, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 2014 | 6
2016 | Yes | Auto Scheduled | Power Supply Interruptions | 0 days | September 28, 2018 8:00 AM | September 28, 2018 8:00 AM | 2018-09-28 | 1 | 2015 | 6
2017 | Yes | Auto Scheduled | Battery Voltage Dropout | 3 days | October 1, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 2016 | 6
2018 | Yes | Auto Scheduled | Sinusoidal Superimposed Voltage | 0 days | October 8, 2018 8:00 AM | October 8, 2018 8:00 AM | 2018-10-08 | 1 | 2017 | 6
2019 | Yes | Auto Scheduled | Pulse Superimposed Voltage | 1 day | October 8, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 2018 | 6
2020 | Yes | Auto Scheduled | Ground Offset | 1 day | October 15, 2018 8:00 AM | October 15, 2018 5:00 PM | 2018-10-15 | 1 | 2019 | 6
2021 | Yes | Auto Scheduled | Power Offset | 0 days | October 15, 2018 5:00 PM | October 15, 2018 5:00 PM | 2018-10-15 | 1 | 2020 | 6
2022 | Yes | Auto Scheduled | Crank Pulse Capability | 3 days | October 16, 2018 8:00 AM | October 18, 2018 5:00 PM | 2018-10-18 | 1 |  | 6
2023 | Yes | Auto Scheduled | 1 point functional/parametric check | 1 day | October 19, 2018 8:00 AM | October 19, 2018 5:00 PM | 2018-10-19 | 1 | 2022FS+2d | 6
2024 | Yes | Auto Scheduled | Leg 7 | 35 days | September 19, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 5
2025 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 3 days | September 19, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 1970 | 6
2026 | Yes | Auto Scheduled | Low Temperature Wakeup | 0 days | September 20, 2018 8:00 AM | September 20, 2018 8:00 AM | 2018-09-20 | 1 | 2025 | 6
2027 | Yes | Auto Scheduled | Temperature measurement | 5 days | October 22, 2018 8:00 AM | October 26, 2018 5:00 PM | 2018-10-26 | 1 | 2026 | 6
2028 | Yes | Auto Scheduled | Mechanical Shock - Collision | 2 days | October 18, 2018 8:00 AM | October 19, 2018 5:00 PM | 2018-10-19 | 1 | 2026 | 6
2029 | Yes | Auto Scheduled | Crush for housing - Elbow load | 0 days | October 19, 2018 8:00 AM | October 19, 2018 8:00 AM | 2018-10-19 | 1 | 2028 | 6
2030 | Yes | Auto Scheduled | 5 point functional/parametric check (Before Free Fall) | 2 days | October 19, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 2029 | 6
2031 | Yes | Auto Scheduled | Free Fall | 0 days | October 23, 2018 8:00 AM | October 23, 2018 8:00 AM | 2018-10-23 | 1 | 2030 | 6
2032 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 5 days | October 31, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 2031 | 6
2033 | Yes | Auto Scheduled | Leg 10 | 25 days | September 19, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 |  | 5
2034 | Yes | Auto Scheduled | 1 point functional/parametric check | 1 day | September 19, 2018 8:00 AM | September 19, 2018 5:00 PM | 2018-09-19 | 1 | 1970 | 6
2035 | Yes | Auto Scheduled | Squeak and Rattle Avoidance | 1 day | October 11, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 | 2034 | 6
2036 | Yes | Auto Scheduled | 1 point functional/parametric check | 2 days | October 22, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 2035 | 6
2037 | Yes | Auto Scheduled | EMC | 50 days | September 19, 2018 8:00 AM | November 27, 2018 5:00 PM | 2018-11-27 | 1 |  | 5
2038 | Yes | Auto Scheduled | 5 point functional/parametric check (Pre-test) | 3 days | September 19, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 1970 | 6
2039 | Yes | Auto Scheduled | RE (ALSE) | 2 days | October 9, 2018 8:00 AM | October 10, 2018 5:00 PM | 2018-10-10 | 1 | 2038FS+2d | 6
2040 | Yes | Auto Scheduled | RF_CE via AN | 1 day | October 17, 2018 8:00 AM | October 17, 2018 5:00 PM | 2018-10-17 | 1 | 2044 | 6
2041 | Yes | Auto Scheduled | Magnetic Fields. (PEPS) | 1 day | November 14, 2018 8:00 AM | November 14, 2018 5:00 PM | 2018-11-14 | 1 | 2038FS+2d | 6
2042 | Yes | Auto Scheduled | RI, Bulk Current Injection (BCI) | 4 days | October 18, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 2040 | 6
2043 | Yes | Auto Scheduled | RI, Anechoic Chamber | 2 days | October 2, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2038FS+2d | 6
2044 | Yes | Auto Scheduled | Near-Field Portable Transmitters | 2 days | October 4, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 2038FS+2d | 6
2045 | Yes | Auto Scheduled | CI, Nominal 12V Lines | 4 days | October 24, 2018 8:00 AM | October 29, 2018 5:00 PM | 2018-10-29 | 1 | 2042 | 6
2046 | Yes | Auto Scheduled | CI, Coupling (CCC or DCC) to I/O (excludes nominal 12V lines) | 1 day | October 30, 2018 8:00 AM | October 30, 2018 5:00 PM | 2018-10-30 | 1 | 2045 | 6
2047 | Yes | Auto Scheduled | CI, Coupling (DCC on I/O and regulated supply lines, 85 V) | 2 days | October 31, 2018 8:00 AM | November 1, 2018 5:00 PM | 2018-11-01 | 1 | 2046 | 6
2048 | Yes | Auto Scheduled | ESD, Power-On Mode | 2 days | November 2, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 | 2047 | 6
2049 | Yes | Auto Scheduled | ESD, Remote I/O | 1 day | November 6, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 2048 | 6
2050 | Yes | Auto Scheduled | ESD, Handling of Devices | 1 day | November 7, 2018 8:00 AM | November 7, 2018 5:00 PM | 2018-11-07 | 1 | 2049 | 6
2051 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 2 days | November 26, 2018 8:00 AM | November 27, 2018 5:00 PM | 2018-11-27 | 1 | 2050FS+2d | 6
2052 | Yes | Auto Scheduled | DV Test Report | 7.8 wks | December 6, 2018 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 | 1986,1999,2003,2032,2036 | 4
2053 | Yes | Auto Scheduled | Load DV EMC and ENV Test Reports in CEMENT | 1 wk | February 13, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 2052 | 4
2054 | Yes | Auto Scheduled | DV02 (Continuation testing) | 88 days | October 19, 2018 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 3
2055 | Yes | Auto Scheduled | DV Test Execution | 88 days | October 19, 2018 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 |  | 4
2056 | Yes | Auto Scheduled | Leg 2c | 69 days | October 29, 2018 5:00 PM | February 1, 2019 5:00 PM | 2019-02-01 | 1 |  | 5
2057 | Yes | Auto Scheduled | Thermal Shock - Air to Air | 17 edays | October 29, 2018 5:00 PM | November 15, 2018 5:00 PM | 2018-11-15 | 1 | 1999 | 6
2058 | Yes | Auto Scheduled | Power Temperature Cycle (PTC) | 25 edays | November 15, 2018 5:00 PM | December 10, 2018 5:00 PM | 2018-12-10 | 1 | 2057 | 6 | 1463h: 339 cycles x 121min total hot / 138min total cold
2059 | Yes | Auto Scheduled | Humid Heat Cyclic | 4 days | December 17, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 | 2058 | 6
2060 | Yes | Auto Scheduled | Humid Heat Constant | 4 days | December 17, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 | 2058 | 6
2061 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 1 day | January 2, 2019 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 | 2060 | 6 | 876h: 339 cycles x 70min total hot / 85min total cold
2062 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 1 day | January 21, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 | 2061 | 6
2063 | Yes | Auto Scheduled | Cross Section and Inspection (Leg.2) | 7 days | January 24, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 2062,2070 | 6
2064 | Yes | Auto Scheduled | Leg 6b | 40 days | October 19, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 5
2065 | Yes | Auto Scheduled | Intermittent Short Circuit to Battery and to Ground for Input/Output | 7 days | November 2, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 2023FS+2d | 6
2066 | Yes | Auto Scheduled | Continuous Short Circuit to Battery and to Ground for Input/Output | 6 days | November 12, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 | 2065 | 6
2067 | Yes | Auto Scheduled | Open Circuit Single Line Integration | 3 days | October 19, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 | 2066 | 6
2068 | Yes | Auto Scheduled | Open Circuit Multiple Line Integration | 1 day | November 20, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 | 2067 | 6
2069 | Yes | Auto Scheduled | 5 point functional/parametric check (Post-test) | 2 days | December 5, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 | 2068 | 6
2070 | Yes | Auto Scheduled | Visual Inspection and Dissection – DRBTR. | 5 days | December 7, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 | 2069 | 6
2071 | Yes | Auto Scheduled | DV Test Report | 1.4 wks | February 4, 2019 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 | 2056,2064 | 5
2072 | Yes | Auto Scheduled | Load DV EMC and ENV Test Reports in CEMENT | 1 wk | February 13, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 2071 | 5
2073 | Yes | Auto Scheduled | D&D samples Build | 98 days | May 21, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 2
2074 | Yes | Auto Scheduled | RFP update | 3 days | May 21, 2018 8:00 AM | May 23, 2018 5:00 PM | 2018-05-23 | 1 |  | 3
2075 | Yes | Auto Scheduled | Build samples (32 Eng Samples) | 1 wk | September 24, 2018 8:00 AM | September 28, 2018 5:00 PM | 2018-09-28 | 1 |  | 3
2076 | Yes | Auto Scheduled | Ship D&D samples to NSI | 3 days | October 1, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2075 | 3
2077 | Yes | Auto Scheduled | IVER 1 (E2UB-S) | 124 days | July 23, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 1
2078 | Yes | Auto Scheduled | Manufacturing | 7 days | November 2, 2018 8:00 AM | November 13, 2018 8:00 AM | 2018-11-13 | 1 |  | 2
2079 | Yes | Auto Scheduled | IVER samples build | 7 days | November 2, 2018 8:00 AM | November 13, 2018 8:00 AM | 2018-11-13 | 1 |  | 3
2080 | Yes | Auto Scheduled | IVER SW release with TWN (sw21.21.140.4) | 0 days | November 2, 2018 8:00 AM | November 2, 2018 8:00 AM | 2018-11-02 | 1 | 2081SF | 4
2081 | Yes | Auto Scheduled | Build IVER | 4 days | November 2, 2018 8:00 AM | November 7, 2018 5:00 PM | 2018-11-07 | 1 | 2082SF | 4
2082 | Yes | Auto Scheduled | Ship to customer | 3 days | November 8, 2018 8:00 AM | November 12, 2018 5:00 PM | 2018-11-12 | 1 | 2083SF | 4
2083 | Yes | Auto Scheduled | IVER MRD | 0 days | November 13, 2018 8:00 AM | November 13, 2018 8:00 AM | 2018-11-13 | 1 | 8,3516 | 4
2084 | Yes | Auto Scheduled | Software Development | 124 days | July 23, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 2
2085 | Yes | Auto Scheduled | 21.21.140 Release | 53 days | July 23, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 3
2086 | Yes | Auto Scheduled | BSP Release to GMTCI | 0 days | August 13, 2018 8:00 AM | August 13, 2018 8:00 AM | 2018-08-13 | 1 |  | 4
2087 | Yes | Auto Scheduled | RC02 from GMTCI to NSI | 2 days | August 13, 2018 8:00 AM | August 14, 2018 5:00 PM | 2018-08-14 | 1 | 2086 | 4
2088 | Yes | Auto Scheduled | Internal SW release | 8 days | August 15, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 | 2087 | 4
2089 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 0 days | August 27, 2018 8:00 AM | August 27, 2018 8:00 AM | 2018-08-27 | 1 | 2088 | 4
2090 | Yes | Auto Scheduled | SWE4 Validation Testing | 10 days | August 27, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 2089 | 4
2091 | Yes | Auto Scheduled | Software Engineering 6 | 13 days | August 27, 2018 8:00 AM | September 12, 2018 5:00 PM | 2018-09-12 | 1 |  | 4
2092 | Yes | Auto Scheduled | SWE6 Verification Testing | 10 days | August 27, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 2089 | 5
2093 | Yes | Auto Scheduled | SWE6 Verification Test Report | 3 days | September 10, 2018 8:00 AM | September 12, 2018 5:00 PM | 2018-09-12 | 1 | 2090 | 5
2094 | Yes | Auto Scheduled | Systems Engineering 4 | 21 days | August 25, 2018 8:00 AM | September 24, 2018 5:00 PM | 2018-09-24 | 1 |  | 4
2095 | Yes | Auto Scheduled | SYS4 Validation Testing | 21 days | August 25, 2018 8:00 AM | September 24, 2018 5:00 PM | 2018-09-24 | 1 |  | 5
2096 | Yes | Auto Scheduled | Bootloader | 2 days | August 25, 2018 8:00 AM | August 26, 2018 3:00 PM | 2018-08-26 | 1 | 2088 | 6
2097 | Yes | Auto Scheduled | Telltales | 4 days | August 25, 2018 8:00 AM | August 28, 2018 3:00 PM | 2018-08-28 | 1 | 2088 | 6
2098 | Yes | Auto Scheduled | Illumination | 3 days | August 25, 2018 8:00 AM | August 27, 2018 3:00 PM | 2018-08-27 | 1 | 2088 | 6
2099 | Yes | Auto Scheduled | Power Mode | 2 days | August 27, 2018 8:00 AM | August 28, 2018 5:00 PM | 2018-08-28 | 1 | 2088 | 6
2100 | Yes | Auto Scheduled | CAN | 3 days | August 27, 2018 8:00 AM | August 29, 2018 5:00 PM | 2018-08-29 | 1 | 2096 | 6
2101 | Yes | Auto Scheduled | LIN | 2 days | August 28, 2018 3:00 PM | August 30, 2018 3:00 PM | 2018-08-30 | 1 | 2097 | 6
2102 | Yes | Auto Scheduled | TFT | 2 days | August 27, 2018 3:00 PM | August 29, 2018 3:00 PM | 2018-08-29 | 1 | 2098 | 6
2103 | Yes | Auto Scheduled | Ethernet | 2 days | August 29, 2018 8:00 AM | August 30, 2018 5:00 PM | 2018-08-30 | 1 | 2099 | 6
2104 | Yes | Auto Scheduled | Gages | 2 days | August 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 2100 | 6
2105 | Yes | Auto Scheduled | HWIOs | 2 days | August 30, 2018 3:00 PM | September 3, 2018 3:00 PM | 2018-09-03 | 1 | 2101 | 6
2106 | Yes | Auto Scheduled | Memory | 2 days | August 29, 2018 3:00 PM | August 31, 2018 3:00 PM | 2018-08-31 | 1 | 2102 | 6
2107 | Yes | Auto Scheduled | Segment Display | 2 days | August 31, 2018 8:00 AM | September 3, 2018 5:00 PM | 2018-09-03 | 1 | 2103 | 6
2108 | Yes | Auto Scheduled | Summary Report approval | 15 days | September 4, 2018 8:00 AM | September 24, 2018 5:00 PM | 2018-09-24 | 1 | 2107 | 6
2109 | Yes | Auto Scheduled | Systems Engineering 5 | 53 days | July 23, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 4
2110 | Yes | Auto Scheduled | SYS5 Requirements Analysis (SRS v5.0 and v6.0) | 4 wks | July 30, 2018 8:00 AM | August 24, 2018 5:00 PM | 2018-08-24 | 1 |  | 5
2111 | Yes | Auto Scheduled | SYS5 Test Case creation (SRS v5.0 and v6.0) | 31 days | July 23, 2018 8:00 AM | September 3, 2018 5:00 PM | 2018-09-03 | 1 |  | 5
2112 | Yes | Auto Scheduled | SYS5 Validation Testing | 24 days | August 27, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 |  | 5
2113 | Yes | Auto Scheduled | Stress Test | 3 days | August 27, 2018 8:00 AM | August 29, 2018 5:00 PM | 2018-08-29 | 1 | 2088 | 6
2114 | Yes | Auto Scheduled | Bootloader | 1 day | August 27, 2018 8:00 AM | August 27, 2018 5:00 PM | 2018-08-27 | 1 | 2088 | 6
2115 | Yes | Auto Scheduled | Teltales | 3 days | August 27, 2018 8:00 AM | August 29, 2018 5:00 PM | 2018-08-29 | 1 | 2088 | 6
2116 | Yes | Auto Scheduled | TFT | 1 day | August 27, 2018 8:00 AM | August 27, 2018 5:00 PM | 2018-08-27 | 1 | 2088 | 6
2117 | Yes | Auto Scheduled | Illumination | 2 days | August 28, 2018 8:00 AM | August 29, 2018 5:00 PM | 2018-08-29 | 1 | 2114 | 6
2118 | Yes | Auto Scheduled | Power Mode | 2 days | August 28, 2018 8:00 AM | August 29, 2018 5:00 PM | 2018-08-29 | 1 | 2116 | 6
2119 | Yes | Auto Scheduled | Gauges | 2 days | August 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 2113 | 6
2120 | Yes | Auto Scheduled | Ethernet | 2 days | August 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 2115 | 6
2121 | Yes | Auto Scheduled | CAN | 2 days | August 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 2117 | 6
2122 | Yes | Auto Scheduled | Cyber Security | 2 days | August 30, 2018 8:00 AM | August 31, 2018 5:00 PM | 2018-08-31 | 1 | 2118 | 6
2123 | Yes | Auto Scheduled | Functional Safety | 2 days | September 3, 2018 8:00 AM | September 4, 2018 5:00 PM | 2018-09-04 | 1 | 2119 | 6
2124 | Yes | Auto Scheduled | NVM | 2 days | September 3, 2018 8:00 AM | September 4, 2018 5:00 PM | 2018-09-04 | 1 | 2120 | 6
2125 | Yes | Auto Scheduled | LIN | 2 days | September 3, 2018 8:00 AM | September 4, 2018 5:00 PM | 2018-09-04 | 1 | 2121 | 6
2126 | Yes | Auto Scheduled | Line Test | 3 days | September 3, 2018 8:00 AM | September 5, 2018 5:00 PM | 2018-09-05 | 1 | 2122 | 6
2127 | Yes | Auto Scheduled | HWIO | 1 day | September 5, 2018 8:00 AM | September 5, 2018 5:00 PM | 2018-09-05 | 1 | 2123 | 6
2128 | Yes | Auto Scheduled | DOORS & Redmine | 3 days | September 25, 2018 8:00 AM | September 27, 2018 5:00 PM | 2018-09-27 | 1 | 2095 | 6
2129 | Yes | Auto Scheduled | Summary Report Approval | 14 days | September 6, 2018 8:00 AM | September 25, 2018 5:00 PM | 2018-09-25 | 1 | 2127 | 6
2130 | Yes | Auto Scheduled | Compliance Testing | 23 days | September 3, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 5
2131 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming | 5 days | September 3, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 2088 | 6 | Test stopped and waiting for sw21.21.141 release
2132 | Yes | Auto Scheduled | CG3877 - CAN Physical Layer Test | 5 days | September 3, 2018 8:00 AM | September 7, 2018 5:00 PM | 2018-09-07 | 1 | 2088 | 6 | Test stopped and waiting for sw21.21.141 release
2133 | No | Auto Scheduled | CG4111 - Global B Serial Data and Diagnostics Test | 20 days | September 17, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 2088 | 6
2134 | No | Auto Scheduled | CG3689 - Ethernet AVB Device Test | 15 days | September 24, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 2088 | 6 | Confirm testing duration
2135 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance | 20 days | September 10, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 2088 | 6
2136 | Yes | Auto Scheduled | Redmines upload | 18 days | September 10, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2131,2132 | 6
2137 | Yes | Auto Scheduled | Fuzz Test Execution | 18 days | September 6, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 5
2138 | Yes | Auto Scheduled | ARP Client | 18 days | September 6, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2088 | 6
2139 | Yes | Auto Scheduled | ARP Server | 18 days | September 6, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2088 | 6
2140 | Yes | Auto Scheduled | Ethernet | 18 days | September 6, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2088 | 6
2141 | Yes | Auto Scheduled | IPv4 | 18 days | September 6, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2088 | 6
2142 | No | Auto Scheduled | TCP Client | 15 days | September 18, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 2088 | 6 | Deviation received from GM to do not test with sw 21.140 as there are issues with TCP protocol. This will be tested with software 21.141
2143 | No | Auto Scheduled | TCP Server | 15 days | September 18, 2018 8:00 AM | October 8, 2018 5:00 PM | 2018-10-08 | 1 | 2088 | 6 | Deviation received from GM to do not test with sw 21.140 as there are issues with TCP protocol. This will be tested with software 21.141
2144 | Yes | Auto Scheduled | SW release to GM (21.21.140.1) | 0 days | September 7, 2018 8:00 AM | September 7, 2018 8:00 AM | 2018-09-07 | 1 |  | 3
2145 | Yes | Auto Scheduled | CG4117 (sw 21.21.140.1) | 12.4 wks | September 7, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 | 2144 | 3
2146 | Yes | Auto Scheduled | Share with GM | 1 day | December 6, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 | 2145 | 3
2147 | Yes | Auto Scheduled | 21.21.140.2 Release | 33 days | September 21, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 3 | Software release required to fix high impact issues for IVER milestone
2148 | Yes | Auto Scheduled | Internal SW release | 1 day | September 21, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 |  | 4
2149 | Yes | Auto Scheduled | Software Engineering 4 | 1 day | September 21, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 |  | 4
2150 | Yes | Auto Scheduled | Unit Test | 1 day | September 21, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 2148 | 5
2151 | Yes | Auto Scheduled | Integration Test | 1 day | September 21, 2018 8:00 AM | September 21, 2018 5:00 PM | 2018-09-21 | 1 | 2148 | 5
2152 | Yes | Auto Scheduled | Software Engineering 6 | 9 days | September 21, 2018 8:00 AM | October 3, 2018 5:00 PM | 2018-10-03 | 1 |  | 4
2153 | Yes | Auto Scheduled | SWE6 Verification Testing | 4 days | September 21, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 |  | 5
2154 | Yes | Auto Scheduled | Ethernet RHMI | 4 days | September 21, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 2148 | 6
2155 | Yes | Auto Scheduled | Booloader updater | 4 days | September 21, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 2148 | 6
2156 | Yes | Auto Scheduled | Software Release Readiness | 4 days | September 21, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 2148 | 6
2157 | Yes | Auto Scheduled | SWE6 Verification Test Report | 5 days | September 26, 2018 5:00 PM | October 3, 2018 5:00 PM | 2018-10-03 | 1 | 2154,2155,2156 | 5
2158 | Yes | Auto Scheduled | Systems Engineering 5 | 11 days | September 21, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 |  | 4
2159 | Yes | Auto Scheduled | SYS5 Validation Testing | 7 days | September 21, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 5
2160 | Yes | Auto Scheduled | Ethernet | 7 days | September 21, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2148 | 6
2161 | Yes | Auto Scheduled | CG3877 (BTR Portion) | 7 days | September 21, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 2148 | 6
2162 | Yes | Auto Scheduled | SYS5 Validation Test Report | 4 days | October 2, 2018 8:00 AM | October 5, 2018 5:00 PM | 2018-10-05 | 1 | 2160,2161 | 5
2163 | Yes | Auto Scheduled | CG2999 | 25 days | October 2, 2018 5:00 PM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 4
2164 | Yes | Auto Scheduled | CG4422 updated | 23 days | October 3, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 | 2157,2162 | 5
2165 | Yes | Auto Scheduled | Black box test results | 0 days | October 2, 2018 5:00 PM | October 2, 2018 5:00 PM | 2018-10-02 | 1 | 2157,2162 | 5
2166 | Yes | Auto Scheduled | TWN sw21.21.140.2 | 2 days | September 24, 2018 8:00 AM | September 25, 2018 5:00 PM | 2018-09-25 | 1 |  | 4
2167 | Yes | Auto Scheduled | Master Update | 2 days | September 24, 2018 8:00 AM | September 25, 2018 5:00 PM | 2018-09-25 | 1 |  | 5
2168 | No | Auto Scheduled | TWN release | 5 days | September 26, 2018 8:00 AM | October 2, 2018 5:00 PM | 2018-10-02 | 1 | 2167 | 5 | TWN cancell due to software issue. New software is needed
2169 | Yes | Auto Scheduled | GM Release | 2 days | September 28, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 |  | 4
2170 | Yes | Auto Scheduled | 21.21.140.3 Release | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 |  | 3 | Software release required to fix NVM issue (RAID Issue ID 74 and 21E3_E2Ux 5 Phase DIT failure sw21.21.140.2)
2171 | Yes | Auto Scheduled | Internal Release | 1 day | October 9, 2018 8:00 AM | October 9, 2018 5:00 PM | 2018-10-09 | 1 |  | 4
2172 | No | Auto Scheduled | Software Engineering 6 | 2 days | October 10, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 |  | 4
2173 | No | Auto Scheduled | SWE6 Verification Testing | 2 days | October 10, 2018 8:00 AM | October 11, 2018 5:00 PM | 2018-10-11 | 1 | 2171 | 5 | Testing cancelled due to software issues
2174 | No | Auto Scheduled | SW release to GM | 1 day | October 12, 2018 8:00 AM | October 12, 2018 5:00 PM | 2018-10-12 | 1 | 2173 | 4
2175 | Yes | Auto Scheduled | 21.21.140.4 Release | 58 days | October 23, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 3 | Software release required to fix NVM issue (RAID Issue ID 74 and 21E3_E2Ux 5 Phase DIT failure sw21.21.140.2)
2176 | Yes | Auto Scheduled | Internal Release | 1 day | October 23, 2018 8:00 AM | October 23, 2018 5:00 PM | 2018-10-23 | 1 |  | 4
2177 | Yes | Auto Scheduled | Software Engineering 6 | 1 day | October 24, 2018 8:00 AM | October 24, 2018 5:00 PM | 2018-10-24 | 1 |  | 4
2178 | Yes | Auto Scheduled | SWE6 Verification Testing | 1 day | October 24, 2018 8:00 AM | October 24, 2018 5:00 PM | 2018-10-24 | 1 | 2176 | 5
2179 | Yes | Auto Scheduled | SW release to GM | 0 days | October 24, 2018 5:00 PM | October 24, 2018 5:00 PM | 2018-10-24 | 1 | 2178 | 4
2180 | Yes | Auto Scheduled | DIT @ GM | 1 day | October 25, 2018 8:00 AM | October 25, 2018 5:00 PM | 2018-10-25 | 1 | 2179 | 4
2181 | Yes | Auto Scheduled | GBFTT @ GM | 1 day | November 5, 2018 8:00 AM | November 5, 2018 5:00 PM | 2018-11-05 | 1 |  | 4
2182 | Yes | Auto Scheduled | Systems Engineering 5 | 51 days | November 1, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 4
2183 | Yes | Auto Scheduled | Compliance Test | 51 days | November 1, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 5
2184 | Yes | Auto Scheduled | CG3877 - CAN Physical Layer Test (Oct 2018) | 51 days | November 1, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 | 2179 | 6 | Pending clarification needed from Mauro, these will be closed by 12/6
2185 | Yes | Auto Scheduled | Temp Chamber and ESD | 19 days | November 19, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 |  | 6
2186 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming | 23 days | November 1, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 | 2179 | 6
2187 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (Jan 2017) | 32 days | November 23, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 | 2179 | 6 | Confirm testing duration
2188 | Yes | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle (Nov 2012) | 12 days | November 19, 2018 8:00 AM | December 4, 2018 5:00 PM | 2018-12-04 | 1 | 2179 | 6
2189 | Yes | Auto Scheduled | IVER 2 (E2UB-N) | 107 days | August 10, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 1
2190 | Yes | Auto Scheduled | Software Development | 82 days | August 10, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 2
2191 | Yes | Auto Scheduled | 21.21.141 Release | 82 days | August 10, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 3
2192 | Yes | Auto Scheduled | RC0 Release | 0 days | August 10, 2018 8:00 AM | August 10, 2018 8:00 AM | 2018-08-10 | 1 |  | 4
2193 | Yes | Auto Scheduled | RC1 Release | 0 days | August 31, 2018 8:00 AM | August 31, 2018 8:00 AM | 2018-08-31 | 1 |  | 4
2194 | Yes | Auto Scheduled | RC2 Release (did not included HMI) | 0 days | September 18, 2018 8:00 AM | September 18, 2018 8:00 AM | 2018-09-18 | 1 |  | 4
2195 | Yes | Auto Scheduled | RC2 Release (new HMI from RAPM/GMTCI) | 1 day | September 28, 2018 8:00 AM | September 28, 2018 5:00 PM | 2018-09-28 | 1 |  | 4 | GMTCI informed this new release on 9/25
2196 | Yes | Auto Scheduled | Internal SW release | 17 days | October 22, 2018 8:00 AM | November 13, 2018 5:00 PM | 2018-11-13 | 1 |  | 4 | Including PCE 026 implementeation. Internal software release pushed to 10/12 due to HMI issue and sw 21.21.140.3 release
2197 | Yes | Auto Scheduled | SWE4 Validation Testing (unit test, integration test) | 6 days | November 14, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2196 | 4
2198 | Yes | Auto Scheduled | Software Engineering 6 | 13 days | November 14, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 |  | 4
2199 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review | 1 day | November 14, 2018 8:00 AM | November 14, 2018 5:00 PM | 2018-11-14 | 1 | 2196 | 5
2200 | Yes | Auto Scheduled | Redmines testing | 5 days | November 14, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 | 2196 | 5
2201 | Yes | Auto Scheduled | Release readiness test | 2 days | November 14, 2018 8:00 AM | November 15, 2018 5:00 PM | 2018-11-15 | 1 | 2196 | 5
2202 | Yes | Auto Scheduled | Systems | 2 days | November 16, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 2201 | 5
2203 | Yes | Auto Scheduled | RHMI | 5 days | November 21, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 | 2200 | 5
2204 | No | Auto Scheduled | JTAG password | 2 days | November 20, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2202 | 5 | JTAG password is not implemented in sw 21.21.141
2205 | Yes | Auto Scheduled | Functional Testing | 9 days | November 14, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 | 2196 | 5
2206 | Yes | Auto Scheduled | SWE6 Verification Test Report | 1 day | November 30, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2205,2204,2203,2202 | 5
2207 | Yes | Auto Scheduled | Systems Engineering 4 | 10 days | November 19, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 |  | 4
2208 | Yes | Auto Scheduled | SYS4 Integration Testing | 8 days | November 19, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 |  | 5
2209 | Yes | Auto Scheduled | FROP List | 2 days | November 19, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 |  | 6
2210 | Yes | Auto Scheduled | Redmines testing | 8 days | November 19, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 |  | 6
2211 | Yes | Auto Scheduled | Telltales | 1 day | November 19, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 |  | 7
2212 | Yes | Auto Scheduled | TFT | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2209 | 7
2213 | Yes | Auto Scheduled | Illumination | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2209 | 7
2214 | Yes | Auto Scheduled | Gauges | 1 day | November 20, 2018 8:00 AM | November 20, 2018 5:00 PM | 2018-11-20 | 1 | 2211 | 7
2215 | Yes | Auto Scheduled | Ethernet | 1 day | November 22, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 | 2213 | 7
2216 | Yes | Auto Scheduled | Segment Display | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2214 | 7
2217 | Yes | Auto Scheduled | CAN | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2215 | 7
2218 | Yes | Auto Scheduled | LIN | 1 day | November 27, 2018 8:00 AM | November 27, 2018 5:00 PM | 2018-11-27 | 1 | 2219 | 7
2219 | Yes | Auto Scheduled | HWIO | 1 day | November 26, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 2217 | 7
2220 | Yes | Auto Scheduled | Memory | 1 day | November 22, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 | 2216 | 7
2221 | Yes | Auto Scheduled | Bootloader | 1 day | November 28, 2018 8:00 AM | November 28, 2018 5:00 PM | 2018-11-28 | 1 | 2218 | 7
2222 | Yes | Auto Scheduled | Power Mode | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2220 | 7
2223 | Yes | Auto Scheduled | SYS Integration Test Report | 2 days | November 29, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2222,2221 | 5
2224 | Yes | Auto Scheduled | Systems Engineering 5 | 12 days | November 16, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 4
2225 | Yes | Auto Scheduled | SYS5 Validation Testing | 10 days | November 16, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 |  | 5
2226 | Yes | Auto Scheduled | FROP List | 4 days | November 19, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 | 2229 | 6
2227 | Yes | Auto Scheduled | Redmines testing | 10 days | November 16, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 | 2196 | 6
2228 | Yes | Auto Scheduled | Gauges | 1 day | November 16, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 7
2229 | Yes | Auto Scheduled | LIN | 1 day | November 16, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 |  | 7
2230 | Yes | Auto Scheduled | Telltales | 1 day | November 19, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 |  | 7
2231 | Yes | Auto Scheduled | Bootloader | 1 day | November 19, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 |  | 7
2232 | Yes | Auto Scheduled | Functional Safety | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2230 | 7
2233 | Yes | Auto Scheduled | TFT | 1 day | November 21, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2231 | 7
2234 | Yes | Auto Scheduled | NVM | 1 day | November 22, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 | 2232 | 7
2235 | Yes | Auto Scheduled | Power Mode | 1 day | November 22, 2018 8:00 AM | November 22, 2018 5:00 PM | 2018-11-22 | 1 | 2232 | 7
2236 | Yes | Auto Scheduled | CAN | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2226 | 7
2237 | Yes | Auto Scheduled | HWIO | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2226 | 7
2238 | Yes | Auto Scheduled | Illumination | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2226 | 7
2239 | Yes | Auto Scheduled | Cyber Security | 1 day | November 23, 2018 8:00 AM | November 23, 2018 5:00 PM | 2018-11-23 | 1 | 2234 | 7
2240 | Yes | Auto Scheduled | Line Test | 2 days | November 26, 2018 8:00 AM | November 27, 2018 5:00 PM | 2018-11-27 | 1 | 2236 | 7
2241 | Yes | Auto Scheduled | Stress Test | 1 day | November 26, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 2239 | 7
2242 | Yes | Auto Scheduled | Ethernet | 2 days | November 28, 2018 8:00 AM | November 29, 2018 5:00 PM | 2018-11-29 | 1 | 2240 | 7
2243 | Yes | Auto Scheduled | SYS Validation Test Report | 2 days | November 30, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 | 2208,2225 | 5
2244 | No | Auto Scheduled | Compliance Test (cancelled) | 25 days | November 14, 2018 8:00 AM | December 18, 2018 5:00 PM | 2018-12-18 | 1 | 2196 | 4 | Compliance test cancelled with software 21.21.141 due to DPS flashing issue.
2245 | No | Auto Scheduled | CG3687 - Bootloader Flash Programming | 20 days | November 14, 2018 8:00 AM | December 11, 2018 5:00 PM | 2018-12-11 | 1 | 2196 | 5
2246 | No | Auto Scheduled | CG3877 - CAN Physical Layer Test | 25 days | November 14, 2018 8:00 AM | December 18, 2018 5:00 PM | 2018-12-18 | 1 | 2196 | 5
2247 | No | Auto Scheduled | CG3689 - Ethernet AVB Device Test | 15 days | November 14, 2018 8:00 AM | December 4, 2018 5:00 PM | 2018-12-04 | 1 | 2196 | 5 | Confirm testing duration
2248 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance | 20 days | November 14, 2018 8:00 AM | December 11, 2018 5:00 PM | 2018-12-11 | 1 | 2196 | 5
2249 | No | Auto Scheduled | Fuzz Test Execution | 17 days | November 14, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 |  | 5
2250 | No | Auto Scheduled | TCP Client | 15 days | November 14, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 | 2196 | 6
2251 | No | Auto Scheduled | TCP Server | 15 days | November 14, 2018 8:00 AM | December 6, 2018 5:00 PM | 2018-12-06 | 1 | 2196 | 6
2252 | No | Auto Scheduled | Line Test and Agene Mode (SW) | 1 day | December 3, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 | 2206 | 4
2253 | No | Auto Scheduled | Software release assesment | 0 days | November 30, 2018 5:00 PM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2206 | 4
2254 | No | Auto Scheduled | SW release to GM | 0 days | November 30, 2018 5:00 PM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2206 | 4
2255 | Yes | Auto Scheduled | CG2999 submit to GM | 14 days | November 14, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 |  | 4
2256 | Yes | Auto Scheduled | Unit Test report | 3 days | November 14, 2018 8:00 AM | November 16, 2018 5:00 PM | 2018-11-16 | 1 | 2196 | 5
2257 | No | Auto Scheduled | SAA update | 4 days | November 14, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 2196 | 5
2258 | Yes | Auto Scheduled | Integratoin Test report | 4 days | November 14, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 2196 | 5
2259 | No | Auto Scheduled | Performance Paramters report | 4 days | November 14, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 | 2196 | 5
2260 | Yes | Auto Scheduled | Stress Test Results | 7 days | November 14, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 2196 | 5
2261 | Yes | Auto Scheduled | Black box test results | 12 days | November 14, 2018 8:00 AM | December 3, 2018 5:00 PM | 2018-12-03 | 1 | 2196 | 5
2262 | Yes | Auto Scheduled | Software Development (21.21.142 Beta) | 37 days | November 16, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 2
2263 | No | Auto Scheduled | Baseline Cadence | 18 days | November 14, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 3
2264 | No | Auto Scheduled | Systems Requirements Spec (SYS2) - 6.0 | 0 days | November 14, 2018 8:00 AM | November 14, 2018 8:00 AM | 2018-11-14 | 1 |  | 4
2265 | No | Auto Scheduled | Systems Architecture (SYS3) - 1.0 | 0 days | November 14, 2018 8:00 AM | November 14, 2018 8:00 AM | 2018-11-14 | 1 | 2264 | 4
2266 | No | Auto Scheduled | Software Functional Specs (SWE1) - 3.0 ??? | 2 days | November 14, 2018 8:00 AM | November 15, 2018 5:00 PM | 2018-11-15 | 1 | 2264,2265 | 4
2267 | No | Auto Scheduled | Software Architecure Design (SWE2) - 2.0 | 9 days | November 16, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2266 | 4
2268 | No | Auto Scheduled | Software Layer Design (SWE3) - 2.0 | 9 days | November 16, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2266 | 4
2269 | No | Auto Scheduled | Software Unit Test Spec (SWE4) - 2.0 | 9 days | November 16, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2266 | 4
2270 | No | Auto Scheduled | Software Integration Test Spec (SWE5) -2.0 | 9 days | November 16, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2266 | 4
2271 | No | Auto Scheduled | Software Qualification Test Spec (SWE6) - 4.0 | 9 days | November 16, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2266 | 4
2272 | No | Auto Scheduled | Systems Integration Test Spec (SYS4) - ?? | 2 days | December 6, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 4
2273 | No | Auto Scheduled | Systems Qualification Test Spec (SYS5) - ?? | 2 days | December 6, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 4
2274 | Yes | Auto Scheduled | 21.21.142 Beta Release | 37 days | November 16, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 3
2275 | Yes | Auto Scheduled | CCB (FROP and Redmine) | 15 days | November 16, 2018 8:00 AM | December 10, 2018 5:00 PM | 2018-12-10 | 1 |  | 4
2276 | No | Auto Scheduled | Software release kick off | 0 days | November 28, 2018 8:00 AM | November 28, 2018 8:00 AM | 2018-11-28 | 1 |  | 4
2277 | Yes | Auto Scheduled | RC2 Release (from GMTCI to NSI with HMI) | 4 days | November 16, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 | 2278FS-2w | 4 | RC2 has not been released by GMTCI
2278 | Yes | Auto Scheduled | Internal SW release | 3 days | December 7, 2018 8:00 AM | December 11, 2018 5:00 PM | 2018-12-11 | 1 | 1093 | 4 | Include 5 Phase 006
2279 | No | Auto Scheduled | SWE4 Validation Testing | 15 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2278 | 4
2280 | No | Auto Scheduled | Software Engineering 6 | 28 days | December 11, 2018 5:00 PM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 4 | Test execution cancelled due to high impact issues with the beta software
2281 | No | Auto Scheduled | SW Validation Test Plan and Readiness Review | 0 days | December 11, 2018 5:00 PM | December 11, 2018 5:00 PM | 2018-12-11 | 1 | 2278 | 5
2282 | No | Auto Scheduled | SWE6 Verification Testing | 10 days | December 12, 2018 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 | 2278 | 5
2283 | No | Auto Scheduled | SWE6 Verification Test Report | 3 days | January 16, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 | 2279 | 5
2284 | Yes | Auto Scheduled | Systems Engineering 4 | 12 days | December 12, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 |  | 4
2285 | Yes | Auto Scheduled | SYS4 Integration Testing | 10 days | December 12, 2018 8:00 AM | December 25, 2018 5:00 PM | 2018-12-25 | 1 | 2278 | 5
2286 | Yes | Auto Scheduled | SYS Integration Test Report | 2 days | December 26, 2018 8:00 AM | December 27, 2018 5:00 PM | 2018-12-27 | 1 | 2285 | 5
2287 | Yes | Auto Scheduled | Systems Engineering 5 | 19 days | December 12, 2018 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 |  | 4
2288 | Yes | Auto Scheduled | SYS5 Validation Testing | 10 days | December 12, 2018 8:00 AM | December 25, 2018 5:00 PM | 2018-12-25 | 1 | 2278 | 5
2289 | Yes | Auto Scheduled | SYS Validation Test Report | 2 days | January 4, 2019 8:00 AM | January 7, 2019 5:00 PM | 2019-01-07 | 1 | 2285,2288 | 5
2290 | No | Auto Scheduled | Compliance Test | 25 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2278 | 4
2291 | No | Auto Scheduled | CG3687 - Bootloader Flash Programming | 20 days | December 12, 2018 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 | 2278 | 5
2292 | No | Auto Scheduled | CG3877 - CAN Physical Layer Test | 25 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2278 | 5
2293 | No | Auto Scheduled | CG3689 - Ethernet AVB Device Test | 15 days | December 12, 2018 8:00 AM | January 1, 2019 5:00 PM | 2019-01-01 | 1 | 2278 | 5
2294 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance | 20 days | December 12, 2018 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 | 2278 | 5
2295 | No | Auto Scheduled | Fuzz Test Execution | 25 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 |  | 5
2296 | No | Auto Scheduled | TCP Client | 15 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2278 | 6
2297 | No | Auto Scheduled | TCP Server | 15 days | December 12, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2278 | 6
2298 | No | Auto Scheduled | Report review | 10 days | December 12, 2018 8:00 AM | December 25, 2018 5:00 PM | 2018-12-25 | 1 |  | 6
2299 | No | Auto Scheduled | Line Test and Agene Mode (SW) | 1 day | January 21, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 | 2283 | 4
2300 | No | Auto Scheduled | Software release readiness | 0 days | December 18, 2018 8:00 AM | December 18, 2018 8:00 AM | 2018-12-18 | 1 | 2301FS-2d | 4
2301 | No | Auto Scheduled | SW release to GM | 0 days | December 20, 2018 8:00 AM | December 20, 2018 8:00 AM | 2018-12-20 | 1 |  | 4
2302 | No | Auto Scheduled | CG2999 submit to GM | 22 days | December 12, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 |  | 4
2303 | No | Auto Scheduled | Unit Test report | 4 days | December 12, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 | 2278 | 5
2304 | No | Auto Scheduled | SAA update | 4 days | December 12, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 | 2278 | 5
2305 | No | Auto Scheduled | Integratoin Test report | 4 days | December 12, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 | 2278 | 5
2306 | No | Auto Scheduled | Performance Paramters report | 4 days | December 12, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 | 2278 | 5
2307 | No | Auto Scheduled | Stress Test Results | 7 days | December 12, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 2278 | 5
2308 | No | Auto Scheduled | Black box test results | 12 days | December 12, 2018 8:00 AM | January 10, 2019 5:00 PM | 2019-01-10 | 1 | 2278 | 5
2309 | No | Auto Scheduled | Software Review Report | 1 day | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
2310 | No | Auto Scheduled | Line Test and Agene Mode (SW) | 1 day | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
2311 | No | Auto Scheduled | SW Engineer on call to support ride | 3 days | January 18, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 |  | 4
2312 | Yes | Auto Scheduled | Implementation 2 (PV Design) (65% BOR Readiness) E2UB-S | 311 days | April 23, 2018 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 1
2313 | Yes | Auto Scheduled | Vehicle Testing | 36 days | April 29, 2019 8:00 AM | June 17, 2019 5:00 PM | 2019-06-17 | 1 |  | 2
2314 | Yes | Auto Scheduled | Vehicle Test Plan | 36 days | April 29, 2019 8:00 AM | June 17, 2019 5:00 PM | 2019-06-17 | 1 |  | 3
2315 | No | Auto Scheduled | GM approval for Vehicle Test Plan | 2 wks | June 18, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 | 2314 | 3
2316 | Yes | Auto Scheduled | Mechanical Development | 173 days | October 31, 2018 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 2
2317 | Yes | Auto Scheduled | Verify VDC | 3 days | November 19, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 |  | 3
2318 | Yes | Auto Scheduled | Spec confirmation report to GM for approval | 10 days | December 3, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 |  | 3 | GM is pending on approving. It was sent by Anshuman to Alex Debek
2319 | Yes | Auto Scheduled | Material selection for production | 12 days | November 20, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 3
2320 | Yes | Auto Scheduled | GM to provide Applique Math for PCE 32 | 8 days | February 6, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 3 | PCE 032 task
2321 | Yes | Auto Scheduled | Update VDC with GM feedback | 22.5 days | January 7, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2320 | 3 | Replanned because Anshuman needs to add internal changes to the presentation before sharing
2322 | Yes | Auto Scheduled | Mold in color visor | 53 days | November 19, 2018 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 |  | 3
2323 | Yes | Auto Scheduled | New visor molding trial @ China | 1 day | November 19, 2018 8:00 AM | November 19, 2018 5:00 PM | 2018-11-19 | 1 |  | 4
2324 | Yes | Auto Scheduled | Ship from Supplier to NSI | 1 wk | November 20, 2018 8:00 AM | November 26, 2018 5:00 PM | 2018-11-26 | 1 | 2323 | 4
2325 | Yes | Auto Scheduled | Review with AAR at GMNA | 4 days | November 27, 2018 8:00 AM | November 30, 2018 5:00 PM | 2018-11-30 | 1 | 2324 | 4
2326 | Yes | Auto Scheduled | Ship to China | 1 wk | December 7, 2018 8:00 AM | December 13, 2018 5:00 PM | 2018-12-13 | 1 | 2325 | 4
2327 | Yes | Auto Scheduled | Review with PATAC AAR at GM China | 4.8 wks | December 14, 2018 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 | 2326 | 4 | Need to confirm with GM China for meeting.
2328 | Yes | Auto Scheduled | PCE 028 - New applique math / Red and Amber LEDs change | 153 days | October 31, 2018 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 3 | PCE 028 - New applique math / Red and Amber LEDs change
2329 | Yes | Auto Scheduled | GM approval on C1UB | 1 wk | October 31, 2018 8:00 AM | November 6, 2018 5:00 PM | 2018-11-06 | 1 |  | 4 | PCE 028 - New applique math / Red and Amber LEDs change
2330 | Yes | Auto Scheduled | LED management Sheet (Final) | 8 days | December 5, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 | 2329 | 4 | PCE 028 - New applique math / Red and Amber LEDs change
2331 | Yes | Auto Scheduled | LED Management Sheet (65% BOR) rev 9 | 1 day | February 6, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 |  | 4
2332 | No | Auto Scheduled | Final PCB keep out / PCB Interface Drawing | 5 days | February 18, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2329 | 4
2333 | Yes | Auto Scheduled | New graphics from GM (applique) PCE 032 | 6 days | February 18, 2019 8:00 AM | February 25, 2019 5:00 PM | 2019-02-25 | 1 | 2320 | 4
2334 | Yes | Auto Scheduled | Variation List New/Release (include calibration points) (1st 3 pages only) | 12 days | February 26, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2329,2333 | 4
2335 | Yes | Auto Scheduled | Variation list approval (1st pages only) | 8.8 wks | March 14, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 2334 | 4
2336 | Yes | Auto Scheduled | EWO from GM | 1 day | March 20, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 4
2337 | No | Auto Scheduled | Variation List Release (Full) | 15 days | March 21, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 2336 | 4
2338 | No | Auto Scheduled | Variation List Release (Full) Approval | 5 days | April 11, 2019 8:00 AM | April 17, 2019 5:00 PM | 2019-04-17 | 1 | 2337 | 4
2339 | Yes | Auto Scheduled | Release graphics to NS (pending with Alex Debek for coming changes) | 1 day | February 18, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2329,2320 | 4 | PCE 028 - New applique math / Red and Amber LEDs change / PCE 012 Included
2340 | Yes | Auto Scheduled | Mechanical Production BOM | 1 wk | May 27, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 2329,2334 | 4 | PCE 028 - New applique math / Red and Amber LEDs change / PCE 012 Included
2341 | No | Auto Scheduled | New screens for applique (To be confirmed) | 12 wks | June 3, 2019 8:00 AM | August 27, 2019 5:00 PM | 2019-08-27 | 0 | 2340 | 4 | PCE 028 - New applique math / Red and Amber LEDs change / PCE 012 Included
2342 | Yes | Auto Scheduled | Design Freeze | 0 days | November 19, 2018 8:00 AM | November 19, 2018 8:00 AM | 2018-11-19 | 1 |  | 3
2343 | Yes | Auto Scheduled | Mechanical Drawings (2Ds and 3Ds) | 90 days | November 19, 2018 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
2344 | Yes | Auto Scheduled | Applique | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2342 | 4
2345 | Yes | Auto Scheduled | Lens | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2342 | 4
2346 | Yes | Auto Scheduled | Visor | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2342 | 4 | PCE 035 Included
2347 | Yes | Auto Scheduled | Outer Case | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2342 | 4 | PCE 034 Included
2348 | Yes | Auto Scheduled | Chromed Rings | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 2342 | 4
2349 | Yes | Auto Scheduled | Review with suppliers | 2 wks | February 7, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 2344,2345,2346,2347,2348 | 4
2350 | Yes | Auto Scheduled | Applique Update | 8 days | February 21, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2349 | 4
2351 | Yes | Auto Scheduled | Lens Update | 11 days | February 21, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 | 2349 | 4
2352 | Yes | Auto Scheduled | Visor Update | 11 days | February 21, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 | 2349 | 4
2353 | Yes | Auto Scheduled | Outer Case Update | 8 days | February 21, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2349 | 4
2354 | Yes | Auto Scheduled | Chromed Rings Update | 22 days | February 21, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2349 | 4 | Pending due to Issue # 119
2355 | Yes | Auto Scheduled | Review DRBFM with GM on Red and Amber changes | 1 wk | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 2349 | 3 | Pending with GM to decide if they need it.
2356 | Yes | Auto Scheduled | DRBFM approval from GM | 1 wk | June 24, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 2355 | 3
2357 | Yes | Auto Scheduled | OK to Tool Drawing release to GM | 0 days | February 25, 2019 5:00 PM | February 25, 2019 5:00 PM | 2019-02-25 | 1 | 2350,2351,2352,2353,2354 | 3
2358 | Yes | Auto Scheduled | OK to Tool Drawing approval by GM | 1 wk | February 26, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2357 | 3
2359 | Yes | Auto Scheduled | Release Drawings to NS | 20 days | February 26, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 3
2360 | Yes | Auto Scheduled | Lens | 11 days | February 26, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2357 | 4
2361 | Yes | Auto Scheduled | Visor | 11 days | February 26, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2357 | 4
2362 | Yes | Auto Scheduled | Outer Case | 11 days | February 26, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2357 | 4
2363 | Yes | Auto Scheduled | Applique | 1 day | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 2357,2354 | 4
2364 | Yes | Auto Scheduled | Chrome Ring | 1 day | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 2357,2354 | 4
2365 | Yes | Auto Scheduled | Hardware Development | 311 days | April 23, 2018 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 2
2366 | Yes | Auto Scheduled | System examination meeting(4) | 231 days | April 23, 2018 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 3
2367 | Yes | Auto Scheduled | SYS/ SW Power Sequence Measurements | 207 days | April 23, 2018 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 |  | 4
2368 | Yes | Auto Scheduled | SW5V Enable from SoC (SL.No 12) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2369 | Yes | Auto Scheduled | PSC (SL.N0 14) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2370 | Yes | Auto Scheduled | SWVBB Monitor (SL 18) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2371 | Yes | Auto Scheduled | SoC Output for Gauges (21) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2372 | Yes | Auto Scheduled | HSCAN TX (22) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2373 | Yes | Auto Scheduled | HSCAN RX (23) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2374 | Yes | Auto Scheduled | Pointer PWM (25) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2375 | Yes | Auto Scheduled | Dial PWM (26) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2376 | Yes | Auto Scheduled | TT SEG WHITE LED PWM (27) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2377 | Yes | Auto Scheduled | TT LED CS (28) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2378 | Yes | Auto Scheduled | SEG LED CS (29) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2379 | Yes | Auto Scheduled | LIN RX (31) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2380 | Yes | Auto Scheduled | LIN TX (32) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2381 | Yes | Auto Scheduled | HyperMemory MCP (33-36) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2382 | Yes | Auto Scheduled | CMI 4.2" TFT (37-43) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2383 | Yes | Auto Scheduled | ENET Reset (45) | 161 days | April 23, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 5
2384 | Yes | Auto Scheduled | Create report | 9 days | December 10, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 2368,2369,2370,2371,2372,2373,2374,2375,2376,2377,2378,2379,2380,2381,2382,2383 | 5
2385 | Yes | Auto Scheduled | Review Report | 3 days | January 4, 2019 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 | 2384 | 5
2386 | Yes | Auto Scheduled | Retake measurements based on feedback | 5 days | January 18, 2019 8:00 AM | January 24, 2019 5:00 PM | 2019-01-24 | 1 | 2385 | 5
2387 | Yes | Auto Scheduled | Report update | 1 day | January 25, 2019 8:00 AM | January 25, 2019 5:00 PM | 2019-01-25 | 1 | 2386 | 5
2388 | Yes | Auto Scheduled | HW review and feedback | 3 days | January 28, 2019 8:00 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 | 2387 | 5
2389 | Yes | Auto Scheduled | Retake measurements based on feedback and update report | 4 days | January 31, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 | 2388 | 5
2390 | Yes | Auto Scheduled | HW Power Sequence Measurements, Judgements, action plan if NG | 3.6 wks | September 3, 2018 8:00 AM | September 26, 2018 5:00 PM | 2018-09-26 | 1 | 2278 | 4
2391 | Yes | Auto Scheduled | System examination meeting 4 | 0 days | January 17, 2019 5:00 PM | January 17, 2019 5:00 PM | 2019-01-17 | 1 | 2772,2390 | 4
2392 | Yes | Auto Scheduled | HW Waveform measurements | 5 days | March 5, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 4 | Activity on hold due to software updates (sw 142)
2393 | Yes | Auto Scheduled | Take measurements (sw21.21.142.1) | 5 days | March 5, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 5
2394 | Yes | Auto Scheduled | TFT waveform measurement (sw21.21.142.1) | 5 days | March 5, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 6
2395 | No | Auto Scheduled | Gauge driver waveform measurements | 6 days | March 18, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 2703 | 6 | Cannot be testing due to RAID Log Issue # 105. It will be tested in sw 21.21.144
2396 | No | Auto Scheduled | TFT Thermistor waveform measurements | 6 days | March 26, 2019 8:00 AM | April 2, 2019 5:00 PM | 2019-04-02 | 1 | 2395 | 6 | Cannot be testing due to RAID Log Issue # 105. It will be tested in sw 21.21.144
2397 | No | Auto Scheduled | Hyperbus waveform measurements | 6 days | March 25, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 2394 | 6 | Resource availability is pushing the date
2398 | No | Auto Scheduled | Telltale driver waveform measurements | 6 days | April 2, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2397 | 6 | PCB has wrong resistors, HW team needs to change the resistors to complete the testing
2399 | No | Auto Scheduled | Review HW waveform measurements | 10 days | April 3, 2019 8:00 AM | April 16, 2019 5:00 PM | 2019-04-16 | 1 | 2397,2396 | 5
2400 | No | Auto Scheduled | Create report | 10 days | April 17, 2019 8:00 AM | April 30, 2019 5:00 PM | 2019-04-30 | 1 | 2399 | 5
2401 | No | Auto Scheduled | Report approval | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 | 2400 | 5
2402 | Yes | Auto Scheduled | PCE 028 - New applique math / Red and Amber LEDs change | 112 days | January 25, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 |  | 3
2403 | Yes | Auto Scheduled | Telltale driver analysis | 10 days | January 25, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 2330,2331 | 4 | Feedback from ME is pending, and tracked in Action Item 227
2404 | Yes | Auto Scheduled | System Design Sheet | 0.6 wks | February 14, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2403 | 4
2405 | No | Auto Scheduled | Update Schematic | 1 wk | February 21, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 2404 | 4 | It is not required to change.
2406 | Yes | Auto Scheduled | Update EBOM | 1 wk | February 21, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 | 2404 | 4 | PCE 028 - New applique math Red and Amber LEDs change
2407 | Yes | Auto Scheduled | Update SDS | 2 wks | June 3, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 4
2408 | Yes | Auto Scheduled | SDS Approval | 2.2 wks | June 17, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 | 2407 | 4
2409 | No | Auto Scheduled | Group Design Review | 1 day | March 14, 2019 8:00 AM | March 15, 2019 8:00 AM | 2019-03-15 | 1 | 2410SF-2w | 3 | Skipped as JPN decided this is carry over from C3HILO and there are no technical matters to be discussed
2410 | No | Auto Scheduled | DR2 (Design Review 2) | 1 day | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2392 | 3 | Skipped as JPN decided this is carry over from C3HILO and there are no technical matters to be discussed
2411 | Yes | Auto Scheduled | Second design change point mgt | 1 day | May 16, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2410 | 3
2412 | Yes | Auto Scheduled | Design Quality Assesment | 0 days | May 30, 2019 8:00 AM | May 30, 2019 8:00 AM | 2019-05-30 | 1 | 2411 | 3
2413 | Yes | Auto Scheduled | Software Development | 10 days | May 28, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 2
2414 | Yes | Auto Scheduled | PCE 028 - New applique math / Red and Amber LEDs change | 10 days | May 28, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 3
2415 | Yes | Auto Scheduled | System Requirement Update | 5 days | May 28, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 2404,2338 | 4
2416 | Yes | Auto Scheduled | LED settings update | 5 days | June 4, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 2415 | 4
2417 | Yes | Auto Scheduled | Software Development (21.21.142.1) | 121 days | November 15, 2018 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 2 | 21.21.143 was cancelled, and now 21.21.142.1 replaces it.
2418 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.142.1) | 24 days | November 15, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 |  | 3
2419 | Yes | Auto Scheduled | Verification Criteria (sw21.21.142.1) | 69 days | November 29, 2018 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 |  | 3
2420 | Yes | Auto Scheduled | SYS5 | 10 days | November 29, 2018 8:00 AM | December 12, 2018 5:00 PM | 2018-12-12 | 1 | 926 | 4
2421 | Yes | Auto Scheduled | SYS5 Phase 2 (142 requirements) | 10 days | February 5, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 |  | 4
2422 | No | Auto Scheduled | Software | 50 days | July 24, 2018 8:00 AM | October 1, 2018 5:00 PM | 2018-10-01 | 1 | 926 | 4 | Verification Criteria will be created in Software Functional Specs
2423 | Yes | Auto Scheduled | Hardware (sw21.21.142.1) | 42 days | January 7, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 |  | 4
2424 | Yes | Auto Scheduled | Verification Criteria for hardware requirements part 1 (sw21.21.142.1) | 10 days | January 7, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 | 926 | 5 | Pending Mauro to define strategy on how to complete verification criteria for HW
2425 | Yes | Auto Scheduled | Verification Criteria for hardware requirements part 2 (sw21.21.142.1) | 10 days | January 21, 2019 8:00 AM | February 1, 2019 5:00 PM | 2019-02-01 | 1 | 2424 | 5
2426 | Yes | Auto Scheduled | Verification Criteria for hardware requirements part 3 (sw21.21.142.1) | 10 days | February 4, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 2425 | 5
2427 | Yes | Auto Scheduled | Internal Review of Verification Criteria (sw21.21.142.1) | 10 days | February 18, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 2426 | 5
2428 | Yes | Auto Scheduled | Update based on feedback (sw21.21.142.1) | 1 day | March 4, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2427 | 5
2429 | Yes | Auto Scheduled | Approval of Verfication Criteria (sw21.21.142.1) | 1 day | March 5, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 2428 | 5
2430 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.142.1) | 1 day | December 11, 2018 8:00 AM | December 11, 2018 5:00 PM | 2018-12-11 | 1 | 2418 | 3
2431 | Yes | Auto Scheduled | Systems Architecture (SYS3) (sw21.21.142.1) | 2.4 days | December 3, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 2418 | 3
2432 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.142.1) | 1 day | December 17, 2018 8:00 AM | December 17, 2018 5:00 PM | 2018-12-17 | 1 | 2431 | 3
2433 | Yes | Auto Scheduled | Software Functional Specs (SWE1) (sw21.21.142.1) | 0 days | December 7, 2018 8:00 AM | December 20, 2018 5:00 PM | 2018-12-20 | 1 | 2418 | 3
2434 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.142.1) | 1 day | January 22, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 2433 | 3
2435 | Yes | Auto Scheduled | Sprint 1 (21.21.142.1) | 113 days | November 27, 2018 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 3
2436 | Yes | Auto Scheduled | Program Management | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 4
2437 | Yes | Auto Scheduled | Release Kick Off meeting (sw21.21.142.1) | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 5
2438 | No | Auto Scheduled | CG2999 for release sw21.21.141 | 1 day | January 21, 2019 8:00 AM | January 21, 2019 5:00 PM | 2019-01-21 | 1 |  | 5 | Released in previous timing
2439 | Yes | Auto Scheduled | Systems Engineering 2 | 51 days | November 27, 2018 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 |  | 4
2440 | Yes | Auto Scheduled | SRS Minor baseline (sw21.21.144) | 21 days | January 8, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 | 2477SF,2681SF,2905SF,3040SF,3180SF,3339SF | 5
2441 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.144) | 10 days | November 27, 2018 8:00 AM | December 11, 2018 8:00 AM | 2018-12-11 | 1 | 2479SF | 5
2442 | Yes | Auto Scheduled | Systems Engineering 3 | 32 days | January 9, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 4
2443 | Yes | Auto Scheduled | SAD Minor baseline (sw21.21.144) | 32 days | January 9, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2481SF | 5
2444 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.144) | 10 days | January 29, 2019 8:00 AM | February 12, 2019 8:00 AM | 2019-02-12 | 1 | 2483SF | 5
2445 | Yes | Auto Scheduled | SAD Hardware Test Case Creation / Baselline (sw21.21.142.1) | 10 days | January 9, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 |  | 5 | 33 Requirements only
2446 | Yes | Auto Scheduled | SAD Hardware Test Case Creation / Baselline (sw21.21.144) | 10 days | January 23, 2019 8:00 AM | February 5, 2019 5:00 PM | 2019-02-05 | 1 | 2445 | 5 | 33 Requirements only
2447 | Yes | Auto Scheduled | SAD Hardware Test Case Creation / Baselline (sw21.21.144) | 8 days | February 6, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 2446 | 5 | 33 Requirements only
2448 | Yes | Auto Scheduled | Software Systems | 10 days | February 12, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 |  | 4
2449 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.144) | 10 days | February 12, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 | 2486SF | 5
2450 | Yes | Auto Scheduled | Software Design | 27 days | November 30, 2018 8:00 AM | January 8, 2019 8:00 AM | 2019-01-08 | 1 |  | 4
2451 | Yes | Auto Scheduled | RC-1 BSP and Bootloader exchange (sw21.21.142.1) | 3 days | November 30, 2018 8:00 AM | December 4, 2018 5:00 PM | 2018-12-04 | 1 | 2473FS-3w | 5 | Software exchange delayed by NSI due to process issues
2452 | No | Auto Scheduled | Architecture Design minor baseline (sw21.21.142.1) | 10 days | December 18, 2018 8:00 AM | January 15, 2019 8:00 AM | 2019-01-15 | 1 | 2489SF | 5
2453 | No | Auto Scheduled | Layer Design minor baseline (sw21.21.142.1) | 10 days | December 18, 2018 8:00 AM | January 15, 2019 8:00 AM | 2019-01-15 | 1 | 2490SF | 5
2454 | No | Auto Scheduled | Unit Design minor baseline (sw21.21.142.1) | 10 days | December 18, 2018 8:00 AM | January 15, 2019 8:00 AM | 2019-01-15 | 1 | 2491SF | 5
2455 | Yes | Auto Scheduled | Redmine Software Implementation (sw21.21.142.1) | 10 days | December 11, 2018 8:00 AM | January 8, 2019 8:00 AM | 2019-01-08 | 1 | 2492SF | 5
2456 | No | Manually Scheduled | Software Verification SWE6 | 0 days | January 17, 2017 8:00 AM | January 17, 2017 8:00 AM | 2017-01-17 | 1 |  | 4
2457 | No | Auto Scheduled | Test Case minor baseline (sw21.21.142.1) | 10 days | December 7, 2018 8:00 AM | January 4, 2019 8:00 AM | 2019-01-04 | 1 | 2502SF | 5 | Team is working only on major baseline.
2458 | Yes | Auto Scheduled | Systems Integration | 10 days | January 2, 2019 8:00 AM | January 16, 2019 8:00 AM | 2019-01-16 | 1 |  | 4
2459 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.142.1) | 10 days | January 2, 2019 8:00 AM | January 16, 2019 8:00 AM | 2019-01-16 | 1 | 2514SF | 5
2460 | Yes | Auto Scheduled | Systems Qualification | 84 days | January 7, 2019 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 |  | 4
2461 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.142.1) | 9 days | January 7, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 | 2525SF | 5
2462 | Yes | Auto Scheduled | SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | 10 days | February 4, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 5 | Applicable for 114 requirements
2463 | Yes | Auto Scheduled | SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | 10 days | February 18, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 2462 | 5 | Applicable for 114 requirements
2464 | Yes | Auto Scheduled | SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | 10 days | March 4, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2463 | 5 | Applicable for 114 requirements
2465 | Yes | Auto Scheduled | SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | 10 days | March 18, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2464 | 5 | Applicable for 114 requirements
2466 | Yes | Auto Scheduled | SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2465 | 5 | Applicable for 114 requirements
2467 | Yes | Auto Scheduled | SRS Hardware Test Case Review by HW team (sw21.21.142.1) | 5 days | April 15, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 2466 | 5 | Applicable for 114 requirements
2468 | Yes | Auto Scheduled | Review Comments Update (sw21.21.142.1) | 3 days | April 22, 2019 8:00 AM | April 24, 2019 5:00 PM | 2019-04-24 | 1 | 2467 | 5
2469 | Yes | Auto Scheduled | Review and provide feedback from Systems | 6 days | April 25, 2019 8:00 AM | May 2, 2019 5:00 PM | 2019-05-02 | 1 | 2468 | 5
2470 | No | Auto Scheduled | SRS Hardware Test Case approval (sw21.21.142.1) | 5 days | May 3, 2019 8:00 AM | May 9, 2019 5:00 PM | 2019-05-09 | 1 | 2469 | 5
2471 | No | Auto Scheduled | CG2999 submit to GM (release 21.21.141) | 3 days | January 17, 2017 8:00 AM | January 19, 2017 5:00 PM | 2017-01-19 | 1 |  | 4
2472 | Yes | Auto Scheduled | Sprint 2 (21.21.142.1) | 74 days | December 3, 2018 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 3
2473 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.142.1) | 0 days | December 21, 2018 8:00 AM | December 21, 2018 8:00 AM | 2018-12-21 | 1 | 2499FS-4w | 4
2474 | Yes | Auto Scheduled | Program Management | 2 days | February 15, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 |  | 4
2475 | Yes | Auto Scheduled | CG4422 updated to GM (sw21.21.142.1) | 2 days | February 15, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2499 | 5
2476 | Yes | Auto Scheduled | Systems Engineering 2 | 35 days | January 8, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 |  | 4
2477 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.144) | 30 days | January 8, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2481SF | 5
2478 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.144) | 0 days | February 18, 2019 8:00 AM | February 18, 2019 8:00 AM | 2019-02-18 | 1 | 2477 | 5
2479 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw 21.21.144) | 10 days | February 12, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 | 2541SF | 5
2480 | Yes | Auto Scheduled | Systems Engineering 3 | 37 days | January 23, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
2481 | Yes | Auto Scheduled | SAD Major baseline (sw21.21.144) | 37 days | January 23, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 2485SF | 5 | There are no updates on SAD for 21.21.144
2482 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.144) | 0 days | March 14, 2019 5:00 PM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 2481 | 5
2483 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw 21.21.144) | 10 days | February 12, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 | 2543SF | 5
2484 | Yes | Auto Scheduled | Software Systems | 27 days | January 8, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 |  | 4
2485 | Yes | Auto Scheduled | Software Functional Specs minor baseline (sw21.21.144) | 4 days | February 8, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 2694SF | 5
2486 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw 21.21.144) | 10 days | January 8, 2019 8:00 AM | January 22, 2019 8:00 AM | 2019-01-22 | 1 | 2545SF | 5
2487 | Yes | Auto Scheduled | Software Design | 37 days | January 8, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 4
2488 | Yes | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw 21.21.144) | 0 days | January 15, 2019 8:00 AM | January 15, 2019 8:00 AM | 2019-01-15 | 1 |  | 5
2489 | Yes | Auto Scheduled | Architecture Design Major basline (sw 21.21.142.1) | 29 days | January 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2498SF | 5
2490 | Yes | Auto Scheduled | Layer Design Major baseline (sw 21.21.142.1) | 29 days | January 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2498SF | 5
2491 | Yes | Auto Scheduled | Unit Design Major baseline (sw 21.21.142.1) | 29 days | January 15, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2498SF | 5
2492 | Yes | Auto Scheduled | Redmine Software Implementation (acc. to FROP) (sw 21.21.142.1) | 15 days | January 8, 2019 8:00 AM | January 28, 2019 5:00 PM | 2019-01-28 | 1 | 2498SF | 5
2493 | Yes | Auto Scheduled | Software Integration Test Spec major baseline (sw21.21.142.1) | 34 days | January 8, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2498SF | 5
2494 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.142.1) | 0.5 days | February 1, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2489 | 5
2495 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.142.1) | 0 days | February 21, 2019 5:00 PM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2490 | 5
2496 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.142.1) | 0 days | February 21, 2019 5:00 PM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2491 | 5
2497 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.142.1) | 0 days | February 21, 2019 5:00 PM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2493 | 5
2498 | Yes | Auto Scheduled | Full Integration Testing (sw 21.21.142.1) | 3 days | January 29, 2019 8:00 AM | January 31, 2019 5:00 PM | 2019-01-31 | 1 | 2499SF | 5
2499 | Yes | Auto Scheduled | Internal SW release (sw 21.21.142.1) | 0 days | February 1, 2019 8:00 AM | February 1, 2019 8:00 AM | 2019-02-01 | 1 | 2532FS-2w | 5 | sw release is delayed due to major issues found during integration testing
2500 | Yes | Auto Scheduled | Sanity Check (sw 21.21.142.1) | 1 day | February 27, 2019 8:00 AM | February 27, 2019 5:00 PM | 2019-02-27 | 1 |  | 5
2501 | Yes | Auto Scheduled | Software Validation | 35 days | January 4, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 4
2502 | Yes | Auto Scheduled | Test Case major baseline (sw21.21.142.1) | 31 days | January 4, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 2433 | 5 | Baseline is delayed, and the team is working in parallel with execution to complete the baseline
2503 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.142.1) | 4.15 days | February 1, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2502 | 5
2504 | Yes | Auto Scheduled | Systems Integration | 59 days | December 3, 2018 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 4
2505 | Yes | Auto Scheduled | FROP Analysis | 59 days | December 3, 2018 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 5
2506 | Yes | Auto Scheduled | Redmine Analysis | 1 day | January 24, 2019 11:12 AM | January 25, 2019 11:12 AM | 2019-01-25 | 1 | 2514 | 6
2507 | Yes | Auto Scheduled | Execution Plan Preparation | 0.5 days | January 25, 2019 11:12 AM | January 25, 2019 4:12 PM | 2019-01-25 | 1 | 2506 | 6
2508 | Yes | Auto Scheduled | Review (Pre-Validation Meeting) | 0.5 days | January 25, 2019 4:12 PM | January 28, 2019 11:12 AM | 2019-01-28 | 1 | 2507 | 6
2509 | Yes | Auto Scheduled | System Architecture Design Analysis | 3 days | December 3, 2018 8:00 AM | December 5, 2018 5:00 PM | 2018-12-05 | 1 |  | 6
2510 | Yes | Auto Scheduled | Test Case Update | 18 days | December 12, 2018 8:00 AM | January 4, 2019 5:00 PM | 2019-01-04 | 1 | 2509 | 6
2511 | Yes | Auto Scheduled | Test Case Review | 2 days | January 7, 2019 8:00 AM | January 8, 2019 5:00 PM | 2019-01-08 | 1 | 2510 | 6
2512 | Yes | Auto Scheduled | Test Case Rework | 10 days | January 9, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 2511 | 6
2513 | Yes | Auto Scheduled | Traceablity Link | 2 days | January 14, 2019 8:00 AM | January 23, 2019 11:12 AM | 2019-01-23 | 1 | 2512 | 6
2514 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.142.1) | 5.6 days | January 23, 2019 11:12 AM | January 30, 2019 5:00 PM | 2019-01-30 | 1 | 2513 | 6
2515 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.142.1) | 16 days | January 31, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2514 | 6
2516 | Yes | Auto Scheduled | Systems Qualification | 33 days | January 8, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 4
2517 | Yes | Auto Scheduled | FROP Analysis | 33 days | January 8, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 5
2518 | Yes | Auto Scheduled | Redmine Analysis | 1 day | January 18, 2019 8:00 AM | January 18, 2019 5:00 PM | 2019-01-18 | 1 |  | 6
2519 | Yes | Auto Scheduled | Execution Plan Preparation | 0.5 days | February 1, 2019 8:00 AM | February 1, 2019 12:00 PM | 2019-02-01 | 1 | 2518 | 6
2520 | Yes | Auto Scheduled | Review (Pre-Validation Meeting) | 0.5 days | February 4, 2019 8:00 AM | February 4, 2019 12:00 PM | 2019-02-04 | 1 | 2518 | 6
2521 | Yes | Auto Scheduled | Baseline 7.1 SRS Analysis | 2 days | January 8, 2019 8:00 AM | January 9, 2019 5:00 PM | 2019-01-09 | 1 |  | 6
2522 | Yes | Auto Scheduled | Test Case Update | 5 days | January 10, 2019 8:00 AM | January 16, 2019 5:00 PM | 2019-01-16 | 1 | 2521 | 6
2523 | Yes | Auto Scheduled | Test Case Review | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 | 2522 | 6
2524 | Yes | Auto Scheduled | Test Case Rework | 3 days | January 18, 2019 8:00 AM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 2523 | 6
2525 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.142.1) | 0 days | January 22, 2019 5:00 PM | January 22, 2019 5:00 PM | 2019-01-22 | 1 | 2524 | 6
2526 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.142.1) | 22 days | January 23, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2525 | 6
2527 | Yes | Auto Scheduled | Sprint 3 (21.21.142.1) | 54 days | January 8, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 3
2528 | Yes | Auto Scheduled | Create Dummy Production CALS | 4 days | February 1, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 | 2499 | 4
2529 | Yes | Auto Scheduled | Program Management | 26 days | February 1, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 4
2530 | Yes | Auto Scheduled | Software Release notes (sw 21.21.142.1) | 2 days | February 20, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2532FS-2d | 5
2531 | Yes | Auto Scheduled | Software Release Assessment (sw 21.21.142.1) | 0 days | February 22, 2019 8:00 AM | February 22, 2019 8:00 AM | 2019-02-22 | 1 | 2532 | 5
2532 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw 21.21.142.1) | 0 days | February 22, 2019 8:00 AM | February 22, 2019 8:00 AM | 2019-02-22 | 1 | 1288 | 5 | Software release affected by 5 Phase 021
2533 | Yes | Auto Scheduled | CG2999 to GM (partial) (sw 21.21.142.1) | 26 days | February 1, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 5
2534 | Yes | Auto Scheduled | Unit Test report | 4 days | February 15, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1288 | 6 | Rescheduled due to sw21.21.142.2 release
2535 | Yes | Auto Scheduled | SAA update | 4 days | February 15, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1288 | 6 | Rescheduled due to sw21.21.142.2 release
2536 | Yes | Auto Scheduled | Integratoin Test report | 16 days | February 15, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 1288 | 6 | Rescheduled due to sw21.21.142.2 release
2537 | No | Auto Scheduled | Performance Paramters report | 4 days | February 15, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 | 1288 | 6 | Rescheduled due to sw21.21.142.2 release
2538 | Yes | Auto Scheduled | Stress Test Results | 0 days | February 1, 2019 8:00 AM | February 1, 2019 8:00 AM | 2019-02-01 | 1 | 2499 | 6
2539 | Yes | Auto Scheduled | Black box test results | 1 day | February 22, 2019 5:00 PM | February 25, 2019 5:00 PM | 2019-02-25 | 1 | 2499,1295,2589 | 6
2540 | Yes | Auto Scheduled | Systems Engineering 2 | 10 days | January 8, 2019 8:00 AM | January 22, 2019 8:00 AM | 2019-01-22 | 1 |  | 4
2541 | Yes | Auto Scheduled | Redmine Analysis complete (sw 21.21.144) | 10 days | January 8, 2019 8:00 AM | January 22, 2019 8:00 AM | 2019-01-22 | 1 | 2545SF | 5
2542 | Yes | Auto Scheduled | Systems Engineering 3 | 10 days | January 8, 2019 8:00 AM | January 22, 2019 8:00 AM | 2019-01-22 | 1 |  | 4
2543 | Yes | Auto Scheduled | Redmine Analysis complete (sw 21.21.144) | 10 days | January 8, 2019 8:00 AM | January 22, 2019 8:00 AM | 2019-01-22 | 1 | 2545SF | 5
2544 | Yes | Auto Scheduled | Software Systems | 32 days | January 22, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 |  | 4
2545 | Yes | Auto Scheduled | Redmine Analysis complete (sw 21.21.144) | 10 days | January 22, 2019 8:00 AM | February 5, 2019 8:00 AM | 2019-02-05 | 1 | 2669SF | 5
2546 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw 21.21.144) | 16 days | February 11, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2666SF | 5
2547 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.144) | 2 days | March 5, 2019 8:00 AM | March 6, 2019 5:00 PM | 2019-03-06 | 1 | 2546 | 5
2548 | Yes | Auto Scheduled | Software Design | 15 days | March 4, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 4
2549 | Yes | Auto Scheduled | CG4117 (sw 21.21.142.1) white box tesging | 15 days | March 4, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2499 | 5 | Sprint 44S2
2550 | Yes | Auto Scheduled | Software Validation | 16 days | February 1, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 4
2551 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.142.1) | 12 days | February 1, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2499 | 5
2552 | Yes | Auto Scheduled | SWE6 Verification Testing (sw21.21.142.1) | 10 days | February 1, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 2499 | 5
2553 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.142.1) | 0 days | February 22, 2019 5:00 PM | February 22, 2019 5:00 PM | 2019-02-22 | 1 | 2552,1295 | 5
2554 | No | Auto Scheduled | OTA reliability test | 54 days | February 27, 2019 8:00 AM | May 13, 2019 5:00 PM | 2019-05-13 | 1 |  | 5 | Affected by 21E3_E2Ux_5 Phase_011_OTA Reflash
2555 | Yes | Auto Scheduled | Systems Integration | 12.5 days | February 1, 2019 8:00 AM | February 19, 2019 12:00 PM | 2019-02-19 | 1 |  | 4
2556 | Yes | Auto Scheduled | Test Execution (sw21.21.142.1) | 10 days | February 1, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 5
2557 | Yes | Auto Scheduled | Externel Interfaces | 2 days | February 1, 2019 8:00 AM | February 4, 2019 5:00 PM | 2019-02-04 | 1 | 2499 | 6
2558 | Yes | Auto Scheduled | Internel Interfaces | 2 days | February 5, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 | 2557 | 6
2559 | Yes | Auto Scheduled | System Safety Strategy | 2 days | February 7, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 | 2558 | 6
2560 | Yes | Auto Scheduled | System Fault Tolerant Timings | 1 day | February 11, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 | 2559 | 6
2561 | Yes | Auto Scheduled | System Safe State Transitions | 1 day | February 12, 2019 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 | 2560 | 6
2562 | Yes | Auto Scheduled | System Dynamic Behaviour | 1 day | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 | 2561 | 6
2563 | Yes | Auto Scheduled | System Communication Integration | 1 day | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 | 2562 | 6
2564 | Yes | Auto Scheduled | Validation Report & Defect Analysis (sw21.21.142.1) | 2.5 days | February 15, 2019 8:00 AM | February 19, 2019 12:00 PM | 2019-02-19 | 1 |  | 5
2565 | Yes | Auto Scheduled | System Integration Test Summary Report | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 | 2563 | 6
2566 | Yes | Auto Scheduled | Test Result Update | 1 day | February 18, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2565 | 6
2567 | Yes | Auto Scheduled | Defect analysis | 0.5 days | February 19, 2019 8:00 AM | February 19, 2019 12:00 PM | 2019-02-19 | 1 | 2566 | 6
2568 | Yes | Auto Scheduled | Systems Qualification | 24 days | February 5, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 |  | 4
2569 | Yes | Auto Scheduled | Test Execution High Priority Module (sw21.21.142.1) | 11 days | February 5, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 2520 | 5
2570 | Yes | Auto Scheduled | Teltales | 2 days | February 5, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 |  | 6
2571 | Yes | Auto Scheduled | TFT | 2 days | February 5, 2019 8:00 AM | February 6, 2019 5:00 PM | 2019-02-06 | 1 |  | 6
2572 | Yes | Auto Scheduled | Power Mode | 3 days | February 5, 2019 8:00 AM | February 7, 2019 5:00 PM | 2019-02-07 | 1 |  | 6
2573 | Yes | Auto Scheduled | Illumination | 3 days | February 5, 2019 8:00 AM | February 7, 2019 5:00 PM | 2019-02-07 | 1 |  | 6
2574 | Yes | Auto Scheduled | Stress Test | 7 days | February 7, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 6
2575 | Yes | Auto Scheduled | Functional Safety | 2 days | February 7, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 |  | 6
2576 | Yes | Auto Scheduled | CAN | 2 days | February 12, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 |  | 6
2577 | Yes | Auto Scheduled | HWIO | 1 day | February 8, 2019 8:00 AM | February 8, 2019 5:00 PM | 2019-02-08 | 1 |  | 6
2578 | Yes | Auto Scheduled | NVM | 2 days | February 8, 2019 8:00 AM | February 11, 2019 5:00 PM | 2019-02-11 | 1 |  | 6
2579 | Yes | Auto Scheduled | Gauges | 2 days | February 11, 2019 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 |  | 6
2580 | Yes | Auto Scheduled | LIN | 2 days | February 12, 2019 8:00 AM | February 13, 2019 5:00 PM | 2019-02-13 | 1 |  | 6
2581 | Yes | Auto Scheduled | Bootloader (use sw21.21.142.2) | 3 days | February 15, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 1288 | 6
2582 | Yes | Auto Scheduled | Ethernet | 2 days | February 13, 2019 8:00 AM | February 14, 2019 5:00 PM | 2019-02-14 | 1 |  | 6
2583 | Yes | Auto Scheduled | DOORS update | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 6
2584 | Yes | Auto Scheduled | Test Reporting | 1 day | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 2019-02-15 | 1 |  | 6
2585 | Yes | Auto Scheduled | Test Execution Low Priority Module (sw21.21.142.1) | 5 days | February 18, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 5
2586 | Yes | Auto Scheduled | Cyber Security | 3 days | February 18, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 |  | 6
2587 | Yes | Auto Scheduled | Line Test | 3 days | February 18, 2019 8:00 AM | February 20, 2019 5:00 PM | 2019-02-20 | 1 |  | 6
2588 | Yes | Auto Scheduled | DOORS update | 1 day | February 21, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 6
2589 | Yes | Auto Scheduled | Test Reporting | 2 days | February 21, 2019 8:00 AM | February 22, 2019 5:00 PM | 2019-02-22 | 1 |  | 6
2590 | Yes | Auto Scheduled | Compliance Test | 11 days | February 22, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 2499 | 5 | Software issues does not allow to test with 21.21.142.1
2591 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw21.21.142.1) | 5 days | February 22, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 2499 | 6 | Testing added as per GM request even issues are not fixed
2592 | Yes | Auto Scheduled | CG3877 - CAN Physical Layer Test (sw21.21.142.1) | 10 days | February 22, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 | 2499 | 6 | Testing added as per GM request even issues are not fixed
2593 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw21.21.142.1) | 6 days | March 1, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 2499,2591 | 6 | Testing added as per GM request even issues are not fixed
2594 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.142.1) | 20 days | February 1, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 2499 | 6 | Software issues does not allow to test with 21.21.142.1
2595 | No | Auto Scheduled | Fuzz Test Execution (sw21.21.142.1) | 547 days | January 17, 2017 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 |  | 6
2596 | No | Auto Scheduled | TCP Client (sw21.21.142.1) | 15 days | February 1, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2499 | 7
2597 | No | Auto Scheduled | TCP Server (sw21.21.142.1) | 15 days | February 1, 2019 8:00 AM | February 21, 2019 5:00 PM | 2019-02-21 | 1 | 2499 | 7 | Software issues does not allow to test with 21.21.142.1
2598 | No | Auto Scheduled | IPv4 (sw21.21.142.1) | 15 days | January 17, 2017 8:00 AM | February 6, 2017 5:00 PM | 2017-02-06 | 1 |  | 7 | Software issues does not allow to test with 21.21.142.1
2599 | Yes | Auto Scheduled | DIT Test @ GM (sw21.21.142.1) | 1 day | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 3
2600 | Yes | Auto Scheduled | GBFTT @ GM (sw21.21.142.1) | 3 days | March 7, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 3
2601 | Yes | Auto Scheduled | TWN (sw21.21.142.1) | 19 days | February 18, 2019 5:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 3
2602 | Yes | Auto Scheduled | Create TWN (sw21.21.142.1) | 0 days | February 18, 2019 5:00 PM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2603SF | 4
2603 | Yes | Auto Scheduled | Release TWN (sw21.21.142.1) | 6 days | March 8, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2599 | 4
2604 | Yes | Auto Scheduled | Parts Build | 10 days | March 18, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2603 | 3
2605 | Yes | Auto Scheduled | Implementation 3 (PV Readiness) (80% BOR Readiness) | 705 days | January 17, 2017 12:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 1
2606 | Yes | Auto Scheduled | Test Plan | 69 days | June 6, 2019 8:00 AM | September 10, 2019 5:00 PM | 2019-09-10 | 0 |  | 2 | Dates will be updated once this is discussed and agreed with GM based on Leg 6 and EMC DV test
2607 | Yes | Auto Scheduled | ENV Test Plan (PV) | 52 days | June 6, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
2608 | Yes | Auto Scheduled | PV Design changes presentation | 6 days | June 6, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
2609 | Yes | Auto Scheduled | PV Design changes review with GM | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 2608 | 4 | Feedback pending from GM
2610 | Yes | Auto Scheduled | Create Test Plan | 2 wks | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 2609 | 4
2611 | Yes | Auto Scheduled | Internal Approval | 1 wk | July 29, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 2610 | 4
2612 | Yes | Auto Scheduled | ENV Test Plan approval | 10 days | August 5, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2611 | 4
2613 | Yes | Auto Scheduled | EMC Test Plan (PV) | 52 days | June 6, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 3
2614 | Yes | Auto Scheduled | PV Design changes presentation | 5 days | June 6, 2019 8:00 AM | June 12, 2019 5:00 PM | 2019-06-12 | 1 |  | 4
2615 | Yes | Auto Scheduled | PV Design changes review with GM | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 2614 | 4
2616 | Yes | Auto Scheduled | Create Test Plan | 2 wks | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 2615 | 4
2617 | Yes | Auto Scheduled | Internal Approval | 1 wk | July 29, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 2616 | 4
2618 | Yes | Auto Scheduled | EMC Test Plan approval | 2 wks | August 5, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 2617 | 4
2619 | Yes | Auto Scheduled | Test Specimen Sheet | 2 days | August 19, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 | 2618,2612 | 3
2620 | Yes | Auto Scheduled | ADVP&R Timing Plan | 1 wk | August 21, 2019 8:00 AM | August 27, 2019 5:00 PM | 2019-08-27 | 0 | 2619 | 3
2621 | Yes | Auto Scheduled | ADVP&R | 2 wks | August 28, 2019 8:00 AM | September 10, 2019 5:00 PM | 2019-09-10 | 0 | 2620 | 3
2622 | Yes | Auto Scheduled | Mechanical | 44 days | April 23, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 2
2623 | Yes | Auto Scheduled | Customer Drawing release for internal approval | 10 days | May 17, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 |  | 3
2624 | Yes | Auto Scheduled | Customer Drawing Approval Systems Software | 2 days | May 31, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 2623 | 3
2625 | Yes | Auto Scheduled | Customer Drawing Approval Systems Application | 2 days | May 31, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 2623 | 3
2626 | Yes | Auto Scheduled | Customer Drawing Approval Hardware | 9 days | May 31, 2019 8:00 AM | June 12, 2019 5:00 PM | 2019-06-12 | 1 | 2623 | 3 | HW manager approval pending only
2627 | Yes | Auto Scheduled | Customer Drawing Release to GM | 5 days | June 13, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 2624,2625,2626 | 3
2628 | Yes | Auto Scheduled | Variation List | 24 days | April 23, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 |  | 3
2629 | Yes | Auto Scheduled | LED Management Sheet rev 10 release for Approval | 5 days | May 8, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 |  | 3
2630 | Yes | Auto Scheduled | LED Management Sheet rev 10 approval HW Lead | 5 days | May 15, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 | 2629 | 3 | HW manager approval pending only
2631 | Yes | Auto Scheduled | LED Management Sheet rev 10 approval HW Manager | 23 days | May 22, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 2630 | 3
2632 | Yes | Auto Scheduled | Software PV | 68 days | June 10, 2019 8:00 AM | September 11, 2019 5:00 PM | 2019-09-11 | 0 |  | 2
2633 | Yes | Auto Scheduled | CANoe Panel for PV (updates from DV) | 4 wks | June 10, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 3
2634 | Yes | Auto Scheduled | ENV / EMC PV Test Software development | 4 wks | June 10, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 3
2635 | Yes | Auto Scheduled | Software Test Report | 2 wks | July 10, 2019 8:00 AM | July 23, 2019 5:00 PM | 2019-07-23 | 1 | 2634 | 3
2636 | Yes | Auto Scheduled | ENV / EMC Test Software Release | 0 days | July 23, 2019 5:00 PM | July 23, 2019 5:00 PM | 2019-07-23 | 1 | 2635 | 3
2637 | Yes | Auto Scheduled | Sabina Test SW check with Galaxy | 6 wks | July 24, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 | 2636 | 3
2638 | Yes | Auto Scheduled | Release PV SW to SHNS via TWN | 1 day | August 23, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 | 2651 | 3
2639 | Yes | Auto Scheduled | Conduct Code Review | 3 days | August 26, 2019 8:00 AM | August 28, 2019 5:00 PM | 2019-08-28 | 0 | 2638 | 3
2640 | Yes | Auto Scheduled | Code Review Report with Checklist (MISRA Compliance) | 1 day | August 29, 2019 8:00 AM | August 29, 2019 5:00 PM | 2019-08-29 | 0 | 2639 | 3
2641 | Yes | Auto Scheduled | Updated Unit Test Specification | 3 days | August 30, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 | 2640 | 3
2642 | Yes | Auto Scheduled | Software Review Report | 1 day | September 4, 2019 8:00 AM | September 4, 2019 5:00 PM | 2019-09-04 | 0 | 2641 | 3
2643 | Yes | Auto Scheduled | Updated Unit Test Report | 2 days | September 5, 2019 8:00 AM | September 6, 2019 5:00 PM | 2019-09-06 | 0 | 2642 | 3
2644 | Yes | Auto Scheduled | Updated Static Test Report | 1 day | September 9, 2019 8:00 AM | September 9, 2019 5:00 PM | 2019-09-09 | 0 | 2643 | 3
2645 | Yes | Auto Scheduled | Final Production function specs | 1 day | September 10, 2019 8:00 AM | September 10, 2019 5:00 PM | 2019-09-10 | 0 | 2644 | 3
2646 | Yes | Auto Scheduled | Line Test and Agene Mode (SW) | 1 day | September 11, 2019 8:00 AM | September 11, 2019 5:00 PM | 2019-09-11 | 0 | 2645 | 3
2647 | Yes | Auto Scheduled | Hardware | 22 days | July 24, 2019 8:00 AM | August 22, 2019 5:00 PM | 2019-08-22 | 1 |  | 2
2648 | Yes | Auto Scheduled | Review Report | 3 days | August 16, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 | 3112 | 3
2649 | Yes | Auto Scheduled | ENV / EMC PV Software validation | 2 wks | July 24, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 2633,2636 | 3
2650 | Yes | Auto Scheduled | ENV / EMC PV Software Report | 2 wks | August 7, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 | 2649 | 3
2651 | Yes | Auto Scheduled | ENV / EMC PV Software Validation Report review /approval | 2 days | August 21, 2019 8:00 AM | August 22, 2019 5:00 PM | 2019-08-22 | 1 | 2650 | 3
2652 | Yes | Auto Scheduled | PV Set up check | 1 wk | August 14, 2019 8:00 AM | August 21, 2019 8:00 AM | 2019-08-21 | 1 | 3472SF-3w | 3
2653 | Yes | Auto Scheduled | Software Development (sw21.21.144) | 110 days | February 5, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 2
2654 | Yes | Auto Scheduled | Sprint 1 (21.21.144) | 31 days | February 5, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 3
2655 | Yes | Auto Scheduled | Program Management | 1 day | March 12, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 4
2656 | Yes | Auto Scheduled | Release Kick Off meeting (sw21.21.144) | 1 day | March 12, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2703SF-3d | 5
2657 | Yes | Auto Scheduled | Systems Engineering 2 | 13 days | March 1, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 4
2658 | Yes | Auto Scheduled | SRS Minor baseline (sw21.21.145) | 13 days | March 1, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 5 | Includes PCE 031
2659 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.145) | 11 days | March 1, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 5
2660 | Yes | Auto Scheduled | Systems Engineering 3 | 13 days | March 1, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 4
2661 | Yes | Auto Scheduled | SAD Minor baseline (sw21.21.145) | 13 days | March 1, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 5
2662 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.145) | 11 days | March 1, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 5
2663 | Yes | Auto Scheduled | Software Systems | 11 days | March 1, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 4
2664 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.145) | 11 days | March 1, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 5
2665 | Yes | Auto Scheduled | Software Design | 19 days | February 5, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 |  | 4
2666 | Yes | Auto Scheduled | Architecture Design minor baseline (sw21.21.144) | 16 days | February 8, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 2694SF | 5
2667 | Yes | Auto Scheduled | Layer Design minor baseline (sw21.21.144) | 16 days | February 8, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 2695SF | 5
2668 | Yes | Auto Scheduled | Unit Design minor baseline (sw21.21.144) | 16 days | February 8, 2019 8:00 AM | March 1, 2019 5:00 PM | 2019-03-01 | 1 | 2696SF | 5
2669 | Yes | Auto Scheduled | Redmine Software Implementation (sw21.21.144) | 10 days | February 5, 2019 8:00 AM | February 18, 2019 5:00 PM | 2019-02-18 | 1 | 2693SF | 5
2670 | Yes | Auto Scheduled | Software Validation | 16 days | February 11, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 |  | 4
2671 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.144) | 16 days | February 11, 2019 8:00 AM | March 4, 2019 5:00 PM | 2019-03-04 | 1 | 2706SF | 5
2672 | Yes | Auto Scheduled | Systems Integration | 8 days | March 1, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 4
2673 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.144) | 8 days | March 1, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2514SF | 5
2674 | Yes | Auto Scheduled | Systems Qualification | 9 days | February 25, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 |  | 4
2675 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.144) | 9 days | February 25, 2019 8:00 AM | March 7, 2019 5:00 PM | 2019-03-07 | 1 | 2525SF | 5
2676 | Yes | Auto Scheduled | Sprint 2 (21.21.144) | 32 days | February 19, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 3
2677 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.144) | 0 days | February 26, 2019 8:00 AM | February 26, 2019 8:00 AM | 2019-02-26 | 1 | 2703FS-2w | 4
2678 | No | Auto Scheduled | Program Management | 2 days | March 7, 2019 8:00 AM | March 11, 2019 8:00 AM | 2019-03-11 | 1 |  | 4
2679 | No | Auto Scheduled | CG4422 updated to GM (sw21.21.144) | 2 days | March 7, 2019 8:00 AM | March 11, 2019 8:00 AM | 2019-03-11 | 1 | 2703SF-2d | 5
2680 | Yes | Auto Scheduled | Systems Engineering 2 | 13 days | March 18, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 4
2681 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.145) | 11 days | March 20, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 | 2658 | 5 | Includes PCE 031
2682 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.145) | 0 days | April 3, 2019 5:00 PM | April 3, 2019 5:00 PM | 2019-04-03 | 1 | 2681 | 5
2683 | Yes | Auto Scheduled | Redmine Analysis Complete (sw 21.21.145) | 11 days | March 18, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 2659 | 5
2684 | Yes | Auto Scheduled | Systems Engineering 3 | 13 days | March 18, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 |  | 4
2685 | Yes | Auto Scheduled | SAD Major baseline (sw21.21.145) | 11 days | March 20, 2019 8:00 AM | April 3, 2019 5:00 PM | 2019-04-03 | 1 | 2661 | 5
2686 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.145) | 0 days | April 3, 2019 5:00 PM | April 3, 2019 5:00 PM | 2019-04-03 | 1 | 2685 | 5
2687 | Yes | Auto Scheduled | Redmine Analysis Complete (sw 21.21.145) | 11 days | March 18, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 2662 | 5
2688 | Yes | Auto Scheduled | Software Systems | 10 days | March 18, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 4
2689 | Yes | Auto Scheduled | Software Functional Specs Minor baseline (sw21.21.145) | 8 days | March 20, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2658 | 5
2690 | Yes | Auto Scheduled | Redmine Analysis Complete (sw 21.21.145) | 5 days | March 18, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2664 | 5
2691 | Yes | Auto Scheduled | Software Design | 19 days | February 19, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 |  | 4
2692 | Yes | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw 21.21.145) | 7 days | March 1, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 |  | 5 | Was not releases as plan on 3/1. Plan is to release by 3/8
2693 | Yes | Auto Scheduled | Redmine Software Implementation (acc. To FROP)(sw 21.21.144) | 12 days | February 19, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 | 2702SF | 5 | Includes PCE 033 Implementation. There is no impact on the timing.
2694 | Yes | Auto Scheduled | Architecture Design major basline (sw 21.21.144) | 13 days | February 27, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2702SF | 5 | Forced baseline
2695 | Yes | Auto Scheduled | Layer Design major baseline (sw 21.21.144) | 13 days | February 27, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2702SF | 5 | Forced baseline
2696 | Yes | Auto Scheduled | Unit Design major baseline (sw 21.21.144) | 13 days | February 27, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2702SF | 5 | Forced baseline
2697 | Yes | Auto Scheduled | Software Integration Test Spec major baseline(sw 21.21.144) | 10 days | February 25, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 2702SF | 5
2698 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.144) | 0 days | March 15, 2019 5:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2694 | 5
2699 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.144) | 0 days | March 15, 2019 5:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2695 | 5
2700 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.144) | 0 days | March 15, 2019 5:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2696 | 5
2701 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.144) | 0 days | March 11, 2019 5:00 PM | March 11, 2019 5:00 PM | 2019-03-11 | 1 | 2697 | 5
2702 | Yes | Auto Scheduled | Full Integration Testing(sw 21.21.144) | 4 days | March 8, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2703SF | 5
2703 | Yes | Auto Scheduled | Internal SW release (sw 21.21.144) | 2 days | March 13, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 2821FS-7d | 5
2704 | Yes | Auto Scheduled | Create Production Study CALS | 7 days | March 7, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2703SF-2d | 4
2705 | Yes | Auto Scheduled | Software Validation | 13 days | February 25, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 |  | 4
2706 | Yes | Auto Scheduled | Test Case major baseline (sw21.21.144) | 13 days | February 25, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2703SF-2d | 5
2707 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.144) | 3 days | March 8, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2706 | 5
2708 | Yes | Auto Scheduled | Systems Integration | 15 days | February 22, 2019 8:00 AM | March 14, 2019 5:00 PM | 2019-03-14 | 1 |  | 4
2709 | Yes | Auto Scheduled | System Architecture Design Analysis | 5 days | February 22, 2019 8:00 AM | February 28, 2019 5:00 PM | 2019-02-28 | 1 | 2481 | 5
2710 | Yes | Auto Scheduled | Test Case Update | 6 days | March 1, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 2709 | 5
2711 | Yes | Auto Scheduled | Test Case Review | 1 day | March 11, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 | 2710 | 5
2712 | Yes | Auto Scheduled | Test Case Rework | 2 days | March 12, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2711 | 5
2713 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.144) | 0 days | March 13, 2019 5:00 PM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2712 | 5
2714 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.144) | 1 day | March 13, 2019 5:00 PM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 2713 | 5
2715 | Yes | Auto Scheduled | Systems Qualification | 14 days | February 22, 2019 8:00 AM | March 13, 2019 5:00 PM | 2019-03-13 | 1 |  | 4
2716 | Yes | Auto Scheduled | Systems Requirement Specification analysis | 3 days | February 22, 2019 8:00 AM | February 26, 2019 5:00 PM | 2019-02-26 | 1 | 2477 | 5
2717 | Yes | Auto Scheduled | Test Case Update | 8 days | February 27, 2019 8:00 AM | March 8, 2019 5:00 PM | 2019-03-08 | 1 | 2716 | 5
2718 | Yes | Auto Scheduled | Test Case Review & Rework | 1 day | March 11, 2019 8:00 AM | March 11, 2019 5:00 PM | 2019-03-11 | 1 | 2717 | 5
2719 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.144) | 2 days | March 11, 2019 5:00 PM | March 13, 2019 5:00 PM | 2019-03-13 | 1 | 2718 | 5
2720 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.144) | 0 days | March 12, 2019 5:00 PM | March 12, 2019 5:00 PM | 2019-03-12 | 1 | 2719 | 5
2721 | Yes | Auto Scheduled | Sprint 3 (21.21.144) | 86 days | March 11, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 3
2722 | Yes | Auto Scheduled | Software Systems | 11 days | April 1, 2019 8:00 AM | April 15, 2019 5:00 PM | 2019-04-15 | 1 |  | 4
2723 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw 21.21.145) | 11 days | April 1, 2019 8:00 AM | April 15, 2019 5:00 PM | 2019-04-15 | 1 | 2689 | 5 | Include PCE 031
2724 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.145) | 0 days | April 15, 2019 5:00 PM | April 15, 2019 5:00 PM | 2019-04-15 | 1 | 2723 | 5
2725 | Yes | Auto Scheduled | Software Validation | 11 days | March 14, 2019 5:00 PM | March 30, 2019 5:00 PM | 2019-03-30 | 1 |  | 4
2726 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.144) | 0 days | March 14, 2019 5:00 PM | March 14, 2019 5:00 PM | 2019-03-14 | 1 | 2703 | 5
2727 | Yes | Auto Scheduled | SWE6 Verification Testing (sw21.21.144) | 11 days | March 15, 2019 8:00 AM | March 30, 2019 5:00 PM | 2019-03-30 | 1 |  | 5
2728 | Yes | Auto Scheduled | Test Execution (High Priority) | 6 days | March 15, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 6
2729 | Yes | Auto Scheduled | Redmine (High Priority) | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 7
2730 | Yes | Auto Scheduled | Telltales | 3 days | March 15, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 2703 | 7
2731 | Yes | Auto Scheduled | Gauges | 3 days | March 15, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 2703 | 7
2732 | Yes | Auto Scheduled | Illumination | 3 days | March 15, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 2703 | 7
2733 | Yes | Auto Scheduled | Diagnostics | 3 days | March 15, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 2703 | 7
2734 | Yes | Auto Scheduled | System | 4 days | March 18, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 7
2735 | Yes | Auto Scheduled | Release Readiness | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 7
2736 | Yes | Auto Scheduled | Bootloader & OTA | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 7
2737 | Yes | Auto Scheduled | CG4879 OTA Testing | 4 days | March 15, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 2703 | 7
2738 | Yes | Auto Scheduled | CG3388 (Bootloader Services) | 1 day | March 21, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2737 | 7
2739 | Yes | Auto Scheduled | Test Summary Report | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2738 | 7
2740 | Yes | Auto Scheduled | Test Execution (Medium & Low Priority) | 5 days | March 22, 2019 5:00 PM | March 30, 2019 5:00 PM | 2019-03-30 | 1 |  | 6
2741 | Yes | Auto Scheduled | Redmine (Medium & Low Priority) | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2742 | Yes | Auto Scheduled | HWIO | 1 day | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 | 2739 | 7
2743 | Yes | Auto Scheduled | TFT | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2744 | Yes | Auto Scheduled | Ethernet | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2745 | Yes | Auto Scheduled | HSCAN | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2746 | Yes | Auto Scheduled | LIN | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2747 | Yes | Auto Scheduled | Line Test | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2739 | 7
2748 | Yes | Auto Scheduled | Data Flash | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2749 | Yes | Auto Scheduled | Cyber Security | 5 days | March 25, 2019 8:00 AM | March 30, 2019 5:00 PM | 2019-03-30 | 1 | 2739 | 7
2750 | Yes | Auto Scheduled | Functional Safety | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2739 | 7
2751 | Yes | Auto Scheduled | RHMI | 4 days | March 25, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2739 | 7
2752 | Yes | Auto Scheduled | Test Summary Report | 1 day | March 29, 2019 8:00 AM | March 30, 2019 5:00 PM | 2019-03-30 | 1 | 2751 | 7
2753 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.144) | 0 days | March 30, 2019 5:00 PM | March 30, 2019 5:00 PM | 2019-03-30 | 1 | 2739,2752 | 5
2754 | Yes | Auto Scheduled | Redmine Estimate (sw21.21.145) | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 5
2755 | Yes | Auto Scheduled | Systems Integration | 67 days | March 11, 2019 8:00 AM | June 11, 2019 5:00 PM | 2019-06-11 | 1 |  | 4
2756 | Yes | Auto Scheduled | Test Execution (sw 21.21.144) | 6 days | March 15, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 5
2757 | Yes | Auto Scheduled | Release Readiness Test | 0.5 days | March 15, 2019 1:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2703 | 6
2758 | Yes | Auto Scheduled | Redmine Testing | 4 days | March 15, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 2703 | 6
2759 | Yes | Auto Scheduled | Externel Interfaces | 0.5 days | March 15, 2019 1:00 PM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2703 | 6
2760 | Yes | Auto Scheduled | Internel Interfaces | 2 days | March 15, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 6
2761 | Yes | Auto Scheduled | System Safety Strategy | 3 days | March 15, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 6
2762 | Yes | Auto Scheduled | System Fault Tolerant Timings | 1 day | March 19, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 |  | 6
2763 | Yes | Auto Scheduled | System Safe State Transitions | 2 days | March 20, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2764 | Yes | Auto Scheduled | System Dynamic Behaviour | 2 days | March 20, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2765 | Yes | Auto Scheduled | System Communication Integration | 0 days | March 21, 2019 5:00 PM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2766 | Yes | Auto Scheduled | System Integration Test Summary Report Review | 0.5 days | March 22, 2019 1:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 6
2767 | Yes | Auto Scheduled | Power Sequence Measurements (sw 21.21.144) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 5
2768 | Yes | Auto Scheduled | Section 21 - SoC Output for Gauges (redmine 6742) (sw 21.21.144) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 2389,2703 | 6 | Redmine implementation is sw21.21.144
2769 | Yes | Auto Scheduled | Section 27D - TT SEG White LED PWM (redmine 6547) (sw 21.21.144) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 2389,2703 | 6 | Redmine implementation is sw21.21.144
2770 | Yes | Auto Scheduled | Section 38 B: Measure TFT STBYB low (redmine 7013) (sw 21.21.144) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 2389,2703 | 6 | Redmine implementation is sw21.21.144
2771 | Yes | Auto Scheduled | Section 39A: TFT DE to TFT STBYB measurement(redmine 6562) (sw 21.21.144) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 2389,2703 | 6 | Redmine implementation is sw21.21.144
2772 | No | Auto Scheduled | Report approval (software report) (sw 21.21.144) | 2 days | May 13, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 2768,2771,2770,2769 | 6
2773 | Yes | Auto Scheduled | Waveform Measurements (sw 21.21.144) | 67 days | March 11, 2019 8:00 AM | June 11, 2019 5:00 PM | 2019-06-11 | 1 |  | 5
2774 | No | Auto Scheduled | Gauge driver waveform measurements (sw 21.21.144) | 6 days | March 21, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 | 2703 | 6 | Refer to Issue # 125, which will be implemeted in sw21.21.145. Cannot be testing due to RAID Log Issue # 105. It will be tested in sw 21.21.144
2775 | Yes | Auto Scheduled | TFT Thermistor waveform measurements (sw 21.21.144) | 6 days | March 29, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2774 | 6 | Cannot be testing due to RAID Log Issue # 105. It will be tested in sw 21.21.144
2776 | Yes | Auto Scheduled | Hyperbus waveform measurements (sw 21.21.144) | 6 days | March 25, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 2394 | 6 | Resource availability is pushing the date
2777 | Yes | Auto Scheduled | LED Sample Order (sw 21.21.144) | 22 days | March 11, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 |  | 6 | Added tasks due to RAID Log Issue #123
2778 | Yes | Auto Scheduled | TER Creation and PCB Rework (sw 21.21.144) | 10 days | March 25, 2019 8:00 AM | April 22, 2019 5:00 PM | 2019-04-22 | 1 | 2777 | 6 | Added tasks due to RAID Log Issue #123
2779 | Yes | Auto Scheduled | Telltale driver waveform measurements (sw 21.21.144) | 6 days | April 23, 2019 8:00 AM | April 30, 2019 5:00 PM | 2019-04-30 | 1 | 2778 | 6 | Added tasks due to RAID Log Issue #123
2780 | No | Auto Scheduled | FCA reflected display and FCA (sw 21.21.144) | 3 days | May 1, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 | 2779 | 6 | There is an issue, it will be implemented in 21.145. Refer to Isue # 126. Cannot be tested with sw21.21.144
2781 | Yes | Auto Scheduled | Create report (sw 21.21.144) | 10 days | May 1, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 2780 | 6
2782 | Yes | Auto Scheduled | Review HW waveform measurements (sw 21.21.144) | 10 days | May 15, 2019 8:00 AM | May 28, 2019 5:00 PM | 2019-05-28 | 1 | 2781 | 6
2783 | Yes | Auto Scheduled | Feedback update and remeasurements (sw 21.21.144) | 10 days | May 29, 2019 8:00 AM | June 11, 2019 5:00 PM | 2019-06-11 | 1 | 2782 | 6
2784 | Yes | Auto Scheduled | Review HW waveform measurements (sw 21.21.144) | 0 days | May 31, 2019 5:00 PM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 2783 | 6
2785 | Yes | Auto Scheduled | Feedback update and remeasurements (sw 21.21.144) | 0 days | May 31, 2019 5:00 PM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 2784 | 6
2786 | Yes | Auto Scheduled | Report approval (sw 21.21.144) | 0 days | May 31, 2019 5:00 PM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 2785 | 6
2787 | Yes | Auto Scheduled | Systems Qualification | 12 days | March 15, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 |  | 4
2788 | Yes | Auto Scheduled | Test Execution (sw 21.21.144) | 11 days | March 15, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5
2789 | Yes | Auto Scheduled | Smoke Test | 1 day | March 15, 2019 8:00 AM | March 15, 2019 5:00 PM | 2019-03-15 | 1 | 2703 | 6
2790 | Yes | Auto Scheduled | Redmine Testing | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 6
2791 | Yes | Auto Scheduled | Gauges | 4 days | March 17, 2019 5:00 PM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2792 | Yes | Auto Scheduled | Telltales | 4 days | March 17, 2019 5:00 PM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2793 | Yes | Auto Scheduled | Illumination | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2794 | Yes | Auto Scheduled | Bootloader | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2795 | Yes | Auto Scheduled | CAN | 4 days | March 15, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 6
2796 | Yes | Auto Scheduled | LineTest | 2 days | March 15, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 6
2797 | Yes | Auto Scheduled | Stress Test | 0 days | March 18, 2019 5:00 PM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 6
2798 | Yes | Auto Scheduled | Telltales , Gauges (manual testing ) | 3 days | March 18, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 6
2799 | Yes | Auto Scheduled | TFT | 2 days | March 19, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 |  | 6
2800 | Yes | Auto Scheduled | Functional Safety | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 6
2801 | Yes | Auto Scheduled | Power Mode | 3 days | March 19, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2802 | Yes | Auto Scheduled | HWIO | 1 day | March 21, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2803 | Yes | Auto Scheduled | LIN | 2 days | March 22, 2019 8:00 AM | March 25, 2019 5:00 PM | 2019-03-25 | 1 |  | 6
2804 | Yes | Auto Scheduled | Cyber Security | 3 days | March 26, 2019 8:00 AM | March 28, 2019 5:00 PM | 2019-03-28 | 1 |  | 6
2805 | Yes | Auto Scheduled | NVM | 1 day | March 22, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 6
2806 | Yes | Auto Scheduled | Ethernet | 0 days | March 21, 2019 5:00 PM | March 21, 2019 5:00 PM | 2019-03-21 | 1 |  | 6
2807 | Yes | Auto Scheduled | System Qualification Test summary report Review (sw 21.21.144) | 1 day | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 6
2808 | Yes | Auto Scheduled | Validation Report & Defect Analysis (sw 21.21.144) | 1 day | April 1, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 | 2788 | 5
2809 | Yes | Auto Scheduled | Compliance Test | 25 days | March 15, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 |  | 4 | Software issues does not allow to test with 21.21.142.1
2810 | Yes | Auto Scheduled | CG3877 - CAN Physical and Protocol Layer Test (sw 21.21.144) | 6 days | March 15, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2703 | 5 | Software issues does not allow to test with 21.21.142.1
2811 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw 21.21.144) | 5 days | March 15, 2019 8:00 AM | March 21, 2019 5:00 PM | 2019-03-21 | 1 | 2703 | 5 | Software issues does not allow to test with 21.21.142.1
2812 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw 21.21.144) | 4.5 days | March 22, 2019 8:00 AM | March 28, 2019 12:00 PM | 2019-03-28 | 1 | 2811 | 5 | Software issues does not allow to test with 21.21.142.1
2813 | Yes | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw 21.21.144) | 6 days | March 22, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2811 | 5 | Software issues does not allow to test with 21.21.142.1
2814 | Yes | Auto Scheduled | Fuzz Test Execution (Cyber Security) | 15 days | March 29, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 |  | 5
2815 | Yes | Auto Scheduled | TCP Client (sw 21.21.144) | 15 days | March 29, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 | 2703 | 6
2816 | Yes | Auto Scheduled | TCP Server (sw 21.21.144) | 15 days | March 29, 2019 8:00 AM | April 18, 2019 5:00 PM | 2019-04-18 | 1 | 2703 | 6 | Software issues does not allow to test with 21.21.142.1
2817 | No | Auto Scheduled | IPv4 (sw 21.21.144) | 15 days | March 25, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2703 | 6 | Software issues does not allow to test with 21.21.142.1
2818 | Yes | Auto Scheduled | Program Management | 5 days | March 18, 2019 8:00 AM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 4
2819 | Yes | Auto Scheduled | Software Release notes (sw 21.21.144) | 2 days | March 18, 2019 8:00 AM | March 19, 2019 5:00 PM | 2019-03-19 | 1 | 2821FS-5d | 5
2820 | Yes | Auto Scheduled | Software Release Assessment (sw 21.21.144) | 0 days | March 22, 2019 8:00 AM | March 22, 2019 8:00 AM | 2019-03-22 | 1 | 2821FS-1d | 5
2821 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw 21.21.144) | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 5
2822 | Yes | Auto Scheduled | FROP Tentative (sw21.21.145) | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 | 2683,2687,2690 | 5
2823 | Yes | Auto Scheduled | Software Design | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 4
2824 | Yes | Auto Scheduled | Architecture Design major basline (sw 21.21.144) Update backlog issues | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5 | Task planned based on Issue ID#124
2825 | Yes | Auto Scheduled | Layer Design major baseline (sw 21.21.144) Update backlog issues | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5
2826 | Yes | Auto Scheduled | Unit Design major baseline (sw 21.21.144) Update backlog issues | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5
2827 | Yes | Auto Scheduled | Software Integration Test Spec major baseline(sw 21.21.144) Update backlog issues | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 |  | 5
2828 | Yes | Auto Scheduled | Redmine Estimation from FROP Final (sw21.21.145) | 5 days | March 25, 2019 8:00 AM | March 29, 2019 5:00 PM | 2019-03-29 | 1 | 2822 | 5 | 69 redmines will be covered
2829 | Yes | Auto Scheduled | Redmine Estimation from FROP Final (sw21.21.145) | 25 days | March 25, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 | 2822 | 4
2830 | Yes | Auto Scheduled | FROP Final (sw21.21.145) | 16 days | March 29, 2019 5:00 PM | April 22, 2019 5:00 PM | 2019-04-22 | 1 | 2828,2829 | 4
2831 | Yes | Auto Scheduled | CG2999 to GM (sw 21.21.144) | 82 days | March 15, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 4
2832 | Yes | Auto Scheduled | Unit Test report (sw 21.21.144) | 2 days | March 15, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 | 2703 | 5
2833 | Yes | Auto Scheduled | Static Analysis (sw 21.21.144) | 2 days | March 15, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 | 2703 | 5
2834 | No | Auto Scheduled | SAA update (sw 21.21.144) | 4 days | March 15, 2019 8:00 AM | March 20, 2019 5:00 PM | 2019-03-20 | 1 | 2703 | 5
2835 | Yes | Auto Scheduled | Integratoin Test report (sw 21.21.144) | 2 days | March 15, 2019 8:00 AM | March 18, 2019 5:00 PM | 2019-03-18 | 1 | 2703 | 5
2836 | Yes | Auto Scheduled | Performance Paramters report (sw 21.21.144) | 14 days | March 26, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2703 | 5
2837 | Yes | Auto Scheduled | Traceability Report | 4 days | July 1, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 5
2838 | Yes | Auto Scheduled | Stress Test Results (sw 21.21.144) | 0 days | March 18, 2019 5:00 PM | March 18, 2019 5:00 PM | 2019-03-18 | 1 |  | 5
2839 | Yes | Auto Scheduled | Black box test results (sw 21.21.144) | 0 days | March 30, 2019 5:00 PM | March 30, 2019 5:00 PM | 2019-03-30 | 1 | 2753,2808 | 5
2840 | Yes | Auto Scheduled | Software Development (sw21.21.144.1) | 6 days | April 3, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 |  | 2
2841 | Yes | Auto Scheduled | Software Release Kick Off meeting | 0 days | April 3, 2019 8:00 AM | April 3, 2019 8:00 AM | 2019-04-03 | 1 |  | 3
2842 | Yes | Auto Scheduled | Software Development | 3 days | April 3, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 |  | 3
2843 | Yes | Auto Scheduled | Implement redmine 10422 (sw21.21.144.1) | 1.5 days | April 3, 2019 8:00 AM | April 4, 2019 12:00 PM | 2019-04-04 | 1 |  | 4
2844 | Yes | Auto Scheduled | Implement redmine 10534 (sw21.21.144.1) | 1.5 days | April 3, 2019 8:00 AM | April 4, 2019 12:00 PM | 2019-04-04 | 1 |  | 4
2845 | Yes | Auto Scheduled | Implemente redmine 9717 (sw21.21.144.1) | 1.5 days | April 3, 2019 8:00 AM | April 4, 2019 12:00 PM | 2019-04-04 | 1 |  | 4
2846 | Yes | Auto Scheduled | Stress Test using scripts for RHMI (sw 21.21.144.1) | 1 day | April 4, 2019 1:00 PM | April 5, 2019 12:00 PM | 2019-04-05 | 1 | 2843 | 4
2847 | Yes | Auto Scheduled | Integration Testing (sw21.21.144.1) | 0.5 days | April 4, 2019 1:00 PM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 2843,2844,2845 | 4
2848 | Yes | Auto Scheduled | Internal Software Release (sw21.21.144.1) | 0 days | April 4, 2019 5:00 PM | April 4, 2019 5:00 PM | 2019-04-04 | 1 | 2847 | 4
2849 | Yes | Auto Scheduled | Stress Test Sleep Cycle | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4
2850 | Yes | Auto Scheduled | Software Systems | 2 days | April 5, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 |  | 3
2851 | Yes | Auto Scheduled | Sanity Check (sw 21.21.144.1) | 2 days | April 5, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 | 2848 | 4
2852 | Yes | Auto Scheduled | Software Validation/Verification | 3.5 days | April 5, 2019 8:00 AM | April 10, 2019 12:00 PM | 2019-04-10 | 1 |  | 3
2853 | Yes | Auto Scheduled | Redmine Testing | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2848 | 4
2854 | Yes | Auto Scheduled | Release Rediness | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2848 | 4 | Partial testing as per impact analysis
2855 | Yes | Auto Scheduled | RHMI | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2848 | 4 | Partial testing as per impact analysis
2856 | Yes | Auto Scheduled | Bootloader Regression Test | 3 days | April 5, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2848 | 4 | Partial testing as per impact analysis
2857 | Yes | Auto Scheduled | Stress Test for ECU Unlock | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4
2858 | Yes | Auto Scheduled | Programming Sequence | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4
2859 | Yes | Auto Scheduled | Test Summary Report | 0.5 days | April 10, 2019 8:00 AM | April 10, 2019 12:00 PM | 2019-04-10 | 1 | 2853,2858 | 4
2860 | Yes | Auto Scheduled | Systems Integration | 3.5 days | April 5, 2019 8:00 AM | April 10, 2019 12:00 PM | 2019-04-10 | 1 |  | 3
2861 | Yes | Auto Scheduled | Smoke Test | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4
2862 | Yes | Auto Scheduled | Production CALs flashing stress test | 1 day | April 8, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 | 2861 | 4
2863 | Yes | Auto Scheduled | DIC partial testing (FUSA) | 1 day | April 9, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2862 | 4
2864 | Yes | Auto Scheduled | Test Summary Report | 0.5 days | April 10, 2019 8:00 AM | April 10, 2019 12:00 PM | 2019-04-10 | 1 | 2863 | 4
2865 | Yes | Auto Scheduled | Systems Qualification | 4 days | April 5, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 |  | 3
2866 | Yes | Auto Scheduled | Telltales | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4 | Using automation and production CALS
2867 | Yes | Auto Scheduled | Gauges | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4 | Using automation and production CALS
2868 | Yes | Auto Scheduled | Illumination | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4 | Using automation and production CALS
2869 | Yes | Auto Scheduled | GM Stress Test | 2 days | April 5, 2019 8:00 AM | April 8, 2019 5:00 PM | 2019-04-08 | 1 | 2848 | 4
2870 | Yes | Auto Scheduled | Test Summary Report | 2 days | April 9, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 2869 | 4
2871 | Yes | Auto Scheduled | Program Management | 4 days | April 5, 2019 8:00 AM | April 10, 2019 5:00 PM | 2019-04-10 | 1 |  | 3
2872 | Yes | Auto Scheduled | Software Release Notes (sw 21.21.144.1) | 1 day | April 5, 2019 8:00 AM | April 5, 2019 5:00 PM | 2019-04-05 | 1 | 2848 | 4
2873 | Yes | Auto Scheduled | Software Release Assessment (sw 21.21.144.1) | 0 days | April 10, 2019 5:00 PM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 2870,2864,2859 | 4
2874 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw 21.21.144.1) | 0 days | April 10, 2019 5:00 PM | April 10, 2019 5:00 PM | 2019-04-10 | 1 | 2873 | 4
2875 | Yes | Auto Scheduled | Software Development (sw21.21.145) | 78 days | April 1, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 2
2876 | Yes | Auto Scheduled | sw21.21.145 cadence start | 0 days | April 1, 2019 8:00 AM | April 1, 2019 8:00 AM | 2019-04-01 | 1 |  | 3
2877 | Yes | Auto Scheduled | Sprint 1 (21.21.145) | 26 days | April 1, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 3
2878 | Yes | Auto Scheduled | Program Management | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 |  | 4
2879 | Yes | Auto Scheduled | Release Kick Off meeting (sw21.21.145) | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 | 2876 | 5
2880 | Yes | Auto Scheduled | Systems Engineering 2 | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 4
2881 | Yes | Auto Scheduled | SRS Minor baseline (sw21.21.146) | 7 days | April 1, 2019 8:00 AM | April 9, 2019 5:00 PM | 2019-04-09 | 1 | 2876 | 5 | Applicable for sw21.21.145.01
2882 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.146) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2876 | 5 | Applicable for sw21.21.145.01
2883 | Yes | Auto Scheduled | Systems Engineering 3 | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 4
2884 | Yes | Auto Scheduled | SAD Minor baseline (sw21.21.146) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2876 | 5 | Applicable for sw21.21.145.01
2885 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.146) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2876 | 5 | Applicable for sw21.21.145.01
2886 | Yes | Auto Scheduled | Software Systems | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 4
2887 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw 21.21.146) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2876 | 5 | Applicable for sw21.21.145.01
2888 | Yes | Auto Scheduled | Software Design | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 |  | 4
2889 | No | Auto Scheduled | Architecture Design minor baseline (sw21.21.145) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2689 | 5
2890 | No | Auto Scheduled | Layer Design minor baseline (sw21.21.145) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2689 | 5
2891 | No | Auto Scheduled | Unit Design minor baseline (sw21.21.145) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2689 | 5
2892 | Yes | Auto Scheduled | Redmine Software Implementation (sw21.21.145) | 10 days | April 1, 2019 8:00 AM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2830 | 5
2893 | Yes | Auto Scheduled | Software Validation | 20 days | April 1, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 4
2894 | Yes | Auto Scheduled | SFS review (sw21.21.145) | 15 days | April 1, 2019 8:00 AM | April 19, 2019 5:00 PM | 2019-04-19 | 1 | 2689 | 5
2895 | Yes | Auto Scheduled | Impact Analysis for features (sw21.21.145) | 20 days | April 1, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 5
2896 | Yes | Auto Scheduled | Impact Analysis for Redmines (sw21.21.145) | 20 days | April 1, 2019 8:00 AM | April 26, 2019 5:00 PM | 2019-04-26 | 1 |  | 5
2897 | Yes | Auto Scheduled | Systems Integration | 23 days | April 4, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 4
2898 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145) | 23 days | April 4, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 | 2685 | 5
2899 | Yes | Auto Scheduled | Systems Qualification | 8 days | April 4, 2019 8:00 AM | April 15, 2019 5:00 PM | 2019-04-15 | 1 |  | 4
2900 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145) | 8 days | April 4, 2019 8:00 AM | April 15, 2019 5:00 PM | 2019-04-15 | 1 | 2681 | 5
2901 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.1) | 0 days | April 12, 2019 5:00 PM | April 12, 2019 5:00 PM | 2019-04-12 | 1 | 2882,2885,2892 | 4
2902 | Yes | Auto Scheduled | Sprint 2 (21.21.145) | 51 days | April 1, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 3
2903 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.145) | 6 days | April 29, 2019 5:00 PM | May 7, 2019 5:00 PM | 2019-05-07 | 1 |  | 4
2904 | Yes | Auto Scheduled | Systems Engineering 2 | 20 days | April 23, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 |  | 4
2905 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.145.1) | 19 days | April 24, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2881 | 5
2906 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.145.1) | 0 days | May 20, 2019 5:00 PM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2905 | 5
2907 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw 21.21.145.1) | 10 days | April 23, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 | 2882 | 5
2908 | No | Auto Scheduled | Systems Engineering 3 | 21 days | April 22, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 |  | 4
2909 | No | Auto Scheduled | SAD Major baseline (sw21.21.145.1) | 20 days | April 23, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2884 | 5
2910 | No | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.145.1) | 0 days | May 20, 2019 5:00 PM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2909 | 5
2911 | No | Auto Scheduled | Redmine Analysis phase 2 (sw 21.21.145.1) | 10 days | April 22, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 | 2885 | 5
2912 | Yes | Auto Scheduled | Software Systems | 15 days | April 15, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 4
2913 | Yes | Auto Scheduled | Redmine Analysis Complete (sw 21.21.145.1) | 15 days | April 15, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 | 2887 | 5
2914 | Yes | Auto Scheduled | Software Design | 46 days | April 1, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 4
2915 | Yes | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw 21.21.146) | 1 day | May 16, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 |  | 5
2916 | Yes | Auto Scheduled | Architecture Design Major basline (sw 21.21.145) | 34 days | April 1, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2889 | 5 | (sw 21.21.144) Update backlog issues
2917 | Yes | Auto Scheduled | Layer Design Major baseline (sw 21.21.145) | 34 days | April 1, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2890 | 5 | (sw 21.21.144) Update backlog issues
2918 | Yes | Auto Scheduled | Unit Design Major baseline (sw 21.21.145) | 34 days | April 1, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2891 | 5 | (sw 21.21.144) Update backlog issues
2919 | Yes | Auto Scheduled | Software Integration Test Spec Major baseline(sw 21.21.145) | 34 days | April 1, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2889,2890,2891 | 5 | Include PCE 031
2920 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2916 | 5
2921 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2917 | 5
2922 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2918 | 5
2923 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2919 | 5
2924 | Yes | Auto Scheduled | Redmine Software Implementation (acc. To FROP)(sw 21.21.145) | 20 days | April 15, 2019 8:00 AM | May 12, 2019 5:00 PM | 2019-05-12 | 1 | 2892 | 5
2925 | Yes | Auto Scheduled | Sanity Check (sw 21.21.145) | 0.9 days | May 13, 2019 8:00 AM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2919,2924 | 5
2926 | Yes | Auto Scheduled | Full Integration Testing(sw 21.21.145) | 4 days | May 13, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2919,2924 | 5 | Pending DCM Diagnostics
2927 | Yes | Auto Scheduled | Internal SW release (sw 21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2926 | 5
2928 | Yes | Auto Scheduled | OTA Reflash Test @ GM Bench with internal release | 1 day | May 14, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 |  | 5
2929 | Yes | Auto Scheduled | GBFTT Reflhas test @ GM Bench with internal release | 1 day | May 20, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 |  | 5
2930 | Yes | Auto Scheduled | Interal Re-Release (sw21.21.145) | 10 days | May 21, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 2928,2929 | 5 | Include GBFTT issue and OTA Reflash issue (redmines: 12561, 12724, 12562)
2931 | Yes | Auto Scheduled | Software Validation | 36 days | April 22, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 4
2932 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145) | 17 days | April 22, 2019 8:00 AM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 2723 | 5
2933 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.145) | 0 days | May 14, 2019 5:00 PM | May 14, 2019 5:00 PM | 2019-05-14 | 1 | 2932 | 5
2934 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.1) | 14 days | May 22, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 2901 | 5
2935 | Yes | Auto Scheduled | Systems Integration | 41 days | April 15, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 4
2936 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145) | 5 days | May 7, 2019 8:00 AM | May 13, 2019 5:00 PM | 2019-05-13 | 1 | 2898 | 5
2937 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.145) | 0 days | May 13, 2019 5:00 PM | May 13, 2019 5:00 PM | 2019-05-13 | 1 | 2936 | 5
2938 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.1) | 41 days | April 15, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 2901 | 5
2939 | Yes | Auto Scheduled | Systems Qualification | 41 days | April 15, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 4
2940 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145) | 16 days | April 22, 2019 8:00 AM | May 13, 2019 5:00 PM | 2019-05-13 | 1 | 2900 | 5
2941 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.145) | 0 days | May 13, 2019 5:00 PM | May 13, 2019 5:00 PM | 2019-05-13 | 1 | 2940 | 5
2942 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.1) | 41 days | April 15, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 2901 | 5
2943 | Yes | Auto Scheduled | Program Management | 4 days | May 1, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 |  | 4
2944 | Yes | Auto Scheduled | CG4422 updated to GM (sw21.21.145) | 1 day | May 1, 2019 8:00 AM | May 1, 2019 5:00 PM | 2019-05-01 | 1 | 2927SF-4d | 5
2945 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.1) | 0 days | May 6, 2019 5:00 PM | May 6, 2019 5:00 PM | 2019-05-06 | 1 | 2907,2911,2913,2934,2938,2942 | 5
2946 | Yes | Auto Scheduled | Sprint 3 (21.21.145) | 53 days | May 6, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 3
2947 | Yes | Auto Scheduled | Create Production Study CALS (sw 21.21.145) | 0 days | May 13, 2019 5:00 PM | May 13, 2019 5:00 PM | 2019-05-13 | 1 | 2927 | 4
2948 | Yes | Auto Scheduled | Software Systems | 25 days | May 6, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 4
2949 | Yes | Auto Scheduled | Software Functional Specs Minor baseline (sw21.21.145.01) | 5 days | May 6, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 | 2881,2884 | 5 | In DOORS is called as 21.21.146, but this has been removed by GM and now it will be 21.21.145.01
2950 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw21.21.145.01) | 14 days | May 21, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2905,2949 | 5
2951 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.145.01) | 0 days | June 7, 2019 5:00 PM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2950 | 5
2952 | Yes | Auto Scheduled | Software Validation | 18 days | May 16, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 |  | 4
2953 | No | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.145) | 0 days | May 15, 2019 5:00 PM | May 15, 2019 5:00 PM | 2019-05-15 | 1 | 2927 | 5
2954 | Yes | Auto Scheduled | SW Verification Testing (sw21.21.145) | 11 days | May 16, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 |  | 5
2955 | Yes | Auto Scheduled | High Priority Test (redmines) | 6 days | May 16, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 | 2927 | 6
2956 | Yes | Auto Scheduled | Medium and Low Priority | 5 days | May 24, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 | 2955 | 6
2957 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.145) | 1 day | May 24, 2019 8:00 AM | May 24, 2019 5:00 PM | 2019-05-24 | 1 | 2955 | 5
2958 | Yes | Auto Scheduled | Redmine testing (sw21.21.145 re-release) | 1 day | June 4, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 2930 | 5
2959 | Yes | Auto Scheduled | Bootloader Testing | 4 days | June 5, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 2958 | 5
2960 | Yes | Auto Scheduled | CG4879 Testing | 3 days | June 5, 2019 8:00 AM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2958 | 5
2961 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.145) | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 2019-05-31 | 1 | 2956 | 5
2962 | Yes | Auto Scheduled | Software Design | 10 days | May 7, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 |  | 4
2963 | Yes | Auto Scheduled | Redmine Estimation from FROP tentative (sw21.21.145.1) | 10 days | May 7, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2945 | 5
2964 | Yes | Auto Scheduled | Systems Integration | 14.5 days | May 16, 2019 8:00 AM | June 5, 2019 12:00 PM | 2019-06-05 | 1 |  | 4
2965 | Yes | Auto Scheduled | Test Execution (sw 21.21.145) | 4 days | May 16, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 |  | 5
2966 | Yes | Auto Scheduled | System Integration Readiness Test (sw 21.21.145) | 1 day | May 16, 2019 8:00 AM | May 16, 2019 5:00 PM | 2019-05-16 | 1 | 2927 | 6
2967 | Yes | Auto Scheduled | Production CAL flashing (stress test) (sw 21.21.145) | 2 days | May 16, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 | 2927 | 6
2968 | Yes | Auto Scheduled | FUSA (telltales) (sw 21.21.145) | 2 days | May 17, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2966 | 6
2969 | Yes | Auto Scheduled | FUSA (TFT, CAN, Monza) (sw 21.21.145) | 1 day | May 21, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 | 2968 | 6
2970 | No | Auto Scheduled | System State Operations (Bootloader) | 2 days | May 22, 2019 8:00 AM | May 23, 2019 5:00 PM | 2019-05-23 | 1 | 2969 | 6
2971 | Yes | Auto Scheduled | SYS Integration Test Report (sw 21.21.145) | 2 days | May 24, 2019 8:00 AM | May 27, 2019 5:00 PM | 2019-05-27 | 1 | 2965 | 5
2972 | Yes | Auto Scheduled | Report review and approval (sw 21.21.145) | 1 day | May 28, 2019 8:00 AM | May 28, 2019 5:00 PM | 2019-05-28 | 1 | 2971 | 5
2973 | Yes | Auto Scheduled | Smoke Test (sw21.21.145 re-release) | 1 day | June 4, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 2930 | 5
2974 | Yes | Auto Scheduled | Flashing Test (sw21.21.145 re-release) | 1 day | June 4, 2019 8:00 AM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 2930 | 5
2975 | Yes | Auto Scheduled | Report review and approval (sw 21.21.145 re-release) | 0.5 days | June 5, 2019 8:00 AM | June 5, 2019 12:00 PM | 2019-06-05 | 1 | 2973,2974 | 5
2976 | Yes | Auto Scheduled | Systems Qualification | 21 days | May 16, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
2977 | Yes | Auto Scheduled | Test Execution (sw 21.21.145) | 13 days | May 16, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 5
2978 | Yes | Auto Scheduled | ESIMs | 2 days | May 16, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 | 2927 | 6
2979 | Yes | Auto Scheduled | Stress Test | 3 days | May 20, 2019 8:00 AM | May 22, 2019 5:00 PM | 2019-05-22 | 1 | 2978 | 6
2980 | Yes | Auto Scheduled | Cyber Security | 2 days | May 16, 2019 8:00 AM | May 17, 2019 5:00 PM | 2019-05-17 | 1 | 2927 | 6
2981 | Yes | Auto Scheduled | Non Automated test cases | 3 days | May 20, 2019 8:00 AM | May 22, 2019 5:00 PM | 2019-05-22 | 1 | 2980 | 6
2982 | Yes | Auto Scheduled | CAN Stress Test | 3 days | May 23, 2019 8:00 AM | May 27, 2019 5:00 PM | 2019-05-27 | 1 | 2981 | 6
2983 | Yes | Auto Scheduled | FROP Issues & Redmines | 2 days | May 28, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 2982 | 6
2984 | Yes | Auto Scheduled | Systems Integration Black Box test | 3 days | May 30, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 2983 | 6
2985 | Yes | Auto Scheduled | SYS Qualification Test Report (sw 21.21.145) | 0.5 days | June 4, 2019 8:00 AM | June 4, 2019 12:00 PM | 2019-06-04 | 1 | 2977 | 5
2986 | Yes | Auto Scheduled | Report review and approval (sw 21.21.145) | 0.5 days | June 4, 2019 1:00 PM | June 4, 2019 5:00 PM | 2019-06-04 | 1 | 2985 | 5
2987 | Yes | Auto Scheduled | Bootloader | 3 days | June 4, 2019 8:00 AM | June 6, 2019 5:00 PM | 2019-06-06 | 1 | 2930 | 5
2988 | Yes | Auto Scheduled | Report review and approval (sw21.21.145 re-release) | 5 days | June 7, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 2987 | 5
2989 | Yes | Auto Scheduled | Compliance Test | 22 days | May 16, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 4
2990 | Yes | Auto Scheduled | CG3877 - CAN Physical and Protocol Layer Test (sw 21.21.145) | 22 days | May 16, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 | 2927 | 5
2991 | No | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw 21.21.145) | 6 days | June 12, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 2927 | 5
2992 | No | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw 21.21.145) | 7.5 days | June 20, 2019 8:00 AM | July 1, 2019 12:00 PM | 2019-07-01 | 1 | 2991 | 5
2993 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw 21.21.145) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 2990 | 5
2994 | No | Auto Scheduled | Fuzz Test Execution (Cyber Security) | 15 days | May 16, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 |  | 5
2995 | No | Auto Scheduled | TCP Client (sw 21.21.145) | 15 days | May 16, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 | 2927 | 6
2996 | No | Auto Scheduled | TCP Server (sw 21.21.145) | 15 days | May 16, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 | 2927 | 6
2997 | No | Auto Scheduled | IPv4 (sw 21.21.145) | 15 days | May 16, 2019 8:00 AM | June 5, 2019 5:00 PM | 2019-06-05 | 1 | 2927 | 6
2998 | Yes | Auto Scheduled | Program Management | 45 days | May 16, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
2999 | Yes | Auto Scheduled | Software Release notes (sw 21.21.145) | 2 days | May 22, 2019 8:00 AM | May 29, 2019 9:36 AM | 2019-05-29 | 1 | 3001FS-5d | 5 | Pending to complete for re-release
3000 | Yes | Auto Scheduled | Software Release Assessment (sw 21.21.145) | 0 days | June 4, 2019 8:00 AM | June 4, 2019 8:00 AM | 2019-06-04 | 1 | 3001FS-1d | 5
3001 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw 21.21.145) | 0 days | June 4, 2019 5:00 PM | June 4, 2019 5:00 PM | 2019-06-04 | 1 |  | 5
3002 | Yes | Auto Scheduled | CG2496 Test Report (sw21.21.145) | 22 days | June 14, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 2988 | 5
3003 | Yes | Auto Scheduled | CG2999 to GM (sw 21.21.145) | 38 days | May 16, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 5
3004 | Yes | Auto Scheduled | Unit Test report (sw 21.21.145) | 4 days | May 16, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 | 2927 | 6
3005 | Yes | Auto Scheduled | SAA update (sw 21.21.145) | 4 days | May 16, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 | 2927 | 6
3006 | Yes | Auto Scheduled | Integratoin Test report (sw 21.21.145) | 4 days | May 16, 2019 8:00 AM | May 21, 2019 5:00 PM | 2019-05-21 | 1 | 2927 | 6
3007 | Yes | Auto Scheduled | Performance Paramters report (sw 21.21.145) | 9 days | May 16, 2019 8:00 AM | May 28, 2019 5:00 PM | 2019-05-28 | 1 | 2927 | 6
3008 | Yes | Auto Scheduled | Stress Test Results (sw 21.21.145) | 10 days | May 16, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 2927 | 6
3009 | Yes | Auto Scheduled | Black box test results (sw 21.21.145) | 20 days | May 16, 2019 8:00 AM | June 12, 2019 5:00 PM | 2019-06-12 | 1 | 2927 | 6
3010 | Yes | Auto Scheduled | SW traceability matrix | 4 days | July 1, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 6
3011 | Yes | Auto Scheduled | FROP Final (sw21.21.145.01) | 0 days | May 20, 2019 5:00 PM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 2963 | 5
3012 | Yes | Auto Scheduled | Software Development (sw21.21.145.01) | 72 days | May 17, 2019 8:00 AM | August 26, 2019 5:00 PM | 2019-08-26 | 1 |  | 2
3013 | Yes | Auto Scheduled | sw21.21.145.01 cadence start | 0 days | May 17, 2019 8:00 AM | May 17, 2019 8:00 AM | 2019-05-17 | 1 |  | 3
3014 | Yes | Auto Scheduled | Sprint 1 (sw21.21.145.01) | 18 days | May 28, 2019 5:00 PM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 3
3015 | No | Auto Scheduled | Program Management | 1 day | May 29, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 |  | 4
3016 | No | Auto Scheduled | Release Kick Off meeting (sw21.21.145.01) | 1 day | May 29, 2019 8:00 AM | May 29, 2019 5:00 PM | 2019-05-29 | 1 | 3013 | 5
3017 | Yes | Auto Scheduled | Systems Engineering 2 | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 4
3018 | No | Auto Scheduled | SRS Minor baseline (sw21.21.145.02) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 3013 | 5
3019 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.02) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 3013 | 5
3020 | Yes | Auto Scheduled | Systems Engineering 3 | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 4
3021 | No | Auto Scheduled | SAD Minor baseline (sw21.21.145.02) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 3013 | 5
3022 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.02) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 3013 | 5
3023 | Yes | Auto Scheduled | Software Systems | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 |  | 4
3024 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.02) | 5 days | June 17, 2019 8:00 AM | June 21, 2019 5:00 PM | 2019-06-21 | 1 | 3013 | 5
3025 | No | Auto Scheduled | Software Design | 14 days | May 20, 2019 5:00 PM | June 7, 2019 5:00 PM | 2019-06-07 | 1 |  | 4
3026 | No | Auto Scheduled | Architecture Design minor baseline (sw21.21.145.01) | 0 days | June 7, 2019 5:00 PM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2950 | 5
3027 | No | Auto Scheduled | Layer Design minor baseline (sw21.21.145.01) | 0 days | June 7, 2019 5:00 PM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2950 | 5
3028 | No | Auto Scheduled | Unit Design minor baseline (sw21.21.145.01) | 0 days | June 7, 2019 5:00 PM | June 7, 2019 5:00 PM | 2019-06-07 | 1 | 2950 | 5
3029 | No | Auto Scheduled | Redmine Software Implementation (sw21.21.145.01) | 0 days | May 20, 2019 5:00 PM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 3011 | 5
3030 | Yes | Auto Scheduled | Software Validation | 4 days | June 7, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
3031 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.01) | 4 days | June 7, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 2950 | 5
3032 | Yes | Auto Scheduled | Systems Integration | 11 days | May 28, 2019 5:00 PM | June 12, 2019 5:00 PM | 2019-06-12 | 1 |  | 4
3033 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.01) | 11 days | May 28, 2019 5:00 PM | June 12, 2019 5:00 PM | 2019-06-12 | 1 | 2972,2909 | 5
3034 | Yes | Auto Scheduled | Systems Qualification | 7 days | June 4, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
3035 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.01) | 7 days | June 4, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 2905,2986 | 5
3036 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.02) | 0 days | June 13, 2019 8:00 AM | June 13, 2019 8:00 AM | 2019-06-13 | 1 | 3019,3022,3029 | 4
3037 | Yes | Auto Scheduled | Sprint 2 (sw21.21.145.01) | 31 days | May 17, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 3
3038 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.145.01) | 0 days | May 28, 2019 5:00 PM | May 28, 2019 5:00 PM | 2019-05-28 | 1 |  | 4 | Pending HMI
3039 | Yes | Auto Scheduled | Systems Engineering 2 | 28 days | May 17, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 |  | 4
3040 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.145.02) | 27 days | May 17, 2019 8:00 AM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3018 | 5
3041 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.145.02) | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3040 | 5
3042 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.02) | 5 days | June 18, 2019 5:00 PM | June 25, 2019 5:00 PM | 2019-06-25 | 1 | 3019 | 5
3043 | Yes | Auto Scheduled | Systems Engineering 3 | 28 days | May 17, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 |  | 4
3044 | Yes | Auto Scheduled | SAD Major baseline (sw21.21.145.02) | 27 days | May 17, 2019 8:00 AM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3021 | 5
3045 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.145.02) | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3044 | 5
3046 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.02) | 2 days | June 24, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 | 3022 | 5
3047 | Yes | Auto Scheduled | Software Systems | 5 days | June 24, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 4
3048 | No | Auto Scheduled | Software Functional Specs Minor baseline (sw21.21.145.02) | 27 days | June 24, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 | 3018,3021 | 5
3049 | Yes | Auto Scheduled | Redmine Analysis Complete (sw21.21.145.02) | 5 days | June 24, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 3024 | 5
3050 | Yes | Auto Scheduled | Software Design | 23.5 days | May 21, 2019 8:00 AM | June 21, 2019 12:00 PM | 2019-06-21 | 1 |  | 4
3051 | No | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw21.21.145.02) | 0 days | May 31, 2019 5:00 PM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 5
3052 | Yes | Auto Scheduled | Architecture Design Major basline (sw21.21.145.01) | 14 days | May 27, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3026 | 5
3053 | Yes | Auto Scheduled | Layer Design Major baseline (sw21.21.145.01) | 14 days | May 27, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3027 | 5
3054 | Yes | Auto Scheduled | Unit Design Major baseline (sw21.21.145.01) | 14 days | May 27, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3028 | 5
3055 | Yes | Auto Scheduled | Software Integration Test Spec Major baseline(sw21.21.145.01) | 8 days | June 10, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3026,3027,3028 | 5
3056 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3052 | 5
3057 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3053 | 5
3058 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3054 | 5
3059 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.145.01) | 0 days | June 19, 2019 5:00 PM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3055 | 5
3060 | Yes | Auto Scheduled | Redmine Software Implementation (acc. To FROP)(sw21.21.145.01) | 15 days | May 21, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 3029 | 5
3061 | Yes | Auto Scheduled | Sanity Check (sw21.21.145.01) | 4 days | June 11, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 | 3055,3060 | 5
3062 | Yes | Auto Scheduled | Full Integration Testing(sw21.21.145.01) | 4 days | June 11, 2019 8:00 AM | June 20, 2019 11:12 AM | 2019-06-20 | 1 | 3055,3060 | 5
3063 | Yes | Auto Scheduled | Internal SW release (sw21.21.145.01) | 0 days | June 14, 2019 8:00 AM | June 14, 2019 8:00 AM | 2019-06-14 | 1 | 3062 | 5
3064 | Yes | Auto Scheduled | Implement SW change | 0.5 days | June 20, 2019 8:00 AM | June 20, 2019 12:00 PM | 2019-06-20 | 1 |  | 5
3065 | Yes | Auto Scheduled | Integration Testing (RHMI, LineTest, Wake/Sleep, Power ON/OFF, Key Provisioning) | 0.5 days | June 20, 2019 1:00 PM | June 20, 2019 5:00 PM | 2019-06-20 | 1 | 3064 | 5
3066 | Yes | Auto Scheduled | Signing code from GM | 0.5 days | June 21, 2019 8:00 AM | June 21, 2019 12:00 PM | 2019-06-21 | 1 | 3065 | 5
3067 | Yes | Auto Scheduled | Internal SW re-release (sw21.21.145.01) | 0 days | June 21, 2019 12:00 PM | June 21, 2019 12:00 PM | 2019-06-21 | 1 | 3066 | 5
3068 | Yes | Auto Scheduled | Software Validation | 13 days | June 3, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 |  | 4
3069 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.01) | 9 days | June 3, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3031 | 5
3070 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3069 | 5
3071 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.02) | 5 days | June 13, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3036 | 5
3072 | Yes | Auto Scheduled | Systems Integration | 21 days | May 29, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 |  | 4
3073 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.01) | 12 days | May 29, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3033 | 5
3074 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3073 | 5
3075 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.02) | 10 days | June 13, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 | 3036 | 5
3076 | Yes | Auto Scheduled | Systems Qualification | 16 days | June 5, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 |  | 4
3077 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.01) | 7 days | June 5, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3035 | 5
3078 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.145.01) | 0 days | June 13, 2019 5:00 PM | June 13, 2019 5:00 PM | 2019-06-13 | 1 | 3077 | 5
3079 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.02) | 10 days | June 13, 2019 8:00 AM | June 26, 2019 5:00 PM | 2019-06-26 | 1 | 3036 | 5
3080 | Yes | Auto Scheduled | Program Management | 6 days | June 5, 2019 8:00 AM | June 12, 2019 5:00 PM | 2019-06-12 | 1 |  | 4
3081 | Yes | Auto Scheduled | CG4422 updated to GM (sw21.21.145.01) | 6 days | June 5, 2019 8:00 AM | June 12, 2019 5:00 PM | 2019-06-12 | 1 | 3063SF-4d | 5
3082 | No | Auto Scheduled | FROP tentative (sw21.21.145.02) | 0 days | June 28, 2019 5:00 PM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 3042,3046,3049,3071,3075,3079 | 5
3083 | Yes | Auto Scheduled | Sprint 3 (sw21.21.145.01) | 58 days | June 6, 2019 8:00 AM | August 26, 2019 5:00 PM | 2019-08-26 | 1 |  | 3
3084 | No | Auto Scheduled | Create Production Study CALS (sw21.21.145.01) | 3 days | June 14, 2019 8:00 AM | June 18, 2019 5:00 PM | 2019-06-18 | 1 | 3063 | 4
3085 | Yes | Auto Scheduled | Software Systems | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 |  | 4
3086 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw21.21.145.02) | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3040 | 5
3087 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.145.02) | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3086 | 5
3088 | Yes | Auto Scheduled | Software Validation | 16 days | June 13, 2019 5:00 PM | July 7, 2019 5:00 PM | 2019-07-07 | 1 |  | 4
3089 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.145.01) | 1 day | June 13, 2019 5:00 PM | June 14, 2019 5:00 PM | 2019-06-14 | 1 | 3063 | 5
3090 | Yes | Auto Scheduled | SWE6 Verification Testing (sw21.21.145.01) | 4 days | June 14, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3063 | 5
3091 | Yes | Auto Scheduled | SWE6 Verification Testing (re-release sw21.21.145.01) | 2 days | June 21, 2019 1:00 PM | June 25, 2019 12:00 PM | 2019-06-25 | 1 | 3067 | 5
3092 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.145.01) | 0.5 days | June 25, 2019 1:00 PM | June 25, 2019 5:00 PM | 2019-06-25 | 1 | 3091 | 5
3093 | Yes | Auto Scheduled | CG4879 Test Execution (sw21.21.145.01) | 6 days | June 26, 2019 8:00 AM | July 7, 2019 5:00 PM | 2019-07-07 | 1 | 3092 | 5
3094 | Yes | Auto Scheduled | Software Design | 2 days | July 1, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 |  | 4
3095 | Yes | Auto Scheduled | Redmine Estimation from FROP tentative (sw21.21.145.02) | 2 days | July 1, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 | 3082 | 5
3096 | Yes | Auto Scheduled | Systems Integration | 7.5 days | June 14, 2019 8:00 AM | June 25, 2019 12:00 PM | 2019-06-25 | 1 |  | 4
3097 | Yes | Auto Scheduled | Test Execution (sw21.21.145.01) | 4 days | June 14, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3063 | 5
3098 | Yes | Auto Scheduled | SYS Integration Test Report (sw21.21.145.01) | 0.5 days | June 20, 2019 8:00 AM | June 20, 2019 12:00 PM | 2019-06-20 | 1 | 3097 | 5
3099 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.01) | 0.5 days | June 20, 2019 1:00 PM | June 20, 2019 5:00 PM | 2019-06-20 | 1 | 3098 | 5
3100 | Yes | Auto Scheduled | SYS Integration Test Report (re-release sw21.21.145.01) | 2 days | June 21, 2019 1:00 PM | June 25, 2019 12:00 PM | 2019-06-25 | 1 | 3067 | 5
3101 | Yes | Auto Scheduled | Systems Qualification | 7.5 days | June 14, 2019 8:00 AM | June 25, 2019 12:00 PM | 2019-06-25 | 1 |  | 4
3102 | Yes | Auto Scheduled | Test Execution (sw21.21.145.01) | 4 days | June 14, 2019 8:00 AM | June 19, 2019 5:00 PM | 2019-06-19 | 1 | 3063 | 5
3103 | Yes | Auto Scheduled | SYS Qualification Test Report (sw21.21.145.01) | 0.5 days | June 20, 2019 8:00 AM | June 20, 2019 12:00 PM | 2019-06-20 | 1 | 3102 | 5
3104 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.01) | 0.5 days | June 20, 2019 1:00 PM | June 20, 2019 5:00 PM | 2019-06-20 | 1 | 3103 | 5
3105 | Yes | Auto Scheduled | SYS Qualification Test Report (sw21.21.145.01) | 2 days | June 21, 2019 1:00 PM | June 25, 2019 12:00 PM | 2019-06-25 | 1 | 3067 | 5
3106 | Yes | Auto Scheduled | HW Test Case Execution | 58 days | June 6, 2019 8:00 AM | August 26, 2019 5:00 PM | 2019-08-26 | 1 |  | 4
3107 | Yes | Auto Scheduled | HW Test Case Execution from SRS (sw21.21.145.01) Phase 1 | 3 days | June 6, 2019 8:00 AM | June 10, 2019 5:00 PM | 2019-06-10 | 1 | 3118 | 5
3108 | Yes | Auto Scheduled | HW Test Case Execution from SRS (sw21.21.145.01) Phase 2 | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 5
3109 | Yes | Auto Scheduled | HW Test Case Execution from SRS (sw21.21.145.01) Phase 3 | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3108 | 5
3110 | Yes | Auto Scheduled | Create Report | 5 days | July 29, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 3109 | 5
3111 | Yes | Auto Scheduled | Review Report | 5 days | August 5, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3110 | 5
3112 | Yes | Auto Scheduled | Feedback update and remeasurements | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3111 | 5
3113 | Yes | Auto Scheduled | Feedback update and remeasurements | 3 days | August 21, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 | 2648 | 5
3114 | Yes | Auto Scheduled | Report Approval | 1 day | August 26, 2019 8:00 AM | August 26, 2019 5:00 PM | 2019-08-26 | 1 | 3113 | 5
3115 | Yes | Auto Scheduled | HW Functional Safety Test | 48 days | June 14, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 |  | 4
3116 | Yes | Auto Scheduled | HSR Test execution phase 2 (sw21.21.145.01) | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144.
3117 | Yes | Auto Scheduled | HSR Test execution phase 2 (sw21.21.145.03) | 10 days | July 22, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 5
3118 | Yes | Auto Scheduled | Test Report creation (sw21.21.145.03) | 5 days | June 28, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3116 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3119 | Yes | Auto Scheduled | Test Report review (sw21.21.145.03) | 5 days | July 9, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3118 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3120 | Yes | Auto Scheduled | Feedback update and remeasurements (sw21.21.145.03) | 5 days | July 16, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3119 | 5
3121 | Yes | Auto Scheduled | Test Report review (sw21.21.145.03) | 5 days | July 23, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 | 3120 | 5
3122 | Yes | Auto Scheduled | Test Report review with FuSa team (sw21.21.145.03) | 5 days | July 23, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 | 3120 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3123 | Yes | Auto Scheduled | Feedback update and remeasurements (sw21.21.145.03) | 5 days | July 30, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 | 3122 | 5
3124 | Yes | Auto Scheduled | Test Report approval (sw21.21.145.03) | 1 day | August 6, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3123 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3125 | Yes | Auto Scheduled | Test Results upload to DOORS (sw21.21.145.03) | 5 days | August 7, 2019 8:00 AM | August 13, 2019 5:00 PM | 2019-08-13 | 1 | 3124 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3126 | Yes | Auto Scheduled | Create Traceability to Test Results (sw21.21.145.03) | 5 days | August 14, 2019 8:00 AM | August 20, 2019 5:00 PM | 2019-08-20 | 1 | 3125 | 5 | RAID Log Issue ID# 97: Activities added to sw21.21.145 as there were issues in sw21.21.142.1 and sw21.21.144
3127 | Yes | Auto Scheduled | Compliance Test | 4.5 days | June 14, 2019 8:00 AM | June 20, 2019 12:00 PM | 2019-06-20 | 1 |  | 4
3128 | No | Auto Scheduled | CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.01) | 12 days | June 14, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 | 3063 | 5
3129 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw21.21.145.01) | 4.5 days | June 14, 2019 8:00 AM | June 20, 2019 12:00 PM | 2019-06-20 | 1 | 3063 | 5
3130 | No | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw21.21.145.01) | 7.5 days | June 20, 2019 1:00 PM | July 1, 2019 5:00 PM | 2019-07-01 | 1 | 3129 | 5
3131 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.01) | 5 days | July 2, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3128 | 5
3132 | No | Auto Scheduled | Fuzz Test Execution (Cyber Security) | 17 days | June 14, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 5
3133 | No | Auto Scheduled | TCP Client (sw21.21.145.01) | 15 days | June 14, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3063 | 6
3134 | No | Auto Scheduled | TCP Server (sw21.21.145.01) | 15 days | June 14, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3063 | 6
3135 | No | Auto Scheduled | IPv4 (sw21.21.145.01) | 15 days | June 14, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3063 | 6
3136 | Yes | Auto Scheduled | Program Management | 27 days | June 14, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 |  | 4
3137 | Yes | Auto Scheduled | Software Release notes (sw21.21.145.01) | 2 days | June 24, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 | 3139FS-2d | 5
3138 | Yes | Auto Scheduled | Software Release Assessment (sw21.21.145.01) | 0 days | June 25, 2019 8:00 AM | June 25, 2019 8:00 AM | 2019-06-25 | 1 | 3139FS-1d | 5
3139 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw21.21.145.01) | 0 days | June 25, 2019 5:00 PM | June 25, 2019 5:00 PM | 2019-06-25 | 1 |  | 5
3140 | Yes | Auto Scheduled | CG2496 Test Report (sw21.21.145.01) | 17.5 days | June 25, 2019 1:00 PM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3105 | 5
3141 | Yes | Auto Scheduled | CG2999 to GM (sw21.21.145.01) | 11 days | June 14, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 5
3142 | Yes | Auto Scheduled | Unit Test report (sw21.21.145.01) | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 6
3143 | Yes | Auto Scheduled | Static Analysis Test report (sw21.21.145.01) | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 6
3144 | Yes | Auto Scheduled | SAA update (sw21.21.145.01) | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 6
3145 | Yes | Auto Scheduled | Integratoin Test report (sw21.21.145.01) | 10 days | June 14, 2019 8:00 AM | June 27, 2019 5:00 PM | 2019-06-27 | 1 | 3063 | 6
3146 | Yes | Auto Scheduled | Performance Paramters report (sw21.21.145.01) | 11 days | June 14, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 3063 | 6
3147 | Yes | Auto Scheduled | Stress Test Results (sw21.21.145.01) | 7 days | June 14, 2019 8:00 AM | June 24, 2019 5:00 PM | 2019-06-24 | 1 | 3063 | 6
3148 | Yes | Auto Scheduled | Black box test results (sw21.21.145.01) | 8 days | June 14, 2019 8:00 AM | June 25, 2019 5:00 PM | 2019-06-25 | 1 | 3063 | 6
3149 | Yes | Auto Scheduled | FROP Final (sw21.21.145.02) | 0 days | June 28, 2019 5:00 PM | June 28, 2019 5:00 PM | 2019-06-28 | 1 | 3095 | 5
3150 | Yes | Auto Scheduled | Software Development (sw21.21.145.02) | 663 days | January 17, 2017 12:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 2
3151 | Yes | Auto Scheduled | sw21.21.145.02 cadence start | 0 days | July 1, 2019 8:00 AM | July 1, 2019 8:00 AM | 2019-07-01 | 1 |  | 3
3152 | Yes | Auto Scheduled | Sprint 1 (sw21.21.145.02) | 15 days | June 25, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 3
3153 | No | Auto Scheduled | Program Management | 1 day | July 9, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 |  | 4
3154 | No | Auto Scheduled | Release Kick Off meeting (sw21.21.145.02) | 1 day | July 9, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 3151 | 5
3155 | Yes | Auto Scheduled | Systems Engineering 2 | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 4
3156 | No | Auto Scheduled | SRS Minor baseline (sw21.21.145.03) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3151 | 5
3157 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.03) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3151 | 5
3158 | Yes | Auto Scheduled | Systems Engineering 3 | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 4
3159 | No | Auto Scheduled | SAD Minor baseline (sw21.21.145.03) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3151 | 5
3160 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.03) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3151 | 5
3161 | Yes | Auto Scheduled | Software Systems | 11 days | July 1, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 4
3162 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.03) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3151 | 5
3163 | Yes | Auto Scheduled | Power Sequence Measurements (redmines: 6742, 6547) (sw21.21.145.02) | 3 days | July 10, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3199 | 5
3164 | Yes | Auto Scheduled | Waveform Measurements | 1 day | July 15, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3163 | 5
3165 | Yes | Auto Scheduled | Software Design | 10 days | June 25, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 4
3166 | Yes | Auto Scheduled | Architecture Design minor baseline (sw21.21.145.02) | 8 days | June 25, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3086 | 5
3167 | Yes | Auto Scheduled | Layer Design minor baseline (sw21.21.145.02) | 8 days | June 25, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3086 | 5
3168 | Yes | Auto Scheduled | Unit Design minor baseline (sw21.21.145.02) | 8 days | June 25, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 | 3086 | 5
3169 | Yes | Auto Scheduled | Redmine Software Implementation (sw21.21.145.02) | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3149 | 5
3170 | Yes | Auto Scheduled | Software Validation | 12 days | June 25, 2019 8:00 AM | July 10, 2019 5:00 PM | 2019-07-10 | 1 |  | 4
3171 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.02) | 10 days | June 25, 2019 8:00 AM | July 10, 2019 5:00 PM | 2019-07-10 | 1 | 3086 | 5
3172 | Yes | Auto Scheduled | Systems Integration | 9 days | June 25, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 |  | 4
3173 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.02) | 9 days | June 25, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 | 3044 | 5
3174 | Yes | Auto Scheduled | Systems Qualification | 9 days | June 25, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 |  | 4
3175 | Yes | Auto Scheduled | Test Case minor baseline (sw21.21.145.02) | 9 days | June 25, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 | 3040 | 5
3176 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.03) | 0 days | July 3, 2019 5:00 PM | July 3, 2019 5:00 PM | 2019-07-03 | 1 | 3157,3160,3169 | 4
3177 | Yes | Auto Scheduled | Sprint 2 (sw21.21.145.02) | 35 days | May 31, 2019 5:00 PM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 3
3178 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.145.02) (HMI Only) | 19 days | May 31, 2019 5:00 PM | June 27, 2019 5:00 PM | 2019-06-27 | 1 |  | 4
3179 | Yes | Auto Scheduled | Systems Engineering 2 | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3180 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.145.04) | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3156 | 5 | Baseline changed from sw21.21.145.03 to sw21.21.145.04 as sw21.21.145.03 will use previous baseline
3181 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.145.04) | 0 days | July 19, 2019 5:00 PM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3180 | 5
3182 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.03) | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3157 | 5
3183 | Yes | Auto Scheduled | Systems Engineering 3 | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3184 | Yes | Auto Scheduled | SAD Major baseline (sw21.21.145.04) | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3159 | 5 | Baseline changed from sw21.21.145.03 to sw21.21.145.04 as sw21.21.145.03 will use previous baseline
3185 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.145.04) | 0 days | July 19, 2019 5:00 PM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3184 | 5
3186 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.03) | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3160 | 5
3187 | Yes | Auto Scheduled | Software Systems | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3188 | Yes | Auto Scheduled | Software Functional Specs Minor baseline (sw21.21.145.04) | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3156,3159 | 5 | Baseline changed from sw21.21.145.03 to sw21.21.145.04 as sw21.21.145.03 will use previous baseline
3189 | Yes | Auto Scheduled | Redmine Analysis Complete (sw21.21.145.03) | 5 days | July 8, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3162 | 5
3190 | Yes | Auto Scheduled | Software Design | 6.5 days | July 8, 2019 8:00 AM | July 16, 2019 12:00 PM | 2019-07-16 | 1 |  | 4
3191 | No | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw21.21.145.03) | 0 days | May 31, 2019 5:00 PM | May 31, 2019 5:00 PM | 2019-05-31 | 1 |  | 5
3192 | Yes | Auto Scheduled | Architecture Design Major basline (sw21.21.145.02) | 5 days | July 9, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3166 | 5
3193 | Yes | Auto Scheduled | Layer Design Major baseline (sw21.21.145.02) | 5 days | July 9, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3167 | 5
3194 | Yes | Auto Scheduled | Unit Design Major baseline (sw21.21.145.02) | 5 days | July 9, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3168 | 5
3195 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3192 | 5
3196 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3193 | 5
3197 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3194 | 5
3198 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3202 | 5
3199 | Yes | Auto Scheduled | Redmine Software Implementation (acc. To FROP)(sw21.21.145.02) | 2 days | July 8, 2019 8:00 AM | July 9, 2019 5:00 PM | 2019-07-09 | 1 | 3169 | 5
3200 | Yes | Auto Scheduled | Sanity Check (sw21.21.145.02) | 0.5 days | July 16, 2019 8:00 AM | July 16, 2019 12:00 PM | 2019-07-16 | 1 | 3202,3199 | 5
3201 | Yes | Auto Scheduled | Full Integration Testing(sw21.21.145.02) | 2 days | July 10, 2019 8:00 AM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3199 | 5
3202 | Yes | Auto Scheduled | Software Integration Test Spec Major baseline(sw21.21.145.02) | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3201 | 5
3203 | Yes | Auto Scheduled | Internal SW release (sw21.21.145.02) | 0 days | July 11, 2019 5:00 PM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3201 | 5
3204 | Yes | Auto Scheduled | Software Validation | 4 days | July 11, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 |  | 4
3205 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.02) | 2 days | July 11, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3171 | 5
3206 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.145.02) | 0 days | July 12, 2019 5:00 PM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3205 | 5
3207 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.03) | 1 day | July 16, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 3176 | 5
3208 | Yes | Auto Scheduled | Systems Integration | 10 days | July 4, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
3209 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.02) | 4 days | July 8, 2019 8:00 AM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3173 | 5
3210 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.145.02) | 0 days | July 11, 2019 5:00 PM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3209 | 5
3211 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.03) | 10 days | July 4, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3176 | 5
3212 | Yes | Auto Scheduled | Systems Qualification | 10 days | July 4, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
3213 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.02) | 4 days | July 8, 2019 8:00 AM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3175 | 5
3214 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.145.02) | 0 days | July 11, 2019 5:00 PM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3213 | 5
3215 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.03) | 10 days | July 4, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3176 | 5
3216 | Yes | Auto Scheduled | Program Management | 5 days | July 12, 2019 5:00 PM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3217 | Yes | Auto Scheduled | CG4422 updated to GM (sw21.21.145.02) | 3 days | July 17, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3203SF-4d | 5
3218 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.03) | 0 days | July 12, 2019 5:00 PM | July 12, 2019 5:00 PM | 2019-07-12 | 1 | 3182,3186,3189,3207,3211,3215 | 5
3219 | Yes | Auto Scheduled | Sprint 3 (sw21.21.145.02) | 663 days | January 17, 2017 12:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 3
3220 | Yes | Auto Scheduled | Create Production Study CALS (sw21.21.145.02) | 0.5 days | July 12, 2019 8:00 AM | July 12, 2019 12:00 PM | 2019-07-12 | 1 | 3203 | 4
3221 | Yes | Auto Scheduled | Software Systems | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3222 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw21.21.145.04) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3180 | 5 | Baseline changed from sw21.21.145.03 to sw21.21.145.04 as sw21.21.145.03 will use previous baseline
3223 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.145.04) | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3222 | 5
3224 | Yes | Auto Scheduled | Software Validation | 2 days | July 11, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 4
3225 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.145.02) | 0 days | July 11, 2019 5:00 PM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3203 | 5
3226 | Yes | Auto Scheduled | SWE6 Verification Testing (sw21.21.145.02) | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3203 | 5
3227 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3226 | 5
3228 | No | Auto Scheduled | CG4879 Test Execution (sw21.21.145.02) | 3 days | July 16, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 | 3226 | 5
3229 | Yes | Auto Scheduled | Software Design | 0 days | January 17, 2017 12:00 AM | January 17, 2017 12:00 AM | 2017-01-17 | 1 |  | 4
3230 | No | Auto Scheduled | Redmine Estimation from FROP tentative (sw21.21.145.03) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3218 | 5
3231 | Yes | Auto Scheduled | Systems Integration | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 4
3232 | Yes | Auto Scheduled | Test Execution (sw21.21.145.02) | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3203 | 5
3233 | Yes | Auto Scheduled | SYS Integration Test Report (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3232 | 5
3234 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3233 | 5
3235 | Yes | Auto Scheduled | Systems Qualification | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 4
3236 | Yes | Auto Scheduled | Test Execution (sw21.21.145.02) | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3203 | 5
3237 | Yes | Auto Scheduled | SYS Qualification Test Report (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3236 | 5
3238 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3237 | 5
3239 | Yes | Auto Scheduled | Compliance Test | 12 days | July 12, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 |  | 4
3240 | Yes | Auto Scheduled | CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.02) | 12 days | July 12, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 | 3203 | 5
3241 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw21.21.145.02) | 4 days | July 12, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3203 | 5
3242 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw21.21.145.02) | 7.5 days | July 18, 2019 8:00 AM | July 29, 2019 12:00 PM | 2019-07-29 | 1 | 3241 | 5
3243 | Yes | Auto Scheduled | CG3926 - Arf Diff (sw21.21.145.02) | 3 days | July 12, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 3203 | 5
3244 | No | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.02) | 5 days | July 30, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 | 3240 | 5
3245 | No | Auto Scheduled | Fuzz Test Execution (Cyber Security) | 15 days | July 12, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 |  | 5
3246 | No | Auto Scheduled | TCP Client (sw21.21.145.02) | 15 days | July 12, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 | 3203 | 6
3247 | No | Auto Scheduled | TCP Server (sw21.21.145.02) | 15 days | July 12, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 | 3203 | 6
3248 | No | Auto Scheduled | IPv4 (sw21.21.145.02) | 15 days | July 12, 2019 8:00 AM | August 1, 2019 5:00 PM | 2019-08-01 | 1 | 3203 | 6
3249 | Yes | Auto Scheduled | Program Management | 16 days | July 11, 2019 5:00 PM | August 2, 2019 5:00 PM | 2019-08-02 | 1 |  | 4
3250 | Yes | Auto Scheduled | Software Release notes (sw21.21.145.02) | 2 days | July 12, 2019 8:00 AM | July 15, 2019 5:00 PM | 2019-07-15 | 1 | 3252FS-2d | 5
3251 | Yes | Auto Scheduled | Software Release Assessment (sw21.21.145.02) | 0 days | July 15, 2019 8:00 AM | July 15, 2019 8:00 AM | 2019-07-15 | 1 | 3252FS-1d | 5
3252 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw21.21.145.02) | 0 days | July 15, 2019 5:00 PM | July 15, 2019 5:00 PM | 2019-07-15 | 1 |  | 5
3253 | Yes | Auto Scheduled | CG2496 Test Report (sw21.21.145.02) | 10 days | July 22, 2019 8:00 AM | August 2, 2019 5:00 PM | 2019-08-02 | 1 | 3238 | 5
3254 | Yes | Auto Scheduled | CG2999 to GM (sw21.21.145.02) | 5 days | July 12, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 |  | 5
3255 | Yes | Auto Scheduled | Unit Test report (sw21.21.145.02) | 4 days | July 12, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3203 | 6
3256 | Yes | Auto Scheduled | SAA update (sw21.21.145.02) | 4 days | July 12, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3203 | 6
3257 | Yes | Auto Scheduled | Integratoin Test report (sw21.21.145.02) | 4 days | July 12, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3203 | 6
3258 | Yes | Auto Scheduled | Performance Paramters report (sw21.21.145.02) | 4 days | July 12, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3203 | 6
3259 | Yes | Auto Scheduled | Stress Test Results (sw21.21.145.02) | 3 days | July 12, 2019 8:00 AM | July 16, 2019 5:00 PM | 2019-07-16 | 1 | 3203 | 6
3260 | Yes | Auto Scheduled | Black box test results (sw21.21.145.02) | 3 days | July 16, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 | 3227,3234,3238 | 6
3261 | Yes | Auto Scheduled | FROP Final (sw21.21.145.03) | 0 days | July 11, 2019 5:00 PM | July 11, 2019 5:00 PM | 2019-07-11 | 1 | 3230 | 5
3262 | Yes | Auto Scheduled | Software Developemt (sw21.21.145.03) | 16.5 days | July 8, 2019 8:00 AM | July 30, 2019 12:00 PM | 2019-07-30 | 1 |  | 2
3263 | Yes | Auto Scheduled | Software Desing (sw21.21.145.03) | 13 days | July 8, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 |  | 3
3264 | Yes | Auto Scheduled | Redmine 14914 root cause and implementation (sw21.21.145.03) | 10 days | July 8, 2019 8:00 AM | July 21, 2019 5:00 PM | 2019-07-21 | 1 |  | 4
3265 | Yes | Auto Scheduled | Redmine 15251 root cause and implementation (sw21.21.145.03) | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3266 | Yes | Auto Scheduled | Redmine 7942 root cause and implementation (sw21.21.145.03) | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 4
3267 | No | Auto Scheduled | Architecture Design Major basline (sw21.21.145.03) | 0.5 days | July 22, 2019 8:00 AM | July 22, 2019 12:00 PM | 2019-07-22 | 1 | 3264,3265,3266 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3268 | No | Auto Scheduled | Layer Design Major baseline (sw21.21.145.03) | 0.5 days | July 22, 2019 8:00 AM | July 22, 2019 12:00 PM | 2019-07-22 | 1 | 3264,3265,3266 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3269 | No | Auto Scheduled | Unit Design Major baseline (sw21.21.145.03) | 0.5 days | July 22, 2019 8:00 AM | July 22, 2019 12:00 PM | 2019-07-22 | 1 | 3264,3265,3266 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3270 | No | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.145.03) | 0.5 days | July 22, 2019 1:00 PM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3267 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3271 | No | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.145.03) | 0.5 days | July 22, 2019 1:00 PM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3268 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3272 | No | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.145.03) | 0.5 days | July 22, 2019 1:00 PM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3269 | 4 | As per baseline strategy, this release will use sw21.21.145.02 baseline
3273 | Yes | Auto Scheduled | Integration Testing (sw21.21.145.03) | 1 day | July 21, 2019 5:00 PM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3264,3265,3266 | 4 | Will be completed by 7/24 COB
3274 | Yes | Auto Scheduled | Software Integration Test Spec Major baseline(sw21.21.145.03) | 0.5 days | July 23, 2019 8:00 AM | July 23, 2019 12:00 PM | 2019-07-23 | 1 | 3273 | 4
3275 | Yes | Auto Scheduled | Internal SW release (sw21.21.145.03) | 0 days | July 23, 2019 12:00 PM | July 23, 2019 12:00 PM | 2019-07-23 | 1 | 3274 | 4
3276 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.145.03) | 0.5 days | July 23, 2019 1:00 PM | July 23, 2019 5:00 PM | 2019-07-23 | 1 | 3275 | 4
3277 | Yes | Auto Scheduled | CG3923 Arf Diff (sw21.21.145.03) | 1.5 days | July 23, 2019 1:00 PM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 3275 | 4
3278 | Yes | Auto Scheduled | Software Validation (sw21.21.145.03) | 10 days | July 16, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 |  | 3
3279 | Yes | Auto Scheduled | Redmine impact analysis (sw21.21.145.03) | 2 days | July 16, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
3280 | Yes | Auto Scheduled | DTC Testing with sw21.21.145.01 | 3 days | July 16, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 |  | 4
3281 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.03) | 0 days | July 17, 2019 5:00 PM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3279 | 4
3282 | Yes | Auto Scheduled | Redmine testing (sw21.21.145.03) | 1 day | July 23, 2019 1:00 PM | July 24, 2019 12:00 PM | 2019-07-24 | 1 | 3281,3275 | 4
3283 | Yes | Auto Scheduled | Test Summary Report (sw21.21.145.03) | 0.5 days | July 24, 2019 1:00 PM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 3282 | 4
3284 | Yes | Auto Scheduled | CG4879 - partial testing (sw21.21.145.03) | 3 days | July 25, 2019 8:00 AM | July 29, 2019 5:00 PM | 2019-07-29 | 1 | 3283 | 4
3285 | Yes | Auto Scheduled | Systems Integration (sw21.21.145.03) | 8 days | July 16, 2019 8:00 AM | July 25, 2019 5:00 PM | 2019-07-25 | 1 |  | 3
3286 | Yes | Auto Scheduled | Redmine impact analysis (sw21.21.145.03) | 2 days | July 16, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
3287 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.03) | 0 days | July 17, 2019 5:00 PM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3286 | 4
3288 | Yes | Auto Scheduled | Test Execution (sw21.21.145.03) | 2 days | July 23, 2019 1:00 PM | July 25, 2019 12:00 PM | 2019-07-25 | 1 |  | 4
3289 | Yes | Auto Scheduled | Flashing Stress (sw21.21.145.03) | 2 days | July 23, 2019 1:00 PM | July 25, 2019 12:00 PM | 2019-07-25 | 1 | 3287,3275 | 5
3290 | Yes | Auto Scheduled | FUSA testing (sw21.21.145.03) | 2 days | July 23, 2019 1:00 PM | July 25, 2019 12:00 PM | 2019-07-25 | 1 | 3287,3275 | 5
3291 | Yes | Auto Scheduled | Test Summary Report (sw21.21.145.03) | 0.5 days | July 25, 2019 1:00 PM | July 25, 2019 5:00 PM | 2019-07-25 | 1 | 3289,3290 | 4
3292 | Yes | Auto Scheduled | Systems Qualification (sw21.21.145.03) | 8 days | July 16, 2019 8:00 AM | July 25, 2019 5:00 PM | 2019-07-25 | 1 |  | 3
3293 | Yes | Auto Scheduled | Redmine impact analysis (sw21.21.145.03) | 2 days | July 16, 2019 8:00 AM | July 17, 2019 5:00 PM | 2019-07-17 | 1 |  | 4
3294 | Yes | Auto Scheduled | DTC Testing with sw21.21.145.01 | 3 days | July 16, 2019 8:00 AM | July 18, 2019 5:00 PM | 2019-07-18 | 1 |  | 4
3295 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.03) | 0 days | July 17, 2019 5:00 PM | July 17, 2019 5:00 PM | 2019-07-17 | 1 | 3293 | 4
3296 | Yes | Auto Scheduled | Test Execution (sw21.21.145.03) | 2 days | July 23, 2019 1:00 PM | July 25, 2019 12:00 PM | 2019-07-25 | 1 | 3295,3275 | 4
3297 | Yes | Auto Scheduled | Test Summary Report (sw21.21.145.03) | 0.5 days | July 25, 2019 1:00 PM | July 25, 2019 5:00 PM | 2019-07-25 | 1 | 3296 | 4
3298 | Yes | Auto Scheduled | Program Management (sw21.21.145.03) | 4 days | July 19, 2019 8:00 AM | July 24, 2019 5:00 PM | 2019-07-24 | 1 |  | 3
3299 | Yes | Auto Scheduled | Software Release notes (sw21.21.145.03) | 2 days | July 19, 2019 8:00 AM | July 23, 2019 8:00 AM | 2019-07-23 | 1 | 3301SF-2d | 4
3300 | Yes | Auto Scheduled | Software Release Assessment (sw21.21.145.03) | 0.5 days | July 24, 2019 1:00 PM | July 24, 2019 5:00 PM | 2019-07-24 | 1 | 3301SF | 4
3301 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw21.21.145.03) | 0 days | July 24, 2019 5:00 PM | July 24, 2019 5:00 PM | 2019-07-24 | 1 |  | 4
3302 | Yes | Auto Scheduled | CG2999 to GM (sw21.21.145.03) | 4 days | July 23, 2019 1:00 PM | July 29, 2019 12:00 PM | 2019-07-29 | 1 |  | 3
3303 | Yes | Auto Scheduled | Unit Test report (sw21.21.145.03) | 3 days | July 23, 2019 1:00 PM | July 26, 2019 12:00 PM | 2019-07-26 | 1 | 3275 | 4
3304 | Yes | Auto Scheduled | SAA update (sw21.21.145.03) | 3 days | July 23, 2019 1:00 PM | July 26, 2019 12:00 PM | 2019-07-26 | 1 | 3275 | 4
3305 | Yes | Auto Scheduled | Integratoin Test report (sw21.21.145.03) | 3 days | July 23, 2019 1:00 PM | July 26, 2019 12:00 PM | 2019-07-26 | 1 | 3275 | 4
3306 | Yes | Auto Scheduled | Performance Paramters report (sw21.21.145.03) | 4 days | July 23, 2019 1:00 PM | July 29, 2019 12:00 PM | 2019-07-29 | 1 | 3275 | 4
3307 | No | Auto Scheduled | Stress Test Results (sw21.21.145.03) | 1 day? | July 23, 2019 1:00 PM | July 24, 2019 12:00 PM | 2019-07-24 | 1 | 3275 | 4
3308 | Yes | Auto Scheduled | Black box test results (sw21.21.145.03) | 3 days | July 23, 2019 1:00 PM | July 26, 2019 12:00 PM | 2019-07-26 | 1 | 3275 | 4
3309 | Yes | Auto Scheduled | FROP Final (sw21.21.145.04) | 5 days | July 23, 2019 1:00 PM | July 30, 2019 12:00 PM | 2019-07-30 | 1 | 3275 | 3
3310 | Yes | Auto Scheduled | Software Development (sw21.21.145.04) | 37 days | July 15, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 |  | 2
3311 | Yes | Auto Scheduled | sw21.21.145.04 cadence start | 0 days | July 15, 2019 8:00 AM | July 15, 2019 8:00 AM | 2019-07-15 | 1 |  | 3
3312 | Yes | Auto Scheduled | Sprint 1 (sw21.21.145.04) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 3
3313 | Yes | Auto Scheduled | Program Management | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 |  | 4
3314 | Yes | Auto Scheduled | Release Kick Off meeting (sw21.21.145.04) | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3311 | 5
3315 | Yes | Auto Scheduled | Systems Engineering 2 | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3316 | Yes | Auto Scheduled | SRS Minor baseline (sw21.21.145.05) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3180 | 5
3317 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.05) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3182 | 5
3318 | Yes | Auto Scheduled | Systems Engineering 3 | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3319 | Yes | Auto Scheduled | SAD Minor baseline (sw21.21.145.05) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3184 | 5
3320 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.05) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3186 | 5
3321 | Yes | Auto Scheduled | Software Systems | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3322 | Yes | Auto Scheduled | Redmine Analysis phase 1 (sw21.21.145.05) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3189 | 5
3323 | Yes | Auto Scheduled | Software Design | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3324 | Yes | Auto Scheduled | A2L from GMTCI and Release Notes | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3203 | 5
3325 | Yes | Auto Scheduled | Architecture Design minor baselines / updates (sw21.21.145.04) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3203 | 5
3326 | Yes | Auto Scheduled | Layer Design minor baseline / updates (sw21.21.145.04) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3203 | 5
3327 | Yes | Auto Scheduled | Unit Design minor baseline / updates (sw21.21.145.04) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3203 | 5
3328 | Yes | Auto Scheduled | Redmine Software Implementation (sw21.21.145.04) | 10 days | July 15, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3203 | 5
3329 | No | Auto Scheduled | Software Validation | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3330 | No | Auto Scheduled | Test Case minor baseline / updates (sw21.21.145.04) | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3222 | 5
3331 | Yes | Auto Scheduled | Systems Integration | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3332 | Yes | Auto Scheduled | Test Case minor baseline /updates (sw21.21.145.04) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3184 | 5
3333 | Yes | Auto Scheduled | Systems Qualification | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3334 | Yes | Auto Scheduled | Test Case minor baseline / updates (sw21.21.145.04) | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3180 | 5
3335 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.05) | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3317,3320,3328 | 4
3336 | Yes | Auto Scheduled | Sprint 2 (sw21.21.145.04) | 10.5 days | July 26, 2019 5:00 PM | August 12, 2019 12:00 PM | 2019-08-12 | 1 |  | 3
3337 | Yes | Auto Scheduled | RC2 App exchange (sw21.21.145.04) | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3338 | Yes | Auto Scheduled | Systems Engineering 2 | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3339 | Yes | Auto Scheduled | SRS Major baseline (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3316 | 5
3340 | Yes | Auto Scheduled | EQA Workproduct Audit SRS (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3339 | 5
3341 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3317 | 5
3342 | Yes | Auto Scheduled | Systems Engineering 3 | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3343 | Yes | Auto Scheduled | SAD Major baseline (sw21.21.145.04) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3319 | 5
3344 | Yes | Auto Scheduled | EQA Workproduct Audit SAD (sw21.21.145.05) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3343 | 5
3345 | Yes | Auto Scheduled | Redmine Analysis phase 2 (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3320 | 5
3346 | Yes | Auto Scheduled | Software Systems | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3347 | Yes | Auto Scheduled | Software Functional Specs Minor baseline (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3316,3319 | 5
3348 | Yes | Auto Scheduled | Redmine Analysis Complete (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3322 | 5
3349 | Yes | Auto Scheduled | Software Design | 10.5 days | July 29, 2019 8:00 AM | August 12, 2019 12:00 PM | 2019-08-12 | 1 |  | 4
3350 | Yes | Auto Scheduled | Architecture Design Major basline (sw21.21.145.04) | 7 days | July 29, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3325 | 5
3351 | Yes | Auto Scheduled | Layer Design Major baseline (sw21.21.145.04) | 7 days | July 29, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3326 | 5
3352 | Yes | Auto Scheduled | Unit Design Major baseline (sw21.21.145.04) | 7 days | July 29, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3327 | 5
3353 | Yes | Auto Scheduled | EQA Workproduct Audit SW AD (sw21.21.145.04) | 0 days | August 6, 2019 5:00 PM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3350 | 5
3354 | Yes | Auto Scheduled | EQA Workproduct Audit SW DD (sw21.21.145.04) | 0 days | August 6, 2019 5:00 PM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3351 | 5
3355 | Yes | Auto Scheduled | EQA Workproduct Audit SW UD (sw21.21.145.04) | 0 days | August 6, 2019 5:00 PM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3352 | 5
3356 | Yes | Auto Scheduled | EQA Workproduct Audit SW INT TS (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3360 | 5
3357 | Yes | Auto Scheduled | Redmine Software Implementation (acc. To FROP)(sw21.21.145.04) | 7 days | July 29, 2019 8:00 AM | August 6, 2019 5:00 PM | 2019-08-06 | 1 | 3328 | 5
3358 | Yes | Auto Scheduled | Sanity Check (sw21.21.145.04) | 0.5 days | August 12, 2019 8:00 AM | August 12, 2019 12:00 PM | 2019-08-12 | 1 | 3357,3360 | 5
3359 | Yes | Auto Scheduled | Full Integration Testing(sw21.21.145.04) | 2 days | August 7, 2019 8:00 AM | August 8, 2019 5:00 PM | 2019-08-08 | 1 | 3357 | 5
3360 | Yes | Auto Scheduled | Software Integration Test Spec Major baseline(sw21.21.145.04) | 1 day | August 9, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3359 | 5
3361 | Yes | Auto Scheduled | Internal SW release (sw21.21.145.04) | 1 day | August 9, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3359 | 5
3362 | Yes | Auto Scheduled | RC-1 Bootloader release to GMTCI (sw21.21.145.05) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3361 | 5
3363 | Yes | Auto Scheduled | Software Validation | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3364 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.04) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3330 | 5
3365 | Yes | Auto Scheduled | EQA Workproduct Audit SW VAL TS (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3364 | 5
3366 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3335 | 5
3367 | Yes | Auto Scheduled | Systems Integration | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3368 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.04) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3332 | 5
3369 | Yes | Auto Scheduled | EQA Workproduct Audit SYS INT TS (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3368 | 5
3370 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3335 | 5
3371 | Yes | Auto Scheduled | Systems Qualification | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3372 | Yes | Auto Scheduled | Test Case Major baseline (sw21.21.145.04) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3334 | 5
3373 | Yes | Auto Scheduled | EQA Workproduct Audit SYS QUAL TS (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3372 | 5
3374 | Yes | Auto Scheduled | Redmine Estimation (sw21.21.145.05) | 10 days | July 29, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3335 | 5
3375 | Yes | Auto Scheduled | Program Management | 8 days | July 31, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3376 | Yes | Auto Scheduled | CG4422 updated to GM (sw21.21.145.04) | 3 days | July 31, 2019 8:00 AM | August 5, 2019 8:00 AM | 2019-08-05 | 1 | 3361SF-4d | 5
3377 | Yes | Auto Scheduled | FROP tentative (sw21.21.145.05) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3341,3345,3348,3366,3370,3374 | 5
3378 | Yes | Auto Scheduled | Sprint 3 (sw21.21.145.04) | 17 days | August 9, 2019 5:00 PM | September 3, 2019 5:00 PM | 2019-09-03 | 0 |  | 3
3379 | Yes | Auto Scheduled | Create Production Study CALS (sw21.21.145.04) | 3 days | August 12, 2019 8:00 AM | August 14, 2019 5:00 PM | 2019-08-14 | 1 | 3361 | 4
3380 | Yes | Auto Scheduled | Software Systems | 5 days | August 12, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 4
3381 | Yes | Auto Scheduled | Software Functional Specs Major baseline (sw21.21.145.05) | 5 days | August 12, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 3339 | 5
3382 | Yes | Auto Scheduled | EQA Workproduct Audit SWFS (sw21.21.145.05) | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 3381 | 5
3383 | Yes | Auto Scheduled | Software Validation | 7.5 days | August 9, 2019 5:00 PM | August 21, 2019 12:00 PM | 2019-08-21 | 1 |  | 4
3384 | Yes | Auto Scheduled | SW Validation Test Plan and Readiness Review (sw21.21.145.04) | 0 days | August 9, 2019 5:00 PM | August 9, 2019 5:00 PM | 2019-08-09 | 1 | 3361 | 5
3385 | Yes | Auto Scheduled | SWE6 Verification Testing (sw21.21.145.04) | 4.5 days | August 12, 2019 8:00 AM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3361 | 5
3386 | Yes | Auto Scheduled | SWE6 Verification Test Report (sw21.21.145.04) | 0.5 days | August 16, 2019 1:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 3385 | 5
3387 | Yes | Auto Scheduled | CG4879 Test Execution (sw21.21.145.04) | 3 days | August 16, 2019 1:00 PM | August 21, 2019 12:00 PM | 2019-08-21 | 1 | 3385 | 5
3388 | Yes | Auto Scheduled | Software Design | 10 days | August 12, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 |  | 4
3389 | Yes | Auto Scheduled | CG3926 - Arf Diff (sw21.21.145.04) | 3 days | August 12, 2019 8:00 AM | August 14, 2019 5:00 PM | 2019-08-14 | 1 | 3361 | 5
3390 | Yes | Auto Scheduled | Redmine Estimation from FROP tentative (sw21.21.145.05) | 10 days | August 12, 2019 8:00 AM | August 23, 2019 5:00 PM | 2019-08-23 | 1 | 3377 | 5
3391 | Yes | Auto Scheduled | Systems Integration | 5 days | August 12, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 4
3392 | Yes | Auto Scheduled | Test Execution (sw21.21.145.04) | 4.5 days | August 12, 2019 8:00 AM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3361 | 5
3393 | Yes | Auto Scheduled | SYS Integration Test Report (sw21.21.145.04) | 0 days | August 16, 2019 12:00 PM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3392 | 5
3394 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.04) | 0.5 days | August 16, 2019 1:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 3393 | 5
3395 | Yes | Auto Scheduled | Systems Qualification | 4.55 days | August 12, 2019 8:00 AM | August 16, 2019 1:24 PM | 2019-08-16 | 1 |  | 4
3396 | Yes | Auto Scheduled | Test Execution (sw21.21.145.04) | 4.5 days | August 12, 2019 8:00 AM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3361 | 5
3397 | Yes | Auto Scheduled | SYS Qualification Test Report (sw21.21.145.04) | 0 days | August 16, 2019 12:00 PM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3396 | 5
3398 | Yes | Auto Scheduled | Report review and approval (sw21.21.145.04) | 0.05 days | August 16, 2019 1:00 PM | August 16, 2019 1:24 PM | 2019-08-16 | 1 | 3397 | 5
3399 | Yes | Auto Scheduled | Compliance Test | 17 days | August 12, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 |  | 4
3400 | Yes | Auto Scheduled | CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.04) | 12 days | August 12, 2019 8:00 AM | August 27, 2019 5:00 PM | 2019-08-27 | 0 | 3361 | 5
3401 | Yes | Auto Scheduled | CG3689 - Ethernet AVB Device Test (sw21.21.145.04) | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3361 | 5
3402 | Yes | Auto Scheduled | CG3687 - Bootloader Flash Programming (sw21.21.145.04) | 7.5 days | August 16, 2019 8:00 AM | August 27, 2019 12:00 PM | 2019-08-27 | 0 | 3401 | 5
3403 | Yes | Auto Scheduled | SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.04) | 5 days | August 28, 2019 8:00 AM | September 3, 2019 5:00 PM | 2019-09-03 | 0 | 3400 | 5
3404 | Yes | Auto Scheduled | Fuzz Test Execution (Cyber Security) | 15 days | August 12, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 |  | 5
3405 | Yes | Auto Scheduled | TCP Client (sw21.21.145.04) | 15 days | August 12, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 | 3361 | 6
3406 | Yes | Auto Scheduled | TCP Server (sw21.21.145.04) | 15 days | August 12, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 | 3361 | 6
3407 | Yes | Auto Scheduled | IPv4 (sw21.21.145.04) | 15 days | August 12, 2019 8:00 AM | August 30, 2019 5:00 PM | 2019-08-30 | 0 | 3361 | 6
3408 | Yes | Auto Scheduled | Program Management | 14.55 days | August 12, 2019 8:00 AM | August 30, 2019 1:24 PM | 2019-08-30 | 0 |  | 4
3409 | Yes | Auto Scheduled | Software Release notes (sw21.21.145.04) | 2 days | August 15, 2019 8:00 AM | August 16, 2019 5:00 PM | 2019-08-16 | 1 | 3411FS-2d | 5
3410 | Yes | Auto Scheduled | Software Release Assessment (sw21.21.145.04) | 0.5 days | August 16, 2019 8:00 AM | August 16, 2019 12:00 PM | 2019-08-16 | 1 | 3411FS-1d | 5
3411 | Yes | Auto Scheduled | Share software packag (SW release) to GM (sw21.21.145.04) | 0 days | August 16, 2019 5:00 PM | August 16, 2019 5:00 PM | 2019-08-16 | 1 |  | 5
3412 | Yes | Auto Scheduled | CG2496 Test Report (sw21.21.145.04) | 10 days | August 16, 2019 1:24 PM | August 30, 2019 1:24 PM | 2019-08-30 | 0 | 3398 | 5
3413 | Yes | Auto Scheduled | CG2999 to GM (sw21.21.145.04) | 8 days | August 12, 2019 8:00 AM | August 21, 2019 5:00 PM | 2019-08-21 | 1 |  | 5
3414 | Yes | Auto Scheduled | Unit Test report (sw21.21.145.04) | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3361 | 6
3415 | Yes | Auto Scheduled | SAA update (sw21.21.145.04) | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3361 | 6
3416 | Yes | Auto Scheduled | Integratoin Test report (sw21.21.145.04) | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3361 | 6
3417 | Yes | Auto Scheduled | Performance Paramters report (sw21.21.145.04) | 4 days | August 12, 2019 8:00 AM | August 15, 2019 5:00 PM | 2019-08-15 | 1 | 3361 | 6
3418 | Yes | Auto Scheduled | Stress Test Results (sw21.21.145.04) | 3 days | August 12, 2019 8:00 AM | August 14, 2019 5:00 PM | 2019-08-14 | 1 | 3361 | 6
3419 | Yes | Auto Scheduled | Black box test results (sw21.21.145.04) | 3 days | August 19, 2019 8:00 AM | August 21, 2019 5:00 PM | 2019-08-21 | 1 | 3386,3394,3398 | 6
3420 | Yes | Auto Scheduled | FROP Final (sw21.21.145.03) | 0 days | August 23, 2019 5:00 PM | August 23, 2019 5:00 PM | 2019-08-23 | 1 | 3390 | 5
3421 | Yes | Auto Scheduled | Manufacturing | 144 days | March 14, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 2
3422 | Yes | Auto Scheduled | IMDS | 10 days | August 20, 2019 8:00 AM | September 2, 2019 5:00 PM | 2019-09-02 | 0 | 3423 | 3
3423 | Yes | Auto Scheduled | PFMEA | 36 days | July 1, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 |  | 3
3424 | Yes | Auto Scheduled | Create PFMEA | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 4
3425 | Yes | Auto Scheduled | PFMEA Review | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3424 | 4
3426 | Yes | Auto Scheduled | Share review with SHNS | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3425 | 4
3427 | Yes | Auto Scheduled | Update PFMEA | 10 days | July 23, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 | 3426 | 4
3428 | Yes | Auto Scheduled | PFMEA Review | 10 days | August 6, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 3427 | 4
3429 | Yes | Auto Scheduled | Control Plan | 36 days | July 1, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 |  | 3
3430 | Yes | Auto Scheduled | Create Control Plan | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 4
3431 | Yes | Auto Scheduled | Control Plan Review | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3430 | 4
3432 | Yes | Auto Scheduled | Share review with SHNS | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3431 | 4
3433 | Yes | Auto Scheduled | Update Control Plan | 10 days | July 23, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 | 3432 | 4
3434 | Yes | Auto Scheduled | Control Plan Review | 10 days | August 6, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 3433 | 4
3435 | Yes | Auto Scheduled | Process Flow | 36 days | July 1, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 |  | 3
3436 | Yes | Auto Scheduled | Create Process Flow | 3 days | July 1, 2019 8:00 AM | July 3, 2019 5:00 PM | 2019-07-03 | 1 |  | 4
3437 | Yes | Auto Scheduled | Process Flow Review | 10 days | July 8, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3436 | 4
3438 | Yes | Auto Scheduled | Share review with SHNS | 1 day | July 22, 2019 8:00 AM | July 22, 2019 5:00 PM | 2019-07-22 | 1 | 3437 | 4
3439 | Yes | Auto Scheduled | Update Process Flow | 10 days | July 23, 2019 8:00 AM | August 5, 2019 5:00 PM | 2019-08-05 | 1 | 3438 | 4
3440 | Yes | Auto Scheduled | Process Flow Review | 10 days | August 6, 2019 8:00 AM | August 19, 2019 5:00 PM | 2019-08-19 | 1 | 3439 | 4
3441 | Yes | Auto Scheduled | PV Tooling | 144 days | March 14, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 3
3442 | Yes | Auto Scheduled | Visor | 97 days | March 28, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 4
3443 | Yes | Auto Scheduled | Tooling | 58 days | March 28, 2019 8:00 AM | June 17, 2019 5:00 PM | 2019-06-17 | 1 |  | 5
3444 | Yes | Auto Scheduled | Tunning | 18 days | June 17, 2019 8:00 AM | July 10, 2019 5:00 PM | 2019-07-10 | 1 |  | 5
3445 | Yes | Auto Scheduled | Graining | 20 days | July 15, 2019 8:00 AM | August 9, 2019 5:00 PM | 2019-08-09 | 1 |  | 5
3446 | Yes | Auto Scheduled | Outer Case | 58 days | March 14, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 4
3447 | Yes | Auto Scheduled | Tooling | 37 days | March 14, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 5
3448 | Yes | Auto Scheduled | Tunning | 21 days | May 6, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 5
3449 | Yes | Auto Scheduled | Chrome Ring | 64 days | April 4, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 |  | 4
3450 | Yes | Auto Scheduled | Tooling | 41 days | April 4, 2019 8:00 AM | May 30, 2019 5:00 PM | 2019-05-30 | 1 |  | 5
3451 | Yes | Auto Scheduled | Tunning | 23 days | May 31, 2019 8:00 AM | July 2, 2019 5:00 PM | 2019-07-02 | 1 |  | 5
3452 | Yes | Auto Scheduled | Lens | 58 days | March 14, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 4
3453 | Yes | Auto Scheduled | Tooling | 37 days | March 14, 2019 8:00 AM | May 3, 2019 5:00 PM | 2019-05-03 | 1 |  | 5
3454 | Yes | Auto Scheduled | Tunning | 21 days | May 6, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 |  | 5
3455 | Yes | Auto Scheduled | OB Jig | 45 days | May 6, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 |  | 4
3456 | Yes | Auto Scheduled | Tooling | 40 days | May 6, 2019 8:00 AM | June 28, 2019 5:00 PM | 2019-06-28 | 1 |  | 5
3457 | Yes | Auto Scheduled | Tunning | 1 day | July 5, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 |  | 5
3458 | Yes | Auto Scheduled | Laser Welding | 84 days | April 2, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 4
3459 | Yes | Auto Scheduled | Tooling | 54 days | April 2, 2019 8:00 AM | June 14, 2019 5:00 PM | 2019-06-14 | 1 |  | 5
3460 | Yes | Auto Scheduled | Modifcation as per supplier request | 1 day | July 12, 2019 8:00 AM | July 12, 2019 5:00 PM | 2019-07-12 | 1 |  | 5
3461 | Yes | Auto Scheduled | Drawing / 3D release | 5 days | July 15, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 | 3460 | 5
3462 | Yes | Auto Scheduled | Tunning | 15 days | July 1, 2019 8:00 AM | July 19, 2019 5:00 PM | 2019-07-19 | 1 |  | 5
3463 | Yes | Auto Scheduled | Trial with modified tooling | 5 days | July 22, 2019 8:00 AM | July 26, 2019 5:00 PM | 2019-07-26 | 1 | 3462 | 5
3464 | Yes | Auto Scheduled | ICT | 29 days | May 6, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 4
3465 | Yes | Auto Scheduled | Deliver to SHNS | 29 days | May 6, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 5
3466 | Yes | Auto Scheduled | FTC | 104 days | May 9, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 4
3467 | Yes | Auto Scheduled | Deliver to SHNS | 104 days | May 9, 2019 8:00 AM | October 1, 2019 5:00 PM | 2019-10-01 | 0 |  | 5
3468 | Yes | Auto Scheduled | Shipping components | 1 wk | August 14, 2019 8:00 AM | August 21, 2019 8:00 AM | 2019-08-21 | 1 | 3469SF | 3
3469 | Yes | Auto Scheduled | PV Parts Build | 1 wk | August 21, 2019 8:00 AM | August 28, 2019 8:00 AM | 2019-08-28 | 0 | 3470SF | 3
3470 | Yes | Auto Scheduled | PV Parts Shipping | 1 wk | August 28, 2019 8:00 AM | September 4, 2019 8:00 AM | 2019-09-04 | 0 | 3472SF-1w | 3
3471 | Yes | Auto Scheduled | Production Validation - PV | 103 days | September 11, 2019 8:00 AM | January 31, 2020 5:00 PM | 2020-01-31 | 0 |  | 1
3472 | Yes | Auto Scheduled | PV Testing | 18 wks | September 11, 2019 8:00 AM | January 31, 2020 8:00 AM | 2020-01-31 | 0 | 19SF-4w | 2
3473 | Yes | Auto Scheduled | Production 1 Meeting | 1 day | January 31, 2020 8:00 AM | January 31, 2020 5:00 PM | 2020-01-31 | 0 | 3472 | 2
3474 | Yes | Auto Scheduled | Matching 1 and 2 | 376 days | March 22, 2019 8:00 AM | August 28, 2020 5:00 PM | 2020-08-28 | 0 |  | 1
3475 | Yes | Auto Scheduled | Production 2 Meeting | 1 day | March 27, 2020 8:00 AM | March 27, 2020 5:00 PM | 2020-03-27 | 0 |  | 2
3476 | Yes | Auto Scheduled | Receive M1 PO from customer | 0 days | March 22, 2019 5:00 PM | March 22, 2019 5:00 PM | 2019-03-22 | 1 |  | 2
3477 | Yes | Auto Scheduled | Sales issues PO to SHNS | 7 days | March 22, 2019 8:00 AM | April 1, 2019 5:00 PM | 2019-04-01 | 1 |  | 2
3478 | Yes | Auto Scheduled | SHNS Deliver M1 parts to Customer | 12 wks | April 2, 2019 8:00 AM | June 24, 2019 5:00 PM | 2019-06-24 | 1 |  | 2
3479 | Yes | Auto Scheduled | SHNS provides measurement data per matching 1 requirements | 12 wks | March 22, 2019 8:00 AM | June 13, 2019 5:00 PM | 2019-06-13 | 1 |  | 2
3480 | Yes | Auto Scheduled | Matching 1 MRD | 0 days | June 1, 2020 5:00 PM | June 1, 2020 5:00 PM | 2020-06-01 | 0 | 13,3520 | 2
3481 | Yes | Auto Scheduled | Receive M2 PO from customer | 1 day | July 3, 2019 8:00 AM | July 5, 2019 5:00 PM | 2019-07-05 | 1 |  | 2
3482 | Yes | Auto Scheduled | Sales issues PO to SHNS | 1 day | July 8, 2019 8:00 AM | July 8, 2019 5:00 PM | 2019-07-08 | 1 |  | 2
3483 | Yes | Auto Scheduled | SHNS Deliver M2 parts to Customer | 12 wks | July 9, 2019 8:00 AM | September 30, 2019 5:00 PM | 2019-09-30 | 0 |  | 2
3484 | Yes | Auto Scheduled | SHNS provides measurement data per matching 2 requirements | 12 wks | July 9, 2019 8:00 AM | September 30, 2019 5:00 PM | 2019-09-30 | 0 |  | 2
3485 | Yes | Auto Scheduled | Matching 2 MRD | 0 days | August 28, 2020 5:00 PM | August 28, 2020 5:00 PM | 2020-08-28 | 0 | 16,3523 | 2
3486 | Yes | Auto Scheduled | Archival/Retention Request to NSI IT Team for E3 Project | 0 days | August 17, 2020 8:00 AM | August 17, 2020 8:00 AM | 2020-08-17 | 0 | 23 | 2
3487 | Yes | Auto Scheduled | PPAP NS | 0 days | April 20, 2018 5:00 PM | April 20, 2018 5:00 PM | 2018-04-20 | 1 |  | 1
3488 | Yes | Auto Scheduled | PPAP 1411 sub | 0 days | April 20, 2018 5:00 PM | April 20, 2018 5:00 PM | 2018-04-20 | 1 |  | 2
3489 | Yes | Auto Scheduled | PPV Release Release to plant | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 1
3490 | Yes | Auto Scheduled | PPV - TWN Release for SW to plant | 0 days | July 26, 2019 5:00 PM | July 26, 2019 5:00 PM | 2019-07-26 | 1 |  | 2
3491 | Yes | Auto Scheduled | Project Closure | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 1
3492 | Yes | Auto Scheduled | Obtain Customer Acceptance Note | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3493 | Yes | Auto Scheduled | Summarize Project Results and Lessons Learned | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3494 | Yes | Auto Scheduled | Review and Recognize Team Performance | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3495 | Yes | Auto Scheduled | Project Work Products move to Project Learning Database | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3496 | Yes | Auto Scheduled | Update the RAID Log and disposition any open items and Move it to Risk Database | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3497 | Yes | Auto Scheduled | Review and Reconcile Financial Performance | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3498 | Yes | Auto Scheduled | Update the PCE and disposition the unresolved changes | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3499 | Yes | Auto Scheduled | Close all the Action items raised in the Project | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3500 | Yes | Auto Scheduled | Close the Audit NCs and Observation | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3501 | Yes | Auto Scheduled | Archive all the Project Records (EQA Audit Reports, Review Reports , Test Reports, Analysis Reports, Work Product Audit Reports, Status Reports, Sub Contractor Status Report) | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3502 | Yes | Auto Scheduled | Renew / Close the Supplier contracts | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3503 | Yes | Auto Scheduled | Provide Subcontractor performance feedback | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3504 | Yes | Auto Scheduled | Close the Project Budget | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3505 | Yes | Auto Scheduled | Release the Resources for other project / activities | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3506 | Yes | Auto Scheduled | Conduct Closure Audit and ensure the audit issues are closed | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3507 | Yes | Auto Scheduled | Conduct the Project Closure Meeting | 1 day | March 2, 2020 8:00 AM | March 2, 2020 5:00 PM | 2020-03-02 | 0 |  | 2
3508 | [6 empty] | #VALUE! | #VALUE! |  | 2
3509 | Yes | Auto Scheduled | E2YB - Program Manegement Timing | 1139 days? | January 17, 2017 12:00 AM | May 31, 2021 5:00 PM | 2021-05-31 | 0 |  | 1 | PCE 012 Implementation Time Line
3510 | Yes | Auto Scheduled | GM Milestones MY21 EU2B | 710 days | September 11, 2018 8:00 AM | May 31, 2021 5:00 PM | 2021-05-31 | 0 |  | 2
3511 | Yes | Auto Scheduled | Styling Freeze (SF) | 0 days | September 11, 2018 8:00 AM | September 11, 2018 8:00 AM | 2018-09-11 | 1 |  | 3
3512 | Yes | Auto Scheduled | IDR (Initial Data Release) | 0 days | January 25, 2019 5:00 PM | January 25, 2019 5:00 PM | 2019-01-25 | 1 |  | 3 | Internal to GM
3513 | Yes | Auto Scheduled | Integration Bench MRD/P-Release | 0 days | April 15, 2019 5:00 PM | April 15, 2019 5:00 PM | 2019-04-15 | 1 |  | 3
3514 | Yes | Auto Scheduled | Verified Data Release (VDR) | 0 days | April 19, 2019 5:00 PM | April 19, 2019 5:00 PM | 2019-04-19 | 1 |  | 3
3515 | Yes | Auto Scheduled | Electrical A-Frame MRD | 0 days | June 24, 2019 5:00 PM | June 24, 2019 5:00 PM | 2019-06-24 | 1 |  | 3
3516 | Yes | Auto Scheduled | IVER MRD | 0 days | August 12, 2019 5:00 PM | August 12, 2019 5:00 PM | 2019-08-12 | 1 |  | 3
3517 | Yes | Auto Scheduled | 65% Buyoff Ride | 0 days | January 17, 2020 5:00 PM | January 17, 2020 5:00 PM | 2020-01-17 | 0 |  | 3
3518 | Yes | Auto Scheduled | 80% Buyoff Ride | 0 days | June 26, 2020 5:00 PM | June 26, 2020 5:00 PM | 2020-06-26 | 0 |  | 3
3519 | Yes | Auto Scheduled | 100% Buyoff Ride | 0 days | December 4, 2020 5:00 PM | December 4, 2020 5:00 PM | 2020-12-04 | 0 |  | 3
3520 | Yes | Auto Scheduled | Matching 1 MRD | 0 days | June 1, 2020 5:00 PM | June 1, 2020 5:00 PM | 2020-06-01 | 0 |  | 3
3521 | Yes | Auto Scheduled | NCT / OTS GM MRD | 0 days | June 19, 2020 5:00 PM | June 19, 2020 5:00 PM | 2020-06-19 | 0 |  | 3
3522 | Yes | Auto Scheduled | PPV MRD | 0 days | August 28, 2020 5:00 PM | August 28, 2020 5:00 PM | 2020-08-28 | 0 |  | 3
3523 | Yes | Auto Scheduled | Matching 2 MRD | 0 days | August 28, 2020 5:00 PM | August 28, 2020 5:00 PM | 2020-08-28 | 0 |  | 3
3524 | Yes | Auto Scheduled | PPAP NS | 0 days | June 15, 2020 5:00 PM | June 15, 2020 5:00 PM | 2020-06-15 | 0 |  | 3
3525 | Yes | Auto Scheduled | MVB-NS MRD | 0 days | December 11, 2020 5:00 PM | December 11, 2020 5:00 PM | 2020-12-11 | 0 |  | 3
3526 | Yes | Auto Scheduled | Validation Testing Complete (VTC MRD) | 0 days | December 11, 2020 5:00 PM | December 11, 2020 5:00 PM | 2020-12-11 | 0 |  | 3
3527 | Yes | Auto Scheduled | PPAP Gate Final | 0 days | February 5, 2021 5:00 PM | February 5, 2021 5:00 PM | 2021-02-05 | 0 |  | 3
3528 | Yes | Auto Scheduled | Validation Documentation Complete (VDC) | 0 days | January 22, 2021 5:00 PM | January 22, 2021 5:00 PM | 2021-01-22 | 0 |  | 3
3529 | Yes | Auto Scheduled | MVB-S (ManVal Saleable) MRD | 0 days | February 19, 2021 5:00 PM | February 19, 2021 5:00 PM | 2021-02-19 | 0 |  | 3
3530 | Yes | Auto Scheduled | SORP | 0 days | May 31, 2021 5:00 PM | May 31, 2021 5:00 PM | 2021-05-31 | 0 |  | 3
3531 | Yes | Auto Scheduled | Quality Gate Reviews | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 2
3532 | Yes | Auto Scheduled | QG1 & QG2 - Concept Design Review | 1 day | January 17, 2019 8:00 AM | January 17, 2019 5:00 PM | 2019-01-17 | 1 |  | 3
3533 | No | Auto Scheduled | QG3 - Prototype Design Review | 1 day | May 14, 2018 8:00 AM | May 14, 2018 5:00 PM | 2018-05-14 | 1 |  | 3 | QGs for this program will be tracked and documented as part of the lead E2UB
3534 | No | Auto Scheduled | QG4 - DV Test Readiness Review | 1 day | September 13, 2018 8:00 AM | September 13, 2018 5:00 PM | 2018-09-13 | 1 |  | 3 | QGs for this program will be tracked and documented as part of the lead E2UB
3535 | No | Auto Scheduled | QG5 - Production Design Review | 1 day | May 10, 2019 8:00 AM | May 10, 2019 5:00 PM | 2019-05-10 | 1 |  | 3 | QGs for this program will be tracked and documented as part of the lead E2UB
3536 | No | Auto Scheduled | QG6 - PV Test Readiness Review | 1 day | October 18, 2019 8:00 AM | October 18, 2019 5:00 PM | 2019-10-18 | 0 |  | 3 | QGs for this program will be tracked and documented as part of the lead E2UB
3537 | No | Auto Scheduled | QG7 - Production Launch Review | 1 day | February 28, 2020 8:00 AM | February 28, 2020 5:00 PM | 2020-02-28 | 0 |  | 3 | QGs for this program will be tracked and documented as part of the lead E2UB
3538 | Yes | Auto Scheduled | Kick Off meeting | 0 days | January 11, 2019 8:00 AM | January 11, 2019 8:00 AM | 2019-01-11 | 1 |  | 2
3539 | No | Auto Scheduled | Bench MRD | 649 days | January 17, 2017 8:00 AM | July 16, 2019 8:00 AM | 2019-07-16 | 1 |  | 2
3540 | No | Auto Scheduled | GM Questionnaires and Procedure | 649 days | January 17, 2017 8:00 AM | July 16, 2019 8:00 AM | 2019-07-16 | 1 |  | 3
3541 | No | Auto Scheduled | CG4090 - HSCAN Questionnaire | 2 wks | March 12, 2019 8:00 AM | March 26, 2019 8:00 AM | 2019-03-26 | 1 | 3543SF | 4
3542 | No | Auto Scheduled | CG4090 - HSCAN Questionnaire - GM Approval | 4 wks | March 26, 2019 8:00 AM | April 22, 2019 5:00 PM | 2019-04-22 | 1 | 3541 | 4
3543 | No | Auto Scheduled | CG4080 - LIN Questionnaire | 2 wks | March 26, 2019 8:00 AM | April 9, 2019 8:00 AM | 2019-04-09 | 1 | 3545SF | 4
3544 | No | Auto Scheduled | CG4080 - LIN Questionnaire - GM Approval | 4 wks | April 9, 2019 8:00 AM | May 6, 2019 5:00 PM | 2019-05-06 | 1 | 3543 | 4
3545 | No | Auto Scheduled | CG4077 - Ethernet Questionnaire | 2 wks | April 9, 2019 8:00 AM | April 23, 2019 8:00 AM | 2019-04-23 | 1 | 3547SF | 4
3546 | No | Auto Scheduled | CG4077 - Ethernet Questionnaire - GM Approval | 4 wks | April 23, 2019 8:00 AM | May 20, 2019 5:00 PM | 2019-05-20 | 1 | 3545 | 4
3547 | No | Auto Scheduled | CG4073 - Global B Diagnostic validation Questionnaire | 2 wks | April 23, 2019 8:00 AM | May 7, 2019 8:00 AM | 2019-05-07 | 1 | 3549SF | 4
3548 | No | Auto Scheduled | CG4073 - Global B Diagnostic validation Questionnaire - GM Approval | 4 wks | May 7, 2019 8:00 AM | June 3, 2019 5:00 PM | 2019-06-03 | 1 | 3547 | 4
3549 | No | Auto Scheduled | CG4748 - OTA Test Plan | 2 wks | May 7, 2019 8:00 AM | May 21, 2019 8:00 AM | 2019-05-21 | 1 | 3551SF | 4
3550 | No | Auto Scheduled | CG4748 - OTA Test Plan - GM Approval | 4 wks | May 21, 2019 8:00 AM | June 17, 2019 5:00 PM | 2019-06-17 | 1 | 3549 | 4
3551 | No | Auto Scheduled | CG4879 - Test Plan | 2 wks | May 21, 2019 8:00 AM | June 4, 2019 8:00 AM | 2019-06-04 | 1 | 3553SF | 4
3552 | No | Auto Scheduled | CG4879 - Test Plan - GM Approval | 4 wks | June 4, 2019 8:00 AM | July 1, 2019 5:00 PM | 2019-07-01 | 1 | 3551 | 4
3553 | No | Auto Scheduled | CG4111 - Global B Serial Data and Diagnostics Test Plan | 2 wks | June 4, 2019 8:00 AM | June 18, 2019 8:00 AM | 2019-06-18 | 1 | 3554SF | 4
3554 | No | Auto Scheduled | CG4111 - Global B Serial Data and Diagnostics Test Plan - GM Approval | 4 wks | June 18, 2019 8:00 AM | July 16, 2019 8:00 AM | 2019-07-16 | 1 | 3516SF-4w | 4
3555 | No | Auto Scheduled | GMW17219 Open Source Document Process (IVER) | 2 wks | January 17, 2017 8:00 AM | January 30, 2017 5:00 PM | 2017-01-30 | 1 |  | 4
3556 | No | Auto Scheduled | GMW17219 Open Source Document Process (VTC) | 2 wks | January 17, 2017 8:00 AM | January 30, 2017 5:00 PM | 2017-01-30 | 1 |  | 4
3557 | No | Auto Scheduled | Systems | 10 days | April 12, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 |  | 4
3558 | No | Auto Scheduled | Systems Requirement Specification | 10 days | April 12, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 |  | 5
3559 | No | Auto Scheduled | Update SRS | 2 wks | April 12, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 | 3560SF | 6
3560 | No | Auto Scheduled | Release SRS | 0 days | April 26, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 | 3565SF-1w | 6
3561 | No | Auto Scheduled | Systems Architecture Design | 10 days | April 12, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 |  | 5
3562 | No | Auto Scheduled | Update SAD | 2 wks | April 12, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 | 3560SF | 6
3563 | No | Auto Scheduled | Release SAD | 0 days | April 26, 2019 8:00 AM | April 26, 2019 8:00 AM | 2019-04-26 | 1 | 3565SF-1w | 6
3564 | No | Auto Scheduled | Mechanial | 15 days | May 3, 2019 8:00 AM | May 24, 2019 8:00 AM | 2019-05-24 | 1 |  | 4
3565 | No | Auto Scheduled | Applique Deisng Freeze | 0 days | May 3, 2019 8:00 AM | May 3, 2019 8:00 AM | 2019-05-03 | 1 | 3566SF | 5
3566 | No | Auto Scheduled | Applique Mechanical Review | 2 wks | May 3, 2019 8:00 AM | May 17, 2019 8:00 AM | 2019-05-17 | 1 | 3567SF | 5
3567 | No | Auto Scheduled | Applique JPN review | 1 wk | May 17, 2019 8:00 AM | May 24, 2019 8:00 AM | 2019-05-24 | 1 | 3578SF | 5
3568 | No | Auto Scheduled | Manufacturing | 15 days | March 22, 2019 8:00 AM | April 12, 2019 8:00 AM | 2019-04-12 | 1 |  | 4 | Alex Debek confirmed bench pars are not neded
3569 | No | Auto Scheduled | Bench Sample Build | 2 wks | March 22, 2019 8:00 AM | April 5, 2019 8:00 AM | 2019-04-05 | 1 | 3570SF | 5 | Alex Debek confirmed bench pars are not neded
3570 | No | Auto Scheduled | Bench Sample Ship to GM | 1 wk | April 5, 2019 8:00 AM | April 12, 2019 8:00 AM | 2019-04-12 | 1 | 3513SF-2d | 5
3571 | Yes | Auto Scheduled | IVER | 667 days? | January 17, 2017 12:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 |  | 2
3572 | Yes | Auto Scheduled | Mechanical Design | 0 days? | January 17, 2017 12:00 AM | January 17, 2017 12:00 AM | 2017-01-17 | 1 |  | 3
3573 | No | Auto Scheduled | Variation List | 1 day? | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
3574 | No | Auto Scheduled | BOM | 1 day? | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
3575 | No | Auto Scheduled | LED management sheet | 1 day? | January 17, 2017 8:00 AM | January 17, 2017 5:00 PM | 2017-01-17 | 1 |  | 4
3576 | Yes | Auto Scheduled | Tooling | 55 days | May 24, 2019 8:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 |  | 3
3577 | Yes | Auto Scheduled | Applique tooling | 55 days | May 24, 2019 8:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 |  | 4
3578 | Yes | Auto Scheduled | Film& Drawing Preparation | 2 wks | May 24, 2019 8:00 AM | June 7, 2019 8:00 AM | 2019-06-07 | 1 | 3579SF | 5
3579 | Yes | Auto Scheduled | Screen preparation and printing | 2 wks | June 7, 2019 8:00 AM | June 21, 2019 8:00 AM | 2019-06-21 | 1 | 3580SF | 5
3580 | Yes | Auto Scheduled | Forming and applique blank tooling lead time | 5 wks | June 21, 2019 8:00 AM | July 30, 2019 8:00 AM | 2019-07-30 | 1 | 3581SF | 5
3581 | No | Auto Scheduled | forming and punching | 2 wks | July 16, 2019 8:00 AM | July 30, 2019 8:00 AM | 2019-07-30 | 1 | 3582SF | 5
3582 | Yes | Auto Scheduled | applique - shipping to OB supplier | 3 days | July 30, 2019 8:00 AM | August 2, 2019 8:00 AM | 2019-08-02 | 1 | 3583SF | 5
3583 | Yes | Auto Scheduled | Applique shipping to NSII for LEG2 and LEG6 - no OB required | 1 wk | August 2, 2019 8:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 | 3593SF | 5
3584 | No | Auto Scheduled | Software | 37 days | May 1, 2019 8:00 AM | June 21, 2019 8:00 AM | 2019-06-21 | 1 |  | 3
3585 | No | Auto Scheduled | 22.22.xxx software development | 4 wks | May 1, 2019 8:00 AM | May 29, 2019 8:00 AM | 2019-05-29 | 1 | 3586SF | 4
3586 | No | Auto Scheduled | Internal Release | 0 days | May 29, 2019 8:00 AM | May 29, 2019 8:00 AM | 2019-05-29 | 1 | 3587SF | 4
3587 | No | Auto Scheduled | Software Validation/Verification | 2 wks | May 29, 2019 8:00 AM | June 12, 2019 8:00 AM | 2019-06-12 | 1 | 3588SF | 4
3588 | No | Auto Scheduled | Release to GM | 0 days | June 12, 2019 8:00 AM | June 12, 2019 8:00 AM | 2019-06-12 | 1 | 3589SF | 4
3589 | No | Auto Scheduled | DIT | 1 wk | June 12, 2019 8:00 AM | June 19, 2019 8:00 AM | 2019-06-19 | 1 | 3592SF-2d | 4
3590 | No | Auto Scheduled | TWN Request | 1 day | June 20, 2019 8:00 AM | June 21, 2019 8:00 AM | 2019-06-21 | 1 | 3592SF | 4
3591 | No | Auto Scheduled | Manufacturing | 35 days | June 21, 2019 8:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 |  | 3
3592 | No | Auto Scheduled | TWN Release | 2 wks | June 21, 2019 8:00 AM | July 9, 2019 8:00 AM | 2019-07-09 | 1 | 3593SF-2w | 4
3593 | No | Auto Scheduled | IVER Samples Build | 2 wks | July 23, 2019 8:00 AM | August 6, 2019 8:00 AM | 2019-08-06 | 1 | 3594SF | 4
3594 | No | Auto Scheduled | IVER Samples Ship | 3 days | August 6, 2019 8:00 AM | August 9, 2019 8:00 AM | 2019-08-09 | 1 | 3516SF-2d | 4
3595 | No | Auto Scheduled | Implementation 2 (PV Design) | 82 days | November 19, 2018 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 2
3596 | No | Auto Scheduled | Verify VDC | 3 days | November 19, 2018 8:00 AM | November 21, 2018 5:00 PM | 2018-11-21 | 1 |  | 3
3597 | No | Auto Scheduled | Spec confirmation report to GM for approval | 10 days | December 3, 2018 8:00 AM | December 14, 2018 5:00 PM | 2018-12-14 | 1 |  | 3
3598 | No | Auto Scheduled | Material selection for production | 12 days | November 20, 2018 8:00 AM | December 7, 2018 5:00 PM | 2018-12-07 | 1 |  | 3
3599 | No | Auto Scheduled | Update VDC with GM feedback | 5 days | January 7, 2019 8:00 AM | January 11, 2019 5:00 PM | 2019-01-11 | 1 |  | 3
3600 | No | Auto Scheduled | Design Freeze | 0 days | November 19, 2018 8:00 AM | November 19, 2018 8:00 AM | 2018-11-19 | 1 |  | 3
3601 | No | Auto Scheduled | Mechanical Drawings (2Ds and 3Ds) | 62 days | November 19, 2018 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 |  | 3
3602 | No | Auto Scheduled | Applique | 6 wks | November 19, 2018 8:00 AM | January 15, 2019 5:00 PM | 2019-01-15 | 1 | 3600 | 4
3603 | No | Auto Scheduled | Review with suppliers | 4 wks | January 16, 2019 8:00 AM | February 12, 2019 5:00 PM | 2019-02-12 | 1 | 3602 | 4
3604 | No | Auto Scheduled | OK to Tool Drawing release to GM | 1 wk | February 13, 2019 8:00 AM | February 19, 2019 5:00 PM | 2019-02-19 | 1 | 3603 | 3
3605 | No | Auto Scheduled | OK to Tool Drawing approval by GM | 2 wks | February 20, 2019 8:00 AM | March 5, 2019 5:00 PM | 2019-03-05 | 1 | 3604 | 3
3606 | No | Auto Scheduled | Release Drawings to NS | 1 day | March 12, 2019 8:00 AM | March 12, 2019 5:00 PM | 2019-03-12 | 1 |  | 3
3607 | No | Auto Scheduled | Implementation 3 (PV Readiness) | 0 days | January 17, 2017 12:00 AM | January 17, 2017 12:00 AM | 2017-01-17 | 1 |  | 2
3608 | No | Auto Scheduled | Production Validation - PV | 0 wks | November 16, 2020 8:00 AM | November 16, 2020 8:00 AM | 2020-11-16 | 0 | 3526SF-4w | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Tharun Kumar | T | Work |  | Eng. - Software Engineering | Tharun.Kumar@nsgr-na.com | i:0#.w¦nsna\tkumar | 100% | $0.00/h | 0
2 | Jeff Skarb | J | Work |  | Eng. - Hardware Engineering | Jeff.Skarb@nsgr-na.com | i:0#.w¦nsna\jskarb | 100% | $0.00/h | 0
3 | Raj Gunaratnam | R | Work |  | Eng. - Software Engineering | Raj.Gunaratnam@nsgr-na.com | i:0#.w¦nsna\rgunaratnam | 100% | $0.00/h | 0
4 | Sachin Karkera | S | Work |  | Eng. - Software Engineering | Sachin.Karkera@nsgr-na.com | i:0#.w¦nsna\skarkera | 100% | $0.00/h | 0
5 | Rahul Kumar | R | Work |  | Eng. - Software Engineering | Rahul.Kumar@nsgr-na.com | i:0#.w¦nsna\rkumar | 100% | $0.00/h | 0
6 | Ni Zhang | N | Work |  | Eng. - Software Engineering | Ni.Zhang@nsgr-na.com | i:0#.w¦nsna\nzhang | 100% | $0.00/h | 0
7 | Neelima Gudem | N | Work |  | Eng. - Software Engineering | Neelima.Gudem@nsgr-na.com | i:0#.w¦nsna\ngudem | 100% | $0.00/h | 0
8 | Shamili Tummala | S | Work |  | Eng. - Software Engineering | Shamili.Tummala@nsgr-na.com | i:0#.w¦nsna\stummala | 100% | $0.00/h | 0
9 | Balaji Rao | BR | Work |  | Eng. - Software Engineering | Balaji.Rao@nsgr-na.com | i:0#.w¦nsna\brao | 100% | $0.00/h | 0
10 | Azad Mohammed | AM | Work |  | Eng. - Software Engineering | Azad.Mohammed@nsgr-na.com | i:0#.w¦nsna\amohammed | 100% | $0.00/h | 0
11 | Bishnu Raveendran | BR | Work |  | Eng. - Software Engineering | Bishnu.Raveendran@nsgr-na.com | i:0#.w¦nsna\braveendran | 100% | $0.00/h | 0
12 | NS | N | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Jiaqi Chen | J | Work |  |  | Jiaqi Chen |  | 100% | $0.00/h | 0
14 | Shailendra Jain | S | Work |  | Eng. - SW Validation & Verification | shailendra.jain@cognizant.com |  | 100% | $0.00/h | 0
15 | Anshuman Mittal | AM | Work |  | Eng. - Mechanical Eng. & Prototyping | Anshuman.Mittal@nsgr-na.com | NSNA\amittal | 100% | $0.00/h | 0
16 | Dmitry Ogorodnikov | D | Work |  | Eng. - SW Validation & Verification | Dmitry.Ogorodnikov@nsgr-na.com |  | 100% | $0.00/h | 0
17 | Leonardo Iratagotia | L | Work |  | Eng. - SW Validation & Verification | Leonardo.Iratagotia@nsgr-na.com |  | 100% | $0.00/h | 0
18 | Senthil Kumar | S | Work |  | Eng. - SW Validation & Verification | Senthil.Kumar@nsgr-na.com |  | 100% | $0.00/h | 0
19 | Akhtar Abbas | AA | Work |  | Eng. - SW Systems & Design | Akhtar Abbas |  | 100% | $0.00/h | 0
20 | Sumalatha Karthikeyan | S | Work |  | Eng. - SW Validation & Verification | Sumalatha Karthikeyan |  | 100% | $0.00/h | 0
21 | Ravi Ramachandrappa | R | Work |  | Eng. - SW Validation & Verification | Ravi Ramachandrappa |  | 100% | $0.00/h | 0
22 | Saravanan Natarajan | S | Work |  | Eng. - SW Validation & Verification | Saravanan.Natarajan@nsgr-na.com |  | 100% | $0.00/h | 0
23 | Hugo Nunez | H | Work |  | Eng. - Hardware Engineering | hugo.nunez@nsgr-na.com |  | 100% | $0.00/h | 0
24 | GM | G | Work |  |  |  |  | 100% | $0.00/h | 0
25 | Alejandro Lopez | AL | Work |  | Eng. - TPL | Alejandro Lopez |  | 100% | $0.00/h | 0
26 | Kristine Hiott | K | Work |  | Program Management | Kristine.Hiott@nsgr-na.com |  | 100% | $0.00/h | 0
27 | Iniyakumar Louis | I | Work |  | Eng. - SW Validation & Verification | Iniyakumar.Louis@nsgr-na.com |  | 100% | $0.00/h | 0
28 | Yoshio Tanaka | Y | Work |  | Eng. - Mechanical Eng. & Prototyping | Yoshio.Tanaka@nsgr-na.com |  | 100% | $0.00/h | 0
29 | Prabhu Kumar | P | Work |  | EQA | Prabhu.Kumar@nsgr-na.com |  | 100% | $0.00/h | 0
30 | Managers | M | Work |  |  |  |  | 100% | $0.00/h | 0
31 | Oscar Espinosa | OE | Work |  | Eng. - SW Validation & Verification | Oscar.Espinosa@nsgr-na.com |  | 100% | $0.00/h | 0
32 | Marco Sosa | M | Work |  | Eng. - TPL | Marco.Sosa@nsgr-na.com |  | 100% | $0.00/h | 0
33 | Antonio Jimenez | AJ | Work |  | Eng. - Hardware Engineering | Antonio.Jimenez@nsgr-na.com |  | 100% | $0.00/h | 0
34 | HCL | H | Work |  |  |  |  | 100% | $0.00/h | 0
35 | Devendra Takola | DT | Work |  | Eng. - SW Systems & Design | Devendra.Takola@nsgr-na.com |  | 100% | $0.00/h | 0
36 | Todd Burnett | T | Work |  | Test Lab | Todd.Burnett@nsgr-na.com |  | 100% | $0.00/h | 0
37 | David Fabila | D | Work |  | Eng. - Systems Engineering | David.Fabila@nsgr-na.com |  | 100% | $0.00/h | 0
38 | Sharmila Kokkera | S | Work |  | Eng. - SW Validation & Verification | Sharmila.Kokkera@nsgr-na.com |  | 100% | $0.00/h | 0
39 | ETAS | E | Work |  |  |  |  | 100% | $0.00/h | 0
40 | Karthikeyan Palanisamy | KP | Work |  | Eng. - Hardware Engineering | Karthikeyan.Palanisamy@nsgr-na.com |  | 100% | $0.00/h | 0
41 | Kunal Kulshrestha | K | Work |  | Eng. - SW Systems & Design | Kunal.Kulshrestha@nsgr-na.com |  | 100% | $0.00/h | 0
42 | Sabina lab | S | Work |  | Test Lab |  |  | 100% | $0.00/h | 0
43 | 3rd party lab | 3 | Work |  | Test Lab |  |  | 100% | $0.00/h | 0
44 | Troy lab | T | Work |  | Test Lab |  |  | 100% | $0.00/h | 0
45 | Sabina Lab (24h) | S | Work |  | Test Lab |  |  | 100% | $0.00/h | 0
46 | KPIT | K | Work |  |  |  |  | 100% | $0.00/h | 0
47 | Sonika | S | Work |  |  |  |  | 100% | $0.00/h | 0
48 | Donnie Baise | D | Work |  | Eng. - Mechanical Eng. & Prototyping | Donnie.Baise@nsgr-na.com |  | 100% | $0.00/h | 0
49 | Amrita Banjha | A | Work |  | ETAS | Amrita.Bhanja@escrypt.com |  | 100% | $0.00/h | 0
50 | Altia | A | Work |  |  |  |  | 100% | $0.00/h | 0
51 | GMTCI | G | Work |  |  |  |  | 100% | $0.00/h | 0
52 | Mauro Lopez | ML | Work |  | Eng. - Systems Engineering | Mauro.Lopez@nsgr-na.com |  | 100% | $0.00/h | 0
53 | Kalpana Dakshnamoorthy | K | Work |  | Eng. - Systems Engineering (HCL) | kalpana.d@hcl.com |  | 100% | $0.00/h | 0
54 | Mathukumar Kuthalingam | M | Work |  | Eng. - Systems Engineering (HCL) | mathukumar.k@hcl.com |  | 100% | $0.00/h | 0
55 | Rajalakshmi M | R | Work |  | Eng. - Systems Engineering (HCL) | M.Rajalakshmi@hcl.com |  | 100% | $0.00/h | 0
56 | John McShane | J | Work |  | ETAS | John.McShane@escrypt.com |  | 100% | $0.00/h | 0
57 | Thom Barber | T | Work |  | Test Lab | Thom.Barber@nsgr-na.com |  | 100% | $0.00/h | 0
58 | Grant Thomas | G | Work |  | Eng. - Software Engineering | Grant.Thomas@nsgr-na.com |  | 100% | $0.00/h | 0
59 | Arul Krishna | AK | Work |  | Eng. - Mechanical Eng. & Prototyping | Arul.Krishna@nsgr-na.com |  | 100% | $0.00/h | 0
60 | Andrea Nustad | A | Work |  | Sales | Andrea.Nustad@nsgr-na.com |  | 100% | $0.00/h | 0
61 | Victor Samson | V | Work |  | Eng. - Systems Engineering (HCL) | victorsamson.t@hcl.com |  | 100% | $0.00/h | 0
62 | Slavko Bogoevski | S | Work |  | Eng. - Hardware Engineering | Slavko.Bogoevski@nsgr-na.com |  | 100% | $0.00/h | 0
63 | Suga Ragunathan | S | Work |  | Eng. - Software Engineering | Suga.Ragunathan@nsgr-na.com |  | 100% | $0.00/h | 0
64 | Takaki Yoshida | T | Work |  | Eng. - Mechanical Eng. & Prototyping | Takaki.Yoshida@nsgr-na.com |  | 100% | $0.00/h | 0
65 | Jon Donegan | J | Work |  | Eng. - SW Validation & Verification | Jon.Donegan@nsgr-na.com |  | 100% | $0.00/h | 0
66 | Hideyuki Inaguma | H | Work |  |  | Hideyuki.Inaguma@nsgr-na.com |  | 100% | $0.00/h | 0
67 | Hemanth | H | Work |  |  |  |  | 100% | $0.00/h | 0
68 | Raymon Benjamin | R | Work |  | Eng. - Desing Release Engineering | Raymon.Benjamin@nsgr-na.com |  | 100% | $0.00/h | 0
69 | Amolshankar Saboji | A | Work |  | Eng. - Functional Safety | amolshankar.s@hcl.com |  | 100% | $0.00/h | 0
70 | Pradeep Kumar | P | Work |  | Eng. - Functional Safety | Pradeep.Kumar@nsgr-na.com |  | 100% | $0.00/h | 0
71 | Sibing Xu | S | Work |  | Eng. - Mechanical Eng. & Prototyping | Sibing.Xu@nsgr-na.com |  | 100% | $0.00/h | 0
72 | Mark Ho | M | Work |  | Eng. - Hardware Engineering | Mark.Ho@nsgr-na.com |  | 100% | $0.00/h | 0
73 | Paresh Dolas | P | Work |  | Eng. - Software Engineering | paresh.dolas@cognizant.com |  | 100% | $0.00/h | 0
74 | Anjaneyulu (HCL) | A | Work |  | Eng. - Systems Engineering (HCL) |  |  | 100% | $0.00/h | 0
75 | Bhargav (HCL) | B | Work |  | Eng. - Systems Engineering (HCL) |  |  | 100% | $0.00/h | 0
76 | Eshwaran (HCL) | E | Work |  | Eng. - Systems Engineering (HCL) |  |  | 100% | $0.00/h | 0
77 | Eliseo Flores | EF | Work |  | Eng. - Software Engineering | Eliseo.Flores@nsgr-na.com |  | 100% | $0.00/h | 0
78 | Nikhil Gupta | N | Work |  | Eng. - SW Validation & Verification | Nikhil.Gupta@nsgr-na.com |  | 100% | $0.00/h | 0
79 | Jyoti Billur | J | Work |  |  |  |  | 100% | $0.00/h | 0
80 | Jyothi K | J | Work |  |  |  |  | 100% | $0.00/h | 0
81 | Supplier | S | Work |  |  |  |  | 100% | $0.00/h | 0
82 | Sreenivas Naik | S | Work |  | Eng. - Software Engineering | Sreenivas.Naik@nsgr-na.com |  | 100% | $0.00/h | 0
83 | Navin Singh | N | Work |  | Eng. - Software Engineering | Navin.Singh@nsgr-na.com |  | 100% | $0.00/h | 0
84 | Nikhil Wakaley | N | Work |  | Eng. - Software Engineering | Nikhil.Wakaley@cognizant.com |  | 100% | $0.00/h | 0
85 | Priyanka Purbe | P | Work |  | Eng. - Software Engineering | Priyanka.Purbe@cognizant.com |  | 100% | $0.00/h | 0
86 | Krishnakumar Joshi | K | Work |  | Eng. - Software Engineering | krishnakumar.joshi@cognizant.com |  | 100% | $0.00/h | 0
87 | Kiran Khallenhali | K | Work |  | Eng. - Software Engineering | Kiran.Kallenahalli@nsgr-na.com |  | 100% | $0.00/h | 0
88 | Kazuhiko Kimura | K | Work |  |  | Kazuhiko.Kimura@nsgr-na.com |  | 100% | $0.00/h | 0
89 | Richard (GM) | R | Work |  |  |  |  | 100% | $0.00/h | 0
90 | Sajitha (GM) | S | Work |  |  |  |  | 100% | $0.00/h | 0
91 | Dayanand Kotla | D | Work |  | Eng. - SW Systems & Design | Dayanand.Kotla@nsgr-na.com |  | 100% | $0.00/h | 0
92 | Tetsuya Tsubame | T | Work |  | Eng. - Hardware Engineering | Tetsuya.Tsubame@nsgr-na.com |  | 100% | $0.00/h | 0
93 | Tien Nguyen | T | Work |  | Eng. - SW Validation & Verification | Tien.Nguyen@nsgr-na.com |  | 100% | $0.00/h | 0
94 | Hemangi Nehete | H | Work |  | Eng. - Software Engineering | Hemangi.Nehete@nsgr-na.com |  | 100% | $0.00/h | 0
95 | Cypress | C | Work |  |  |  |  | 100% | $0.00/h | 0
96 | Tooling Supplier | T | Work |  |  |  |  | 100% | $0.00/h | 0
97 | Supplier: Branson | S | Work |  |  |  |  | 100% | $0.00/h | 0
98 | Vignesh Sridhar | V | Work |  |  | vignesh.sridhar@nsgr-na.com |  | 100% | $0.00/h | 0
99 | Kaushik Narasimhan | K | Work |  |  | Kaushik.Narasimhan@nsgr-na.com |  | 100% | $0.00/h | 0
100 | Kunal Kulshrestha | K | Work |  |  | Kunal.Kulshrestha@nsgr-na.com |  | 100% | $0.00/h | 0
101 | Manufacturing JPN | M | Work |  |  |  |  | 100% | $0.00/h | 0
102 | Kazuhiko Kimura | K | Work |  |  | Kazuhiko.Kimura@nsgr-na.com |  | 100% | $0.00/h | 0
103 | Test Lab | T | Work |  | Test Lab |  |  | 100% | $0.00/h | 0
104 | Rajeshakar | R | Work |  |  |  |  | 100% | $0.00/h | 0
105 | Nagender | N | Work |  |  |  |  | 100% | $0.00/h | 0
106 | Kalyani | K | Work |  |  |  |  | 100% | $0.00/h | 0
107 | Lawrence Buie | L | Work |  |  |  |  | 100% | $0.00/h | 0
108 | Kannan Venkadachalam | K | Work |  |  | Kannan.Venkadachalam@nsgr-na.com |  | 100% | $0.00/h | 0
109 | NSJPN | N | Work |  |  |  |  | 100% | $0.00/h | 0
110 | Antonio Cacho | A | Work |  |  | Antonio.Cacho@nsgr-na.com |  | 100% | $0.00/h | 0
111 | Naveen Gujjari | N | Work |  |  | Naveen.Gujjari@nsgr-na.com |  | 100% | $0.00/h | 0
112 | Prasanth J | P | Work |  |  |  |  | 100% | $0.00/h | 0
113 | Mahalakshmi Thangasamy | M | Work |  |  | Mahalakshmi.Thangasamy@nsgr-na.com |  | 100% | $0.00/h | 0
114 | Gary Kempen | G | Work |  | Eng. - Systems Engineering | Gary.Kempen@nsgr-na.com |  | 100% | $0.00/h | 0
115 | Masanori Kaise | M | Work |  |  | Masanori.Kaise@nsgr-na.com |  | 100% | $0.00/h | 0
116 | Kevin G | K | Work |  |  |  |  | 100% | $0.00/h | 0
117 | Huaping Ni | H | Work |  |  |  |  | 100% | $0.00/h | 0
118 | K.Umezawa | K | Work |  |  | kumezawa@nippon-seiki.co.jp |  | 100% | $0.00/h | 0
119 | Ananda Kopalli | A | Work |  |  | Ananda.Kopalli@nsgr-na.com |  | 100% | $0.00/h | 0
120 | Dennis Shinkonis | D | Work |  | Eng - Resident Eng | Dennis.Shinkonis@nsgr-na.com |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Styling Freeze (SF) | GM | 1 | 0h | 100%
IDR (Initial Data Release) | GM | 1 | 0h | 100%
Integration Bench MRD/P-Release | GM | 1 | 0h | 100%
Verified Data Release (VDR) | GM | 0 | 0h | 100%
Electrical A-Frame MRD | GM | 1 | 0h | 100%
IVER MRD (E2UB-S) | GM | 1 | 0h | 100%
IVER MRD (E2UB-N) | GM | 1 | 0h | 100%
65% Buyoff Ride | GM | 1 | 0h | 100%
80% Buyoff Ride | GM | 0 | 0h | 100%
100% Buyoff Ride | GM | 0 | 0h | 100%
Matching 1 MRD | GM | 0 | 0h | 100%
NCT / OTS GM MRD | GM | 0 | 0h | 100%
PPV MRD | GM | 0 | 0h | 100%
Matching 2 MRD | GM | 0 | 0h | 100%
PPAP NS | GM | 0 | 0h | 100%
MVB-NS MRD | GM | 0 | 0h | 100%
MRD (Validation Testing Complete) | GM | 0 | 0h | 100%
PPAP Gate Final | GM | 0 | 0h | 100%
Validation Documentation Complete (VDC) | GM | 0 | 0h | 100%
MVB-S (ManVal Saleable) MRD | GM | 0 | 0h | 100%
SORP | GM | 0 | 0h | 100%
GM Bench Delivery Development | GM | 1 | 1,192h | 100%
Define BOM for Bench Sample (Mecha) | GM | 1 | 8h | 100%
Order C1UB board for bench | GM | 1 | 560h | 100%
Build bench sample | GM | 1 | 104h | 100%
Bench Sample MRD | GM | 1 | 0h | 100%
QG2 - Concept Design Review | Akhtar Abbas | 1 | 8h | 100%
QG2 - Concept Design Review | Anshuman Mittal | 1 | 8h | 100%
QG2 - Concept Design Review | Antonio Jimenez | 1 | 8h | 100%
QG2 - Concept Design Review | Mauro Lopez | 1 | 8h | 100%
QG2 - Concept Design Review | Prabhu Kumar | 1 | 0h | 100%
QG3 - Prototype Design Review | Akhtar Abbas | 1 | 8h | 100%
QG3 - Prototype Design Review | Anshuman Mittal | 1 | 8h | 100%
QG3 - Prototype Design Review | Antonio Jimenez | 1 | 8h | 100%
QG3 - Prototype Design Review | Mauro Lopez | 1 | 8h | 100%
QG3 - Prototype Design Review | Prabhu Kumar | 1 | 0h | 100%
QG4 - DV Test Readiness Review | Akhtar Abbas | 1 | 8h | 100%
QG4 - DV Test Readiness Review | Anshuman Mittal | 1 | 8h | 100%
QG4 - DV Test Readiness Review | Antonio Jimenez | 1 | 8h | 100%
QG4 - DV Test Readiness Review | Mauro Lopez | 1 | 8h | 100%
QG4 - DV Test Readiness Review | Prabhu Kumar | 1 | 0h | 100%
QG5 - Production Design Review | Akhtar Abbas | 1 | 8h | 100%
QG5 - Production Design Review | Anshuman Mittal | 1 | 8h | 100%
QG5 - Production Design Review | Antonio Jimenez | 1 | 8h | 100%
QG5 - Production Design Review | Mauro Lopez | 1 | 8h | 100%
QG5 - Production Design Review | Prabhu Kumar | 1 | 8h | 100%
QG6 - PV Test Readiness Review | Akhtar Abbas | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Anshuman Mittal | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Antonio Jimenez | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Mauro Lopez | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Prabhu Kumar | 0 | 8h | 100%
QG7 - Production Launch Review | Akhtar Abbas | 0 | 8h | 100%
QG7 - Production Launch Review | Anshuman Mittal | 0 | 8h | 100%
QG7 - Production Launch Review | Antonio Jimenez | 0 | 8h | 100%
QG7 - Production Launch Review | Mauro Lopez | 0 | 8h | 100%
QG7 - Production Launch Review | Prabhu Kumar | 0 | 8h | 100%
Internal PDT meeting 1 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 2 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 3 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 4 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 5 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 6 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 7 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 8 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 9 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 10 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 11 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 12 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 13 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 14 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 15 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 16 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 17 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 18 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 19 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 20 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 21 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 22 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 23 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 24 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 25 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 26 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 27 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 28 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 29 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 30 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 31 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 32 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 33 | Marco Sosa | 1 | 8h | 100%
Internal PDT meeting 34 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 35 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 36 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 37 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 38 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 39 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 40 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 41 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 42 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 43 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 44 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 45 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 46 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 47 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 48 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 49 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 50 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 51 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 52 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 53 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 54 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 55 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 56 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 57 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 58 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 59 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 60 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 61 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 62 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 63 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 64 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 65 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 66 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 67 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 68 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 69 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 70 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 71 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 72 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 73 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 74 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 75 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 76 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 77 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 78 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 79 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 80 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 81 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 82 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 83 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 84 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 85 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 86 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 87 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 88 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 89 | Marco Sosa | 0 | 8h | 100%
Internal PDT meeting 90 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 1 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 2 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 3 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 4 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 5 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 6 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 7 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 8 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 9 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 10 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 11 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 12 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 13 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 14 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 15 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 16 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 17 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 18 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 19 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 20 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 21 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 22 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 23 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 24 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 25 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 26 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 27 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 28 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 29 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 30 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 31 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 32 | Marco Sosa | 1 | 8h | 100%
Internal RAID meeting 33 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 34 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 35 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 36 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 37 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 38 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 39 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 40 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 41 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 42 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 43 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 44 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 45 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 46 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 47 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 48 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 49 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 50 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 51 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 52 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 53 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 54 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 55 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 56 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 57 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 58 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 59 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 60 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 61 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 62 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 63 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 64 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 65 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 66 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 67 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 68 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 69 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 70 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 71 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 72 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 73 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 74 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 75 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 76 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 77 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 78 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 79 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 80 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 81 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 82 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 83 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 84 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 85 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 86 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 87 | Marco Sosa | 0 | 8h | 100%
Internal RAID meeting 88 | Marco Sosa | 0 | 8h | 100%
NC Reporting and Closure 1 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 2 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 3 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 4 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 5 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 6 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 7 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 8 | Prabhu Kumar | 1 | 0h | 100%
NC Reporting and Closure 9 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 11 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 12 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 13 | Prabhu Kumar | 1 | 24h | 100%
NC Reporting and Closure 14 | Prabhu Kumar | 1 | 24h | 100%
NC Reporting and Closure 15 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 16 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 17 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 18 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 19 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 20 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 21 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 22 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 23 | Prabhu Kumar | 1 | 8h | 100%
NC Reporting and Closure 24 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 25 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 26 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 27 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 28 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 29 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 30 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 31 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 32 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 33 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 34 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 35 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 36 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 37 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 38 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 39 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 40 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 41 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 42 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 43 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 44 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 45 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 46 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 47 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 48 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 49 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 50 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 51 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 52 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 53 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 54 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 55 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 56 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 57 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 58 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 59 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 60 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 61 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 62 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 63 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 64 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 65 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 66 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 67 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 68 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 69 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 70 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 71 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 72 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 73 | Prabhu Kumar | 0 | 8h | 100%
NC Reporting and Closure 74 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 1 | Prabhu Kumar | 1 | 16h | 100%
QA Status Reporting 2 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 5 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 6 | Prabhu Kumar | 1 | 24h | 100%
QA Status Reporting 7 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 8 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 9 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 10 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 11 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 12 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 13 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 14 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 15 | Prabhu Kumar | 1 | 8h | 100%
QA Status Reporting 16 | Prabhu Kumar | 1 | 0h | 100%
QA Status Reporting 17 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 18 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 19 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 20 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 21 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 22 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 23 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 24 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 25 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 26 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 27 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 28 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 29 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 30 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 31 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 32 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 33 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 34 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 35 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 36 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 37 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 38 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 39 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 40 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 41 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 42 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 43 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 44 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 45 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 46 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 47 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 48 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 49 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 50 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 51 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 52 | Prabhu Kumar | 0 | 8h | 100%
QA Status Reporting 53 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit TPL 1 | Marco Sosa | 1 | 8h | 100%
QA Compliance Audit TPL 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit TPL 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit TPL 2 | Marco Sosa | 1 | 8h | 100%
QA Compliance Audit TPL 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit TPL 3 | Prabhu Kumar | 1 | 72h | 100%
QA Compliance Audit TPL 3 | Marco Sosa | 1 | 72h | 100%
QA Compliance Audit TPL 3 | Kaushik Narasimhan | 1 | 72h | 100%
QA Compliance Audit TPL 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit TPL 4 | Marco Sosa | 1 | 8h | 100%
QA Compliance Audit TPL 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit TPL 5 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 5 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 5 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 6 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 7 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 8 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 9 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 10 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 11 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 12 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 13 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 14 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 15 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 16 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit TPL 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit TPL 17 | Marco Sosa | 0 | 8h | 100%
QA Compliance Audit TPL 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SPL 1 | Akhtar Abbas | 1 | 8h | 100%
QA Compliance Audit SPL 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SPL 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SPL 2 | Akhtar Abbas | 1 | 8h | 100%
QA Compliance Audit SPL 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SPL 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SPL 3 | Akhtar Abbas | 1 | 8h | 100%
QA Compliance Audit SPL 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SPL 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SPL 4 | Akhtar Abbas | 1 | 8h | 100%
QA Compliance Audit SPL 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SPL 5 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 5 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 5 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 6 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 7 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 8 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 9 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 10 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 11 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 12 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 13 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 14 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 15 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 16 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SPL 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SPL 17 | Akhtar Abbas | 0 | 8h | 100%
QA Compliance Audit SPL 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Systems 1 | Mauro Lopez | 1 | 8h | 100%
QA Compliance Audit Systems 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Systems 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Systems 2 | Mauro Lopez | 1 | 8h | 100%
QA Compliance Audit Systems 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Systems 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Systems 3 | Mauro Lopez | 1 | 8h | 100%
QA Compliance Audit Systems 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Systems 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Systems 4 | Mauro Lopez | 1 | 8h | 100%
QA Compliance Audit Systems 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Systems 5 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Systems 5 | Mauro Lopez | 1 | 8h | 100%
QA Compliance Audit Systems 5 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Systems 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 6 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 7 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 8 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 9 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 10 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 11 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 12 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 13 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 14 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 15 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 16 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Systems 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Systems 17 | Mauro Lopez | 0 | 8h | 100%
QA Compliance Audit Systems 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 1 | Prabhu Kumar | 1 | 0h | 100%
QA Compliance Audit SW System 1 | Devendra Takola | 1 | 0h | 100%
QA Compliance Audit SW System 1 | Dmitry Ogorodnikov | 1 | 0h | 100%
QA Compliance Audit SW System 1 | Leonardo Iratagotia | 1 | 0h | 100%
QA Compliance Audit SW System 1 | Tien Nguyen | 1 | 0h | 100%
QA Compliance Audit SW System 1 | Kaushik Narasimhan | 1 | 0h | 100%
QA Compliance Audit SW System 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW System 2 | Devendra Takola | 1 | 8h | 100%
QA Compliance Audit SW System 2 | Dmitry Ogorodnikov | 1 | 8h | 100%
QA Compliance Audit SW System 2 | Leonardo Iratagotia | 1 | 8h | 100%
QA Compliance Audit SW System 2 | Tien Nguyen | 1 | 8h | 100%
QA Compliance Audit SW System 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Devendra Takola | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Dmitry Ogorodnikov | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Leonardo Iratagotia | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Tien Nguyen | 1 | 8h | 100%
QA Compliance Audit SW System 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Devendra Takola | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Dmitry Ogorodnikov | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Leonardo Iratagotia | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Tien Nguyen | 1 | 8h | 100%
QA Compliance Audit SW System 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW System 5 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 5 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 5 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 5 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 5 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 5 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Devendra Takola | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Dmitry Ogorodnikov | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Leonardo Iratagotia | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Tien Nguyen | 0 | 8h | 100%
QA Compliance Audit SW System 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 1 | Prabhu Kumar | 1 | 136h | 100%
QA Compliance Audit SW Design 1 | Eliseo Flores | 1 | 136h | 100%
QA Compliance Audit SW Design 1 | Neelima Gudem | 1 | 136h | 100%
QA Compliance Audit SW Design 1 | Sachin Karkera | 1 | 136h | 100%
QA Compliance Audit SW Design 1 | Kaushik Narasimhan | 1 | 136h | 100%
QA Compliance Audit SW Design 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Design 2 | Eliseo Flores | 1 | 8h | 100%
QA Compliance Audit SW Design 2 | Neelima Gudem | 1 | 8h | 100%
QA Compliance Audit SW Design 2 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit SW Design 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Design 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Design 3 | Eliseo Flores | 1 | 8h | 100%
QA Compliance Audit SW Design 3 | Neelima Gudem | 1 | 8h | 100%
QA Compliance Audit SW Design 3 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit SW Design 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Design 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Design 4 | Eliseo Flores | 1 | 8h | 100%
QA Compliance Audit SW Design 4 | Neelima Gudem | 1 | 8h | 100%
QA Compliance Audit SW Design 4 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit SW Design 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Design 5 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Design 5 | Eliseo Flores | 1 | 8h | 100%
QA Compliance Audit SW Design 5 | Neelima Gudem | 1 | 8h | 100%
QA Compliance Audit SW Design 5 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit SW Design 5 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Design 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 6 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 6 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 6 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 7 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 7 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 7 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 8 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 8 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 8 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 9 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 9 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 9 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 10 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 10 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 10 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 11 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 11 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 11 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 12 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 12 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 12 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 13 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 13 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 13 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 14 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 14 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 14 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 15 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 15 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 15 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 16 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 16 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 16 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Design 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Design 17 | Eliseo Flores | 0 | 8h | 100%
QA Compliance Audit SW Design 17 | Neelima Gudem | 0 | 8h | 100%
QA Compliance Audit SW Design 17 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit SW Design 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Validation 1 | Oscar Espinosa | 1 | 8h | 100%
QA Compliance Audit SW Validation 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Validation 2 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 2 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 2 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Validation 3 | Oscar Espinosa | 1 | 8h | 100%
QA Compliance Audit SW Validation 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Validation 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Validation 4 | Oscar Espinosa | 1 | 8h | 100%
QA Compliance Audit SW Validation 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Validation 5 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit SW Validation 5 | Oscar Espinosa | 1 | 8h | 100%
QA Compliance Audit SW Validation 5 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit SW Validation 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 6 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 7 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 8 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 9 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 10 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 11 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 12 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 13 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 14 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 15 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 16 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit SW Validation 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit SW Validation 17 | Oscar Espinosa | 0 | 8h | 100%
QA Compliance Audit SW Validation 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 1 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 1 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 1 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 1 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Hardware 2 | Antonio Jimenez | 1 | 8h | 100%
QA Compliance Audit Hardware 2 | Karthikeyan Palanisamy | 1 | 8h | 100%
QA Compliance Audit Hardware 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Hardware 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Hardware 3 | Antonio Jimenez | 1 | 8h | 100%
QA Compliance Audit Hardware 3 | Karthikeyan Palanisamy | 1 | 8h | 100%
QA Compliance Audit Hardware 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Hardware 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Hardware 4 | Antonio Jimenez | 1 | 8h | 100%
QA Compliance Audit Hardware 4 | Karthikeyan Palanisamy | 1 | 8h | 100%
QA Compliance Audit Hardware 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Hardware 5 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 5 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 5 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 5 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 6 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 6 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 7 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 7 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 8 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 8 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 9 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 9 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 10 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 10 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 11 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 11 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 12 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 12 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 13 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 13 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 14 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 14 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 15 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 15 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 16 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 16 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Hardware 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Hardware 17 | Antonio Jimenez | 0 | 8h | 100%
QA Compliance Audit Hardware 17 | Karthikeyan Palanisamy | 0 | 8h | 100%
QA Compliance Audit Hardware 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Mechanical 1 | Anshuman Mittal | 1 | 8h | 100%
QA Compliance Audit Mechanical 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Mechanical 2 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 2 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 2 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Mechanical 3 | Anshuman Mittal | 1 | 8h | 100%
QA Compliance Audit Mechanical 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Mechanical 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit Mechanical 4 | Anshuman Mittal | 1 | 8h | 100%
QA Compliance Audit Mechanical 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit Mechanical 5 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 5 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 5 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 6 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 7 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 8 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 9 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 10 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 11 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 12 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 13 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 14 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 15 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 16 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit Mechanical 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit Mechanical 17 | Anshuman Mittal | 0 | 8h | 100%
QA Compliance Audit Mechanical 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit CM 1 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit CM 1 | Vignesh Sridhar | 1 | 8h | 100%
QA Compliance Audit CM 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit CM 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit CM 2 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit CM 2 | Vignesh Sridhar | 1 | 8h | 100%
QA Compliance Audit CM 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit CM 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit CM 3 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit CM 3 | Vignesh Sridhar | 1 | 8h | 100%
QA Compliance Audit CM 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit CM 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit CM 4 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit CM 4 | Vignesh Sridhar | 1 | 8h | 100%
QA Compliance Audit CM 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit CM 5 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit CM 5 | Sachin Karkera | 1 | 8h | 100%
QA Compliance Audit CM 5 | Vignesh Sridhar | 1 | 8h | 100%
QA Compliance Audit CM 5 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit CM 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 6 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 6 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 7 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 7 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 8 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 8 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 9 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 9 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 9 | Kaushik Narasimhan | 0 | 16h | 100%
QA Compliance Audit CM 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 10 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 10 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 11 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 11 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 12 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 12 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 13 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 13 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 14 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 14 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 15 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 15 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 15 | Kaushik Narasimhan | 0 | 16h | 100%
QA Compliance Audit CM 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 16 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 16 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit CM 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit CM 17 | Sachin Karkera | 0 | 8h | 100%
QA Compliance Audit CM 17 | Vignesh Sridhar | 0 | 8h | 100%
QA Compliance Audit CM 17 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 1 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit EQA 1 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit EQA 2 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit EQA 2 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit EQA 3 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit EQA 3 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit EQA 4 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit EQA 4 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit EQA 5 | Prabhu Kumar | 1 | 8h | 100%
QA Compliance Audit EQA 5 | Kaushik Narasimhan | 1 | 8h | 100%
QA Compliance Audit EQA 6 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 6 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 7 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 7 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 8 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 8 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 9 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 9 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 10 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 10 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 11 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 11 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 12 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 12 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 13 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 13 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 14 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 14 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 15 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 15 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 16 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 16 | Kaushik Narasimhan | 0 | 8h | 100%
QA Compliance Audit EQA 17 | Prabhu Kumar | 0 | 8h | 100%
QA Compliance Audit EQA 17 | Kaushik Narasimhan | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 1 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 2 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 3 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 4 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 5 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 6 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 7 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 8 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 9 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 10 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 11 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 12 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 13 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 14 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 15 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 16 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 17 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 18 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 19 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 20 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 21 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 22 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 23 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 24 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 25 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 26 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 27 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 28 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 29 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 30 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 31 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 32 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 33 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 34 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 35 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 36 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 37 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 38 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 39 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 40 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 41 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 42 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 43 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 44 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 45 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 46 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 47 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 48 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 49 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 50 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 51 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 52 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 53 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 54 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 55 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 56 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 57 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 58 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 59 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 60 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 61 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 62 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 63 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 64 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 65 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 66 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 67 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 68 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 69 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 70 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 71 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 72 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 73 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 74 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 75 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 76 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 77 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 78 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 79 | Vignesh Sridhar | 1 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 80 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 81 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 82 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 83 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 84 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 85 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 86 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 87 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 88 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 89 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 90 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 91 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 92 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 93 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 94 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 95 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 96 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 97 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 98 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 99 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 100 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 101 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 102 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 103 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 104 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 105 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 106 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 107 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 108 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 109 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 110 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 111 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 112 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 113 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 114 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 115 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 116 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 117 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 118 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 119 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 120 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 121 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 122 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 123 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 124 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 125 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 126 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 127 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 128 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 129 | Vignesh Sridhar | 0 | 8h | 100%
SharePoint, DOORS and Document Approval Status Review 130 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 1 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 2 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 3 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 4 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 5 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 6 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 7 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 8 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 9 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 10 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 11 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 12 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 13 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 14 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 15 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 16 | Vignesh Sridhar | 1 | 8h | 100%
CM Audit and NC Closure 17 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 18 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 19 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 20 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 21 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 22 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 23 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 24 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 25 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 26 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 27 | Vignesh Sridhar | 0 | 8h | 100%
CM Audit and NC Closure 28 | Vignesh Sridhar | 0 | 8h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 1 | 352h | 100%
Work Product Review (CM) | Vignesh Sridhar | 1 | 312h | 100%
SharePoint Baseline Library Management activity | Vignesh Sridhar | 1 | 48h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 1 | 160h | 100%
Work Product Review (CM) | Vignesh Sridhar | 1 | 160h | 100%
SharePoint Baseline Library Management activity | Vignesh Sridhar | 1 | 16h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 1 | 24h | 100%
Work Product Review (CM) | Vignesh Sridhar | 1 | 8h | 100%
SharePoint Baseline Library Management activity | Vignesh Sridhar | 1 | 8h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 1 | 280h | 100%
Work Product Review (CM) | Vignesh Sridhar | 1 | 8h | 100%
SharePoint Baseline Library Management activity | Vignesh Sridhar | 1 | 16h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 0.80000000000000004 | 8h | 100%
Work Product Review (CM) | Vignesh Sridhar | 0.80000000000000004 | 24h | 100%
SharePoint Baseline Library Management activity | Vignesh Sridhar | 0 | 16h | 100%
CI list Updation - Baseline applicability & Version | Vignesh Sridhar | 0 | 152h | 100%
Work Product Review (CM) | Vignesh Sridhar | 0 | 16h | 100%
Create PMP | Alejandro Lopez | 1 | 120h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 16h | 100%
PMP Updated | Alejandro Lopez | 1 | 16h | 100%
PMP Peer Reviewed | Akhtar Abbas | 1 | 8h | 100%
PMP Peer Reviewed | Anshuman Mittal | 1 | 8h | 100%
PMP Peer Reviewed | Antonio Jimenez | 1 | 8h | 100%
PMP Peer Reviewed | Mauro Lopez | 1 | 8h | 100%
Approved by Managers | Managers | 1 | 48h | 100%
PMP Review Checklist | Akhtar Abbas | 1 | 16h | 100%
PMP Review Checklist | Anshuman Mittal | 1 | 16h | 100%
PMP Review Checklist | Antonio Jimenez | 1 | 16h | 100%
PMP Review Checklist | Mauro Lopez | 1 | 16h | 100%
PMP Update | Marco Sosa | 1 | 560h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 280h | 100%
PMP Update | Marco Sosa | 1 | 120h | 100%
PMP release | Marco Sosa | 1 | 24h | 100%
Scope update | Marco Sosa | 1 | 56h | 100%
Life cycle update | Marco Sosa | 1 | 144h | 100%
Trainign Plan update | Marco Sosa | 1 | 24h | 100%
Project governance update | Marco Sosa | 1 | 0h | 100%
Redmine life cycle update | Marco Sosa | 1 | 16h | 100%
Redmine life cycle update | Akhtar Abbas | 1 | 16h | 100%
PMP review/feedback | Alejandro Lopez | 1 | 40h | 100%
PMP review/feedback | Jon Donegan | 1 | 40h | 100%
PMP review/feedback | Slavko Bogoevski | 1 | 40h | 100%
PMP review/feedback | Arul Krishna | 1 | 40h | 100%
PMP review/feedback | Prabhu Kumar | 1 | 40h | 100%
PMP update based on feedback | Marco Sosa | 1 | 88h | 100%
PMP check list review | Alejandro Lopez | 1 | 232h | 100%
PMP check list review | Vignesh Sridhar | 1 | 232h | 100%
PMP check list review | Arul Krishna | 1 | 232h | 100%
PMP check list review | Jon Donegan | 1 | 232h | 100%
PMP check list review | Slavko Bogoevski | 1 | 232h | 100%
PMP update based on feedback | Marco Sosa | 1 | 40h | 100%
PMP Approval | Alejandro Lopez | 1 | 0h | 100%
PMP Approval | Vignesh Sridhar | 1 | 0h | 100%
Review of current PMP | Marco Sosa | 0 | 8h | 100%
Update PMP | Marco Sosa | 0 | 8h | 100%
PMP review/feedback | Alejandro Lopez | 0 | 16h | 100%
PMP review/feedback | Jon Donegan | 0 | 16h | 100%
PMP review/feedback | Slavko Bogoevski | 0 | 16h | 100%
PMP review/feedback | Arul Krishna | 0 | 16h | 100%
PMP review/feedback | Prabhu Kumar | 0 | 16h | 100%
PMP update based on feedback | Marco Sosa | 0 | 8h | 100%
PMP check list review | Alejandro Lopez | 0 | 8h | 100%
PMP check list review | Jon Donegan | 0 | 8h | 100%
PMP check list review | Slavko Bogoevski | 0 | 8h | 100%
PMP check list review | Arul Krishna | 0 | 8h | 100%
PMP check list review | Prabhu Kumar | 0 | 8h | 100%
PMP update based on feedback | Marco Sosa | 0 | 16h | 100%
PMP Approval | Alejandro Lopez | 0 | 40h | 100%
Develop Quality Assurance Plan | Prabhu Kumar | 1 | 192h | 100%
Review and Update of the QA Plan | Prabhu Kumar | 1 | 0h | 100%
Review and Update of the QA Plan | Prabhu Kumar | 1 | 136h | 100%
Review and Update of the QA Plan | Prabhu Kumar | 0 | 80h | 100%
Create PRMP | Alejandro Lopez | 1 | 56h | 100%
PRMP Peer Review | Akhtar Abbas | 1 | 16h | 100%
PRMP Peer Review | Anshuman Mittal | 1 | 16h | 100%
PRMP Peer Review | Antonio Jimenez | 1 | 16h | 100%
PRMP Peer Review | Mauro Lopez | 1 | 16h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 16h | 100%
PRMP Updated | Alejandro Lopez | 1 | 16h | 100%
Approved by Managers | Managers | 1 | 40h | 100%
PRMP Review Checklist | Akhtar Abbas | 1 | 16h | 100%
PRMP Review Checklist | Anshuman Mittal | 1 | 16h | 100%
PRMP Review Checklist | Antonio Jimenez | 1 | 16h | 100%
PRMP Review Checklist | Mauro Lopez | 1 | 16h | 100%
PRMP update | Marco Sosa | 1 | 32h | 100%
Review/Feedback via TPL workproduct list | Akhtar Abbas | 1 | 24h | 100%
Review/Feedback via TPL workproduct list | Alejandro Lopez | 1 | 24h | 100%
Review/Feedback via TPL workproduct list | Anshuman Mittal | 1 | 24h | 100%
Review/Feedback via TPL workproduct list | Antonio Jimenez | 1 | 24h | 100%
Review/Feedback via TPL workproduct list | Devendra Takola | 1 | 24h | 100%
Review/Feedback via TPL workproduct list | Eliseo Flores | 1 | 24h | 100%
PRMP update based on feedback | Marco Sosa | 1 | 8h | 100%
PRMP review Checklist | Alejandro Lopez | 1 | 248h | 100%
PRMP review Checklist | Akhtar Abbas | 1 | 248h | 100%
PRMP review Checklist | Anshuman Mittal | 1 | 248h | 100%
PRMP review Checklist | Antonio Jimenez | 1 | 248h | 100%
PRMP review Checklist | Eliseo Flores | 1 | 248h | 100%
PRMP review Checklist | Mauro Lopez | 1 | 248h | 100%
PRMP review Checklist | Vignesh Sridhar | 1 | 248h | 100%
PRMP update based on feedback | Marco Sosa | 1 | 24h | 100%
PRMP approval | Alejandro Lopez | 1 | 152h | 100%
PRMP approval | Vignesh Sridhar | 1 | 152h | 100%
PRMP approval | Arul Krishna | 1 | 152h | 100%
PRMP approval | Jon Donegan | 1 | 152h | 100%
PRMP approval | Slavko Bogoevski | 1 | 152h | 100%
PRMP update | Marco Sosa | 0 | 8h | 100%
Review/Feedback via TPL workproduct list | Akhtar Abbas | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Alejandro Lopez | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Anshuman Mittal | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Antonio Jimenez | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Devendra Takola | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Eliseo Flores | 0 | 16h | 100%
PRMP update based on feedback | Marco Sosa | 0 | 8h | 100%
PRMP review Checklist | Alejandro Lopez | 0 | 8h | 100%
PRMP review Checklist | Akhtar Abbas | 0 | 8h | 100%
PRMP review Checklist | Anshuman Mittal | 0 | 8h | 100%
PRMP review Checklist | Antonio Jimenez | 0 | 8h | 100%
PRMP review Checklist | Eliseo Flores | 0 | 8h | 100%
PRMP review Checklist | Mauro Lopez | 0 | 8h | 100%
PRMP review Checklist | Vignesh Sridhar | 0 | 8h | 100%
PRMP update based on feedback | Marco Sosa | 0 | 24h | 100%
PRMP approval | Alejandro Lopez | 0 | 40h | 100%
PRMP approval | Vignesh Sridhar | 0 | 40h | 100%
PRMP approval | Arul Krishna | 0 | 40h | 100%
PRMP approval | Jon Donegan | 0 | 40h | 100%
PRMP approval | Slavko Bogoevski | 0 | 40h | 100%
Health Report | Alejandro Lopez | 1 | 8h | 100%
Update RAID Log and clean file | Alejandro Lopez | 1 | 240h | 100%
Update Change Management Plan | Alejandro Lopez | 1 | 120h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 16h | 100%
CMP Updated | Alejandro Lopez | 1 | 16h | 100%
CMP Peer Reviewed | Akhtar Abbas | 1 | 8h | 100%
CMP Peer Reviewed | Anshuman Mittal | 1 | 8h | 100%
CMP Peer Reviewed | Antonio Jimenez | 1 | 8h | 100%
CMP Peer Reviewed | Mauro Lopez | 1 | 8h | 100%
Approved by Managers | Managers | 1 | 48h | 100%
CMP Review Checklist | Akhtar Abbas | 1 | 1,056h | 100%
CMP Review Checklist | Anshuman Mittal | 1 | 1,056h | 100%
CMP Review Checklist | Antonio Jimenez | 1 | 1,056h | 100%
CMP Review Checklist | Mauro Lopez | 1 | 1,056h | 100%
Update CMP | Marco Sosa | 1 | 688h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 0h | 100%
CMP Updated | Marco Sosa | 1 | 0h | 100%
CHMP update | Marco Sosa | 1 | 16h | 100%
Review/Feedback via TPL workproduct list | Akhtar Abbas | 1 | 40h | 100%
Review/Feedback via TPL workproduct list | Alejandro Lopez | 1 | 40h | 100%
Review/Feedback via TPL workproduct list | Anshuman Mittal | 1 | 40h | 100%
Review/Feedback via TPL workproduct list | Antonio Jimenez | 1 | 40h | 100%
Review/Feedback via TPL workproduct list | Devendra Takola | 1 | 40h | 100%
Review/Feedback via TPL workproduct list | Eliseo Flores | 1 | 40h | 100%
CHMP update based on feedback | Marco Sosa | 1 | 40h | 100%
CHMP check list review | Akhtar Abbas | 1 | 64h | 100%
CHMP check list review | Alejandro Lopez | 1 | 64h | 100%
CHMP check list review | Anshuman Mittal | 1 | 64h | 100%
CHMP check list review | Antonio Jimenez | 1 | 64h | 100%
CHMP check list review | Devendra Takola | 1 | 64h | 100%
CHMP check list review | Eliseo Flores | 1 | 64h | 100%
CHMP check list review | Nikhil Gupta | 1 | 0h | 100%
CHMP check list review | Slavko Bogoevski | 1 | 0h | 100%
CHMP update based on feedback | Marco Sosa | 1 | 32h | 100%
CHMP approval | Alejandro Lopez | 0 | 24h | 100%
CHMP approval | Anshuman Mittal | 0 | 24h | 100%
CHMP approval | Devendra Takola | 0 | 24h | 100%
CHMP approval | Eliseo Flores | 0 | 24h | 100%
CHMP approval | Nikhil Gupta | 0 | 24h | 100%
CHMP approval | Slavko Bogoevski | 0 | 24h | 100%
CHMP update | Marco Sosa | 0 | 16h | 100%
Review/Feedback via TPL workproduct list | Akhtar Abbas | 0 | 40h | 100%
Review/Feedback via TPL workproduct list | Alejandro Lopez | 0 | 40h | 100%
Review/Feedback via TPL workproduct list | Anshuman Mittal | 0 | 40h | 100%
Review/Feedback via TPL workproduct list | Antonio Jimenez | 0 | 40h | 100%
Review/Feedback via TPL workproduct list | Devendra Takola | 0 | 40h | 100%
Review/Feedback via TPL workproduct list | Eliseo Flores | 0 | 40h | 100%
CHMP update based on feedback | Marco Sosa | 0 | 8h | 100%
CHMP check list review | Akhtar Abbas | 0 | 8h | 100%
CHMP check list review | Alejandro Lopez | 0 | 8h | 100%
CHMP check list review | Anshuman Mittal | 0 | 8h | 100%
CHMP check list review | Antonio Jimenez | 0 | 8h | 100%
CHMP check list review | Devendra Takola | 0 | 8h | 100%
CHMP check list review | Eliseo Flores | 0 | 8h | 100%
CHMP check list review | Nikhil Gupta | 0 | 0h | 100%
CHMP check list review | Slavko Bogoevski | 0 | 0h | 100%
CHMP update based on feedback | Marco Sosa | 0 | 24h | 100%
CHMP approval | Alejandro Lopez | 0 | 40h | 100%
CHMP approval | Anshuman Mittal | 0 | 40h | 100%
CHMP approval | Devendra Takola | 0 | 40h | 100%
CHMP approval | Eliseo Flores | 0 | 40h | 100%
CHMP approval | Nikhil Gupta | 0 | 40h | 100%
CHMP approval | Slavko Bogoevski | 0 | 40h | 100%
Update CMP - First Version | Vignesh Sridhar | 1 | 160h | 100%
Update CMP - First Version | Sachin Karkera | 1 | 160h | 100%
Review & Approval of CM Plan - First Version | Vignesh Sridhar | 1 | 72h | 100%
Review & Approval of CM Plan - First Version | Akhtar Abbas | 1 | 80h | 100%
Review & Approval of CM Plan - First Version | Alejandro Lopez | 1 | 80h | 100%
Review & Approval of CM Plan - First Version | Marco Sosa | 1 | 80h | 100%
Review & Approval of CM Plan - First Version | Prabhu Kumar | 1 | 80h | 100%
Update CMP - Second Version | Vignesh Sridhar | 1 | 440h | 100%
Update CMP - Second Version | Sachin Karkera | 1 | 360h | 100%
Review of CM Plan - Second Version | Prabhu Kumar | 1 | 104h | 100%
Review of CM Plan - Second Version | Marco Sosa | 1 | 90.4h | 100%
Review of CM Plan - Second Version | Akhtar Abbas | 1 | 90.4h | 100%
Approval of CM Plan - Second Version | Alejandro Lopez | 1 | 56h | 100%
Systems Integration Test Strategy | Rajalakshmi M | 1 | 320h | 100%
System Integration Test Strategy Review Checklist | Rajalakshmi M | 1 | 36h | 100%
System Integration Test Strategy Approval | Alejandro Lopez | 1 | 48h | 100%
System Integration Test Strategy Approval | Mauro Lopez | 1 | 48h | 100%
System Integration Test Strategy Approval | Marco Sosa | 1 | 48h | 100%
Systems Integration Test Strategy update | Victor Samson | 1 | 88h | 100%
Systems Integration Test Strategy update | Mauro Lopez | 1 | 0h | 100%
Systems Integration Test Strategy Review | Mauro Lopez | 1 | 40h | 100%
Systems Integration Test Strategy Review | Alejandro Lopez | 1 | 40h | 100%
Systems Integration Test Strategy Review | Antonio Jimenez | 1 | 40h | 100%
Systems Integration Test Strategy Review | Prabhu Kumar | 1 | 40h | 100%
Systems Integration Test Strategy Appoval | Mauro Lopez | 1 | 24h | 100%
Systems Integration Test Strategy Appoval | Alejandro Lopez | 1 | 24h | 100%
Systems Integration Test Strategy Appoval | Antonio Jimenez | 1 | 24h | 100%
Systems Integration Test Strategy Appoval | Prabhu Kumar | 1 | 24h | 100%
System Qualification Test Strategy | Kalpana Dakshnamoorthy | 1 | 640h | 100%
System Qualification Test Strategy | Marco Sosa | 1 | 179.2h | 100%
Systems Validation Strategy Review Checklist | Kalpana Dakshnamoorthy | 1 | 46.4h | 100%
System Validation Test Strategy Approval | Alejandro Lopez | 1 | 8h | 100%
System Validation Test Strategy Approval | Mauro Lopez | 1 | 8h | 100%
System Validation Test Strategy Approval | Marco Sosa | 1 | 8h | 100%
System Qualification Test Strategy | Kalpana Dakshnamoorthy | 1 | 104h | 100%
System Qualification Test Strategy | Marco Sosa | 1 | 104h | 100%
System Qualification Test Strategy | Mauro Lopez | 1 | 104h | 100%
Systems Validation Strategy Review Checklist | Kalpana Dakshnamoorthy | 1 | 16h | 100%
System Validation Test Strategy Approval | Alejandro Lopez | 1 | 32h | 100%
System Validation Test Strategy Approval | Mauro Lopez | 1 | 32h | 100%
System Validation Test Strategy Approval | Marco Sosa | 1 | 32h | 100%
Develop Project Tracker document | Alejandro Lopez | 1 | 16h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 24h | 100%
Project Tracker Updated Updated | Alejandro Lopez | 1 | 40h | 100%
First Version created | Alejandro Lopez | 1 | 0h | 100%
Reviewed and approved by HW Team | Hugo Nunez | 1 | 7.2h | 100%
Reviewed and approved by ME Team | Anshuman Mittal | 1 | 120h | 100%
Reviewed and approved by SW Team | Akhtar Abbas | 1 | 7.2h | 100%
Reviewed and approved by PM Team | Kristine Hiott | 1 | 8h | 100%
Reviewed and approved by SW Validation Team | Oscar Espinosa | 1 | 8h | 100%
Approved by Managers | Managers | 1 | 40h | 100%
Sharepoint | Akhtar Abbas | 1 | 8h | 100%
Sharepoint | Alejandro Lopez | 1 | 8h | 100%
Sharepoint | Anshuman Mittal | 1 | 8h | 100%
Sharepoint | Antonio Jimenez | 1 | 8h | 100%
Sharepoint | Azad Mohammed | 1 | 8h | 100%
Sharepoint | Balaji Rao | 1 | 8h | 100%
Sharepoint | Dayanand Kotla | 1 | 8h | 100%
Sharepoint | Devendra Takola | 1 | 8h | 100%
Sharepoint | Dmitry Ogorodnikov | 1 | 8h | 100%
Sharepoint | Eliseo Flores | 1 | 8h | 100%
Sharepoint | Grant Thomas | 1 | 8h | 100%
Sharepoint | Hemangi Nehete | 1 | 8h | 100%
Sharepoint | Iniyakumar Louis | 1 | 8h | 100%
Sharepoint | Karthikeyan Palanisamy | 1 | 8h | 100%
Sharepoint | Kaushik Narasimhan | 1 | 8h | 100%
Sharepoint | Kunal Kulshrestha | 1 | 8h | 100%
DOORS | Akhtar Abbas | 1 | 8h | 100%
DOORS | Alejandro Lopez | 1 | 8h | 100%
DOORS | Anshuman Mittal | 1 | 8h | 100%
DOORS | Antonio Jimenez | 1 | 8h | 100%
DOORS | Azad Mohammed | 1 | 8h | 100%
DOORS | Balaji Rao | 1 | 8h | 100%
DOORS | Dayanand Kotla | 1 | 8h | 100%
DOORS | Devendra Takola | 1 | 8h | 100%
DOORS | Dmitry Ogorodnikov | 1 | 8h | 100%
DOORS | Eliseo Flores | 1 | 8h | 100%
DOORS | Grant Thomas | 1 | 8h | 100%
DOORS | Hemangi Nehete | 1 | 8h | 100%
DOORS | Iniyakumar Louis | 1 | 8h | 100%
DOORS | Karthikeyan Palanisamy | 1 | 8h | 100%
DOORS | Kaushik Narasimhan | 1 | 8h | 100%
DOORS | Kunal Kulshrestha | 1 | 8h | 100%
Redmine | Akhtar Abbas | 0 | 8h | 100%
Redmine | Alejandro Lopez | 0 | 8h | 100%
Redmine | Anshuman Mittal | 0 | 8h | 100%
Redmine | Antonio Jimenez | 0 | 8h | 100%
Redmine | Azad Mohammed | 0 | 8h | 100%
Redmine | Balaji Rao | 0 | 8h | 100%
Redmine | Dayanand Kotla | 0 | 8h | 100%
Redmine | Devendra Takola | 0 | 8h | 100%
Redmine | Dmitry Ogorodnikov | 0 | 8h | 100%
Redmine | Eliseo Flores | 0 | 8h | 100%
Redmine | Grant Thomas | 0 | 8h | 100%
Redmine | Hemangi Nehete | 0 | 8h | 100%
Redmine | Iniyakumar Louis | 0 | 8h | 100%
Redmine | Karthikeyan Palanisamy | 0 | 8h | 100%
Redmine | Kaushik Narasimhan | 0 | 8h | 100%
Redmine | Kunal Kulshrestha | 0 | 8h | 100%
Vector CAST session 1 | Azad Mohammed | 1 | 8h | 100%
Vector CAST session 1 | Balaji Rao | 1 | 8h | 100%
Vector CAST session 1 | Bishnu Raveendran | 1 | 8h | 100%
Vector CAST session 1 | Dayanand Kotla | 1 | 8h | 100%
Vector CAST session 1 | Hemangi Nehete | 1 | 8h | 100%
Vector CAST session 1 | Kiran Khallenhali | 1 | 8h | 100%
Vector CAST session 1 | Neelima Gudem | 1 | 8h | 100%
Vector CAST session 1 | Nikhil Wakaley | 1 | 8h | 100%
Vector CAST session 1 | Paresh Dolas | 1 | 8h | 100%
Vector CAST session 1 | Priyanka Purbe | 1 | 8h | 100%
Vector CAST session 1 | Rahul Kumar | 1 | 8h | 100%
Vector CAST session 1 | Ravi Ramachandrappa | 1 | 8h | 100%
Vector CAST session 1 | Sachin Karkera | 1 | 8h | 100%
Vector CAST session 1 | Shailendra Jain | 1 | 8h | 100%
Vector CAST session 1 | Sreenivas Naik | 1 | 8h | 100%
Vector CAST session 1 | Sumalatha Karthikeyan | 1 | 8h | 100%
Vector CAST session 1 | Akhtar Abbas | 1 | 8h | 100%
Vector CAST session 2 | Azad Mohammed | 1 | 8h | 100%
Vector CAST session 2 | Balaji Rao | 1 | 8h | 100%
Vector CAST session 2 | Bishnu Raveendran | 1 | 8h | 100%
Vector CAST session 2 | Dayanand Kotla | 1 | 8h | 100%
Vector CAST session 2 | Hemangi Nehete | 1 | 8h | 100%
Vector CAST session 2 | Kiran Khallenhali | 1 | 8h | 100%
Vector CAST session 2 | Neelima Gudem | 1 | 8h | 100%
Vector CAST session 2 | Nikhil Wakaley | 1 | 8h | 100%
Vector CAST session 2 | Paresh Dolas | 1 | 8h | 100%
Vector CAST session 2 | Priyanka Purbe | 1 | 8h | 100%
Vector CAST session 2 | Rahul Kumar | 1 | 8h | 100%
Vector CAST session 2 | Ravi Ramachandrappa | 1 | 8h | 100%
Vector CAST session 2 | Sachin Karkera | 1 | 8h | 100%
Vector CAST session 2 | Shailendra Jain | 1 | 8h | 100%
Vector CAST session 2 | Sreenivas Naik | 1 | 8h | 100%
Vector CAST session 2 | Sumalatha Karthikeyan | 1 | 8h | 100%
Vector CAST session 2 | Akhtar Abbas | 1 | 0h | 100%
Functional Safety session 1 | Akhtar Abbas | 1 | 8h | 100%
Functional Safety session 1 | Azad Mohammed | 1 | 8h | 100%
Functional Safety session 1 | Karthikeyan Palanisamy | 1 | 8h | 100%
Functional Safety session 1 | Kunal Kulshrestha | 1 | 8h | 100%
Functional Safety session 1 | Prabhu Kumar | 1 | 8h | 100%
Functional Safety session 2 | Akhtar Abbas | 1 | 8h | 100%
Functional Safety session 2 | Azad Mohammed | 1 | 8h | 100%
Functional Safety session 2 | Karthikeyan Palanisamy | 1 | 8h | 100%
Functional Safety session 2 | Kunal Kulshrestha | 1 | 8h | 100%
Functional Safety session 2 | Marco Sosa | 1 | 8h | 100%
Functional Safety session 2 | Prabhu Kumar | 1 | 8h | 100%
ASPICE | Akhtar Abbas | 1 | 8h | 100%
ASPICE | Alejandro Lopez | 1 | 8h | 100%
ASPICE | Antonio Jimenez | 1 | 8h | 100%
ASPICE | Karthikeyan Palanisamy | 1 | 8h | 100%
ASPICE | Marco Sosa | 1 | 8h | 100%
ASPICE | Mauro Lopez | 1 | 8h | 100%
ASPICE | Navin Singh | 1 | 8h | 100%
ASPICE | Neelima Gudem | 1 | 8h | 100%
ASPICE | Nikhil Wakaley | 1 | 8h | 100%
ASPICE | Oscar Espinosa | 1 | 8h | 100%
ASPICE | Paresh Dolas | 1 | 8h | 100%
ASPICE | Prabhu Kumar | 1 | 8h | 100%
ASPICE | Priyanka Purbe | 1 | 8h | 100%
ASPICE | Rahul Kumar | 1 | 8h | 100%
ASPICE | Ravi Ramachandrappa | 1 | 8h | 100%
ASPICE | Shailendra Jain | 1 | 8h | 100%
ASPICE | Sharmila Kokkera | 1 | 8h | 100%
ASPICE | Sreenivas Naik | 1 | 8h | 100%
ASPICE | Tharun Kumar | 1 | 8h | 100%
ASPICE | Tien Nguyen | 1 | 8h | 100%
ASPICE | Vignesh Sridhar | 1 | 8h | 100%
Cyber Security | Marco Sosa | 1 | 8h | 100%
Cyber Security | Dmitry Ogorodnikov | 1 | 0h | 100%
HSCAN Questionnaire - CG4090 | Alejandro Lopez | 1 | 1,112h | 100%
HSCAN Questionnaire - CG4090 GM Approval | Alejandro Lopez | 1 | 40h | 100%
HSCAN Questionnaire Update | Marco Sosa | 1 | 16h | 100%
HSCAN Questionnaire Approval | GM | 1 | 96h | 100%
LIN Questionnaire - CG4080 | Akhtar Abbas | 1 | 0h | 100%
LIN Questionnaire - CG4080 GM Approval | GM | 1 | 80h | 100%
Ethernet Questionnaire - CG4077 | Alejandro Lopez | 1 | 152h | 100%
Ethernet Questionnaire - CG4077 GM Approval | GM | 1 | 48h | 100%
Diagnostic validation Questionnaire –CG4422 | GM | 1 | 40h | 100%
OTA Questionnaire - CG4879 | Alejandro Lopez | 1 | 40h | 100%
FUSA (DIA)---CG2694 | Alejandro Lopez | 1 | 704h | 100%
Flash Bootloader Test Procedure -----CG3687 | Sharmila Kokkera | 1 | 40h | 100%
CG4879 Test Procedure | Oscar Espinosa | 1 | 632h | 100%
CG4748 Test Plan | Oscar Espinosa | 1 | 40h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Mauro Lopez | 1 | 440h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Victor Samson | 1 | 443.2h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Marco Sosa | 1 | 427.2h | 100%
CG4111 Approval from GM | Marco Sosa | 1 | 24h | 100%
CG4073 Diagnostics Questionnaire | Marco Sosa | 1 | 144h | 100%
CG4073 Diagnostics Questionnaire | Akhtar Abbas | 1 | 144h | 100%
CG4073 Diagnostics Questionnaire | Eliseo Flores | 1 | 144h | 100%
CG4073 Diagnostics Questionnaire GM feedback | GM | 1 | 40h | 100%
CG4073 Dianostics Questionnaire Update | Marco Sosa | 1 | 232h | 100%
CG4073 Dianostics Questionnaire Update | Akhtar Abbas | 1 | 232h | 100%
CG4073 Dianostics Questionnaire Update | Eliseo Flores | 1 | 232h | 100%
CG4073 Diagsnostics Questionnaire GM Feedback | GM | 1 | 80h | 100%
CG4073 Diagnostics Questionnaire Update | Marco Sosa | 1 | 80h | 100%
CG4073 CG4073 Diagsnostics Questionnaire GM Approval | GM | 0 | 80h | 100%
Indicator Alerts | Akhtar Abbas | 1 | 0h | 100%
GMW17219 Open Source Document Process (IVER) | Akhtar Abbas | 1 | 0h | 100%
CGXXX VCRI | Anshuman Mittal | 0.5 | 80h | 100%
CGXXX VCRI | Karthikeyan Palanisamy | 0.5 | 80h | 100%
CGXXX VCRI | Marco Sosa | 0.5 | 80h | 100%
CGXXX VCRI | Mauro Lopez | 0.5 | 80h | 100%
CGXXX VCRI | Sachin Karkera | 0.5 | 80h | 100%
DIA Complete | Amrita Banjha | 1 | 1,456h | 100%
CG3532 Hardening requirement tracing | Amrita Banjha | 0.90000000000000002 | 1,360h | 100%
GM Vehicle Cybersecurity Questionnaire - Supplier Cryptographic Library Usage | Amrita Banjha | 1 | 480h | 100%
Cybersecurity Capability Assessment Questionnaire | Amrita Banjha | 0 | 8h | 100%
SAQ | Amrita Banjha | 0 | 8h | 100%
GM Service Programming System Non-Disclose Agreement | Amrita Banjha | 0 | 8h | 100%
Supplier Provisioning Portal Access Request Form | Amrita Banjha | 1 | 608h | 100%
GB IECS NDA Questionnaire | Amrita Banjha | 1 | 128h | 100%
Security Peripheral Review Template | Amrita Banjha | 1 | 80h | 100%
Complete Review Templeate | Grant Thomas | 1 | 2,072h | 100%
GM Review | GM | 1 | 160h | 100%
Update Template based on the feedback from GM Phase 1 (3 items) | Grant Thomas | 1 | 40h | 100%
Update Template based on the feedback from GM Phase 2 (4 items) | Grant Thomas | 1 | 72h | 100%
GM Review and Approval | GM | 0 | 80h | 100%
Cyber-Security Design Review | Amrita Banjha | 1 | 472h | 100%
Cyber Security Final Validation Review and Final RAT (initial) | Antonio Cacho | 1 | 96h | 100%
GM review and Approval | GM | 0 | 80h | 100%
Update from NSI | Antonio Cacho | 0 | 40h | 100%
Final Review and approval from GM | GM | 0 | 80h | 100%
GMW17219 Open Source Document Process (VTC) | Marco Sosa | 0 | 40h | 100%
Gathering Customer Requirements | Alejandro Lopez | 1 | 240h | 100%
Allocating Customer Requirements to Competencies | Alejandro Lopez | 1 | 120h | 100%
Requirement Analysis on RFQ and PWR SUPP packages | Akhtar Abbas | 1 | 360h | 100%
Requirement Analysis on RFQ and PWR SUPP packages | Anshuman Mittal | 1 | 360h | 100%
Requirement Analysis on RFQ and PWR SUPP packages | Antonio Jimenez | 1 | 360h | 100%
Requirement Analysis on RFQ and PWR SUPP packages | Mauro Lopez | 1 | 360h | 100%
CTRS update and competency allocation | Alejandro Lopez | 1 | 40h | 100%
Query Log Completion for RFQ and Supp Power | Akhtar Abbas | 1 | 488h | 100%
Query Log Completion for RFQ and Supp Power | Anshuman Mittal | 1 | 488h | 100%
Query Log Completion for RFQ and Supp Power | Antonio Jimenez | 1 | 488h | 100%
Query Log Completion for RFQ and Supp Power | Mauro Lopez | 1 | 488h | 100%
Create Requirement Analysis Plan for CTRS reference Documents | Akhtar Abbas | 1 | 248h | 100%
Create Requirement Analysis Plan for CTRS reference Documents | Anshuman Mittal | 1 | 248h | 100%
Create Requirement Analysis Plan for CTRS reference Documents | Antonio Jimenez | 1 | 248h | 100%
Create Requirement Analysis Plan for CTRS reference Documents | Mauro Lopez | 1 | 248h | 100%
EE Analysis | Hugo Nunez | 1 | 328h | 100%
ME Analysis | Anshuman Mittal | 1 | 152h | 100%
SW Analysis | Akhtar Abbas | 1 | 416h | 100%
TPL Analysis | Alejandro Lopez | 1 | 416h | 100%
Review Resuls from Req Analysis | Alejandro Lopez | 1 | 24h | 100%
Query Log Completion for CTRS reference document | Akhtar Abbas | 1 | 532.8h | 100%
Query Log Completion for CTRS reference document | Anshuman Mittal | 1 | 532.8h | 100%
Query Log Completion for CTRS reference document | Antonio Jimenez | 1 | 532.8h | 100%
Query Log Completion for CTRS reference document | Mauro Lopez | 1 | 532.8h | 100%
Software CTRS analysis | Akhtar Abbas | 1 | 192h | 100%
Create TSR | Alejandro Lopez | 1 | 80h | 100%
Release for Review | Akhtar Abbas | 1 | 16h | 100%
Release for Review | Anshuman Mittal | 1 | 16h | 100%
Release for Review | Antonio Jimenez | 1 | 16h | 100%
Release for Review | Mauro Lopez | 1 | 16h | 100%
Reviewed by QA | Prabhu Kumar | 1 | 40h | 100%
Update based on feedback | Alejandro Lopez | 1 | 40h | 100%
Release for Review | Akhtar Abbas | 1 | 16h | 100%
Release for Review | Anshuman Mittal | 1 | 16h | 100%
Release for Review | Antonio Jimenez | 1 | 16h | 100%
Release for Review | Mauro Lopez | 1 | 16h | 100%
Reviewed by QA and Team | Akhtar Abbas | 1 | 40h | 100%
Reviewed by QA and Team | Anshuman Mittal | 1 | 40h | 100%
Reviewed by QA and Team | Antonio Jimenez | 1 | 40h | 100%
Reviewed by QA and Team | Mauro Lopez | 1 | 40h | 100%
Update based on feedback | Marco Sosa | 1 | 40h | 100%
Release for Review | Marco Sosa | 1 | 16h | 100%
Reviewed by QA and team | Akhtar Abbas | 1 | 40h | 100%
Reviewed by QA and team | Anshuman Mittal | 1 | 40h | 100%
Reviewed by QA and team | Antonio Jimenez | 1 | 40h | 100%
Reviewed by QA and team | Mauro Lopez | 1 | 40h | 100%
Update based on feedback | Marco Sosa | 1 | 40h | 100%
Release for review | Marco Sosa | 1 | 48h | 100%
Reviewed by QA and Team | Akhtar Abbas | 1 | 40h | 100%
Reviewed by QA and Team | Anshuman Mittal | 1 | 40h | 100%
Reviewed by QA and Team | Antonio Jimenez | 1 | 40h | 100%
Reviewed by QA and Team | Mauro Lopez | 1 | 40h | 100%
Update based on feedback | David Fabila | 1 | 40h | 100%
Release for review | Marco Sosa | 1 | 80h | 100%
Update based on feedback | Mauro Lopez | 0 | 40h | 100%
Release for review | Marco Sosa | 1 | 168h | 100%
Review by SYS5 of SRS 5.0 and SRS 6.0 | Kalpana Dakshnamoorthy | 1 | 200h | 100%
Review by Software SYS of SRS 5.0 and SRS 6.0 | Shailendra Jain | 1 | 480h | 100%
Review by HW team of SRS 5.0 and SRS 6.0 | Antonio Jimenez | 1 | 240h | 100%
Review by ME team of SRS 5.0 and SRS 6.0 | Anshuman Mittal | 1 | 240h | 100%
Update based on feedback | Mauro Lopez | 1 | 200h | 100%
Reviewed by QA of SRS 5.0 and SRS 6.0 | Prabhu Kumar | 1 | 24h | 100%
Release for review | Mauro Lopez | 0 | 8h | 100%
Review by HW team of SRS 7.0 | Antonio Jimenez | 0 | 160h | 100%
Bootloader | Mauro Lopez | 1 | 40h | 100%
CAN | Mauro Lopez | 1 | 224h | 100%
LIN | Mauro Lopez | 1 | 88h | 100%
Ethernet | Mauro Lopez | 1 | 12h | 100%
GB Specs from May | Mauro Lopez | 1 | 80h | 100%
CTRS | Mauro Lopez | 1 | 96h | 100%
Close rejections from SRS | Mauro Lopez | 1 | 48h | 100%
CTRS to SRS | Mauro Lopez | 1 | 320h | 100%
SRS to SFS | Shailendra Jain | 1 | 400h | 100%
SRS to SYS5 Test Cases | Kalpana Dakshnamoorthy | 1 | 360h | 100%
System Architecture document | Alejandro Lopez | 1 | 1,176h | 100%
System Architecture document | Marco Sosa | 1 | 1,176h | 100%
Create PCE | Alejandro Lopez | 1 | 24h | 100%
Software | Kunal Kulshrestha | 1 | 160h | 100%
Software | Suga Ragunathan | 1 | 160h | 100%
Software Systems | Suga Ragunathan | 1 | 168h | 100%
Software Systems | Azad Mohammed | 1 | 0h | 100%
Create PCE | Alejandro Lopez | 1 | 176h | 100%
Hardware | Hugo Nunez | 1 | 24h | 100%
Hardware | Slavko Bogoevski | 1 | 0h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Hardware | Antonio Jimenez | 1 | 152h | 100%
Hardware | Slavko Bogoevski | 1 | 152h | 100%
Mechanical | Anshuman Mittal | 1 | 96h | 100%
Mechanical | Arul Krishna | 1 | 96h | 100%
Software | Akhtar Abbas | 1 | 792h | 100%
Software | Jon Donegan | 1 | 792h | 100%
TPL/Systems | Marco Sosa | 1 | 392h | 100%
TPL/Systems | Alejandro Lopez | 1 | 392h | 100%
TPL/Systems | Mauro Lopez | 1 | 392h | 100%
Create PCE | Alejandro Lopez | 1 | 8h | 100%
Hardware | Antonio Jimenez | 1 | 640h | 100%
Hardware | Slavko Bogoevski | 1 | 640h | 100%
Mechanical | Takaki Yoshida | 1 | 32h | 100%
Mechanical | Arul Krishna | 1 | 32h | 100%
Create PCE | Alejandro Lopez | 1 | 8h | 100%
Mechanical | Arul Krishna | 1 | 40h | 100%
Mechanical | Anshuman Mittal | 1 | 40h | 100%
Create PCE | Alejandro Lopez | 1 | 8h | 100%
Mechanical | Arul Krishna | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 8h | 100%
Hardware | Antonio Jimenez | 1 | 504h | 100%
Hardware | Slavko Bogoevski | 1 | 504h | 100%
Mechanical | Takaki Yoshida | 1 | 80h | 100%
Mechanical | Arul Krishna | 1 | 80h | 100%
Software | Suga Ragunathan | 1 | 200h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Hardware | Antonio Jimenez | 1 | 360h | 100%
Hardware | Slavko Bogoevski | 1 | 0h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 16h | 100%
Mechanical | Arul Krishna | 1 | 16h | 100%
Mechanical | Anshuman Mittal | 0 | 40h | 100%
Approval | Arul Krishna | 0 | 8h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Software Design | Suga Ragunathan | 1 | 416h | 100%
Software Design | Akhtar Abbas | 1 | 0h | 100%
Software Systems | Leonardo Iratagotia | 1 | 336h | 100%
Software Systems | Devendra Takola | 1 | 0h | 100%
Software Verification | Oscar Espinosa | 1 | 424h | 100%
Software Verification | Jon Donegan | 1 | 424h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
TPL/Systems | Marco Sosa | 1 | 80h | 100%
TPL/Systems | Alejandro Lopez | 1 | 80h | 100%
Software Design | Suga Ragunathan | 1 | 80h | 100%
Software Design | Akhtar Abbas | 1 | 0h | 100%
Software Systems | Suga Ragunathan | 1 | 80h | 100%
Software Systems | Akhtar Abbas | 1 | 0h | 100%
Software Verification | Jon Donegan | 1 | 80h | 100%
Hardware | Antonio Jimenez | 1 | 72h | 100%
Hardware | Slavko Bogoevski | 1 | 72h | 100%
Mechanical | Anshuman Mittal | 1 | 32h | 100%
Mechanical | Arul Krishna | 1 | 0h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 8h | 100%
Hardware | Antonio Jimenez | 1 | 24h | 100%
Software Development | Akhtar Abbas | 1 | 32h | 100%
Software SYS | Akhtar Abbas | 1 | 32h | 100%
Software Verification | Oscar Espinosa | 1 | 8h | 100%
TPL | Marco Sosa | 1 | 16h | 100%
JPN feeback | Andrea Nustad | 1 | 40h | 100%
Customer EWO | GM | 1 | 120h | 100%
EWO approval at NSI | Marco Sosa | 1 | 64h | 100%
EWO release from GM to NSI | GM | 1 | 8h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Arul Krishna | 1 | 400h | 100%
Mechanical | Hideyuki Inaguma | 1 | 400h | 100%
Hardware | Antonio Jimenez | 1 | 88h | 100%
Hardware | Slavko Bogoevski | 1 | 88h | 100%
Mechanical | Anshuman Mittal | 0 | 40h | 100%
Mechanical | Arul Krishna | 0 | 40h | 100%
Software | Akhtar Abbas | 0 | 40h | 100%
Software | Jon Donegan | 0 | 40h | 100%
TPL/Systems | Marco Sosa | 0 | 40h | 100%
TPL/Systems | Alejandro Lopez | 0 | 40h | 100%
TPL/Systems | Mauro Lopez | 0 | 40h | 100%
Test Labs | Kazuhiko Kimura | 1 | 40h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Software | Akhtar Abbas | 1 | 464h | 100%
Software | Jon Donegan | 1 | 464h | 100%
TPL/Systems | Marco Sosa | 1 | 56h | 100%
TPL/Systems | Alejandro Lopez | 1 | 56h | 100%
TPL/Systems | Mauro Lopez | 1 | 56h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 64h | 100%
Mechanical | Arul Krishna | 1 | 64h | 100%
TPL/Systems | Marco Sosa | 1 | 64h | 100%
TPL/Systems | Alejandro Lopez | 1 | 64h | 100%
TPL/Systems | Mauro Lopez | 1 | 64h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Software | Akhtar Abbas | 0.5 | 984h | 100%
TPL/Systems | Marco Sosa | 1 | 176h | 100%
TPL/Systems | Alejandro Lopez | 1 | 176h | 100%
TPL/Systems | Mauro Lopez | 1 | 176h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 16h | 100%
Mechanical | Arul Krishna | 1 | 16h | 100%
TPL / Systems | Marco Sosa | 1 | 40h | 100%
TPL / Systems | Alejandro Lopez | 1 | 40h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 16h | 100%
Mechanical | Arul Krishna | 1 | 16h | 100%
TPL / Systems | Marco Sosa | 1 | 40h | 100%
TPL / Systems | Alejandro Lopez | 1 | 40h | 100%
Create PCE | Marco Sosa | 1 | 8h | 100%
Mechanical | Anshuman Mittal | 1 | 16h | 100%
Mechanical | Arul Krishna | 1 | 16h | 100%
TPL / Systems | Marco Sosa | 1 | 472h | 100%
TPL / Systems | Alejandro Lopez | 1 | 472h | 100%
Hardware | Antonio Jimenez | 0.5 | 776h | 100%
Hardware | Slavko Bogoevski | 0.5 | 776h | 100%
Mechanical | Anshuman Mittal | 1 | 8h | 100%
Mechanical | Arul Krishna | 1 | 8h | 100%
Software | Akhtar Abbas | 1 | 696h | 100%
Software | Eliseo Flores | 1 | 696h | 100%
Software | Jon Donegan | 1 | 696h | 100%
Update document with new information | Azad Mohammed | 1 | 32h | 100%
Review with GM | Azad Mohammed | 1 | 8h | 100%
Review with GM | Akhtar Abbas | 1 | 8h | 100%
Review with GM | Marco Sosa | 1 | 8h | 100%
Update 5 phases | Azad Mohammed | 1 | 24h | 100%
Review with NSI management and agreement on Action Plan | Azad Mohammed | 0 | 8h | 100%
Review with NSI management and agreement on Action Plan | Akhtar Abbas | 0 | 8h | 100%
Review with NSI management and agreement on Action Plan | Marco Sosa | 0 | 8h | 100%
Create 5 phase with issue description | Marco Sosa | 1 | 8h | 100%
Reproduce issue | Sreenivas Naik | 1 | 8h | 100%
Root cause analysis | Sreenivas Naik | 1 | 16h | 100%
Software implemantation | Sreenivas Naik | 1 | 8h | 100%
Demo with DPS at NSI | Akhtar Abbas | 1 | 8h | 100%
Create 5 Phase with description | Suga Ragunathan | 1 | 8h | 100%
Issue analysis to identify watchdog trigger | Nikhil Wakaley | 1 | 56h | 100%
Take measurements of all task execution timing | Navin Singh | 1 | 56h | 100%
Identify module causing the watch dog reset | Navin Singh | 1 | 8h | 100%
Gather timing measurement for SHE module processing and Work with Cypress on further root cause | Grant Thomas | 1 | 8h | 100%
Validate DPS testing with RID 200 | Oscar Espinosa | 1 | 56h | 100%
Revalidate with SW 21.21.142.1 | Oscar Espinosa | 1 | 128h | 100%
Provide Impact Analysis on other solutions to GM | Grant Thomas | 0 | 96h | 100%
Create 5 Phase with issue description | Marco Sosa | 1 | 8h | 100%
Issue Debugging | Paresh Dolas | 1 | 72h | 100%
Implementation for Power resume handle shifting from CAN Error message for DID to CAN busload | Paresh Dolas | 1 | 24h | 100%
Verification of Fix | Paresh Dolas | 1 | 224h | 100%
Verification of Fix | Leonardo Iratagotia | 1 | 208h | 100%
Update 5 Phase with respective test results | Paresh Dolas | 1 | 72h | 100%
Release new CANoe tool. | Leonardo Iratagotia | 1 | 224h | 100%
Retest with new CANoe tool | Test Lab | 1 | 80h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Reproduce issue with current DV software | Leonardo Iratagotia | 1 | 80h | 100%
Retest issue with updated CANoe panel | Leonardo Iratagotia | 1 | 160h | 100%
Reproduce issue with IVER software (21.21.140.4) | Leonardo Iratagotia | 1 | 16h | 100%
Contact GM TCI about the issue | Leonardo Iratagotia | 1 | 80h | 100%
Reproduct the issue at GM TCI | GMTCI | 1 | 40h | 100%
Determine if root cause is in application code | GMTCI | 1 | 16h | 100%
Release new application code | GMTCI | 0 | 80h | 100%
Integrate test code | Leonardo Iratagotia | 1 | 40h | 100%
Verify the fix at NSI | Leonardo Iratagotia | 1 | 320h | 100%
Run test with new DV software | Test Lab | 1 | 80h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Issue Debugging | Nikhil Wakaley | 1 | 24h | 100%
Implementation for Gauge Configuration | Nikhil Wakaley | 1 | 16h | 100%
Verification of Fix | Nikhil Wakaley | 1 | 24h | 100%
Update 5 Phase with respective results | Krishnakumar Joshi | 1 | 128h | 100%
Release new software version | Neelima Gudem | 1 | 224h | 100%
Re-test with releases software version. | Test Lab | 1 | 40h | 100%
Create 5 phase with description | Marco Sosa | 1 | 8h | 100%
Fix ERR Correction Issue | Sreenivas Naik | 1 | 32h | 100%
Perform White Box testing to validate the fix | Sreenivas Naik | 1 | 72h | 100%
Release the Software for Validation Team to test the fix | Sachin Karkera | 1 | 0h | 100%
Provide Feedback to SW team if need/SW Team to fix the issue if need | Sharmila Kokkera | 1 | 8h | 100%
Investigate why tool is sending reset request | Sharmila Kokkera | 1 | 40h | 100%
Investigate why tool is sending reset request | GM | 1 | 40h | 100%
Re-run test with new tool 2.3.5 and software to generate separate log files to be able to analyze. | Sharmila Kokkera | 1 | 136h | 100%
Analyze logs to determine if OTA tool or IPC software is the issue. | Sharmila Kokkera | 1 | 96h | 100%
Analyze logs to determine if OTA tool or IPC software is the issue. | GM | 1 | 96h | 100%
Analyze logs to determine if OTA tool or IPC software is the issue. | Sreenivas Naik | 1 | 96h | 100%
Provoide Delta packages to SWE6 | Balaji Rao | 1 | 88h | 100%
Re-evaluate timeline for OTA Reliability and get Plan approved with GM | Oscar Espinosa | 1 | 56h | 100%
Re-evaluate timeline for OTA Reliability and get Plan approved with GM | Marco Sosa | 1 | 56h | 100%
Run 10000 cycles | Oscar Espinosa | 0 | 320h | 100%
Root cause "memory fault" | Eliseo Flores | 0.10000000000000001 | 80h | 100%
Root cause "pending fault" issue | Kiran Khallenhali | 1 | 32h | 100%
Run test at CGM bench | Balaji Rao | 1 | 8h | 100%
Root cause reponses on HSCAN instead of Ethernet | Balaji Rao | 1 | 24h | 100%
Release new sw21.21.145 | Balaji Rao | 1 | 8h | 100%
Run test at CGM bench | Balaji Rao | 1 | 8h | 100%
Run 10000 cycles | Oscar Espinosa | 0.71999999999999997 | 200h | 100%
Create 5 phase with issue description | Sibing Xu | 1 | 8h | 100%
Root cause analysis at Sibina | Sibing Xu | 1 | 24h | 100%
Run DoE with new pointer | Sibing Xu | 1 | 80h | 100%
Tear down failed parts | Sibing Xu | 1 | 72h | 100%
Tear down failed parts | Marco Sosa | 1 | 72h | 100%
New pointer assembly with supplier | Anshuman Mittal | 1 | 8h | 100%
Review new pointers with GM | Anshuman Mittal | 1 | 16h | 100%
DOE BSR with new pointers | Anshuman Mittal | 1 | 40h | 100%
New pointer jig fabrication | Manufacturing JPN | 1 | 96h | 100%
Build C1UB pointer samples off process | Manufacturing JPN | 1 | 112h | 100%
Retest with C1UB PV testing updated pointers | Anshuman Mittal | 1 | 200h | 100%
Create 5 phase with issue description | Sibing Xu | 1 | 8h | 100%
CAE Static Analysis | Sibing Xu | 1 | 48h | 100%
CAE Dynamic Analysis | Sibing Xu | 1 | 120h | 100%
Review with GM on root cause | Marco Sosa | 1 | 8h | 100%
Review with GM on root cause | Anshuman Mittal | 1 | 8h | 100%
Review with GM on root cause | GM | 1 | 8h | 100%
Customer drawing and data release to Team Center | Anshuman Mittal | 1 | 8h | 100%
Issue EWO | GM | 0 | 120h | 100%
ENV Test Plan for DV03 | Marco Sosa | 1 | 168h | 100%
ENV Test PlanDV03 Review and internal approval | Alejandro Lopez | 1 | 80h | 100%
ENV Test PlanDV03 Review and internal approval | Anshuman Mittal | 1 | 80h | 100%
ENV Test PlanDV03 Review and internal approval | Mauro Lopez | 1 | 80h | 100%
ENV Test Plan for DV03 GM Approval | GM | 1 | 56h | 100%
Test Request Sheet | Marco Sosa | 1 | 16h | 100%
Math data to Team Center | Anshuman Mittal | 1 | 96h | 100%
Kick off tooling | Anshuman Mittal | 1 | 8h | 100%
Tooling Modification (Visor & Outercase) | Tooling Supplier | 1 | 120h | 100%
Mold in color parts | Tooling Supplier | 1 | 56h | 100%
Ship to Branson | Tooling Supplier | 1 | 40h | 100%
Laser welding for new desing | Supplier: Branson | 1 | 40h | 100%
Ship to new Sabina | Supplier: Branson | 1 | 24h | 100%
Build IPCs | Yoshio Tanaka | 1 | 8h | 100%
Retest countermeasure (DV03 Testing) | Sabina lab | 1 | 80h | 100%
Create 5 phase with issue description | Marco Sosa | 1 | 8h | 100%
Open redmine for software team. | Leonardo Iratagotia | 1 | 0h | 100%
Test previous software version to confirm if the issue is present. | Neelima Gudem | 1 | 32h | 100%
Update 5 Phase with results of previous software (add pictures) | Neelima Gudem | 1 | 8h | 100%
Root cause analysis – identify changes between the 2 software versions | Krishnakumar Joshi | 1 | 16h | 100%
Root cause analysis – identify the changes for IVER (port configs) | Krishnakumar Joshi | 0 | 48h | 100%
Fix software | Krishnakumar Joshi | 1 | 40h | 100%
Test new software and update results in 5 Phase | Krishnakumar Joshi | 1 | 16h | 100%
Release new software version | Neelima Gudem | 1 | 400h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 0h | 100%
Open redmine for software team. | Leonardo Iratagotia | 1 | 8h | 100%
Analyze CANoe panel to confirm issue is in the tool | Leonardo Iratagotia | 1 | 56h | 100%
Reproduce issue at EMC lab | Leonardo Iratagotia | 1 | 56h | 100%
Test updated CANoe configuration | Leonardo Iratagotia | 1 | 32h | 100%
Release new CANoe tool. | Leonardo Iratagotia | 1 | 216h | 100%
Retest with new CANoe tool | Test Lab | 1 | 80h | 100%
HW review and investigation | Karthikeyan Palanisamy | 1 | 80h | 100%
HW review and investigation | Antonio Jimenez | 1 | 80h | 100%
HW review and investigation | Leonardo Iratagotia | 1 | 40h | 100%
SW review and investigation | Leonardo Iratagotia | 1 | 440h | 100%
Test DV code at test lab | Leonardo Iratagotia | 1 | 72h | 100%
5 Phase update | Marco Sosa | 1 | 128h | 100%
5 Phase update | Leonardo Iratagotia | 1 | 108.8h | 100%
5 Phase review and approval by management | Marco Sosa | 1 | 32h | 100%
5 Phase review and approval by management | Alejandro Lopez | 1 | 32h | 100%
5 Phase review and approval by management | Akhtar Abbas | 1 | 32h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
Create 5 Phase with issue description | Akhtar Abbas | 1 | 0h | 100%
Investigate the issue behavior through DPS | Sreenivas Naik | 1 | 176h | 100%
Investigate the issue behavior through DPS | Sharmila Kokkera | 1 | 176h | 100%
Investigate the issue behavior through Vflash | Sreenivas Naik | 1 | 176h | 100%
Conduct a Design analysis to improve performance | Sreenivas Naik | 1 | 176h | 100%
Conduct a Design analysis to improve performance | Balaji Rao | 1 | 176h | 100%
Perform changes to implement the design change | Sreenivas Naik | 1 | 56h | 100%
Perform changes to implement the design change | Balaji Rao | 1 | 56h | 100%
Validate the Change through Integration testing | Sreenivas Naik | 1 | 104h | 100%
Validate the Change through Integration testing | Balaji Rao | 1 | 104h | 100%
Perform testing at CGM Bench | Sreenivas Naik | 1 | 104h | 100%
Perform testing at CGM Bench | Sharmila Kokkera | 1 | 104h | 100%
Validate the improvement through OTA Tool | Sreenivas Naik | 1 | 88h | 100%
Validate the improvement through OTA Tool | Sharmila Kokkera | 1 | 88h | 100%
Improve SW flashing time | Balaji Rao | 1 | 80h | 100%
Test at GM bench | Balaji Rao | 1 | 56h | 100%
Implement Pending Response | Balaji Rao | 1 | 56h | 100%
Test at GM bench | Balaji Rao | 1 | 8h | 100%
Root cause issue with HSCAN response | Balaji Rao | 1 | 24h | 100%
Release new software version | Balaji Rao | 1 | 8h | 100%
Test at GM bench | Balaji Rao | 1 | 8h | 100%
Run test with 21.21.145 Official version | Masanori Kaise | 1 | 80h | 100%
Run test with sw21.21.145.01 official version | Balaji Rao | 0 | 40h | 100%
Run test with sw21.21.145.01 official version | Masanori Kaise | 0 | 40h | 100%
5 Phase update | Marco Sosa | 0 | 8h | 100%
5 Phase review and approval by management | Alejandro Lopez | 0 | 8h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
Create 5 Phase with issue description | Marco Sosa | 1 | 0h | 100%
Reproduce issue manually (40 Cycles) | Devendra Takola | 1 | 8h | 100%
Reproduce issue automatically (>200 Cycles) | Sachin Karkera | 1 | 8h | 100%
Trace back the DET through GHS debugger and call stack | Sachin Karkera | 1 | 24h | 100%
Identify block causing issue | Sachin Karkera | 1 | 24h | 100%
RAM Buffer update | Sachin Karkera | 1 | 8h | 100%
Temporary fix | Sachin Karkera | 1 | 8h | 100%
Test temporary fix with automated script | Devendra Takola | 0 | 8h | 100%
Software validation testing | Oscar Espinosa | 0 | 56h | 100%
Permanent solution with Vector | Sreenivas Naik | 1 | 48h | 100%
Analyze AUTOSAR requirements for Write Verify | Sreenivas Naik | 1 | 16h | 100%
Analyze Vector Techcnical reference manual for NVM/FEE | Sreenivas Naik | 1 | 16h | 100%
Analyze Task Priority | Sreenivas Naik | 1 | 16h | 100%
Check with Vector if any NVM block can create the issue | Sreenivas Naik | 1 | 48h | 100%
Run 1000 cycles to confirm the issue is fixed | Naveen Gujjari | 1 | 24h | 100%
Implement permanent fix with sw21.21.144 | Naveen Gujjari | 1 | 56h | 100%
Create 5 Phase with issue description | Sibing Xu | 1 | 0h | 100%
Review failed cluster | Sibing Xu | 1 | 8h | 100%
Study potential root cause and alternate solutions | Sibing Xu | 1 | 48h | 100%
Root cause confirmation through CAE | Anshuman Mittal | 1 | 48h | 100%
Feasibility confirmation of alternate design from GM IPC Eng | GM | 1 | 144h | 100%
Alternate fix: Add rib to front of bumper pad | Anshuman Mittal | 1 | 96h | 100%
Feasibility confirmation of alternate design from molding | Anshuman Mittal | 1 | 40h | 100%
Feasibility confirmation of alternate design from welding | Anshuman Mittal | 1 | 40h | 100%
Provide updated design for visor change to GM | Anshuman Mittal | 1 | 8h | 100%
GM to review updated design provided by NSI | GM | 1 | 312h | 100%
Implementation | Anshuman Mittal | 1 | 80h | 100%
PV testing | Test Lab | 0 | 80h | 100%
Create 5 Phase with issue description | Akhtar Abbas | 1 | 8h | 100%
Investigate Time out and NRC issue | Grant Thomas | 1 | 64h | 100%
Design a solution to solve the issue | Grant Thomas | 0 | 256h | 100%
Perform White Box Testing to validate the fix | Grant Thomas | 0 | 88h | 100%
Perform validation testing to confirm the fix | Oscar Espinosa | 0 | 96h | 100%
Release the software to GMTCI for their testing | Akhtar Abbas | 0 | 80h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Reproduce issue | Karthikeyan Palanisamy | 1 | 8h | 100%
Test with ADC Calibration updated (suggested by Cypress) | Karthikeyan Palanisamy | 1 | 8h | 100%
Determine if issue is due to software implementation | Karthikeyan Palanisamy | 1 | 24h | 100%
Determine if issue is due to software implementation | Leonardo Iratagotia | 1 | 24h | 100%
Test with IVER software 21.21.140.4 | Karthikeyan Palanisamy | 1 | 64h | 100%
Review solution with GM | Marco Sosa | 1 | 40h | 100%
Review solution with GM | Antonio Jimenez | 1 | 40h | 100%
Approval of change by GM | GM | 1 | 40h | 100%
System Design Sheet update with new hysteresis values | Karthikeyan Palanisamy | 0 | 32h | 100%
Approve System Design Sheet | Antonio Jimenez | 0 | 24h | 100%
Approve System Design Sheet | Karthikeyan Palanisamy | 0 | 24h | 100%
Approve System Design Sheet | Slavko Bogoevski | 0 | 24h | 100%
Software update and release | Leonardo Iratagotia | 0 | 40h | 100%
Test and confirm issue is fixed | Karthikeyan Palanisamy | 0 | 40h | 100%
Update Test Plan | Antonio Jimenez | 1 | 80h | 100%
Update Test Plan | Marco Sosa | 1 | 0h | 100%
Review and approve test plan | Marco Sosa | 1 | 80h | 100%
Review and approve test plan | Antonio Jimenez | 1 | 80h | 100%
Test Plan approval in CEMENT | Marco Sosa | 1 | 128h | 100%
Build DV04 parts | Marco Sosa | 1 | 160h | 100%
Intermittent Short Circuit | Test Lab | 1 | 72h | 100%
Continues Short Circuit | Test Lab | 1 | 24h | 100%
5 Phase update | Marco Sosa | 1 | 16h | 100%
5 Phase review and approval by management | Alejandro Lopez | 0 | 16h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Add details to the 5 phase | Balaji Rao | 1 | 16h | 100%
Add details to the 5 phase | Akhtar Abbas | 1 | 16h | 100%
Add details to the 5 phase | Eliseo Flores | 1 | 16h | 100%
Review with GM | Balaji Rao | 1 | 8h | 100%
Review with GM | Akhtar Abbas | 1 | 8h | 100%
Review with GM | Eliseo Flores | 1 | 8h | 100%
Fix Programming Session to do software reset | Balaji Rao | 1 | 8h | 100%
Fix Network Management Issue | Dayanand Kotla | 1 | 56h | 100%
Integration Testing (partial) | Balaji Rao | 1 | 24h | 100%
sw21.21.142.1 software internal release | Balaji Rao | 1 | 0h | 100%
Redmine testing | Iniyakumar Louis | 1 | 32h | 100%
Redmine testing | Oscar Espinosa | 1 | 32h | 100%
Redmine testing | Sharmila Kokkera | 1 | 32h | 100%
Release rediness test | Iniyakumar Louis | 1 | 16h | 100%
CG3388 Bootloader Tests | Sharmila Kokkera | 1 | 8h | 100%
CG4879 OTA testing | Sharmila Kokkera | 1 | 16h | 100%
Bootloader test | Sharmila Kokkera | 1 | 40h | 100%
Test Report Review | Oscar Espinosa | 1 | 8h | 100%
Update 5 Phases based on the feedback | Balaji Rao | 1 | 40h | 100%
Review with managers | Balaji Rao | 1 | 8h | 100%
Review with managers | Akhtar Abbas | 1 | 8h | 100%
Review with managers | Eliseo Flores | 1 | 8h | 100%
Review with managers | Marco Sosa | 1 | 8h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Reproduce issue | Nikhil Wakaley | 1 | 0h | 100%
Disable alive monitoring | Nikhil Wakaley | 1 | 16h | 100%
Temporary solution verification | Sachin Karkera | 1 | 8h | 100%
Release sw21.21.142.1 with alive monitoring diabled | Neelima Gudem | 1 | 48h | 100%
Re Test software | Nikhil Wakaley | 1 | 8h | 100%
Identify permanent solution | Sachin Karkera | 1 | 72h | 100%
Implement permanent solution | Nikhil Wakaley | 1 | 88h | 100%
Release with Alive Monitoring enabled sw21.21.144 | Neelima Gudem | 1 | 64h | 100%
Retest | Oscar Espinosa | 1 | 56h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Root cause analyis | Azad Mohammed | 1 | 80h | 100%
Permanent solution | Azad Mohammed | 1 | 72h | 100%
Internal SW release | Eliseo Flores | 1 | 24h | 100%
Internal sw testing | Oscar Espinosa | 1 | 56h | 100%
Confirmation at GM Bench | GM | 0 | 0h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Impact analysis for NVM change review | Akhtar Abbas | 1 | 32h | 100%
Implement Cypress Fee in Beta Software 21.145 | Navin Singh | 1 | 48h | 100%
Perform Stress Testing with MAC tester with Beta Software | Oscar Espinosa | 1 | 16h | 100%
Release beta software to GMTCI | Sachin Karkera | 1 | 16h | 100%
GMTCI validation on beta software | GMTCI | 1 | 16h | 100%
Release sw21.21.145 | Akhtar Abbas | 1 | 48h | 100%
GMTCI validation (use sw21.21.145.01) | GMTCI | 0.10000000000000001 | 40h | 100%
5 Phase update | Marco Sosa | 0 | 8h | 100%
5 Phase review and approval by management | Alejandro Lopez | 0 | 8h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
Implement priority change in sw21.21.145.01 | Kiran Khallenhali | 1 | 80h | 100%
Demo fix to GM | Marco Sosa | 1 | 40h | 100%
5 Phase update | Marco Sosa | 1 | 72h | 100%
5 Phase review and approval by management | Alejandro Lopez | 1 | 8h | 100%
Share 5 phase with GM | Marco Sosa | 1 | 0h | 100%
5 Phase update | Marco Sosa | 0 | 32h | 100%
5 Phase review and approval by management | Alejandro Lopez | 0 | 16h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
Create 5 Phase with description | Marco Sosa | 1 | 8h | 100%
Update 5 phase with details from issue | Antonio Jimenez | 1 | 32h | 100%
Update 5 phase with details from issue | Azad Mohammed | 1 | 32h | 100%
Update 5 phase with details from issue | Karthikeyan Palanisamy | 1 | 32h | 100%
Update 5 phase with details from issue | Marco Sosa | 1 | 32h | 100%
Perform Intensity Measurements | Anshuman Mittal | 1 | 16h | 100%
Run HW test with updated software and hardware | Karthikeyan Palanisamy | 1 | 64h | 100%
Run SW test with updated software and hardware | Azad Mohammed | 1 | 64h | 100%
Update 5 whys | Antonio Jimenez | 1 | 40h | 100%
Update 5 whys | Marco Sosa | 1 | 40h | 100%
5 Phase update | Marco Sosa | 0.40000000000000002 | 24h | 100%
5 Phase update | Antonio Jimenez | 0.40000000000000002 | 24h | 100%
5 Phase review and approval by management | Alejandro Lopez | 0 | 16h | 100%
Share 5 phase with GM | Marco Sosa | 0 | 8h | 100%
System Safety Program Plan agreement | KPIT | 1 | 32h | 100%
DIA agreement with GM | KPIT | 1 | 40h | 100%
DIA agreement with GM | Sonika | 1 | 40h | 100%
Basic System Architecture | Alejandro Lopez | 1 | 8h | 100%
Draft FTA design Sketch | Kunal Kulshrestha | 1 | 8h | 100%
FTA (in Medini) | Kunal Kulshrestha | 1 | 72h | 100%
FTA Review | Kunal Kulshrestha | 1 | 8h | 100%
FTA Review | Alejandro Lopez | 1 | 8h | 100%
FTA Review | Karthikeyan Palanisamy | 1 | 8h | 100%
FTA Review | Marco Sosa | 1 | 8h | 100%
FTA Finalization | Kunal Kulshrestha | 1 | 40h | 100%
Cut Set Generation | Kunal Kulshrestha | 1 | 48h | 100%
Cut Set Generation | KPIT | 1 | 48h | 100%
Quantitative Analysis | Sonika | 1 | 40h | 100%
Draft FTA design Sketch | Kunal Kulshrestha | 1 | 144h | 100%
FTA (in Medini) | Kunal Kulshrestha | 1 | 72h | 100%
FTA Review | Kunal Kulshrestha | 1 | 0h | 100%
FTA Finalization | Sonika | 1 | 40h | 100%
Cut Set Generation | Sonika | 1 | 40h | 100%
Quantitative Analysis | Sonika | 1 | 40h | 100%
Concept HW SEFA (SCS-050) | Karthikeyan Palanisamy | 1 | 80h | 100%
Cut-Set Analysis Template (SCS-053) | KPIT | 1 | 48h | 100%
Fault Categorization | Akhtar Abbas | 1 | 8h | 100%
Fault Categorization | Alejandro Lopez | 1 | 8h | 100%
Fault Categorization | Karthikeyan Palanisamy | 1 | 8h | 100%
Fault Categorization | Kunal Kulshrestha | 1 | 8h | 100%
System Degradation Strategy | Akhtar Abbas | 1 | 8h | 100%
System Degradation Strategy | Alejandro Lopez | 1 | 8h | 100%
System Degradation Strategy | Karthikeyan Palanisamy | 1 | 8h | 100%
System Degradation Strategy | Kunal Kulshrestha | 1 | 8h | 100%
Hardware Integrity Strategy | Karthikeyan Palanisamy | 1 | 48h | 100%
Hardware Integrity Strategy | Kunal Kulshrestha | 1 | 48h | 100%
Review of Safety Concept | Alejandro Lopez | 1 | 32h | 100%
Finalization of System Safety Concept (SCS-015) | Akhtar Abbas | 1 | 32h | 100%
Finalization of System Safety Concept (SCS-015) | Alejandro Lopez | 1 | 32h | 100%
Finalization of System Safety Concept (SCS-015) | Karthikeyan Palanisamy | 1 | 32h | 100%
Finalization of System Safety Concept (SCS-015) | Kunal Kulshrestha | 1 | 32h | 100%
Best Practices Evaulation (SCS-094) Concept Phase | Sonika | 1 | 40h | 100%
Concept Review Presentation (SCS-057) Preperation | KPIT | 1 | 16h | 100%
Send SCS-015 to GM for review | Alejandro Lopez | 1 | 8h | 100%
Concept Review Presentation with GM Peer Review Board | Kunal Kulshrestha | 1 | 8h | 100%
Concept Review Presentation with GM Peer Review Board | Alejandro Lopez | 1 | 8h | 100%
Concept Review Presentation with GM Peer Review Board | Karthikeyan Palanisamy | 1 | 8h | 100%
Concept Review Presentation with GM Peer Review Board | Marco Sosa | 1 | 8h | 100%
System Functional Interface Analysis (SCS-016) | Akhtar Abbas | 1 | 24h | 100%
Translation of Hazard Metric (SCS-052) | Akhtar Abbas | 1 | 40h | 100%
Translation of Hazard Metric (SCS-052) | Anshuman Mittal | 1 | 40h | 100%
Translation of Hazard Metric (SCS-052) | Antonio Jimenez | 1 | 40h | 100%
Translation of Hazard Metric (SCS-052) | Mauro Lopez | 1 | 40h | 100%
System Safety Requirements (TSR) | Alejandro Lopez | 1 | 16h | 100%
Hardware Safety Requirements (HSR) | Karthikeyan Palanisamy | 1 | 8h | 100%
Software Safety Requirements (SSR) | Kunal Kulshrestha | 1 | 184h | 100%
Safety Verification / Validation Plan (SCS-017) | Marco Sosa | 1 | 48h | 100%
Safety Verification / Validation Plan (SCS-017) | Karthikeyan Palanisamy | 1 | 0h | 100%
Safety Verification / Validation Plan (SCS-017) | Kunal Kulshrestha | 1 | 0h | 100%
Best Practices Evaulation (SCS-094) Requirement Analysis Phase | KPIT | 1 | 40h | 100%
Requirement Analysis Review Presentation (SCS-058) Preperation | KPIT | 1 | 16h | 100%
Send Requirements Documents to GM for review | Alejandro Lopez | 1 | 8h | 100%
Requirement Analysis Review Presentation (SCS-058) | Kunal Kulshrestha | 1 | 8h | 100%
Requirement Analysis Review Presentation (SCS-058) | Alejandro Lopez | 1 | 8h | 100%
Requirement Analysis Review Presentation (SCS-058) | Karthikeyan Palanisamy | 1 | 8h | 100%
Requirement Analysis Review Presentation (SCS-058) | Marco Sosa | 1 | 8h | 100%
System FMEA Draft | Alejandro Lopez | 1 | 40h | 100%
System FMEA Review | Alejandro Lopez | 1 | 8h | 100%
System FMEA Finalization | Alejandro Lopez | 1 | 24h | 100%
System FMEA Report (SCS-055) Updated by SW | Alejandro Lopez | 1 | 16h | 100%
System FMEA Report (SCS-055) Updated by HW | Alejandro Lopez | 1 | 24h | 100%
System FMEA Report (SCS-055) Finalization | Alejandro Lopez | 1 | 232h | 100%
Software System DFMEA Template (SCS-064) | Azad Mohammed | 1 | 40h | 100%
Software Safety Analysis Report (SCS-063) | Azad Mohammed | 1 | 40h | 100%
Draft FMEDA (Excel Sheet) | KPIT | 1 | 80h | 100%
Draft FMEDA (in Medini) | KPIT | 1 | 40h | 100%
Review of FMEDA | KPIT | 1 | 32h | 100%
Final review by HW Team | Karthikeyan Palanisamy | 1 | 8h | 100%
Final review by HW Team | Slavko Bogoevski | 1 | 8h | 100%
FMEDA Finalization | KPIT | 1 | 24h | 100%
Common Cause Analysis (CCA) | Kunal Kulshrestha | 1 | 8h | 100%
Common Cause Analysis (CCA) | Alejandro Lopez | 1 | 8h | 100%
Common Cause Analysis (CCA) | Karthikeyan Palanisamy | 1 | 8h | 100%
Common Cause Analysis (CCA) | Marco Sosa | 1 | 8h | 100%
System Safety Concept (SCS-015 Update) | Alejandro Lopez | 1 | 32h | 100%
SW Coding Guideline Review (SCS-047) | Azad Mohammed | 1 | 40h | 100%
Safety V&V Plan (SCS-017) Update | Kunal Kulshrestha | 1 | 48h | 100%
Safety V&V Plan (SCS-017) Update | Marco Sosa | 1 | 48h | 100%
Best Practices Evaulation (SCS-094) Design Phase | KPIT | 1 | 40h | 100%
Safety Design Solution Review Presentation (SCS-059) Preperation | KPIT | 1 | 16h | 100%
Safety Design Solution Review Presentation (SCS-059) | Kunal Kulshrestha | 1 | 8h | 100%
Safety Design Solution Review Presentation (SCS-059) | Alejandro Lopez | 1 | 8h | 100%
Safety Design Solution Review Presentation (SCS-059) | Karthikeyan Palanisamy | 1 | 8h | 100%
Safety Design Solution Review Presentation (SCS-059) | Marco Sosa | 1 | 8h | 100%
Diagnostics Coverage (SCS-054) | Kunal Kulshrestha | 1 | 168h | 100%
Update documentation from GM Review 1 according to MOM | Kunal Kulshrestha | 1 | 128h | 100%
Update documentation from GM Review 1 according to MOM | Alejandro Lopez | 1 | 128h | 100%
Update documentation from GM Review 1 according to MOM | Karthikeyan Palanisamy | 1 | 128h | 100%
Update documentation from GM Review 1 according to MOM | Marco Sosa | 1 | 128h | 100%
Share Concept, Requirement Analysis and Design updated presentations to GM | Alejandro Lopez | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 2 with GM | Kunal Kulshrestha | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 2 with GM | Alejandro Lopez | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 2 with GM | Karthikeyan Palanisamy | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 2 with GM | Marco Sosa | 1 | 8h | 100%
Update documentation from GM Review 2 according to MOM | Kunal Kulshrestha | 1 | 240h | 100%
Update documentation from GM Review 2 according to MOM | Marco Sosa | 1 | 240h | 100%
Share Concept, Requirement Analysis and Design updated presentations to GM | Alejandro Lopez | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 3 with GM | Kunal Kulshrestha | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 3 with GM | Alejandro Lopez | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 3 with GM | Marco Sosa | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 3 with GM | Karthikeyan Palanisamy | 1 | 8h | 100%
Concept, Requirement Analysis and Design peer review 3 with GM | David Fabila | 1 | 8h | 100%
SSRs rework | Tien Nguyen | 1 | 64h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 32h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 32h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 32h | 100%
SSRs reviews / update | Leonardo Iratagotia | 1 | 32h | 100%
Architechture Design | Azad Mohammed | 1 | 16h | 100%
Architechture Design | Hemangi Nehete | 1 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 1 | 8h | 100%
Architechture Design Review | Azad Mohammed | 1 | 8h | 100%
Architechture Design Review | Hemangi Nehete | 1 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 1 | 8h | 100%
Unit Design | Azad Mohammed | 1 | 16h | 100%
Unit Design | Hemangi Nehete | 1 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 1 | 8h | 100%
Unit Design Review | Azad Mohammed | 1 | 16h | 100%
Unit Design Review | Hemangi Nehete | 1 | 8h | 100%
Unit Design Review | Pradeep Kumar | 1 | 16h | 100%
Design Implementation | Azad Mohammed | 1 | 48h | 100%
Design Implementation | Hemangi Nehete | 1 | 48h | 100%
Final Integration | Azad Mohammed | 1 | 16h | 100%
Final Integration | Hemangi Nehete | 1 | 16h | 100%
Design Implementation | Priyanka Purbe | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 80h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 40h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 40h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 40h | 100%
SSRs reviews / update | Priyanka Purbe | 1 | 40h | 100%
Architechture Design | Priyanka Purbe | 0 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Priyanka Purbe | 0 | 16h | 100%
Unit Design | Priyanka Purbe | 0 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Priyanka Purbe | 0 | 16h | 100%
Design Implementation | Priyanka Purbe | 0 | 40h | 100%
Design Implementation | Priyanka Purbe | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 80h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 40h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 40h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 40h | 100%
SSRs reviews / update | Priyanka Purbe | 1 | 40h | 100%
Architechture Design | Priyanka Purbe | 0 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Priyanka Purbe | 0 | 16h | 100%
Unit Design | Priyanka Purbe | 0 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Priyanka Purbe | 0 | 16h | 100%
Design Implementation | Priyanka Purbe | 0 | 40h | 100%
Design Implementation | Priyanka Purbe | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 0h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 0h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 0h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 0h | 100%
SSRs reviews / update | Priyanka Purbe | 1 | 0h | 100%
Architechture Design | Priyanka Purbe | 1 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Priyanka Purbe | 0 | 16h | 100%
Unit Design | Priyanka Purbe | 1 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Priyanka Purbe | 0 | 16h | 100%
Design Implementation | Priyanka Purbe | 1 | 40h | 100%
RAM ECC BIST (sw21.21.142.1) | Eliseo Flores | 0.89000000000000001 | 288h | 100%
Design Implementation | Nikhil Wakaley | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 80h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 8h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 8h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 8h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 8h | 100%
Architechture Design | Nikhil Wakaley | 1 | 24h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 16h | 100%
Unit Design | Nikhil Wakaley | 1 | 24h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 16h | 100%
Design Implementation | Nikhil Wakaley | 1 | 40h | 100%
Design Implementation | Nikhil Wakaley | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 80h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 16h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 16h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 16h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 16h | 100%
Architechture Design | Nikhil Wakaley | 1 | 16h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 16h | 100%
Unit Design | Nikhil Wakaley | 1 | 16h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 16h | 100%
Design Implementation | Nikhil Wakaley | 1 | 40h | 100%
Cypress implementation (included in RC-1 for sw21.21.144) | Cypress | 1 | 264h | 100%
RAMP/Altia implementation (include in RC2) | GMTCI | 0.90000000000000002 | 80h | 100%
Error Display and Reporting (include in RC2) | GMTCI | 0.90000000000000002 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 56h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 24h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 24h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 24h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 0h | 100%
Architechture Design | Dayanand Kotla | 0 | 16h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 16h | 100%
Architechture Design Review | Azad Mohammed | 0 | 16h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 16h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 16h | 100%
Unit Design | Dayanand Kotla | 0 | 16h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 16h | 100%
Unit Design Review | Azad Mohammed | 0 | 16h | 100%
Unit Design Review | Pradeep Kumar | 0 | 16h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 16h | 100%
Design Implementation | Dayanand Kotla | 0 | 40h | 100%
SSRs rework | Tien Nguyen | 1 | 80h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 16h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 16h | 100%
SSRs reviews / update | Leonardo Iratagotia | 1 | 16h | 100%
SSRs reviews / update | Balaji Rao | 1 | 16h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 0h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 0h | 100%
Architechture Design | Balaji Rao | 1 | 16h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 16h | 100%
Unit Design | Balaji Rao | 1 | 16h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 16h | 100%
Design Implementation | Balaji Rao | 1 | 40h | 100%
SSRs rework | Tien Nguyen | 1 | 16h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 32h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 32h | 100%
SSRs reviews / update | Leonardo Iratagotia | 1 | 32h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 32h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 32h | 100%
Architechture Design | Nikhil Wakaley | 1 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 24h | 100%
Unit Design | Nikhil Wakaley | 1 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 24h | 100%
Design Implementation | Nikhil Wakaley | 1 | 40h | 100%
SSRs rework | Tien Nguyen | 1 | 16h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 32h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 32h | 100%
SSRs reviews / update | Leonardo Iratagotia | 1 | 32h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 32h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 32h | 100%
Architechture Design | Nikhil Wakaley | 1 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 24h | 100%
Unit Design | Nikhil Wakaley | 1 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 24h | 100%
Design Implementation | Nikhil Wakaley | 1 | 40h | 100%
SSRs rework | Tien Nguyen | 1 | 16h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 32h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 32h | 100%
SSRs reviews / update | Leonardo Iratagotia | 1 | 32h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 32h | 100%
SSRs reviews / update | Nikhil Wakaley | 1 | 32h | 100%
Architechture Design | Nikhil Wakaley | 1 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Architechture Design Review | Nikhil Wakaley | 0 | 24h | 100%
Unit Design | Nikhil Wakaley | 1 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Leonardo Iratagotia | 0 | 24h | 100%
Unit Design Review | Nikhil Wakaley | 0 | 24h | 100%
Design Implementation | Nikhil Wakaley | 1 | 40h | 100%
Application SW-C | Balaji Rao | 0.12 | 384h | 100%
Design Implementation (sw21.21.142.beta) | Balaji Rao | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 16h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 40h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 40h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 40h | 100%
SSRs reviews / update | Balaji Rao | 1 | 40h | 100%
Architechture Design | Kiran Khallenhali | 1 | 24h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Balaji Rao | 0 | 16h | 100%
Unit Design | Kiran Khallenhali | 1 | 24h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Balaji Rao | 0 | 16h | 100%
Design Implementation | Kiran Khallenhali | 1 | 24h | 100%
Design Implementation (sw21.21.142.beta) | Balaji Rao | 1 | 80h | 100%
SSRs rework | Tien Nguyen | 1 | 16h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 40h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 40h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 40h | 100%
SSRs reviews / update | Balaji Rao | 1 | 40h | 100%
Architechture Design | Kiran Khallenhali | 1 | 24h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Balaji Rao | 0 | 16h | 100%
Unit Design | Kiran Khallenhali | 1 | 24h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Balaji Rao | 0 | 16h | 100%
Design Implementation | Kiran Khallenhali | 1 | 24h | 100%
SSRs rework | Tien Nguyen | 1 | 56h | 100%
SSRs reviews / update | Amolshankar Saboji | 1 | 24h | 100%
SSRs reviews / update | Azad Mohammed | 1 | 24h | 100%
SSRs reviews / update | Pradeep Kumar | 1 | 24h | 100%
SSRs reviews / update | Balaji Rao | 1 | 24h | 100%
Architechture Design | Kiran Khallenhali | 0 | 48h | 100%
Architechture Design Review | Amolshankar Saboji | 0 | 8h | 100%
Architechture Design Review | Azad Mohammed | 0 | 8h | 100%
Architechture Design Review | Pradeep Kumar | 0 | 8h | 100%
Architechture Design Review | Balaji Rao | 0 | 16h | 100%
Unit Design | Kiran Khallenhali | 0 | 48h | 100%
Unit Design Review | Amolshankar Saboji | 0 | 8h | 100%
Unit Design Review | Azad Mohammed | 0 | 8h | 100%
Unit Design Review | Pradeep Kumar | 0 | 8h | 100%
Unit Design Review | Balaji Rao | 0 | 16h | 100%
Design Implementation | Kiran Khallenhali | 1 | 40h | 100%
Creation of Tester Drawings | Antonio Jimenez | 1 | 0h | 100%
Creation of Tester Drawings | Karthikeyan Palanisamy | 1 | 0h | 100%
BOM Creation | Antonio Jimenez | 1 | 16h | 100%
BOM Creation | Karthikeyan Palanisamy | 1 | 0h | 100%
Parts ordering | Antonio Jimenez | 1 | 8h | 100%
Parts ordering | Karthikeyan Palanisamy | 1 | 0h | 100%
IPCs with new artwork | Kristine Hiott | 1 | 40h | 100%
IPCs with new artwork | Marco Sosa | 1 | 40h | 100%
Tester build proto 1 | Antonio Jimenez | 1 | 144h | 100%
Tester build proto 1 | Karthikeyan Palanisamy | 1 | 0h | 100%
Integration with IPC | Antonio Jimenez | 1 | 120h | 100%
Integration with IPC | Karthikeyan Palanisamy | 1 | 0h | 100%
Tester build (2 parts) | Antonio Jimenez | 1 | 256h | 100%
Tester build (2 parts) | Karthikeyan Palanisamy | 1 | 0h | 100%
Tester 2 (SYS) | Karthikeyan Palanisamy | 1 | 40h | 100%
Tester 3 (SW) | Karthikeyan Palanisamy | 1 | 176h | 100%
Integration with IPC | Antonio Jimenez | 1 | 40h | 100%
Integration with IPC | Karthikeyan Palanisamy | 1 | 40h | 100%
Creation of HSR Test cases | Antonio Jimenez | 1 | 168h | 100%
Creation of HSR Test cases | Karthikeyan Palanisamy | 1 | 0h | 100%
Update SW FMEA (SCS 063) - sw21.21.145.04 | Pradeep Kumar | 0 | 40h | 100%
Update SW FMEA (SCS 063) - sw21.21.145.04 | Sachin Karkera | 0 | 40h | 100%
Update SW FMEA (SCS 063) - sw21.21.145.05 | Pradeep Kumar | 0 | 40h | 100%
Update SW FMEA (SCS 063) - sw21.21.145.05 | Sachin Karkera | 0 | 40h | 100%
Update System FTA (SCS 061) - sw21.21.145.05 | Pradeep Kumar | 0 | 40h | 100%
Update System FTA (SCS 061) - sw21.21.145.05 | Antonio Jimenez | 0 | 40h | 100%
Update System FTA (SCS 061) - sw21.21.145.05 | Mauro Lopez | 0 | 40h | 100%
Update System FTA (SCS 061) - sw21.21.145.05 | Sachin Karkera | 0 | 40h | 100%
Update Common Mode / Common Cause Analysis - sw21.21.145.04 | Pradeep Kumar | 0 | 24h | 100%
Update System Safety Verification / Validation Planning (SCS 017) - sw21.21.145.04 | Pradeep Kumar | 0 | 40h | 100%
Update System Safety Verification / Validation Planning (SCS 017) - sw21.21.145.04 | Mauro Lopez | 0 | 40h | 100%
Update System Safety Verification / Validation Planning (SCS 017) - sw21.21.145.04 | Sachin Karkera | 0 | 40h | 100%
Safety Process and GM Vehicle Milestone Timing | Pradeep Kumar | 0 | 8h | 100%
NSI GM IPC V&V RASIC Functional Safety | Pradeep Kumar | 0 | 8h | 100%
Technical Safety Requirements | Pradeep Kumar | 0 | 16h | 100%
Technical Safety Requirements | Mauro Lopez | 0 | 16h | 100%
Hardware Safety Requirements | Pradeep Kumar | 0 | 16h | 100%
Hardware Safety Requirements | Karthikeyan Palanisamy | 0 | 16h | 100%
Software Safety Requirements | Pradeep Kumar | 0 | 40h | 100%
Software Safety Requirements | Sachin Karkera | 0 | 40h | 100%
Software Safety Requirements | Tien Nguyen | 0 | 40h | 100%
Safety Concept Report (SCS-015) | Pradeep Kumar | 0 | 16h | 100%
Safety Concept Report (SCS-015) | Antonio Jimenez | 0 | 16h | 100%
Safety Concept Report (SCS-015) | Mauro Lopez | 0 | 16h | 100%
Safety Concept Report (SCS-015) | Sachin Karkera | 0 | 16h | 100%
Safety Concept Report (SCS-015) | Marco Sosa | 0 | 16h | 100%
Common Mode/Common Cause Analysis Report | Pradeep Kumar | 0 | 0h | 100%
FTA Report (SCS_061) | Pradeep Kumar | 0 | 0h | 100%
FMEDA Report (SCS_055) | Pradeep Kumar | 0 | 0h | 100%
SW FMEA Report (SCS_063) | Pradeep Kumar | 0 | 0h | 100%
Presentation Internal review | Pradeep Kumar | 0 | 8h | 100%
Presentation Internal review | Antonio Jimenez | 0 | 8h | 100%
Presentation Internal review | Mauro Lopez | 0 | 8h | 100%
Presentation Internal review | Sachin Karkera | 0 | 8h | 100%
Presentation Internal review | Marco Sosa | 0 | 8h | 100%
Update presentation | Pradeep Kumar | 0 | 16h | 100%
Share with GM Update Safety Implementation Review presentation | Pradeep Kumar | 0 | 0h | 100%
Update safety Implementation review presentation after GM review | Pradeep Kumar | 0 | 56h | 100%
Share safety Implementation review presentation with GM after review comment fix | Pradeep Kumar | 0 | 0h | 100%
Safety Implementation Review with GM | Pradeep Kumar | 0 | 8h | 100%
HSR Test execution phase 1 (HW releated test cases only sw21.21.142.1) | Mark Ho | 1 | 80h | 100%
HSR Test execution phase 2 (pending for new sw to fix redmine) | Mark Ho | 0 | 80h | 100%
Test Report creation | Mark Ho | 0 | 40h | 100%
Test Report review with hardware team | Karthikeyan Palanisamy | 0 | 40h | 100%
Test Report review with hardware team | Antonio Jimenez | 0 | 40h | 100%
Test Report review with hardware team | Slavko Bogoevski | 0 | 40h | 100%
Test Report review with FuSa team | Karthikeyan Palanisamy | 0 | 40h | 100%
Test Report review with FuSa team | Pradeep Kumar | 0 | 40h | 100%
Test Report approval | Antonio Jimenez | 0 | 8h | 100%
Test Report approval | Karthikeyan Palanisamy | 0 | 8h | 100%
Test Report approval | Pradeep Kumar | 0 | 8h | 100%
Test Report approval | Slavko Bogoevski | 0 | 8h | 100%
Test Results upload to DOORS | Karthikeyan Palanisamy | 0 | 40h | 100%
Create Traceability to Test Results | Karthikeyan Palanisamy | 0 | 40h | 100%
Code inspection | Azad Mohammed | 0 | 0h | 100%
Code inspection | Balaji Rao | 0 | 0h | 100%
Code inspection | Hemangi Nehete | 0 | 0h | 100%
Code inspection | Neelima Gudem | 0 | 0h | 100%
Code inspection | Nikhil Wakaley | 0 | 0h | 100%
Static code analysis | Azad Mohammed | 0 | 0h | 100%
Static code analysis | Balaji Rao | 0 | 0h | 100%
Static code analysis | Hemangi Nehete | 0 | 0h | 100%
Static code analysis | Neelima Gudem | 0 | 0h | 100%
Static code analysis | Nikhil Wakaley | 0 | 0h | 100%
Analysis of requirements | Azad Mohammed | 0 | 0h | 100%
Analysis of requirements | Balaji Rao | 0 | 0h | 100%
Analysis of requirements | Hemangi Nehete | 0 | 0h | 100%
Analysis of requirements | Neelima Gudem | 0 | 0h | 100%
Analysis of requirements | Nikhil Wakaley | 0 | 0h | 100%
Equivalence classes generation | Azad Mohammed | 0 | 0h | 100%
Equivalence classes generation | Balaji Rao | 0 | 0h | 100%
Equivalence classes generation | Hemangi Nehete | 0 | 0h | 100%
Equivalence classes generation | Neelima Gudem | 0 | 0h | 100%
Equivalence classes generation | Nikhil Wakaley | 0 | 0h | 100%
Boundary Classes | Azad Mohammed | 0 | 0h | 100%
Boundary Classes | Balaji Rao | 0 | 0h | 100%
Boundary Classes | Hemangi Nehete | 0 | 0h | 100%
Boundary Classes | Neelima Gudem | 0 | 0h | 100%
Boundary Classes | Nikhil Wakaley | 0 | 0h | 100%
Requirements based | Azad Mohammed | 0 | 0h | 100%
Requirements based | Balaji Rao | 0 | 0h | 100%
Requirements based | Hemangi Nehete | 0 | 0h | 100%
Requirements based | Neelima Gudem | 0 | 0h | 100%
Requirements based | Nikhil Wakaley | 0 | 0h | 100%
Statement Coverage/Branch Coverage | Azad Mohammed | 0 | 0h | 100%
Statement Coverage/Branch Coverage | Balaji Rao | 0 | 0h | 100%
Statement Coverage/Branch Coverage | Hemangi Nehete | 0 | 0h | 100%
Statement Coverage/Branch Coverage | Neelima Gudem | 0 | 0h | 100%
Statement Coverage/Branch Coverage | Nikhil Wakaley | 0 | 0h | 100%
Requirements based Testing | Azad Mohammed | 0 | 0h | 100%
Requirements based Testing | Balaji Rao | 0 | 0h | 100%
Requirements based Testing | Hemangi Nehete | 0 | 0h | 100%
Requirements based Testing | Neelima Gudem | 0 | 0h | 100%
Requirements based Testing | Nikhil Wakaley | 0 | 0h | 100%
Fault Injection | Azad Mohammed | 0 | 0h | 100%
Fault Injection | Balaji Rao | 0 | 0h | 100%
Fault Injection | Hemangi Nehete | 0 | 0h | 100%
Fault Injection | Neelima Gudem | 0 | 0h | 100%
Fault Injection | Nikhil Wakaley | 0 | 0h | 100%
Analysis of requirements | Azad Mohammed | 0 | 0h | 100%
Analysis of requirements | Balaji Rao | 0 | 0h | 100%
Analysis of requirements | Hemangi Nehete | 0 | 0h | 100%
Analysis of requirements | Neelima Gudem | 0 | 0h | 100%
Analysis of requirements | Nikhil Wakaley | 0 | 0h | 100%
Equivalence classes generation | Azad Mohammed | 0 | 0h | 100%
Equivalence classes generation | Balaji Rao | 0 | 0h | 100%
Equivalence classes generation | Hemangi Nehete | 0 | 0h | 100%
Equivalence classes generation | Neelima Gudem | 0 | 0h | 100%
Equivalence classes generation | Nikhil Wakaley | 0 | 0h | 100%
Boundary Classes | Azad Mohammed | 0 | 0h | 100%
Boundary Classes | Balaji Rao | 0 | 0h | 100%
Boundary Classes | Hemangi Nehete | 0 | 0h | 100%
Boundary Classes | Neelima Gudem | 0 | 0h | 100%
Boundary Classes | Nikhil Wakaley | 0 | 0h | 100%
Requirements based | Azad Mohammed | 0 | 0h | 100%
Requirements based | Balaji Rao | 0 | 0h | 100%
Requirements based | Hemangi Nehete | 0 | 0h | 100%
Requirements based | Neelima Gudem | 0 | 0h | 100%
Requirements based | Nikhil Wakaley | 0 | 0h | 100%
Interface Test | Azad Mohammed | 0 | 0h | 100%
Interface Test | Balaji Rao | 0 | 0h | 100%
Interface Test | Hemangi Nehete | 0 | 0h | 100%
Interface Test | Neelima Gudem | 0 | 0h | 100%
Interface Test | Nikhil Wakaley | 0 | 0h | 100%
Requirements based Testing | Azad Mohammed | 0 | 0h | 100%
Requirements based Testing | Balaji Rao | 0 | 0h | 100%
Requirements based Testing | Hemangi Nehete | 0 | 0h | 100%
Requirements based Testing | Neelima Gudem | 0 | 0h | 100%
Requirements based Testing | Nikhil Wakaley | 0 | 0h | 100%
Fault Injection | Azad Mohammed | 0 | 0h | 100%
Fault Injection | Balaji Rao | 0 | 0h | 100%
Fault Injection | Hemangi Nehete | 0 | 0h | 100%
Fault Injection | Neelima Gudem | 0 | 0h | 100%
Fault Injection | Nikhil Wakaley | 0 | 0h | 100%
Analysis of requirements | Oscar Espinosa | 0 | 0h | 100%
Equivalence classes generation | Oscar Espinosa | 0 | 0h | 100%
Boundary Classes | Oscar Espinosa | 0 | 0h | 100%
Requirements based | Oscar Espinosa | 0 | 0h | 100%
Interface Test | Oscar Espinosa | 0 | 0h | 100%
Requirements based Testing | Oscar Espinosa | 0 | 0h | 100%
Fault Injection | Oscar Espinosa | 0 | 0h | 100%
Environmental conditions analysis, Internal, External Interfaces | Mauro Lopez | 0 | 0h | 100%
Test of interaction and communication | Mauro Lopez | 0 | 0h | 100%
Fault Injection | Mauro Lopez | 0 | 0h | 100%
Requirement based | Mauro Lopez | 0 | 0h | 100%
Resource Usage test | Mauro Lopez | 0 | 0h | 100%
Performance Test | Mauro Lopez | 0 | 0h | 100%
Requirement based | GM | 0 | 0h | 100%
Fault Injection | GM | 0 | 0h | 100%
Long-Term test | GM | 0 | 0h | 100%
User test under real life scenarios | GM | 0 | 0h | 100%
Performance Test | GM | 0 | 0h | 100%
Safety plan | Amolshankar Saboji | 0 | 0h | 100%
Safety plan | Pradeep Kumar | 0 | 0h | 100%
Technical safety requirements | Amolshankar Saboji | 1 | 40h | 100%
Technical safety requirements | Pradeep Kumar | 1 | 40h | 100%
Technical architecture | Amolshankar Saboji | 1 | 40h | 100%
Technical architecture | Pradeep Kumar | 1 | 40h | 100%
Technical safety concept | Amolshankar Saboji | 1 | 40h | 100%
Technical safety concept | Pradeep Kumar | 1 | 40h | 100%
System design | Amolshankar Saboji | 0 | 0h | 100%
System design | Pradeep Kumar | 0 | 0h | 100%
Hardware-software integration and testing. | Amolshankar Saboji | 0 | 40h | 100%
Hardware-software integration and testing. | Pradeep Kumar | 0 | 40h | 100%
Item integration and testing.(System integration and testing) | Amolshankar Saboji | 0 | 8h | 100%
Item integration and testing.(System integration and testing) | Pradeep Kumar | 0 | 8h | 100%
Hardware safety requirements | Amolshankar Saboji | 1 | 24h | 100%
Hardware safety requirements | Pradeep Kumar | 1 | 24h | 100%
Hardware architectural design | Pradeep Kumar | 0 | 0h | 100%
Safety analyses(See Part 8 section 12 Annexure 12) Hardware | Pradeep Kumar | 0 | 0h | 100%
Hardware detailed design | Pradeep Kumar | 0 | 0h | 100%
Diagnostics requirements | Pradeep Kumar | 0 | 0h | 100%
Diagnostics Coverage Implementation | Pradeep Kumar | 0 | 0h | 100%
hardware architectural metrics(SPF, LFM, PMHF, FTA) | Pradeep Kumar | 0 | 0h | 100%
Random hardware failures | Pradeep Kumar | 0 | 0h | 100%
Review of Hardware test case, test procedure and test results(boardlevel and integration testing) | Amolshankar Saboji | 1 | 40h | 100%
Review of Hardware test case, test procedure and test results(boardlevel and integration testing) | Pradeep Kumar | 1 | 40h | 100%
Software safety requirements 1st review | Amolshankar Saboji | 1 | 64h | 100%
Software safety requirements 1st review | Pradeep Kumar | 1 | 64h | 100%
Software architectural design 1st review | Amolshankar Saboji | 1 | 32h | 100%
Software architectural design 1st review | Pradeep Kumar | 1 | 32h | 100%
Software unit design and implementation | Amolshankar Saboji | 0 | 320h | 100%
Review of MISRA coding guidelines. | Amolshankar Saboji | 1 | 24h | 100%
Software unit testing (safety requirements) | Amolshankar Saboji | 0 | 320h | 100%
Software integration and testing (safety requirements) | Amolshankar Saboji | 0 | 320h | 100%
Software qualification testing (end to end) | Amolshankar Saboji | 0 | 320h | 100%
SYS4 and SYS5 Tese Cases review | Amolshankar Saboji | 1 | 192h | 100%
Software component qualification report | Amolshankar Saboji | 0 | 0h | 100%
Hardware component qualification report | Amolshankar Saboji | 0 | 0h | 100%
Freedom from Inteference | Amolshankar Saboji | 0 | 0h | 100%
Safety case | Amolshankar Saboji | 0 | 616h | 100%
Confirmation measures | Amolshankar Saboji | 0 | 40h | 100%
Functional safety audit | Amolshankar Saboji | 0 | 40h | 100%
Functional safety assessment | Amolshankar Saboji | 0 | 40h | 100%
Update Safety V&V Presentation | Pradeep Kumar | 0 | 80h | 100%
Share with GM Update Safety V&V Review presentation | Pradeep Kumar | 0 | 0h | 100%
Update safety V&V review presentation after GM review | Pradeep Kumar | 0 | 56h | 100%
Share safety V&V review presentation with GM after review comment fix | Pradeep Kumar | 0 | 0h | 100%
Safety V&V Review with GM | Pradeep Kumar | 0 | 8h | 100%
Collect order quantity needed for pre IVER samples (bench, DV01,NSNADC samples, TCI) | Alejandro Lopez | 1 | 40h | 100%
Create RFP for bench, DV01 and other pre IVER samples (mod C1UC parts) | Alejandro Lopez | 1 | 32h | 100%
Build PCBs | NS | 1 | 328h | 100%
Ship to NSI | NS | 1 | 40h | 100%
Rework IPCs with new PCB | Marco Sosa | 0 | 40h | 100%
Define Reflash plan and tools for Bench and IVER parts | Akhtar Abbas | 1 | 336h | 100%
Develop SW Validation Test Plan (strategy) | Oscar Espinosa | 1 | 1,144h | 100%
Internal SW release | Akhtar Abbas | 1 | 16h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 40h | 100%
SW Validation Testing | Oscar Espinosa | 1 | 120h | 100%
SW Validation Test Report | Oscar Espinosa | 1 | 344h | 100%
Internal SW Release | Akhtar Abbas | 1 | 16h | 100%
SW issues report and status of the SW | Akhtar Abbas | 1 | 16h | 100%
Memory and Cal Release for testing (both variants) | Akhtar Abbas | 1 | 48h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 64h | 100%
SW Validation Testing | Oscar Espinosa | 1 | 298.4h | 100%
SW Validation Test Report | Oscar Espinosa | 1 | 8h | 100%
SW Release | Akhtar Abbas | 1 | 16h | 100%
Develop SW Validation Test Specification | Oscar Espinosa | 1 | 168h | 100%
Develop SW Validation Test Specification | HCL | 1 | 168h | 100%
SWE6 Test Case Creation | Oscar Espinosa | 1 | 408h | 100%
Internal SW release | Akhtar Abbas | 1 | 16h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 24h | 100%
SWE4 Integration Testing | Sachin Karkera | 1 | 288h | 100%
SWE6 Verification Testing | Oscar Espinosa | 1 | 208h | 100%
SWE6 Verification Test Report | Oscar Espinosa | 1 | 272h | 100%
SYS4 Validation Testing | Oscar Espinosa | 1 | 208h | 100%
SYS5 Validation Testing | Oscar Espinosa | 1 | 208h | 100%
SYS Validation Test Report | Oscar Espinosa | 1 | 224h | 100%
SW Release to GM (138.0) | Akhtar Abbas | 1 | 0h | 100%
Internal SW release (W3) | Sachin Karkera | 1 | 8h | 100%
Master TWN | Marco Sosa | 1 | 8h | 100%
TWN to JPN | Kunal Kulshrestha | 1 | 80h | 100%
Integration Test Cases creation | Sachin Karkera | 1 | 720h | 100%
Internal SW release | Akhtar Abbas | 1 | 64h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 8h | 100%
SWE4 Validation Testing | Akhtar Abbas | 1 | 160h | 100%
SWE6 Verification Testing | Oscar Espinosa | 1 | 328h | 100%
SWE6 Test Case Creation and Updates | Oscar Espinosa | 1 | 120h | 100%
Test Execution | Oscar Espinosa | 1 | 144h | 100%
SW Validation Test Report | Akhtar Abbas | 1 | 16h | 100%
Power Mode | Rajalakshmi M | 1 | 120h | 100%
CAN | Rajalakshmi M | 1 | 104h | 100%
LIN | Rajalakshmi M | 1 | 152h | 100%
TFT | Rajalakshmi M | 1 | 160h | 100%
Telltales | Rajalakshmi M | 1 | 120h | 100%
Ethernet | Rajalakshmi M | 1 | 136h | 100%
Gages | Rajalakshmi M | 1 | 64h | 100%
IOs | Rajalakshmi M | 1 | 56h | 100%
Illumination | Rajalakshmi M | 1 | 64h | 100%
Memory | Rajalakshmi M | 1 | 56h | 100%
Segment Display | Rajalakshmi M | 1 | 64h | 100%
Bootloader | Rajalakshmi M | 1 | 40h | 100%
Bootloader | Rajalakshmi M | 1 | 16h | 100%
Telltales | Rajalakshmi M | 1 | 32h | 100%
Illumination | Rajalakshmi M | 1 | 24h | 100%
Power Mode | Rajalakshmi M | 1 | 16h | 100%
CAN | Rajalakshmi M | 1 | 24h | 100%
LIN | Rajalakshmi M | 1 | 16h | 100%
TFT | Rajalakshmi M | 1 | 16h | 100%
Ethernet | Rajalakshmi M | 1 | 16h | 100%
Gages | Rajalakshmi M | 1 | 16h | 100%
HWIOs | Rajalakshmi M | 1 | 16h | 100%
Memory | Rajalakshmi M | 1 | 16h | 100%
Segment Display | Rajalakshmi M | 1 | 16h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 80h | 100%
Power Moding | Kalpana Dakshnamoorthy | 1 | 96h | 100%
Line Test | Kalpana Dakshnamoorthy | 1 | 96h | 100%
CAN | Kalpana Dakshnamoorthy | 1 | 112h | 100%
Gauges | Kalpana Dakshnamoorthy | 1 | 112h | 100%
LIN | Kalpana Dakshnamoorthy | 1 | 64h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 48h | 100%
Ethernet | Kalpana Dakshnamoorthy | 1 | 48h | 100%
Telltales | Kalpana Dakshnamoorthy | 1 | 48h | 100%
Illumination | Kalpana Dakshnamoorthy | 1 | 48h | 100%
TFT | Kalpana Dakshnamoorthy | 1 | 56h | 100%
NVM | Kalpana Dakshnamoorthy | 1 | 56h | 100%
Functional Safety | Kalpana Dakshnamoorthy | 1 | 48h | 100%
Software Stress Test Case creation | Kalpana Dakshnamoorthy | 1 | 120h | 100%
Fuzz Test CG4579 Test Case creation | ETAS | 1 | 56h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Telltales | Kalpana Dakshnamoorthy | 1 | 24h | 100%
TFT | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Illumination | Kalpana Dakshnamoorthy | 1 | 32h | 100%
Power Moding | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Gauges | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Ethernet | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Stress Testing | Kalpana Dakshnamoorthy | 1 | 56h | 100%
Line Test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
CAN | Kalpana Dakshnamoorthy | 1 | 56h | 100%
LIN | Kalpana Dakshnamoorthy | 1 | 32h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 48h | 100%
NVM | Kalpana Dakshnamoorthy | 1 | 56h | 100%
Functional Safety | Kalpana Dakshnamoorthy | 1 | 16h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance | Mathukumar Kuthalingam | 0 | 160h | 100%
CG3687 - Bootloader Flash Programming | Mathukumar Kuthalingam | 1 | 200h | 100%
CG3877 - CAN Physical Layer Test | Mathukumar Kuthalingam | 1 | 216h | 100%
CG3689 - Ethernet AVB Device Test | Mathukumar Kuthalingam | 0 | 152h | 100%
CG4111 - Global B Serial Data and Diagnostics Test | Mathukumar Kuthalingam | 0 | 144h | 100%
Fuzz Test Execution | ETAS | 0 | 200h | 100%
SYS Validation Test Report | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Master TWN | Marco Sosa | 1 | 8h | 100%
TWN to JPN | Kunal Kulshrestha | 1 | 80h | 100%
CG4422 (Form for CG2999) | Akhtar Abbas | 1 | 96h | 100%
CG4422 (Form for CG2999) | Akhtar Abbas | 1 | 80h | 100%
SW release to GM | Akhtar Abbas | 1 | 0h | 100%
SCS-057 Safety Concept Review Presentation | Akhtar Abbas | 1 | 40h | 100%
SCS-057 Safety Concept Review Presentation | Anshuman Mittal | 1 | 40h | 100%
SCS-057 Safety Concept Review Presentation | Antonio Jimenez | 1 | 40h | 100%
SCS-057 Safety Concept Review Presentation | Mauro Lopez | 1 | 40h | 100%
SCS-058 Safety Requirement Review Presentation | Akhtar Abbas | 1 | 40h | 100%
SCS-058 Safety Requirement Review Presentation | Anshuman Mittal | 1 | 40h | 100%
SCS-058 Safety Requirement Review Presentation | Antonio Jimenez | 1 | 40h | 100%
SCS-058 Safety Requirement Review Presentation | Mauro Lopez | 1 | 40h | 100%
SCS-059 Safety Design Review Presentation | Akhtar Abbas | 1 | 40h | 100%
SCS-059 Safety Design Review Presentation | Anshuman Mittal | 1 | 40h | 100%
SCS-059 Safety Design Review Presentation | Antonio Jimenez | 1 | 40h | 100%
SCS-059 Safety Design Review Presentation | Mauro Lopez | 1 | 40h | 100%
Concept, Design & Requirements Phase Review with GM | Akhtar Abbas | 1 | 0h | 100%
Concept, Design & Requirements Phase Review with GM | Anshuman Mittal | 1 | 0h | 100%
Concept, Design & Requirements Phase Review with GM | Antonio Jimenez | 1 | 0h | 100%
Concept, Design & Requirements Phase Review with GM | Mauro Lopez | 1 | 0h | 100%
Mechanical Design | Anshuman Mittal | 1 | 560h | 100%
Draft LED Management Sheet | Anshuman Mittal | 1 | 120h | 100%
Draft PCB Interface DWG | Anshuman Mittal | 1 | 120h | 100%
Variation List - First 3 pages | Anshuman Mittal | 1 | 120h | 100%
Final LED Management Sheet | Anshuman Mittal | 1 | 120h | 100%
Final PCB Interface DWG | Anshuman Mittal | 1 | 120h | 100%
DFMEA | Anshuman Mittal | 1 | 0h | 100%
Graphic freeze from GM | Anshuman Mittal | 1 | 0h | 100%
Graphic Check | Anshuman Mittal | 1 | 40h | 100%
NS Review of graphics | Anshuman Mittal | 1 | 80h | 100%
Supplier Selection and Drawing Release | Anshuman Mittal | 1 | 1,136h | 100%
Advanced drawing for tooling quotes | Anshuman Mittal | 1 | 8h | 100%
Advanced BOM released for Quoting DV02 and IVER | Anshuman Mittal | 1 | 8h | 100%
Advanced BOM for DV01 Parts (Modified C1UB) | Anshuman Mittal | 1 | 0h | 100%
Final Supplier selection | Kristine Hiott | 1 | 80h | 100%
Tooling Design Review | Anshuman Mittal | 1 | 584h | 100%
Applique final drawing release | Anshuman Mittal | 1 | 8h | 100%
Kick off lens & Visor 3D & 2D | Anshuman Mittal | 1 | 8h | 100%
OK to tool Drawing from Customer | Anshuman Mittal | 1 | 0h | 100%
Plastic Outer case and Chrome ring Drawing Release | Anshuman Mittal | 1 | 0h | 100%
Final IVER BOM | Anshuman Mittal | 1 | 72h | 100%
Final Variation List | Anshuman Mittal | 1 | 232h | 100%
Final LED Management Sheet Received | Hugo Nunez | 1 | 0h | 100%
Final PCB Interface DWG Received | Hugo Nunez | 1 | 0h | 100%
DV and IVER PCB BOM Release | Antonio Jimenez | 1 | 568h | 100%
DV and IVER PCB BOM Release | Antonio Jimenez | 1 | 451.2h | 100%
PCB prototype check template | Antonio Jimenez | 1 | 496h | 100%
NS PCB Blank | Yoshio Tanaka | 1 | 160h | 100%
Deliver Line Test to NS | Akhtar Abbas | 1 | 2,160h | 100%
NS PCB Assy& testing | Yoshio Tanaka | 1 | 200h | 100%
NS Ship PCB to NSII | Yoshio Tanaka | 1 | 40h | 100%
Sys / SW to decide Micro Strategy, Architecture, & Type | Akhtar Abbas | 1 | 0h | 100%
SW/SYS: Decide External or Emulated EEPROM & Capacity | Akhtar Abbas | 1 | 0h | 100%
HW: Complete Block Diagram | Hugo Nunez | 1 | 0h | 100%
MECHA: Provide Stepper Motor Movement Type, Pointer Inertial Moment all per variation | Anshuman Mittal | 1 | 40h | 100%
SW/SYS: Stepper Motor Drive Duty (Normal Operation & Initial Response) | Akhtar Abbas | 1 | 80h | 100%
SW/SYS: Decide Strategy for Linetest Communication | Akhtar Abbas | 1 | 400h | 100%
SW/SYS: Strategy for data Re-writing for all ROM | Akhtar Abbas | 1 | 400h | 100%
SW/SYS: Requirements for Switchbox | Akhtar Abbas | 1 | 0h | 100%
SW/SYS: HW based functions implementation schedule & All Clocks | Akhtar Abbas | 1 | 0h | 100%
HW: Port Function Definition & HW Settings | Hugo Nunez | 1 | 0h | 100%
HW: Provide Initial Proposal for System Frequencies | Hugo Nunez | 1 | 0h | 100%
SW/SYS: Provide and Set Full System Clock Tree | Hugo Nunez | 1 | 0h | 100%
HW: Review Clock tree and Provide Feedback on selected Frequencies | Hugo Nunez | 1 | 0h | 100%
HW: Create HW Power Sequence Spec | Hugo Nunez | 1 | 40h | 100%
SW/SYS: Create SW Power Sequence Spec | Akhtar Abbas | 1 | 80h | 100%
EMC SW/Canoe Panel Draft | Akhtar Abbas | 1 | 400h | 100%
EMC DV Spec | Akhtar Abbas | 1 | 464h | 100%
EMC DV Test software released | Akhtar Abbas | 1 | 1,128h | 100%
EMC SW/CANoe panel Final | Devendra Takola | 1 | 744h | 100%
EMC & DV SW | Antonio Jimenez | 1 | 320h | 100%
DV CANoe Panel | Devendra Takola | 1 | 64h | 100%
TWN for Sabina | Marco Sosa | 1 | 16h | 100%
Master TWN | Marco Sosa | 1 | 8h | 100%
TWN to Sabina | Devendra Takola | 1 | 8h | 100%
ENV DV test software validated by Sabina with Galaxy | Thom Barber | 1 | 88h | 100%
Receive Tooling PO from GM | Kristine Hiott | 1 | 0h | 100%
NSI PO to suppliers | Kristine Hiott | 1 | 112h | 100%
Tooling lead time | Kristine Hiott | 1 | 200h | 100%
T0 part including measurement data / shipping | Kristine Hiott | 1 | 80h | 100%
T1 part including measurement data / shipping | Kristine Hiott | 1 | 40h | 100%
Mold Lens DV/IVER parts | Kristine Hiott | 1 | 40h | 100%
Ship to welder | Kristine Hiott | 1 | 40h | 100%
Tooling lead time | Kristine Hiott | 1 | 220h | 100%
T1 part including measurement data / shipping | Kristine Hiott | 1 | 80h | 100%
T2 part including measurement data / shipping | Kristine Hiott | 1 | 40h | 100%
Mold Visor weilding trail parts | Kristine Hiott | 1 | 16h | 100%
Ship Visor to welder | Kristine Hiott | 1 | 40h | 100%
Round trip & graining | Anshuman Mittal | 1 | 136h | 100%
Mold grain visors | Tooling Supplier | 1 | 24h | 100%
Ship grained visor to welder | Anshuman Mittal | 1 | 32h | 100%
Tooling lead time | Anshuman Mittal | 1 | 280h | 100%
T0 part including measurement data / shipping | Anshuman Mittal | 1 | 80h | 100%
T1 part including measurement data / shipping | Anshuman Mittal | 1 | 80h | 100%
Mold Back Cover DV/IVER parts | Anshuman Mittal | 1 | 80h | 100%
Ship Back cover to NSII | Anshuman Mittal | 1 | 40h | 100%
Tooling lead time | Anshuman Mittal | 1 | 440h | 100%
Mold Decorative DV/IVER parts | Anshuman Mittal | 1 | 40h | 100%
Ship Decorative ring to NSII for heat staking | Anshuman Mittal | 1 | 40h | 100%
Film& Drawing Preparation | Anshuman Mittal | 1 | 80h | 100%
Screen preparation and printing | Anshuman Mittal | 1 | 80h | 100%
Forming and applique blank tooling lead time | Yoshio Tanaka | 1 | 200h | 100%
forming and punching | Anshuman Mittal | 1 | 80h | 100%
applique - shipping to OB supplier | Yoshio Tanaka | 1 | 24h | 100%
Applique shipping to NSII for LEG2 and LEG6 - no OB required | Yoshio Tanaka | 1 | 40h | 100%
TFT to NS | Anshuman Mittal | 1 | 40h | 100%
Receive applique | Anshuman Mittal | 1 | 16h | 100%
Optical bonding process | Anshuman Mittal | 1 | 200h | 100%
Ship OB assembly to NSII for heat staking | Anshuman Mittal | 1 | 40h | 100%
Laser Weld tooling lead time | Anshuman Mittal | 1 | 440h | 100%
Tune Weld fix | Anshuman Mittal | 1 | 24h | 100%
Weld samples | Anshuman Mittal | 1 | 24h | 100%
Ship lens+Visor assembly to NSII | Anshuman Mittal | 1 | 16h | 100%
Draft EMC test plan | Hugo Nunez | 1 | 0h | 100%
Final EMC test plan | Hugo Nunez | 1 | 160h | 100%
EMC test plan negotiation with Richard Grunow | Hugo Nunez | 1 | 88h | 100%
EMC DV test plan approval | Alejandro Lopez | 1 | 0h | 100%
Environmental Test Plan Creation | Alejandro Lopez | 1 | 40h | 100%
Environmental Test Plan update | Marco Sosa | 1 | 480h | 100%
ENV Test Plan Submission to Customer and Negotiation | Marco Sosa | 1 | 40h | 100%
Update ENV Test Plan | Marco Sosa | 1 | 40h | 100%
ENV Tests Plan approval (DV01) | GM | 1 | 144h | 100%
ENV Test Plan Update (DV01) - Resubmit for Vibration Fixture deviation | Marco Sosa | 1 | 120h | 100%
ENV Test Plan approval (DV01) - Resubmit for Vibration Fixture deviation | GM | 1 | 40h | 100%
ENV Tests Plan approval (DV02) | GM | 1 | 256h | 100%
Test request / test specimen sheet format | Marco Sosa | 1 | 16h | 100%
Receive PCB board | Yoshio Tanaka | 1 | 16h | 100%
Flash PCB baords with DV test SW | Yoshio Tanaka | 1 | 16h | 100%
Receive ME components | Yoshio Tanaka | 1 | 16h | 100%
Trial Assembly | Yoshio Tanaka | 1 | 8h | 100%
Build clusters | Yoshio Tanaka | 1 | 40h | 100%
DV samples delivery | Donnie Baise | 1 | 16h | 100%
Visual Inspection and Dissection – DRBTR (Leg 0a) | Marco Sosa | 1 | 8h | 100%
Cross Section and Inspection | Sabina lab | 1 | 24h | 100%
Thermal Cycle Profile Development | Sabina lab | 1 | 64h | 100%
Vibration Transmissibility Demonstration | Sabina lab | 1 | 80h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 8h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 16h | 100%
High Temperature Degradation | Sabina Lab (24h) | 1 | 129h | 100%
Mechanical Shock Pothole | Sabina lab | 1 | 8h | 100%
Vibration with Thermal Cycling | Sabina lab | 1 | 56h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 16h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 40h | 100%
Cross Section and Inspection | Sabina lab | 1 | 32h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 8h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 8h | 100%
Humid Heat Cyclic | Sabina Lab (24h) | 1 | 249h | 100%
Humid Heat Constant | Sabina Lab (24h) | 1 | 249h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 16h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 40h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 8h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 16h | 100%
Thermal Shock Air to Air (100 cycles) | Sabina lab | 1 | 56h | 100%
Power Temperature Cycle (100 cycles) | Sabina lab | 1 | 64h | 100%
1 point functional/parametric check | Sabina lab | 1 | 8h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 24h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 16h | 100%
Dust | Sabina lab | 1 | 16h | 100%
Water | Sabina lab | 1 | 8h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 8h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 40h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 16h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 8h | 100%
Jump Start | Troy lab | 1 | 40h | 100%
Reverse Polarity | Troy lab | 1 | 40h | 100%
Over Voltage | Troy lab | 1 | 40h | 100%
State Change Waveform Characterization | Troy lab | 1 | 24h | 100%
Ground Path Inductive Sensitivity | Troy lab | 1 | 0h | 100%
Parasitic Current | Troy lab | 1 | 8h | 100%
Power Supply Interruptions | Troy lab | 1 | 0h | 100%
Battery Voltage Dropout | Troy lab | 1 | 24h | 100%
Sinusoidal Superimposed Voltage | Troy lab | 1 | 0h | 100%
Pulse Superimposed Voltage | Troy lab | 1 | 8h | 100%
Ground Offset | Troy lab | 1 | 8h | 100%
Power Offset | Troy lab | 1 | 0h | 100%
Crank Pulse Capability | Troy lab | 1 | 24h | 100%
1 point functional/parametric check | Sabina lab | 1 | 8h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 24h | 100%
Low Temperature Wakeup | Sabina lab | 1 | 0h | 100%
Temperature measurement | Sabina lab | 1 | 40h | 100%
Mechanical Shock - Collision | Sabina lab | 1 | 16h | 100%
Crush for housing - Elbow load | Sabina lab | 1 | 0h | 100%
5 point functional/parametric check (Before Free Fall) | Sabina lab | 1 | 16h | 100%
Free Fall | Sabina lab | 1 | 0h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 40h | 100%
1 point functional/parametric check | Sabina lab | 1 | 8h | 100%
Squeak and Rattle Avoidance | Sabina lab | 1 | 8h | 100%
1 point functional/parametric check | Sabina lab | 1 | 16h | 100%
5 point functional/parametric check (Pre-test) | Sabina lab | 1 | 24h | 100%
RE (ALSE) | 3rd party lab | 1 | 16h | 100%
RF_CE via AN | Troy lab | 1 | 8h | 100%
Magnetic Fields. (PEPS) | 3rd party lab | 1 | 8h | 100%
RI, Bulk Current Injection (BCI) | Troy lab | 1 | 32h | 100%
RI, Anechoic Chamber | 3rd party lab | 1 | 16h | 100%
Near-Field Portable Transmitters | 3rd party lab | 1 | 16h | 100%
CI, Nominal 12V Lines | Troy lab | 1 | 32h | 100%
CI, Coupling (CCC or DCC) to I/O (excludes nominal 12V lines) | Troy lab | 1 | 8h | 100%
CI, Coupling (DCC on I/O and regulated supply lines, 85 V) | Troy lab | 1 | 16h | 100%
ESD, Power-On Mode | Troy lab | 1 | 16h | 100%
ESD, Remote I/O | Troy lab | 1 | 8h | 100%
ESD, Handling of Devices | Troy lab | 1 | 8h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 16h | 100%
DV Test Report | Todd Burnett | 1 | 312h | 100%
Load DV EMC and ENV Test Reports in CEMENT | Marco Sosa | 1 | 40h | 100%
Thermal Shock - Air to Air | Sabina Lab (24h) | 1 | 408h | 100%
Power Temperature Cycle (PTC) | Sabina Lab (24h) | 1 | 600h | 100%
Humid Heat Cyclic | Sabina lab | 1 | 32h | 100%
Humid Heat Constant | Sabina lab | 1 | 32h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 8h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 8h | 100%
Cross Section and Inspection (Leg.2) | Sabina lab | 1 | 56h | 100%
Intermittent Short Circuit to Battery and to Ground for Input/Output | Troy lab | 1 | 56h | 100%
Continuous Short Circuit to Battery and to Ground for Input/Output | Troy lab | 1 | 48h | 100%
Open Circuit Single Line Integration | Troy lab | 1 | 24h | 100%
Open Circuit Multiple Line Integration | Troy lab | 1 | 8h | 100%
5 point functional/parametric check (Post-test) | Sabina lab | 1 | 16h | 100%
Visual Inspection and Dissection – DRBTR. | Marco Sosa | 1 | 40h | 100%
DV Test Report | Todd Burnett | 1 | 56h | 100%
Load DV EMC and ENV Test Reports in CEMENT | Marco Sosa | 1 | 40h | 100%
RFP update | Marco Sosa | 1 | 24h | 100%
Build samples (32 Eng Samples) | Yoshio Tanaka | 1 | 40h | 100%
Ship D&D samples to NSI | Yoshio Tanaka | 1 | 24h | 100%
IVER SW release with TWN (sw21.21.140.4) | Marco Sosa | 1 | 0h | 100%
IVER SW release with TWN (sw21.21.140.4) | Kunal Kulshrestha | 1 | 0h | 100%
Build IVER | Yoshio Tanaka | 1 | 32h | 100%
Ship to customer | Yoshio Tanaka | 1 | 24h | 100%
IVER MRD | Kristine Hiott | 1 | 0h | 100%
BSP Release to GMTCI | Akhtar Abbas | 1 | 0h | 100%
RC02 from GMTCI to NSI | GMTCI | 1 | 16h | 100%
Internal SW release | Akhtar Abbas | 1 | 64h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 0h | 100%
SWE4 Validation Testing | Akhtar Abbas | 1 | 80h | 100%
SWE6 Verification Testing | Oscar Espinosa | 1 | 80h | 100%
SWE6 Verification Test Report | Oscar Espinosa | 1 | 24h | 100%
Bootloader | Rajalakshmi M | 1 | 16h | 100%
Telltales | Rajalakshmi M | 1 | 32h | 100%
Illumination | Rajalakshmi M | 1 | 24h | 100%
Power Mode | Rajalakshmi M | 1 | 16h | 100%
CAN | Rajalakshmi M | 1 | 24h | 100%
LIN | Rajalakshmi M | 1 | 16h | 100%
TFT | Rajalakshmi M | 1 | 16h | 100%
Ethernet | Rajalakshmi M | 1 | 16h | 100%
Gages | Rajalakshmi M | 1 | 16h | 100%
HWIOs | Rajalakshmi M | 1 | 16h | 100%
Memory | Rajalakshmi M | 1 | 16h | 100%
Segment Display | Rajalakshmi M | 1 | 16h | 100%
Summary Report approval | Mauro Lopez | 1 | 120h | 100%
SYS5 Requirements Analysis (SRS v5.0 and v6.0) | Kalpana Dakshnamoorthy | 1 | 160h | 100%
SYS5 Test Case creation (SRS v5.0 and v6.0) | Kalpana Dakshnamoorthy | 1 | 248h | 100%
Stress Test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Teltales | Kalpana Dakshnamoorthy | 1 | 24h | 100%
TFT | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Illumination | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Power Mode | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Gauges | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Ethernet | Kalpana Dakshnamoorthy | 1 | 16h | 100%
CAN | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Functional Safety | Kalpana Dakshnamoorthy | 1 | 16h | 100%
NVM | Kalpana Dakshnamoorthy | 1 | 16h | 100%
LIN | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Line Test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
HWIO | Kalpana Dakshnamoorthy | 1 | 8h | 100%
DOORS & Redmine | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Summary Report Approval | Mauro Lopez | 1 | 112h | 100%
CG3687 - Bootloader Flash Programming | Mathukumar Kuthalingam | 1 | 40h | 100%
CG3877 - CAN Physical Layer Test | Mathukumar Kuthalingam | 1 | 40h | 100%
CG4111 - Global B Serial Data and Diagnostics Test | Mathukumar Kuthalingam | 0 | 160h | 100%
CG3689 - Ethernet AVB Device Test | Mathukumar Kuthalingam | 0 | 120h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance | Mathukumar Kuthalingam | 0 | 160h | 100%
Redmines upload | Hemanth | 1 | 144h | 100%
ARP Client | John McShane | 1 | 144h | 100%
ARP Server | John McShane | 1 | 144h | 100%
Ethernet | John McShane | 1 | 144h | 100%
IPv4 | John McShane | 1 | 144h | 100%
TCP Client | John McShane | 0 | 120h | 100%
TCP Server | John McShane | 0 | 120h | 100%
SW release to GM (21.21.140.1) | Akhtar Abbas | 1 | 0h | 100%
CG4117 (sw 21.21.140.1) | Grant Thomas | 1 | 496h | 100%
Share with GM | Marco Sosa | 1 | 8h | 100%
Internal SW release | Sachin Karkera | 1 | 8h | 100%
Unit Test | Sachin Karkera | 1 | 8h | 100%
Integration Test | Sachin Karkera | 1 | 8h | 100%
Ethernet RHMI | Oscar Espinosa | 1 | 32h | 100%
Booloader updater | Oscar Espinosa | 1 | 32h | 100%
Software Release Readiness | Oscar Espinosa | 1 | 32h | 100%
SWE6 Verification Test Report | Oscar Espinosa | 1 | 40h | 100%
Ethernet | Kalpana Dakshnamoorthy | 1 | 56h | 100%
CG3877 (BTR Portion) | Kalpana Dakshnamoorthy | 1 | 56h | 100%
SYS5 Validation Test Report | Mauro Lopez | 1 | 32h | 100%
CG4422 updated | Marco Sosa | 1 | 184h | 100%
Black box test results | Marco Sosa | 1 | 0h | 100%
Master Update | Marco Sosa | 1 | 16h | 100%
TWN release | Kunal Kulshrestha | 0 | 40h | 100%
GM Release | Akhtar Abbas | 1 | 16h | 100%
Internal Release | Sachin Karkera | 1 | 8h | 100%
SWE6 Verification Testing | Sharmila Kokkera | 0 | 16h | 100%
SW release to GM | Akhtar Abbas | 0 | 8h | 100%
Internal Release | Sachin Karkera | 1 | 8h | 100%
SWE6 Verification Testing | Sharmila Kokkera | 1 | 8h | 100%
SW release to GM | Akhtar Abbas | 1 | 0h | 100%
DIT @ GM | Raymon Benjamin | 1 | 8h | 100%
GBFTT @ GM | GM | 1 | 8h | 100%
CG3877 - CAN Physical Layer Test (Oct 2018) | Anjaneyulu (HCL) | 1 | 408h | 100%
CG3877 - CAN Physical Layer Test (Oct 2018) | Eshwaran (HCL) | 1 | 408h | 100%
Temp Chamber and ESD | Anjaneyulu (HCL) | 1 | 152h | 100%
CG3687 - Bootloader Flash Programming | Bhargav (HCL) | 1 | 184h | 100%
CG3689 - Ethernet AVB Device Test (Jan 2017) | Bhargav (HCL) | 1 | 256h | 100%
SAE J2602-2 - LIN Network for Vehicle (Nov 2012) | Bhargav (HCL) | 1 | 96h | 100%
RC0 Release | GMTCI | 1 | 0h | 100%
RC1 Release | GMTCI | 1 | 0h | 100%
RC2 Release (did not included HMI) | GMTCI | 1 | 0h | 100%
RC2 Release (new HMI from RAPM/GMTCI) | GMTCI | 1 | 8h | 100%
Internal SW release | Akhtar Abbas | 1 | 136h | 100%
SWE4 Validation Testing (unit test, integration test) | Eliseo Flores | 1 | 48h | 100%
SWE4 Validation Testing (unit test, integration test) | Neelima Gudem | 1 | 48h | 100%
SWE4 Validation Testing (unit test, integration test) | Sachin Karkera | 1 | 48h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 1 | 8h | 100%
Redmines testing | Iniyakumar Louis | 1 | 40h | 100%
Redmines testing | Oscar Espinosa | 1 | 40h | 100%
Redmines testing | Sharmila Kokkera | 1 | 40h | 100%
Release readiness test | Iniyakumar Louis | 1 | 16h | 100%
Systems | Sharmila Kokkera | 1 | 16h | 100%
RHMI | Iniyakumar Louis | 1 | 40h | 100%
JTAG password | Sharmila Kokkera | 0 | 16h | 100%
Functional Testing | Oscar Espinosa | 1 | 72h | 100%
SWE6 Verification Test Report | Oscar Espinosa | 1 | 8h | 100%
FROP List | Victor Samson | 1 | 16h | 100%
Telltales | Jyothi K | 1 | 8h | 100%
TFT | Victor Samson | 1 | 8h | 100%
Illumination | Victor Samson | 1 | 8h | 100%
Gauges | Jyothi K | 1 | 8h | 100%
Ethernet | Victor Samson | 1 | 8h | 100%
Segment Display | Jyothi K | 1 | 8h | 100%
CAN | Victor Samson | 1 | 8h | 100%
LIN | Victor Samson | 1 | 8h | 100%
HWIO | Victor Samson | 1 | 8h | 100%
Memory | Jyothi K | 1 | 8h | 100%
Bootloader | Victor Samson | 1 | 8h | 100%
Power Mode | Jyothi K | 1 | 8h | 100%
SYS Integration Test Report | Victor Samson | 1 | 16h | 100%
SYS Integration Test Report | Mauro Lopez | 1 | 16h | 100%
FROP List | Jyoti Billur | 1 | 32h | 100%
Gauges | Jyoti Billur | 1 | 8h | 100%
LIN | Jyoti Billur | 1 | 8h | 100%
Telltales | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Functional Safety | Kalpana Dakshnamoorthy | 1 | 8h | 100%
TFT | Kalpana Dakshnamoorthy | 1 | 8h | 100%
NVM | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Power Mode | Kalpana Dakshnamoorthy | 1 | 8h | 100%
CAN | Jyoti Billur | 1 | 8h | 100%
HWIO | Jyoti Billur | 1 | 8h | 100%
Illumination | Jyoti Billur | 1 | 8h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Line Test | Jyoti Billur | 1 | 16h | 100%
Stress Test | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Ethernet | Jyoti Billur | 1 | 16h | 100%
SYS Validation Test Report | Mauro Lopez | 1 | 16h | 100%
SYS Validation Test Report | Kalpana Dakshnamoorthy | 1 | 16h | 100%
CG3687 - Bootloader Flash Programming | Mathukumar Kuthalingam | 0 | 160h | 100%
CG3877 - CAN Physical Layer Test | Mathukumar Kuthalingam | 0 | 200h | 100%
CG3689 - Ethernet AVB Device Test | Mathukumar Kuthalingam | 0 | 120h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance | Mathukumar Kuthalingam | 0 | 160h | 100%
TCP Client | John McShane | 0 | 120h | 100%
TCP Server | John McShane | 0 | 120h | 100%
Line Test and Agene Mode (SW) | Akhtar Abbas | 0 | 8h | 100%
Software release assesment | Akhtar Abbas | 0 | 0h | 100%
SW release to GM | Akhtar Abbas | 0 | 0h | 100%
Unit Test report | Neelima Gudem | 1 | 24h | 100%
SAA update | Marco Sosa | 0 | 32h | 100%
Integratoin Test report | Neelima Gudem | 1 | 32h | 100%
Performance Paramters report | Sachin Karkera | 0 | 32h | 100%
Stress Test Results | Marco Sosa | 1 | 56h | 100%
Black box test results | Marco Sosa | 1 | 96h | 100%
Black box test results | Oscar Espinosa | 1 | 96h | 100%
Systems Requirements Spec (SYS2) - 6.0 | Mauro Lopez | 0 | 0h | 100%
Systems Architecture (SYS3) - 1.0 | Mauro Lopez | 0 | 0h | 100%
Software Functional Specs (SWE1) - 3.0 ??? | Leonardo Iratagotia | 0 | 16h | 100%
Software Functional Specs (SWE1) - 3.0 ??? | Devendra Takola | 0 | 16h | 100%
Software Functional Specs (SWE1) - 3.0 ??? | Shailendra Jain | 0 | 16h | 100%
Software Architecure Design (SWE2) - 2.0 | Eliseo Flores | 0 | 72h | 100%
Software Layer Design (SWE3) - 2.0 | Eliseo Flores | 0 | 72h | 100%
Software Unit Test Spec (SWE4) - 2.0 | Eliseo Flores | 0 | 72h | 100%
Software Unit Test Spec (SWE4) - 2.0 | Neelima Gudem | 0 | 72h | 100%
Software Integration Test Spec (SWE5) -2.0 | Eliseo Flores | 0 | 72h | 100%
Software Qualification Test Spec (SWE6) - 4.0 | Oscar Espinosa | 0 | 72h | 100%
Software Qualification Test Spec (SWE6) - 4.0 | Nikhil Gupta | 0 | 72h | 100%
Systems Integration Test Spec (SYS4) - ?? | Victor Samson | 0 | 16h | 100%
Systems Qualification Test Spec (SYS5) - ?? | Kalpana Dakshnamoorthy | 0 | 16h | 100%
CCB (FROP and Redmine) | Akhtar Abbas | 1 | 120h | 100%
CCB (FROP and Redmine) | Marco Sosa | 1 | 120h | 100%
CCB (FROP and Redmine) | Mauro Lopez | 1 | 120h | 100%
Software release kick off | Akhtar Abbas | 0 | 0h | 100%
RC2 Release (from GMTCI to NSI with HMI) | GMTCI | 1 | 32h | 100%
Internal SW release | Eliseo Flores | 1 | 24h | 100%
SWE4 Validation Testing | Akhtar Abbas | 0 | 120h | 100%
SW Validation Test Plan and Readiness Review | Oscar Espinosa | 0 | 0h | 100%
SWE6 Verification Testing | Oscar Espinosa | 0 | 80h | 100%
SWE6 Verification Test Report | Oscar Espinosa | 0 | 24h | 100%
SYS4 Integration Testing | Victor Samson | 1 | 80h | 100%
SYS Integration Test Report | Victor Samson | 1 | 16h | 100%
SYS5 Validation Testing | Kalpana Dakshnamoorthy | 1 | 80h | 100%
SYS Validation Test Report | Mauro Lopez | 1 | 16h | 100%
CG3687 - Bootloader Flash Programming | Mathukumar Kuthalingam | 0 | 160h | 100%
CG3877 - CAN Physical Layer Test | Mathukumar Kuthalingam | 0 | 200h | 100%
CG3689 - Ethernet AVB Device Test | Mathukumar Kuthalingam | 0 | 120h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance | Mathukumar Kuthalingam | 0 | 160h | 100%
TCP Client | John McShane | 0 | 120h | 100%
TCP Server | John McShane | 0 | 120h | 100%
Line Test and Agene Mode (SW) | Akhtar Abbas | 0 | 8h | 100%
Software release readiness | Akhtar Abbas | 0 | 0h | 100%
SW release to GM | Akhtar Abbas | 0 | 0h | 100%
Unit Test report | Neelima Gudem | 0 | 32h | 100%
SAA update | Marco Sosa | 0 | 32h | 100%
Integratoin Test report | Neelima Gudem | 0 | 32h | 100%
Performance Paramters report | Sachin Karkera | 0 | 32h | 100%
Stress Test Results | Marco Sosa | 0 | 56h | 100%
Black box test results | Marco Sosa | 0 | 96h | 100%
Black box test results | Oscar Espinosa | 0 | 96h | 100%
Software Review Report | Akhtar Abbas | 0 | 8h | 100%
Line Test and Agene Mode (SW) | Akhtar Abbas | 0 | 8h | 100%
SW Engineer on call to support ride | Akhtar Abbas | 0 | 24h | 100%
Vehicle Test Plan | Mauro Lopez | 1 | 288h | 100%
Vehicle Test Plan | Marco Sosa | 1 | 288h | 100%
GM approval for Vehicle Test Plan | GM | 0 | 80h | 100%
Verify VDC | Anshuman Mittal | 1 | 24h | 100%
Spec confirmation report to GM for approval | Anshuman Mittal | 1 | 80h | 100%
Material selection for production | Anshuman Mittal | 1 | 96h | 100%
GM to provide Applique Math for PCE 32 | GM | 1 | 64h | 100%
Update VDC with GM feedback | Anshuman Mittal | 1 | 180h | 100%
New visor molding trial @ China | Anshuman Mittal | 1 | 8h | 100%
Ship from Supplier to NSI | Supplier | 1 | 40h | 100%
Review with AAR at GMNA | Anshuman Mittal | 1 | 32h | 100%
Ship to China | Marco Sosa | 1 | 40h | 100%
Review with PATAC AAR at GM China | Marco Sosa | 1 | 192h | 100%
GM approval on C1UB | GM | 1 | 40h | 100%
LED management Sheet (Final) | Anshuman Mittal | 1 | 64h | 100%
LED Management Sheet (65% BOR) rev 9 | Anshuman Mittal | 1 | 8h | 100%
Final PCB keep out / PCB Interface Drawing | Anshuman Mittal | 0 | 40h | 100%
New graphics from GM (applique) PCE 032 | GM | 1 | 48h | 100%
Variation List New/Release (include calibration points) (1st 3 pages only) | Anshuman Mittal | 1 | 96h | 100%
Variation list approval (1st pages only) | Anshuman Mittal | 1 | 352h | 100%
Variation list approval (1st pages only) | Antonio Jimenez | 1 | 352h | 100%
Variation list approval (1st pages only) | Leonardo Iratagotia | 1 | 352h | 100%
EWO from GM | GM | 1 | 8h | 100%
Variation List Release (Full) | Anshuman Mittal | 0 | 120h | 100%
Variation List Release (Full) Approval | Anshuman Mittal | 0 | 40h | 100%
Variation List Release (Full) Approval | Antonio Jimenez | 0 | 40h | 100%
Variation List Release (Full) Approval | Leonardo Iratagotia | 0 | 40h | 100%
Release graphics to NS (pending with Alex Debek for coming changes) | Anshuman Mittal | 1 | 8h | 100%
Mechanical Production BOM | Anshuman Mittal | 1 | 40h | 100%
New screens for applique (To be confirmed) | Kristine Hiott | 0 | 480h | 100%
New screens for applique (To be confirmed) | Marco Sosa | 0 | 480h | 100%
Design Freeze | GM | 1 | 0h | 100%
Applique | Anshuman Mittal | 1 | 240h | 100%
Lens | Anshuman Mittal | 1 | 240h | 100%
Visor | Anshuman Mittal | 1 | 240h | 100%
Outer Case | Anshuman Mittal | 1 | 240h | 100%
Chromed Rings | Anshuman Mittal | 1 | 240h | 100%
Review with suppliers | Anshuman Mittal | 1 | 80h | 100%
Applique Update | Anshuman Mittal | 1 | 64h | 100%
Lens Update | Anshuman Mittal | 1 | 88h | 100%
Visor Update | Anshuman Mittal | 1 | 88h | 100%
Outer Case Update | Anshuman Mittal | 1 | 64h | 100%
Chromed Rings Update | Anshuman Mittal | 1 | 176h | 100%
Review DRBFM with GM on Red and Amber changes | Anshuman Mittal | 0 | 40h | 100%
DRBFM approval from GM | GM | 0 | 40h | 100%
OK to Tool Drawing release to GM | Anshuman Mittal | 1 | 0h | 100%
OK to Tool Drawing approval by GM | GM | 1 | 40h | 100%
Lens | Anshuman Mittal | 1 | 88h | 100%
Visor | Anshuman Mittal | 1 | 88h | 100%
Outer Case | Anshuman Mittal | 1 | 88h | 100%
Applique | Anshuman Mittal | 1 | 8h | 100%
Chrome Ring | Anshuman Mittal | 1 | 8h | 100%
SW5V Enable from SoC (SL.No 12) | Leonardo Iratagotia | 1 | 1,288h | 100%
PSC (SL.N0 14) | Leonardo Iratagotia | 1 | 1,288h | 100%
SWVBB Monitor (SL 18) | Leonardo Iratagotia | 1 | 1,288h | 100%
SoC Output for Gauges (21) | Leonardo Iratagotia | 1 | 1,288h | 100%
HSCAN TX (22) | Leonardo Iratagotia | 1 | 1,288h | 100%
HSCAN RX (23) | Leonardo Iratagotia | 1 | 1,288h | 100%
Pointer PWM (25) | Leonardo Iratagotia | 1 | 1,288h | 100%
Dial PWM (26) | Leonardo Iratagotia | 1 | 1,288h | 100%
TT SEG WHITE LED PWM (27) | Leonardo Iratagotia | 1 | 1,288h | 100%
TT LED CS (28) | Leonardo Iratagotia | 1 | 1,288h | 100%
SEG LED CS (29) | Leonardo Iratagotia | 1 | 1,288h | 100%
LIN RX (31) | Leonardo Iratagotia | 1 | 1,288h | 100%
LIN TX (32) | Leonardo Iratagotia | 1 | 1,288h | 100%
HyperMemory MCP (33-36) | Leonardo Iratagotia | 1 | 1,288h | 100%
CMI 4.2" TFT (37-43) | Leonardo Iratagotia | 1 | 1,288h | 100%
ENET Reset (45) | Leonardo Iratagotia | 1 | 1,288h | 100%
Create report | Leonardo Iratagotia | 1 | 72h | 100%
Review Report | Karthikeyan Palanisamy | 1 | 24h | 100%
Review Report | Antonio Jimenez | 1 | 24h | 100%
Retake measurements based on feedback | Leonardo Iratagotia | 1 | 40h | 100%
Report update | Leonardo Iratagotia | 1 | 8h | 100%
HW review and feedback | Karthikeyan Palanisamy | 1 | 24h | 100%
Retake measurements based on feedback and update report | Leonardo Iratagotia | 1 | 32h | 100%
HW Power Sequence Measurements, Judgements, action plan if NG | Antonio Jimenez | 1 | 144h | 100%
System examination meeting 4 | Antonio Jimenez | 1 | 0h | 100%
System examination meeting 4 | Karthikeyan Palanisamy | 1 | 0h | 100%
System examination meeting 4 | Slavko Bogoevski | 1 | 0h | 100%
System examination meeting 4 | Akhtar Abbas | 1 | 0h | 100%
System examination meeting 4 | Devendra Takola | 1 | 0h | 100%
System examination meeting 4 | Eliseo Flores | 1 | 0h | 100%
System examination meeting 4 | Jon Donegan | 1 | 0h | 100%
System examination meeting 4 | Leonardo Iratagotia | 1 | 0h | 100%
System examination meeting 4 | Marco Sosa | 1 | 0h | 100%
TFT waveform measurement (sw21.21.142.1) | Mark Ho | 1 | 40h | 100%
Gauge driver waveform measurements | Mark Ho | 0 | 48h | 100%
TFT Thermistor waveform measurements | Mark Ho | 0 | 48h | 100%
Hyperbus waveform measurements | Karthikeyan Palanisamy | 0 | 48h | 100%
Telltale driver waveform measurements | Mark Ho | 0 | 48h | 100%
Review HW waveform measurements | Antonio Jimenez | 0 | 80h | 100%
Create report | Mark Ho | 0 | 80h | 100%
Report approval | Antonio Jimenez | 0 | 8h | 100%
Report approval | Karthikeyan Palanisamy | 0 | 8h | 100%
Report approval | Mark Ho | 0 | 8h | 100%
Report approval | Slavko Bogoevski | 0 | 8h | 100%
Telltale driver analysis | Antonio Jimenez | 1 | 80h | 100%
System Design Sheet | Antonio Jimenez | 1 | 24h | 100%
Update Schematic | Antonio Jimenez | 0 | 40h | 100%
Update EBOM | Antonio Jimenez | 1 | 40h | 100%
Update SDS | Antonio Jimenez | 1 | 80h | 100%
SDS Approval | Slavko Bogoevski | 1 | 88h | 100%
SDS Approval | Antonio Jimenez | 1 | 88h | 100%
SDS Approval | Tetsuya Tsubame | 1 | 88h | 100%
Group Design Review | Antonio Jimenez | 0 | 8h | 100%
Group Design Review | Slavko Bogoevski | 0 | 8h | 100%
Group Design Review | Karthikeyan Palanisamy | 0 | 8h | 100%
DR2 (Design Review 2) | Antonio Jimenez | 0 | 8h | 100%
DR2 (Design Review 2) | Karthikeyan Palanisamy | 0 | 8h | 100%
DR2 (Design Review 2) | Slavko Bogoevski | 0 | 8h | 100%
DR2 (Design Review 2) | Tetsuya Tsubame | 0 | 8h | 100%
Second design change point mgt | Antonio Jimenez | 1 | 8h | 100%
Design Quality Assesment | Antonio Jimenez | 1 | 0h | 100%
Design Quality Assesment | Slavko Bogoevski | 1 | 0h | 100%
Design Quality Assesment | Karthikeyan Palanisamy | 1 | 0h | 100%
System Requirement Update | Leonardo Iratagotia | 1 | 40h | 100%
LED settings update | Eliseo Flores | 1 | 40h | 100%
SRS Major baseline (sw21.21.142.1) | Mauro Lopez | 1 | 192h | 100%
SYS5 | Kalpana Dakshnamoorthy | 1 | 80h | 100%
SYS5 Phase 2 (142 requirements) | Kalpana Dakshnamoorthy | 1 | 80h | 100%
Software | Shailendra Jain | 0 | 400h | 100%
Verification Criteria for hardware requirements part 1 (sw21.21.142.1) | Antonio Jimenez | 1 | 80h | 100%
Verification Criteria for hardware requirements part 2 (sw21.21.142.1) | Antonio Jimenez | 1 | 80h | 100%
Verification Criteria for hardware requirements part 3 (sw21.21.142.1) | Antonio Jimenez | 1 | 80h | 100%
Internal Review of Verification Criteria (sw21.21.142.1) | Antonio Jimenez | 1 | 80h | 100%
Internal Review of Verification Criteria (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
Internal Review of Verification Criteria (sw21.21.142.1) | Slavko Bogoevski | 1 | 80h | 100%
Update based on feedback (sw21.21.142.1) | Antonio Jimenez | 1 | 8h | 100%
Approval of Verfication Criteria (sw21.21.142.1) | Antonio Jimenez | 1 | 8h | 100%
Approval of Verfication Criteria (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 8h | 100%
Approval of Verfication Criteria (sw21.21.142.1) | Slavko Bogoevski | 1 | 8h | 100%
EQA Workproduct Audit SRS (sw21.21.142.1) | Prabhu Kumar | 1 | 8h | 100%
Systems Architecture (SYS3) (sw21.21.142.1) | Mauro Lopez | 1 | 19.2h | 100%
EQA Workproduct Audit SAD (sw21.21.142.1) | Prabhu Kumar | 1 | 8h | 100%
Software Functional Specs (SWE1) (sw21.21.142.1) | Leonardo Iratagotia | 1 | 0h | 100%
Software Functional Specs (SWE1) (sw21.21.142.1) | Devendra Takola | 1 | 0h | 100%
Software Functional Specs (SWE1) (sw21.21.142.1) | Shailendra Jain | 1 | 0h | 100%
EQA Workproduct Audit SWFS (sw21.21.142.1) | Prabhu Kumar | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Akhtar Abbas | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Eliseo Flores | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Leonardo Iratagotia | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Marco Sosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Mauro Lopez | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Oscar Espinosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.142.1) | Prabhu Kumar | 1 | 8h | 100%
SRS Minor baseline (sw21.21.144) | Mauro Lopez | 1 | 168h | 100%
Redmine Analysis phase 1 (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
SAD Minor baseline (sw21.21.144) | Mauro Lopez | 1 | 256h | 100%
Redmine Analysis phase 1 (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
SAD Hardware Test Case Creation / Baselline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SAD Hardware Test Case Creation / Baselline (sw21.21.144) | Karthikeyan Palanisamy | 1 | 80h | 100%
SAD Hardware Test Case Creation / Baselline (sw21.21.144) | Karthikeyan Palanisamy | 1 | 64h | 100%
Redmine Analysis phase 1 (sw 21.21.144) | Leonardo Iratagotia | 1 | 80h | 100%
RC-1 BSP and Bootloader exchange (sw21.21.142.1) | Eliseo Flores | 1 | 24h | 100%
Architecture Design minor baseline (sw21.21.142.1) | Eliseo Flores | 0 | 80h | 100%
Layer Design minor baseline (sw21.21.142.1) | Eliseo Flores | 0 | 80h | 100%
Unit Design minor baseline (sw21.21.142.1) | Eliseo Flores | 0 | 80h | 100%
Redmine Software Implementation (sw21.21.142.1) | Eliseo Flores | 1 | 80h | 100%
Test Case minor baseline (sw21.21.142.1) | Oscar Espinosa | 0 | 80h | 100%
Test Case minor baseline (sw21.21.142.1) | Victor Samson | 1 | 80h | 100%
Test Case minor baseline (sw21.21.142.1) | Kalpana Dakshnamoorthy | 1 | 72h | 100%
SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SRS Hardware Test Case Creation / Baseline (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 80h | 100%
SRS Hardware Test Case Review by HW team (sw21.21.142.1) | Antonio Jimenez | 1 | 40h | 100%
Review Comments Update (sw21.21.142.1) | Karthikeyan Palanisamy | 1 | 24h | 100%
Review Comments Update (sw21.21.142.1) | Mark Ho | 1 | 24h | 100%
Review and provide feedback from Systems | Mauro Lopez | 1 | 48h | 100%
SRS Hardware Test Case approval (sw21.21.142.1) | Slavko Bogoevski | 0 | 40h | 100%
CG2999 submit to GM (release 21.21.141) | Marco Sosa | 0 | 24h | 100%
RC2 App exchange (sw21.21.142.1) | GMTCI | 1 | 0h | 100%
CG4422 updated to GM (sw21.21.142.1) | Marco Sosa | 1 | 16h | 100%
SRS Major baseline (sw21.21.144) | Mauro Lopez | 1 | 240h | 100%
EQA Workproduct Audit SRS (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis phase 2 (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
SAD Major baseline (sw21.21.144) | Mauro Lopez | 1 | 296h | 100%
EQA Workproduct Audit SAD (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis phase 2 (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
Software Functional Specs minor baseline (sw21.21.144) | Leonardo Iratagotia | 1 | 32h | 100%
Redmine Analysis phase 2 (sw 21.21.144) | Leonardo Iratagotia | 1 | 80h | 100%
RC-1 Bootloader release to GMTCI (sw 21.21.144) | Akhtar Abbas | 1 | 0h | 100%
RC-1 Bootloader release to GMTCI (sw 21.21.144) | Eliseo Flores | 1 | 0h | 100%
Architecture Design Major basline (sw 21.21.142.1) | Akhtar Abbas | 1 | 232h | 100%
Architecture Design Major basline (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Layer Design Major baseline (sw 21.21.142.1) | Akhtar Abbas | 1 | 232h | 100%
Layer Design Major baseline (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Unit Design Major baseline (sw 21.21.142.1) | Akhtar Abbas | 1 | 232h | 100%
Unit Design Major baseline (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Redmine Software Implementation (acc. to FROP) (sw 21.21.142.1) | Akhtar Abbas | 1 | 120h | 100%
Redmine Software Implementation (acc. to FROP) (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Software Integration Test Spec major baseline (sw21.21.142.1) | Akhtar Abbas | 1 | 272h | 100%
Software Integration Test Spec major baseline (sw21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
EQA Workproduct Audit SW AD (sw21.21.142.1) | Prabhu Kumar | 1 | 4h | 100%
EQA Workproduct Audit SW DD (sw21.21.142.1) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.142.1) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.142.1) | Prabhu Kumar | 1 | 0h | 100%
Full Integration Testing (sw 21.21.142.1) | Akhtar Abbas | 1 | 24h | 100%
Full Integration Testing (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Internal SW release (sw 21.21.142.1) | Akhtar Abbas | 1 | 0h | 100%
Internal SW release (sw 21.21.142.1) | Eliseo Flores | 1 | 0h | 100%
Sanity Check (sw 21.21.142.1) | Leonardo Iratagotia | 1 | 8h | 100%
Test Case major baseline (sw21.21.142.1) | Oscar Espinosa | 1 | 248h | 100%
Test Case major baseline (sw21.21.142.1) | Nikhil Gupta | 1 | 248h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.142.1) | Prabhu Kumar | 1 | 33.2h | 100%
Redmine Analysis | Victor Samson | 1 | 8h | 100%
Execution Plan Preparation | Victor Samson | 1 | 4h | 100%
Review (Pre-Validation Meeting) | Victor Samson | 1 | 4h | 100%
System Architecture Design Analysis | Victor Samson | 1 | 24h | 100%
Test Case Update | Victor Samson | 1 | 144h | 100%
Test Case Review | Victor Samson | 1 | 16h | 100%
Test Case Rework | Jyothi K | 1 | 80h | 100%
Traceablity Link | Victor Samson | 1 | 16h | 100%
Traceablity Link | Jyothi K | 1 | 0h | 100%
Test Case Major baseline (sw21.21.142.1) | Victor Samson | 1 | 44.8h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.142.1) | Prabhu Kumar | 1 | 128h | 100%
Redmine Analysis | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Execution Plan Preparation | Kalpana Dakshnamoorthy | 1 | 4h | 100%
Review (Pre-Validation Meeting) | Kalpana Dakshnamoorthy | 1 | 4h | 100%
Baseline 7.1 SRS Analysis | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Test Case Update | Kalpana Dakshnamoorthy | 1 | 40h | 100%
Test Case Review | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Test Case Rework | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Test Case Major baseline (sw21.21.142.1) | Kalpana Dakshnamoorthy | 1 | 0h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.142.1) | Prabhu Kumar | 1 | 176h | 100%
Create Dummy Production CALS | Dennis Shinkonis | 1 | 32h | 100%
Software Release notes (sw 21.21.142.1) | Akhtar Abbas | 1 | 16h | 100%
Software Release notes (sw 21.21.142.1) | Eliseo Flores | 1 | 16h | 100%
Software Release Assessment (sw 21.21.142.1) | Akhtar Abbas | 1 | 0h | 100%
Share software packag (SW release) to GM (sw 21.21.142.1) | Akhtar Abbas | 1 | 0h | 100%
Unit Test report | Neelima Gudem | 1 | 32h | 100%
SAA update | Eliseo Flores | 1 | 32h | 100%
Integratoin Test report | Neelima Gudem | 1 | 128h | 100%
Performance Paramters report | Sachin Karkera | 0 | 32h | 100%
Stress Test Results | Marco Sosa | 1 | 0h | 100%
Black box test results | Marco Sosa | 1 | 8h | 100%
Black box test results | Oscar Espinosa | 1 | 8h | 100%
Redmine Analysis complete (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
Redmine Analysis complete (sw 21.21.144) | Mauro Lopez | 1 | 80h | 100%
Redmine Analysis complete (sw 21.21.144) | Leonardo Iratagotia | 1 | 80h | 100%
Software Functional Specs Major baseline (sw 21.21.144) | Leonardo Iratagotia | 1 | 128h | 100%
EQA Workproduct Audit SWFS (sw21.21.144) | Prabhu Kumar | 1 | 16h | 100%
CG4117 (sw 21.21.142.1) white box tesging | Grant Thomas | 1 | 120h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.142.1) | Oscar Espinosa | 1 | 96h | 100%
SWE6 Verification Testing (sw21.21.142.1) | Oscar Espinosa | 1 | 80h | 100%
SWE6 Verification Test Report (sw21.21.142.1) | Oscar Espinosa | 1 | 0h | 100%
OTA reliability test | Oscar Espinosa | 0 | 432h | 100%
Externel Interfaces | Victor Samson | 1 | 16h | 100%
Internel Interfaces | Victor Samson | 1 | 16h | 100%
System Safety Strategy | Victor Samson | 1 | 16h | 100%
System Fault Tolerant Timings | Victor Samson | 1 | 8h | 100%
System Safe State Transitions | Victor Samson | 1 | 8h | 100%
System Dynamic Behaviour | Victor Samson | 1 | 8h | 100%
System Communication Integration | Victor Samson | 1 | 8h | 100%
System Integration Test Summary Report | Victor Samson | 1 | 8h | 100%
Test Result Update | Victor Samson | 1 | 8h | 100%
Defect analysis | Victor Samson | 1 | 4h | 100%
Teltales | Jyothi K | 1 | 16h | 100%
TFT | Rajeshakar | 1 | 16h | 100%
Power Mode | Nagender | 1 | 24h | 100%
Illumination | Kalyani | 1 | 24h | 100%
Stress Test | Kalpana Dakshnamoorthy | 1 | 56h | 100%
Functional Safety | Jyothi K | 1 | 16h | 100%
CAN | Kalpana Dakshnamoorthy | 1 | 16h | 100%
HWIO | Nagender | 1 | 8h | 100%
NVM | Rajeshakar | 1 | 16h | 100%
Gauges | Jyothi K | 1 | 16h | 100%
LIN | Rajeshakar | 1 | 16h | 100%
Bootloader (use sw21.21.142.2) | Nagender | 1 | 24h | 100%
Ethernet | Jyothi K | 1 | 16h | 100%
DOORS update | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Test Reporting | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Cyber Security | Nagender | 1 | 24h | 100%
Line Test | Rajeshakar | 1 | 24h | 100%
DOORS update | Jyothi K | 1 | 8h | 100%
Test Reporting | Kalpana Dakshnamoorthy | 1 | 16h | 100%
CG3687 - Bootloader Flash Programming (sw21.21.142.1) | Kannan Venkadachalam | 1 | 40h | 100%
CG3877 - CAN Physical Layer Test (sw21.21.142.1) | Kannan Venkadachalam | 1 | 80h | 100%
CG3689 - Ethernet AVB Device Test (sw21.21.142.1) | Kannan Venkadachalam | 1 | 48h | 100%
TCP Client (sw21.21.142.1) | John McShane | 0 | 120h | 100%
TCP Server (sw21.21.142.1) | John McShane | 0 | 120h | 100%
IPv4 (sw21.21.142.1) | John McShane | 0 | 120h | 100%
DIT Test @ GM (sw21.21.142.1) | GM | 1 | 8h | 100%
GBFTT @ GM (sw21.21.142.1) | GM | 1 | 24h | 100%
Create TWN (sw21.21.142.1) | Marco Sosa | 1 | 0h | 100%
Release TWN (sw21.21.142.1) | Devendra Takola | 1 | 48h | 100%
Parts Build | NSJPN | 1 | 80h | 100%
PV Design changes presentation | Marco Sosa | 1 | 48h | 100%
PV Design changes presentation | Anshuman Mittal | 1 | 48h | 100%
PV Design changes presentation | Antonio Jimenez | 1 | 48h | 100%
PV Design changes presentation | Kristine Hiott | 1 | 48h | 100%
PV Design changes review with GM | Marco Sosa | 1 | 40h | 100%
PV Design changes review with GM | Anshuman Mittal | 1 | 40h | 100%
PV Design changes review with GM | Antonio Jimenez | 1 | 40h | 100%
Create Test Plan | Marco Sosa | 0 | 80h | 100%
Internal Approval | Marco Sosa | 0 | 40h | 100%
Internal Approval | Alejandro Lopez | 0 | 40h | 100%
Internal Approval | Anshuman Mittal | 0 | 40h | 100%
Internal Approval | Antonio Jimenez | 0 | 40h | 100%
ENV Test Plan approval | Marco Sosa | 0 | 64h | 100%
ENV Test Plan approval | Sajitha (GM) | 0 | 80h | 100%
PV Design changes presentation | Antonio Jimenez | 1 | 40h | 100%
PV Design changes presentation | Marco Sosa | 1 | 40h | 100%
PV Design changes review with GM | Marco Sosa | 1 | 40h | 100%
PV Design changes review with GM | Anshuman Mittal | 1 | 40h | 100%
PV Design changes review with GM | Antonio Jimenez | 1 | 40h | 100%
PV Design changes review with GM | Kristine Hiott | 1 | 40h | 100%
Create Test Plan | Antonio Jimenez | 0 | 80h | 100%
Internal Approval | Antonio Jimenez | 0 | 40h | 100%
Internal Approval | Slavko Bogoevski | 0 | 40h | 100%
EMC Test Plan approval | Antonio Jimenez | 0 | 80h | 100%
EMC Test Plan approval | Richard (GM) | 0 | 80h | 100%
Test Specimen Sheet | Marco Sosa | 0.5 | 16h | 100%
ADVP&R Timing Plan | Kazuhiko Kimura | 0 | 40h | 100%
ADVP&R | Kazuhiko Kimura | 0 | 80h | 100%
Customer Drawing release for internal approval | Anshuman Mittal | 1 | 80h | 100%
Customer Drawing Approval Systems Software | Leonardo Iratagotia | 1 | 16h | 100%
Customer Drawing Approval Systems Software | Akhtar Abbas | 1 | 16h | 100%
Customer Drawing Approval Systems Application | Mauro Lopez | 1 | 16h | 100%
Customer Drawing Approval Systems Application | Gary Kempen | 1 | 16h | 100%
Customer Drawing Approval Hardware | Antonio Jimenez | 1 | 72h | 100%
Customer Drawing Approval Hardware | Slavko Bogoevski | 1 | 72h | 100%
Customer Drawing Release to GM | Anshuman Mittal | 1 | 40h | 100%
Variation List | Anshuman Mittal | 1 | 192h | 100%
LED Management Sheet rev 10 release for Approval | Anshuman Mittal | 1 | 40h | 100%
LED Management Sheet rev 10 approval HW Lead | Antonio Jimenez | 1 | 40h | 100%
LED Management Sheet rev 10 approval HW Manager | Slavko Bogoevski | 1 | 184h | 100%
CANoe Panel for PV (updates from DV) | Leonardo Iratagotia | 0.5 | 160h | 100%
ENV / EMC PV Test Software development | Leonardo Iratagotia | 0.69999999999999996 | 160h | 100%
Software Test Report | Leonardo Iratagotia | 0 | 80h | 100%
ENV / EMC Test Software Release | Leonardo Iratagotia | 0 | 0h | 100%
Sabina Test SW check with Galaxy | Kevin G | 0 | 240h | 100%
Release PV SW to SHNS via TWN | Akhtar Abbas | 0 | 8h | 100%
Conduct Code Review | Akhtar Abbas | 0 | 24h | 100%
Code Review Report with Checklist (MISRA Compliance) | Akhtar Abbas | 0 | 8h | 100%
Updated Unit Test Specification | Akhtar Abbas | 0 | 24h | 100%
Software Review Report | Akhtar Abbas | 0 | 8h | 100%
Updated Unit Test Report | Akhtar Abbas | 0 | 16h | 100%
Updated Static Test Report | Akhtar Abbas | 0 | 8h | 100%
Final Production function specs | Akhtar Abbas | 0 | 8h | 100%
Line Test and Agene Mode (SW) | Akhtar Abbas | 0 | 8h | 100%
Review Report | Tetsuya Tsubame | 0 | 24h | 100%
ENV / EMC PV Software validation | Mark Ho | 0 | 80h | 100%
ENV / EMC PV Software Report | Mark Ho | 0 | 80h | 100%
ENV / EMC PV Software Validation Report review /approval | Antonio Jimenez | 0 | 16h | 100%
PV Set up check | Mark Ho | 0 | 40h | 100%
PV Set up check | Antonio Jimenez | 0 | 40h | 100%
Release Kick Off meeting (sw21.21.144) | Akhtar Abbas | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Eliseo Flores | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Leonardo Iratagotia | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Marco Sosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Mauro Lopez | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Oscar Espinosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.144) | Prabhu Kumar | 1 | 8h | 100%
SRS Minor baseline (sw21.21.145) | Mauro Lopez | 1 | 104h | 100%
Redmine Analysis phase 1 (sw 21.21.145) | Mauro Lopez | 1 | 88h | 100%
SAD Minor baseline (sw21.21.145) | Mauro Lopez | 1 | 104h | 100%
Redmine Analysis phase 1 (sw 21.21.145) | Mauro Lopez | 1 | 88h | 100%
Redmine Analysis phase 1 (sw 21.21.145) | Leonardo Iratagotia | 1 | 88h | 100%
Architecture Design minor baseline (sw21.21.144) | Eliseo Flores | 1 | 128h | 100%
Layer Design minor baseline (sw21.21.144) | Eliseo Flores | 1 | 128h | 100%
Unit Design minor baseline (sw21.21.144) | Eliseo Flores | 1 | 128h | 100%
Redmine Software Implementation (sw21.21.144) | Eliseo Flores | 1 | 80h | 100%
Test Case minor baseline (sw21.21.144) | Oscar Espinosa | 1 | 128h | 100%
Test Case minor baseline (sw21.21.144) | Victor Samson | 1 | 64h | 100%
Test Case minor baseline (sw21.21.144) | Kalpana Dakshnamoorthy | 1 | 72h | 100%
RC2 App exchange (sw21.21.144) | GMTCI | 1 | 0h | 100%
CG4422 updated to GM (sw21.21.144) | Marco Sosa | 0 | 16h | 100%
SRS Major baseline (sw21.21.145) | Mauro Lopez | 1 | 88h | 100%
EQA Workproduct Audit SRS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis Complete (sw 21.21.145) | Mauro Lopez | 1 | 88h | 100%
SAD Major baseline (sw21.21.145) | Mauro Lopez | 1 | 88h | 100%
EQA Workproduct Audit SAD (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis Complete (sw 21.21.145) | Mauro Lopez | 1 | 88h | 100%
Software Functional Specs Minor baseline (sw21.21.145) | Leonardo Iratagotia | 1 | 64h | 100%
Redmine Analysis Complete (sw 21.21.145) | Leonardo Iratagotia | 1 | 40h | 100%
RC-1 Bootloader release to GMTCI (sw 21.21.145) | Eliseo Flores | 1 | 56h | 100%
Redmine Software Implementation (acc. To FROP)(sw 21.21.144) | Eliseo Flores | 1 | 96h | 100%
Architecture Design major basline (sw 21.21.144) | Eliseo Flores | 1 | 104h | 100%
Layer Design major baseline (sw 21.21.144) | Eliseo Flores | 1 | 104h | 100%
Unit Design major baseline (sw 21.21.144) | Eliseo Flores | 1 | 104h | 100%
Software Integration Test Spec major baseline(sw 21.21.144) | Eliseo Flores | 1 | 80h | 100%
EQA Workproduct Audit SW AD (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW DD (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
Full Integration Testing(sw 21.21.144) | Akhtar Abbas | 1 | 32h | 100%
Internal SW release (sw 21.21.144) | Akhtar Abbas | 1 | 16h | 100%
Create Production Study CALS | Dennis Shinkonis | 1 | 56h | 100%
Test Case major baseline (sw21.21.144) | Oscar Espinosa | 1 | 104h | 100%
Test Case major baseline (sw21.21.144) | Nikhil Gupta | 1 | 104h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.144) | Prabhu Kumar | 1 | 24h | 100%
System Architecture Design Analysis | Victor Samson | 1 | 40h | 100%
Test Case Update | Victor Samson | 1 | 48h | 100%
Test Case Review | Victor Samson | 1 | 8h | 100%
Test Case Rework | Victor Samson | 1 | 16h | 100%
Test Case Major baseline (sw21.21.144) | Victor Samson | 1 | 0h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.144) | Prabhu Kumar | 1 | 8h | 100%
Systems Requirement Specification analysis | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Test Case Update | Kalpana Dakshnamoorthy | 1 | 64h | 100%
Test Case Review & Rework | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Test Case Major baseline (sw21.21.144) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.144) | Prabhu Kumar | 1 | 0h | 100%
Software Functional Specs Major baseline (sw 21.21.145) | Leonardo Iratagotia | 1 | 88h | 100%
EQA Workproduct Audit SWFS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.144) | Oscar Espinosa | 1 | 0h | 100%
Redmine (High Priority) | Oscar Espinosa | 1 | 40h | 100%
Redmine (High Priority) | Iniyakumar Louis | 1 | 40h | 100%
Redmine (High Priority) | Sharmila Kokkera | 1 | 40h | 100%
Telltales | HCL | 1 | 24h | 100%
Gauges | HCL | 1 | 24h | 100%
Illumination | HCL | 1 | 24h | 100%
Diagnostics | HCL | 1 | 24h | 100%
System | HCL | 1 | 32h | 100%
Release Readiness | Iniyakumar Louis | 1 | 40h | 100%
Bootloader & OTA | HCL | 1 | 40h | 100%
CG4879 OTA Testing | Sharmila Kokkera | 1 | 32h | 100%
CG3388 (Bootloader Services) | Sharmila Kokkera | 1 | 8h | 100%
Test Summary Report | Oscar Espinosa | 1 | 8h | 100%
Test Summary Report | Nikhil Gupta | 1 | 8h | 100%
Test Summary Report | Jon Donegan | 1 | 8h | 100%
Redmine (Medium & Low Priority) | HCL | 1 | 32h | 100%
HWIO | HCL | 1 | 8h | 100%
TFT | HCL | 1 | 32h | 100%
Ethernet | HCL | 1 | 32h | 100%
HSCAN | HCL | 1 | 32h | 100%
LIN | HCL | 1 | 32h | 100%
Line Test | HCL | 1 | 0h | 100%
Data Flash | HCL | 1 | 32h | 100%
Cyber Security | HCL | 1 | 40h | 100%
Functional Safety | HCL | 1 | 0h | 100%
RHMI | HCL | 1 | 32h | 100%
Test Summary Report | Oscar Espinosa | 1 | 8h | 100%
Test Summary Report | Nikhil Gupta | 1 | 8h | 100%
Test Summary Report | Jon Donegan | 1 | 8h | 100%
SWE6 Verification Test Report (sw21.21.144) | Oscar Espinosa | 1 | 0h | 100%
Redmine Estimate (sw21.21.145) | Oscar Espinosa | 1 | 8h | 100%
Release Readiness Test | Victor Samson | 1 | 4h | 100%
Redmine Testing | Victor Samson | 1 | 32h | 100%
Externel Interfaces | Victor Samson | 1 | 4h | 100%
Internel Interfaces | Victor Samson | 1 | 16h | 100%
System Safety Strategy | Victor Samson | 1 | 24h | 100%
System Fault Tolerant Timings | Victor Samson | 1 | 8h | 100%
System Safe State Transitions | Victor Samson | 1 | 16h | 100%
System Dynamic Behaviour | Victor Samson | 1 | 16h | 100%
System Communication Integration | Victor Samson | 1 | 0h | 100%
System Integration Test Summary Report Review | Victor Samson | 1 | 4h | 100%
System Integration Test Summary Report Review | Mauro Lopez | 1 | 4h | 100%
Section 21 - SoC Output for Gauges (redmine 6742) (sw 21.21.144) | Leonardo Iratagotia | 1 | 40h | 100%
Section 27D - TT SEG White LED PWM (redmine 6547) (sw 21.21.144) | Leonardo Iratagotia | 1 | 40h | 100%
Section 38 B: Measure TFT STBYB low (redmine 7013) (sw 21.21.144) | Leonardo Iratagotia | 1 | 40h | 100%
Section 39A: TFT DE to TFT STBYB measurement(redmine 6562) (sw 21.21.144) | Leonardo Iratagotia | 1 | 40h | 100%
Report approval (software report) (sw 21.21.144) | Karthikeyan Palanisamy | 0 | 16h | 100%
Report approval (software report) (sw 21.21.144) | Antonio Jimenez | 0 | 16h | 100%
Gauge driver waveform measurements (sw 21.21.144) | Mark Ho | 0 | 48h | 100%
TFT Thermistor waveform measurements (sw 21.21.144) | Mark Ho | 1 | 48h | 100%
Hyperbus waveform measurements (sw 21.21.144) | Karthikeyan Palanisamy | 1 | 48h | 100%
LED Sample Order (sw 21.21.144) | Mark Ho | 1 | 176h | 100%
TER Creation and PCB Rework (sw 21.21.144) | Mark Ho | 1 | 80h | 100%
Telltale driver waveform measurements (sw 21.21.144) | Mark Ho | 1 | 48h | 100%
FCA reflected display and FCA (sw 21.21.144) | Mark Ho | 0 | 24h | 100%
Create report (sw 21.21.144) | Mark Ho | 1 | 80h | 100%
Create report (sw 21.21.144) | Karthikeyan Palanisamy | 1 | 80h | 100%
Review HW waveform measurements (sw 21.21.144) | Antonio Jimenez | 1 | 80h | 100%
Feedback update and remeasurements (sw 21.21.144) | Mark Ho | 1 | 80h | 100%
Review HW waveform measurements (sw 21.21.144) | Tetsuya Tsubame | 1 | 0h | 100%
Feedback update and remeasurements (sw 21.21.144) | Mark Ho | 1 | 0h | 100%
Report approval (sw 21.21.144) | Slavko Bogoevski | 1 | 0h | 100%
Smoke Test | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Redmine Testing | Kalpana Dakshnamoorthy | 1 | 40h | 100%
Gauges | Kalpana Dakshnamoorthy | 1 | 32h | 100%
Telltales | Kalpana Dakshnamoorthy | 1 | 32h | 100%
Illumination | Kalpana Dakshnamoorthy | 1 | 40h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 40h | 100%
CAN | Kalpana Dakshnamoorthy | 1 | 32h | 100%
LineTest | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Stress Test | Kalpana Dakshnamoorthy | 1 | 0h | 100%
Telltales , Gauges (manual testing ) | Kalpana Dakshnamoorthy | 1 | 24h | 100%
TFT | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Functional Safety | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Power Mode | Kalpana Dakshnamoorthy | 1 | 24h | 100%
HWIO | Kalpana Dakshnamoorthy | 1 | 8h | 100%
LIN | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 24h | 100%
NVM | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Ethernet | Kalpana Dakshnamoorthy | 1 | 0h | 100%
System Qualification Test summary report Review (sw 21.21.144) | Kalpana Dakshnamoorthy | 1 | 8h | 100%
System Qualification Test summary report Review (sw 21.21.144) | Mauro Lopez | 1 | 8h | 100%
Validation Report & Defect Analysis (sw 21.21.144) | Mauro Lopez | 1 | 8h | 100%
Validation Report & Defect Analysis (sw 21.21.144) | Kalpana Dakshnamoorthy | 1 | 8h | 100%
CG3877 - CAN Physical and Protocol Layer Test (sw 21.21.144) | Eshwaran (HCL) | 1 | 48h | 100%
CG3687 - Bootloader Flash Programming (sw 21.21.144) | Eshwaran (HCL) | 1 | 40h | 100%
CG3689 - Ethernet AVB Device Test (sw 21.21.144) | Eshwaran (HCL) | 1 | 36h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw 21.21.144) | Eshwaran (HCL) | 1 | 48h | 100%
TCP Client (sw 21.21.144) | John McShane | 1 | 120h | 100%
TCP Server (sw 21.21.144) | John McShane | 1 | 120h | 100%
IPv4 (sw 21.21.144) | John McShane | 0 | 120h | 100%
Software Release notes (sw 21.21.144) | Akhtar Abbas | 1 | 16h | 100%
Software Release notes (sw 21.21.144) | Eliseo Flores | 1 | 16h | 100%
Software Release Assessment (sw 21.21.144) | Akhtar Abbas | 1 | 0h | 100%
Share software packag (SW release) to GM (sw 21.21.144) | Akhtar Abbas | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Akhtar Abbas | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Eliseo Flores | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Leonardo Iratagotia | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Marco Sosa | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Mauro Lopez | 1 | 0h | 100%
FROP Tentative (sw21.21.145) | Oscar Espinosa | 1 | 0h | 100%
Architecture Design major basline (sw 21.21.144) Update backlog issues | Eliseo Flores | 1 | 40h | 100%
Layer Design major baseline (sw 21.21.144) Update backlog issues | Eliseo Flores | 1 | 40h | 100%
Unit Design major baseline (sw 21.21.144) Update backlog issues | Eliseo Flores | 1 | 40h | 100%
Software Integration Test Spec major baseline(sw 21.21.144) Update backlog issues | Eliseo Flores | 1 | 40h | 100%
Redmine Estimation from FROP Final (sw21.21.145) | Eliseo Flores | 1 | 40h | 100%
Redmine Estimation from FROP Final (sw21.21.145) | Oscar Espinosa | 1 | 200h | 100%
FROP Final (sw21.21.145) | Akhtar Abbas | 1 | 128h | 100%
FROP Final (sw21.21.145) | Eliseo Flores | 1 | 128h | 100%
FROP Final (sw21.21.145) | Leonardo Iratagotia | 1 | 128h | 100%
FROP Final (sw21.21.145) | Marco Sosa | 1 | 128h | 100%
FROP Final (sw21.21.145) | Mauro Lopez | 1 | 128h | 100%
FROP Final (sw21.21.145) | Oscar Espinosa | 1 | 128h | 100%
Unit Test report (sw 21.21.144) | Neelima Gudem | 1 | 16h | 100%
Static Analysis (sw 21.21.144) | Neelima Gudem | 1 | 16h | 100%
SAA update (sw 21.21.144) | Eliseo Flores | 0 | 32h | 100%
Integratoin Test report (sw 21.21.144) | Neelima Gudem | 1 | 16h | 100%
Performance Paramters report (sw 21.21.144) | Sachin Karkera | 1 | 112h | 100%
Traceability Report | Eliseo Flores | 0.29999999999999999 | 32h | 100%
Traceability Report | Marco Sosa | 0.29999999999999999 | 32h | 100%
Stress Test Results (sw 21.21.144) | Marco Sosa | 1 | 0h | 100%
Black box test results (sw 21.21.144) | Marco Sosa | 1 | 0h | 100%
Black box test results (sw 21.21.144) | Oscar Espinosa | 1 | 0h | 100%
Software Release Kick Off meeting | Akhtar Abbas | 1 | 0h | 100%
Implement redmine 10422 (sw21.21.144.1) | Eliseo Flores | 1 | 12h | 100%
Implement redmine 10534 (sw21.21.144.1) | Eliseo Flores | 1 | 12h | 100%
Implemente redmine 9717 (sw21.21.144.1) | Eliseo Flores | 1 | 12h | 100%
Stress Test using scripts for RHMI (sw 21.21.144.1) | Azad Mohammed | 1 | 8h | 100%
Integration Testing (sw21.21.144.1) | Eliseo Flores | 1 | 4h | 100%
Internal Software Release (sw21.21.144.1) | Eliseo Flores | 1 | 0h | 100%
Stress Test Sleep Cycle | Eliseo Flores | 1 | 8h | 100%
Sanity Check (sw 21.21.144.1) | Tien Nguyen | 1 | 16h | 100%
Redmine Testing | Oscar Espinosa | 1 | 24h | 100%
Release Rediness | Oscar Espinosa | 1 | 24h | 100%
RHMI | Oscar Espinosa | 1 | 24h | 100%
Bootloader Regression Test | Oscar Espinosa | 1 | 24h | 100%
Stress Test for ECU Unlock | Ananda Kopalli | 1 | 8h | 100%
Programming Sequence | Ananda Kopalli | 1 | 8h | 100%
Test Summary Report | Oscar Espinosa | 1 | 4h | 100%
Smoke Test | Victor Samson | 1 | 8h | 100%
Production CALs flashing stress test | Victor Samson | 1 | 8h | 100%
DIC partial testing (FUSA) | Victor Samson | 1 | 8h | 100%
Test Summary Report | Victor Samson | 1 | 4h | 100%
Telltales | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Gauges | Kalpana Dakshnamoorthy | 1 | 8h | 100%
Illumination | Kalpana Dakshnamoorthy | 1 | 8h | 100%
GM Stress Test | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Test Summary Report | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Software Release Notes (sw 21.21.144.1) | Akhtar Abbas | 1 | 8h | 100%
Software Release Assessment (sw 21.21.144.1) | Akhtar Abbas | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Marco Sosa | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Alejandro Lopez | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Eliseo Flores | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Lawrence Buie | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Mauro Lopez | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Nikhil Gupta | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Oscar Espinosa | 1 | 0h | 100%
Software Release Assessment (sw 21.21.144.1) | Prabhu Kumar | 1 | 0h | 100%
Share software packag (SW release) to GM (sw 21.21.144.1) | Akhtar Abbas | 1 | 0h | 100%
sw21.21.145 cadence start | Akhtar Abbas | 1 | 0h | 100%
sw21.21.145 cadence start | Eliseo Flores | 1 | 0h | 100%
sw21.21.145 cadence start | Leonardo Iratagotia | 1 | 0h | 100%
sw21.21.145 cadence start | Marco Sosa | 1 | 0h | 100%
sw21.21.145 cadence start | Mauro Lopez | 1 | 0h | 100%
sw21.21.145 cadence start | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145 cadence start | Prabhu Kumar | 1 | 0h | 100%
Release Kick Off meeting (sw21.21.145) | Akhtar Abbas | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Eliseo Flores | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Leonardo Iratagotia | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Marco Sosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Mauro Lopez | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Oscar Espinosa | 1 | 8h | 100%
Release Kick Off meeting (sw21.21.145) | Prabhu Kumar | 1 | 8h | 100%
SRS Minor baseline (sw21.21.146) | Mauro Lopez | 1 | 56h | 100%
Redmine Analysis phase 1 (sw 21.21.146) | Mauro Lopez | 1 | 80h | 100%
SAD Minor baseline (sw21.21.146) | Mauro Lopez | 1 | 80h | 100%
Redmine Analysis phase 1 (sw 21.21.146) | Mauro Lopez | 1 | 80h | 100%
Redmine Analysis phase 1 (sw 21.21.146) | Leonardo Iratagotia | 1 | 80h | 100%
Architecture Design minor baseline (sw21.21.145) | Eliseo Flores | 0 | 80h | 100%
Layer Design minor baseline (sw21.21.145) | Eliseo Flores | 0 | 80h | 100%
Unit Design minor baseline (sw21.21.145) | Eliseo Flores | 0 | 80h | 100%
Redmine Software Implementation (sw21.21.145) | Eliseo Flores | 1 | 80h | 100%
SFS review (sw21.21.145) | Oscar Espinosa | 1 | 120h | 100%
Impact Analysis for features (sw21.21.145) | Oscar Espinosa | 1 | 160h | 100%
Impact Analysis for Redmines (sw21.21.145) | Oscar Espinosa | 1 | 160h | 100%
Test Case minor baseline (sw21.21.145) | Victor Samson | 1 | 184h | 100%
Test Case minor baseline (sw21.21.145) | Kalpana Dakshnamoorthy | 1 | 64h | 100%
FROP tentative (sw21.21.145.1) | Akhtar Abbas | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Eliseo Flores | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Leonardo Iratagotia | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Marco Sosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Mauro Lopez | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Oscar Espinosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Prabhu Kumar | 1 | 0h | 100%
RC2 App exchange (sw21.21.145) | GMTCI | 1 | 48h | 100%
SRS Major baseline (sw21.21.145.1) | Mauro Lopez | 1 | 152h | 100%
EQA Workproduct Audit SRS (sw21.21.145.1) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis phase 2 (sw 21.21.145.1) | Mauro Lopez | 1 | 80h | 100%
SAD Major baseline (sw21.21.145.1) | Mauro Lopez | 0 | 160h | 100%
EQA Workproduct Audit SAD (sw21.21.145.1) | Prabhu Kumar | 0 | 0h | 100%
Redmine Analysis phase 2 (sw 21.21.145.1) | Mauro Lopez | 0 | 80h | 100%
Redmine Analysis Complete (sw 21.21.145.1) | Leonardo Iratagotia | 1 | 120h | 100%
RC-1 Bootloader release to GMTCI (sw 21.21.146) | Eliseo Flores | 1 | 8h | 100%
Architecture Design Major basline (sw 21.21.145) | Eliseo Flores | 1 | 272h | 100%
Layer Design Major baseline (sw 21.21.145) | Eliseo Flores | 1 | 272h | 100%
Unit Design Major baseline (sw 21.21.145) | Eliseo Flores | 1 | 272h | 100%
Software Integration Test Spec Major baseline(sw 21.21.145) | Eliseo Flores | 1 | 272h | 100%
EQA Workproduct Audit SW AD (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW DD (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Software Implementation (acc. To FROP)(sw 21.21.145) | Eliseo Flores | 1 | 160h | 100%
Sanity Check (sw 21.21.145) | Leonardo Iratagotia | 1 | 7.2h | 100%
Full Integration Testing(sw 21.21.145) | Eliseo Flores | 1 | 32h | 100%
Internal SW release (sw 21.21.145) | Eliseo Flores | 1 | 0h | 100%
OTA Reflash Test @ GM Bench with internal release | Balaji Rao | 1 | 8h | 100%
OTA Reflash Test @ GM Bench with internal release | Marco Sosa | 1 | 0h | 100%
GBFTT Reflhas test @ GM Bench with internal release | Balaji Rao | 1 | 8h | 100%
GBFTT Reflhas test @ GM Bench with internal release | Marco Sosa | 1 | 0h | 100%
Interal Re-Release (sw21.21.145) | Balaji Rao | 1 | 80h | 100%
Test Case Major baseline (sw21.21.145) | Oscar Espinosa | 1 | 136h | 100%
Test Case Major baseline (sw21.21.145) | Nikhil Gupta | 1 | 136h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.1) | Oscar Espinosa | 1 | 112h | 100%
Test Case Major baseline (sw21.21.145) | Victor Samson | 1 | 40h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.1) | Victor Samson | 1 | 328h | 100%
Test Case Major baseline (sw21.21.145) | Kalpana Dakshnamoorthy | 1 | 128h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.145) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.1) | Kalpana Dakshnamoorthy | 1 | 328h | 100%
CG4422 updated to GM (sw21.21.145) | Marco Sosa | 1 | 8h | 100%
FROP tentative (sw21.21.145.1) | Akhtar Abbas | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Eliseo Flores | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Leonardo Iratagotia | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Marco Sosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Mauro Lopez | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Oscar Espinosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.1) | Prabhu Kumar | 1 | 0h | 100%
Create Production Study CALS (sw 21.21.145) | Dennis Shinkonis | 1 | 0h | 100%
Software Functional Specs Minor baseline (sw21.21.145.01) | Leonardo Iratagotia | 1 | 40h | 100%
Software Functional Specs Major baseline (sw21.21.145.01) | Leonardo Iratagotia | 1 | 112h | 100%
EQA Workproduct Audit SWFS (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.145) | Oscar Espinosa | 0 | 0h | 100%
High Priority Test (redmines) | Oscar Espinosa | 1 | 48h | 100%
Medium and Low Priority | Oscar Espinosa | 1 | 40h | 100%
SWE6 Verification Test Report (sw21.21.145) | Oscar Espinosa | 1 | 8h | 100%
Redmine testing (sw21.21.145 re-release) | Mahalakshmi Thangasamy | 1 | 8h | 100%
Bootloader Testing | Mahalakshmi Thangasamy | 1 | 32h | 100%
CG4879 Testing | Mahalakshmi Thangasamy | 1 | 24h | 100%
SWE6 Verification Test Report (sw21.21.145) | Oscar Espinosa | 1 | 8h | 100%
Redmine Estimation from FROP tentative (sw21.21.145.1) | Eliseo Flores | 1 | 80h | 100%
System Integration Readiness Test (sw 21.21.145) | Prasanth J | 1 | 8h | 100%
Production CAL flashing (stress test) (sw 21.21.145) | Victor Samson | 1 | 16h | 100%
FUSA (telltales) (sw 21.21.145) | Prasanth J | 1 | 16h | 100%
FUSA (TFT, CAN, Monza) (sw 21.21.145) | Prasanth J | 1 | 8h | 100%
System State Operations (Bootloader) | Prasanth J | 0 | 16h | 100%
SYS Integration Test Report (sw 21.21.145) | Victor Samson | 1 | 16h | 100%
Report review and approval (sw 21.21.145) | Mauro Lopez | 1 | 8h | 100%
Smoke Test (sw21.21.145 re-release) | Victor Samson | 1 | 8h | 100%
Flashing Test (sw21.21.145 re-release) | Victor Samson | 1 | 8h | 100%
Report review and approval (sw 21.21.145 re-release) | Victor Samson | 1 | 4h | 100%
Report review and approval (sw 21.21.145 re-release) | Mauro Lopez | 1 | 4h | 100%
ESIMs | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Stress Test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Cyber Security | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Non Automated test cases | Kalpana Dakshnamoorthy | 1 | 24h | 100%
CAN Stress Test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
FROP Issues & Redmines | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Systems Integration Black Box test | Kalpana Dakshnamoorthy | 1 | 24h | 100%
SYS Qualification Test Report (sw 21.21.145) | Kalpana Dakshnamoorthy | 1 | 4h | 100%
Report review and approval (sw 21.21.145) | Mauro Lopez | 1 | 4h | 100%
Bootloader | Kalpana Dakshnamoorthy | 1 | 24h | 100%
Report review and approval (sw21.21.145 re-release) | Kalpana Dakshnamoorthy | 1 | 40h | 100%
Report review and approval (sw21.21.145 re-release) | Mauro Lopez | 1 | 40h | 100%
CG3877 - CAN Physical and Protocol Layer Test (sw 21.21.145) | Eshwaran (HCL) | 1 | 176h | 100%
CG3689 - Ethernet AVB Device Test (sw 21.21.145) | Eshwaran (HCL) | 0 | 48h | 100%
CG3687 - Bootloader Flash Programming (sw 21.21.145) | Eshwaran (HCL) | 0 | 60h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw 21.21.145) | Eshwaran (HCL) | 0 | 40h | 100%
TCP Client (sw 21.21.145) | John McShane | 0 | 120h | 100%
TCP Server (sw 21.21.145) | John McShane | 0 | 120h | 100%
IPv4 (sw 21.21.145) | John McShane | 0 | 120h | 100%
Software Release notes (sw 21.21.145) | Akhtar Abbas | 1 | 16h | 100%
Software Release notes (sw 21.21.145) | Eliseo Flores | 1 | 16h | 100%
Software Release Assessment (sw 21.21.145) | Akhtar Abbas | 1 | 0h | 100%
Share software packag (SW release) to GM (sw 21.21.145) | Akhtar Abbas | 1 | 0h | 100%
CG2496 Test Report (sw21.21.145) | Pradeep Kumar | 1 | 176h | 100%
Unit Test report (sw 21.21.145) | Neelima Gudem | 1 | 32h | 100%
SAA update (sw 21.21.145) | Eliseo Flores | 1 | 32h | 100%
Integratoin Test report (sw 21.21.145) | Neelima Gudem | 1 | 32h | 100%
Performance Paramters report (sw 21.21.145) | Sachin Karkera | 1 | 72h | 100%
Stress Test Results (sw 21.21.145) | Marco Sosa | 1 | 80h | 100%
Black box test results (sw 21.21.145) | Marco Sosa | 1 | 160h | 100%
Black box test results (sw 21.21.145) | Oscar Espinosa | 1 | 160h | 100%
SW traceability matrix | Marco Sosa | 0.29999999999999999 | 32h | 100%
FROP Final (sw21.21.145.01) | Akhtar Abbas | 1 | 0h | 100%
FROP Final (sw21.21.145.01) | Eliseo Flores | 1 | 0h | 100%
FROP Final (sw21.21.145.01) | Leonardo Iratagotia | 1 | 0h | 100%
FROP Final (sw21.21.145.01) | Marco Sosa | 1 | 0h | 100%
FROP Final (sw21.21.145.01) | Mauro Lopez | 1 | 0h | 100%
FROP Final (sw21.21.145.01) | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145.01 cadence start | Akhtar Abbas | 1 | 0h | 100%
sw21.21.145.01 cadence start | Eliseo Flores | 1 | 0h | 100%
sw21.21.145.01 cadence start | Leonardo Iratagotia | 1 | 0h | 100%
sw21.21.145.01 cadence start | Marco Sosa | 1 | 0h | 100%
sw21.21.145.01 cadence start | Mauro Lopez | 1 | 0h | 100%
sw21.21.145.01 cadence start | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145.01 cadence start | Prabhu Kumar | 1 | 0h | 100%
Release Kick Off meeting (sw21.21.145.01) | Eliseo Flores | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Leonardo Iratagotia | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Marco Sosa | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Mauro Lopez | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Oscar Espinosa | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Prabhu Kumar | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.01) | Azad Mohammed | 0 | 8h | 100%
SRS Minor baseline (sw21.21.145.02) | Mauro Lopez | 0 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.02) | Mauro Lopez | 1 | 40h | 100%
SAD Minor baseline (sw21.21.145.02) | Mauro Lopez | 0 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.02) | Mauro Lopez | 1 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.02) | Leonardo Iratagotia | 1 | 40h | 100%
Architecture Design minor baseline (sw21.21.145.01) | Eliseo Flores | 0 | 0h | 100%
Layer Design minor baseline (sw21.21.145.01) | Eliseo Flores | 0 | 0h | 100%
Unit Design minor baseline (sw21.21.145.01) | Eliseo Flores | 0 | 0h | 100%
Redmine Software Implementation (sw21.21.145.01) | Eliseo Flores | 0 | 0h | 100%
Test Case minor baseline (sw21.21.145.01) | Oscar Espinosa | 1 | 32h | 100%
Test Case minor baseline (sw21.21.145.01) | Victor Samson | 1 | 88h | 100%
Test Case minor baseline (sw21.21.145.01) | Kalpana Dakshnamoorthy | 1 | 56h | 100%
FROP tentative (sw21.21.145.02) | Eliseo Flores | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Leonardo Iratagotia | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Marco Sosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Mauro Lopez | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Oscar Espinosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
FROP tentative (sw21.21.145.02) | Azad Mohammed | 1 | 0h | 100%
RC2 App exchange (sw21.21.145.01) | GMTCI | 1 | 0h | 100%
SRS Major baseline (sw21.21.145.02) | Mauro Lopez | 1 | 216h | 100%
EQA Workproduct Audit SRS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.02) | Mauro Lopez | 1 | 40h | 100%
SAD Major baseline (sw21.21.145.02) | Mauro Lopez | 1 | 216h | 100%
EQA Workproduct Audit SAD (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.02) | Mauro Lopez | 1 | 16h | 100%
Software Functional Specs Minor baseline (sw21.21.145.02) | Leonardo Iratagotia | 0 | 216h | 100%
Redmine Analysis Complete (sw21.21.145.02) | Leonardo Iratagotia | 1 | 40h | 100%
RC-1 Bootloader release to GMTCI (sw21.21.145.02) | Eliseo Flores | 0 | 0h | 100%
Architecture Design Major basline (sw21.21.145.01) | Eliseo Flores | 1 | 112h | 100%
Layer Design Major baseline (sw21.21.145.01) | Eliseo Flores | 1 | 112h | 100%
Unit Design Major baseline (sw21.21.145.01) | Eliseo Flores | 1 | 112h | 100%
Software Integration Test Spec Major baseline(sw21.21.145.01) | Eliseo Flores | 1 | 64h | 100%
EQA Workproduct Audit SW AD (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW DD (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
Redmine Software Implementation (acc. To FROP)(sw21.21.145.01) | Eliseo Flores | 1 | 120h | 100%
Sanity Check (sw21.21.145.01) | Leonardo Iratagotia | 1 | 32h | 100%
Full Integration Testing(sw21.21.145.01) | Eliseo Flores | 1 | 32h | 100%
Internal SW release (sw21.21.145.01) | Eliseo Flores | 1 | 0h | 100%
Implement SW change | Kiran Khallenhali | 1 | 4h | 100%
Integration Testing (RHMI, LineTest, Wake/Sleep, Power ON/OFF, Key Provisioning) | Eliseo Flores | 1 | 4h | 100%
Signing code from GM | GM | 1 | 4h | 100%
Internal SW re-release (sw21.21.145.01) | Masanori Kaise | 1 | 0h | 100%
Test Case Major baseline (sw21.21.145.01) | Oscar Espinosa | 1 | 72h | 100%
Test Case Major baseline (sw21.21.145.01) | Nikhil Gupta | 1 | 72h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.02) | Oscar Espinosa | 1 | 40h | 100%
Test Case Major baseline (sw21.21.145.01) | Victor Samson | 1 | 96h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.02) | Victor Samson | 1 | 80h | 100%
Test Case Major baseline (sw21.21.145.01) | Kalpana Dakshnamoorthy | 1 | 56h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.02) | Kalpana Dakshnamoorthy | 1 | 80h | 100%
CG4422 updated to GM (sw21.21.145.01) | Marco Sosa | 1 | 48h | 100%
FROP tentative (sw21.21.145.02) | Akhtar Abbas | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Eliseo Flores | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Leonardo Iratagotia | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Marco Sosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Mauro Lopez | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Oscar Espinosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.02) | Prabhu Kumar | 0 | 0h | 100%
Create Production Study CALS (sw21.21.145.01) | Dennis Shinkonis | 0 | 24h | 100%
Software Functional Specs Major baseline (sw21.21.145.02) | Leonardo Iratagotia | 1 | 0h | 100%
EQA Workproduct Audit SWFS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.145.01) | Oscar Espinosa | 1 | 8h | 100%
SWE6 Verification Testing (sw21.21.145.01) | Oscar Espinosa | 1 | 32h | 100%
SWE6 Verification Testing (re-release sw21.21.145.01) | Oscar Espinosa | 1 | 16h | 100%
SWE6 Verification Test Report (sw21.21.145.01) | Oscar Espinosa | 1 | 4h | 100%
CG4879 Test Execution (sw21.21.145.01) | Oscar Espinosa | 1 | 48h | 100%
Redmine Estimation from FROP tentative (sw21.21.145.02) | Eliseo Flores | 1 | 16h | 100%
Test Execution (sw21.21.145.01) | Victor Samson | 1 | 32h | 100%
SYS Integration Test Report (sw21.21.145.01) | Victor Samson | 1 | 4h | 100%
Report review and approval (sw21.21.145.01) | Mauro Lopez | 1 | 4h | 100%
SYS Integration Test Report (re-release sw21.21.145.01) | Victor Samson | 1 | 16h | 100%
Test Execution (sw21.21.145.01) | Kalpana Dakshnamoorthy | 1 | 32h | 100%
SYS Qualification Test Report (sw21.21.145.01) | Kalpana Dakshnamoorthy | 1 | 4h | 100%
Report review and approval (sw21.21.145.01) | Mauro Lopez | 1 | 4h | 100%
SYS Qualification Test Report (sw21.21.145.01) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
HW Test Case Execution from SRS (sw21.21.145.01) Phase 1 | Mark Ho | 1 | 24h | 100%
HW Test Case Execution from SRS (sw21.21.145.01) Phase 2 | Mark Ho | 1 | 80h | 100%
HW Test Case Execution from SRS (sw21.21.145.01) Phase 3 | Mark Ho | 0 | 80h | 100%
Create Report | Mark Ho | 0 | 40h | 100%
Review Report | Karthikeyan Palanisamy | 0 | 40h | 100%
Review Report | Antonio Jimenez | 0 | 40h | 100%
Feedback update and remeasurements | Mark Ho | 0 | 32h | 100%
Feedback update and remeasurements | Mark Ho | 0 | 24h | 100%
Report Approval | Slavko Bogoevski | 0 | 8h | 100%
HSR Test execution phase 2 (sw21.21.145.01) | Mark Ho | 1 | 80h | 100%
HSR Test execution phase 2 (sw21.21.145.03) | Mark Ho | 0 | 80h | 100%
Test Report creation (sw21.21.145.03) | Mark Ho | 0 | 40h | 100%
Test Report review (sw21.21.145.03) | Karthikeyan Palanisamy | 0 | 40h | 100%
Test Report review (sw21.21.145.03) | Antonio Jimenez | 0 | 40h | 100%
Test Report review (sw21.21.145.03) | Slavko Bogoevski | 0 | 40h | 100%
Feedback update and remeasurements (sw21.21.145.03) | Mark Ho | 0 | 40h | 100%
Test Report review (sw21.21.145.03) | Tetsuya Tsubame | 0 | 40h | 100%
Test Report review with FuSa team (sw21.21.145.03) | Karthikeyan Palanisamy | 0 | 40h | 100%
Test Report review with FuSa team (sw21.21.145.03) | Pradeep Kumar | 0 | 40h | 100%
Feedback update and remeasurements (sw21.21.145.03) | Mark Ho | 0 | 40h | 100%
Test Report approval (sw21.21.145.03) | Slavko Bogoevski | 0 | 8h | 100%
Test Results upload to DOORS (sw21.21.145.03) | Karthikeyan Palanisamy | 0 | 40h | 100%
Create Traceability to Test Results (sw21.21.145.03) | Karthikeyan Palanisamy | 0 | 40h | 100%
CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.01) | Eshwaran (HCL) | 0 | 96h | 100%
CG3689 - Ethernet AVB Device Test (sw21.21.145.01) | Eshwaran (HCL) | 1 | 36h | 100%
CG3687 - Bootloader Flash Programming (sw21.21.145.01) | Eshwaran (HCL) | 0 | 60h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.01) | Eshwaran (HCL) | 0 | 40h | 100%
TCP Client (sw21.21.145.01) | John McShane | 0 | 120h | 100%
TCP Server (sw21.21.145.01) | John McShane | 0 | 120h | 100%
IPv4 (sw21.21.145.01) | John McShane | 0 | 120h | 100%
Software Release notes (sw21.21.145.01) | Eliseo Flores | 1 | 16h | 100%
Software Release notes (sw21.21.145.01) | Sachin Karkera | 1 | 16h | 100%
Software Release Assessment (sw21.21.145.01) | Azad Mohammed | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Eliseo Flores | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Gary Kempen | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Jon Donegan | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Lawrence Buie | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Marco Sosa | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Mauro Lopez | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Nikhil Gupta | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Oscar Espinosa | 1 | 0h | 100%
Software Release Assessment (sw21.21.145.01) | Prabhu Kumar | 1 | 0h | 100%
Share software packag (SW release) to GM (sw21.21.145.01) | Azad Mohammed | 1 | 0h | 100%
CG2496 Test Report (sw21.21.145.01) | Pradeep Kumar | 1 | 140h | 100%
Unit Test report (sw21.21.145.01) | Neelima Gudem | 1 | 80h | 100%
Static Analysis Test report (sw21.21.145.01) | Neelima Gudem | 1 | 80h | 100%
SAA update (sw21.21.145.01) | Eliseo Flores | 1 | 80h | 100%
Integratoin Test report (sw21.21.145.01) | Neelima Gudem | 1 | 80h | 100%
Performance Paramters report (sw21.21.145.01) | Sachin Karkera | 1 | 88h | 100%
Stress Test Results (sw21.21.145.01) | Marco Sosa | 1 | 56h | 100%
Black box test results (sw21.21.145.01) | Marco Sosa | 1 | 64h | 100%
Black box test results (sw21.21.145.01) | Oscar Espinosa | 1 | 64h | 100%
FROP Final (sw21.21.145.02) | Akhtar Abbas | 1 | 0h | 100%
FROP Final (sw21.21.145.02) | Eliseo Flores | 1 | 0h | 100%
FROP Final (sw21.21.145.02) | Leonardo Iratagotia | 1 | 0h | 100%
FROP Final (sw21.21.145.02) | Marco Sosa | 1 | 0h | 100%
FROP Final (sw21.21.145.02) | Mauro Lopez | 1 | 0h | 100%
FROP Final (sw21.21.145.02) | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145.02 cadence start | Akhtar Abbas | 1 | 0h | 100%
sw21.21.145.02 cadence start | Eliseo Flores | 1 | 0h | 100%
sw21.21.145.02 cadence start | Leonardo Iratagotia | 1 | 0h | 100%
sw21.21.145.02 cadence start | Marco Sosa | 1 | 0h | 100%
sw21.21.145.02 cadence start | Mauro Lopez | 1 | 0h | 100%
sw21.21.145.02 cadence start | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145.02 cadence start | Prabhu Kumar | 1 | 0h | 100%
Release Kick Off meeting (sw21.21.145.02) | Eliseo Flores | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Leonardo Iratagotia | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Marco Sosa | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Mauro Lopez | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Oscar Espinosa | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Prabhu Kumar | 0 | 8h | 100%
Release Kick Off meeting (sw21.21.145.02) | Azad Mohammed | 0 | 8h | 100%
SRS Minor baseline (sw21.21.145.03) | Mauro Lopez | 0 | 24h | 100%
Redmine Analysis phase 1 (sw21.21.145.03) | Mauro Lopez | 1 | 24h | 100%
SAD Minor baseline (sw21.21.145.03) | Mauro Lopez | 0 | 24h | 100%
Redmine Analysis phase 1 (sw21.21.145.03) | Mauro Lopez | 1 | 24h | 100%
Redmine Analysis phase 1 (sw21.21.145.03) | Leonardo Iratagotia | 1 | 24h | 100%
Power Sequence Measurements (redmines: 6742, 6547) (sw21.21.145.02) | Navin Singh | 0 | 24h | 100%
Waveform Measurements | Navin Singh | 0 | 8h | 100%
Architecture Design minor baseline (sw21.21.145.02) | Eliseo Flores | 1 | 64h | 100%
Layer Design minor baseline (sw21.21.145.02) | Eliseo Flores | 1 | 64h | 100%
Unit Design minor baseline (sw21.21.145.02) | Eliseo Flores | 1 | 64h | 100%
Redmine Software Implementation (sw21.21.145.02) | Eliseo Flores | 1 | 24h | 100%
Test Case minor baseline (sw21.21.145.02) | Oscar Espinosa | 1 | 80h | 100%
Test Case minor baseline (sw21.21.145.02) | Victor Samson | 1 | 72h | 100%
Test Case minor baseline (sw21.21.145.02) | Kalpana Dakshnamoorthy | 1 | 72h | 100%
FROP tentative (sw21.21.145.03) | Akhtar Abbas | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Eliseo Flores | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Leonardo Iratagotia | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Marco Sosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Mauro Lopez | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Oscar Espinosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Prabhu Kumar | 1 | 0h | 100%
RC2 App exchange (sw21.21.145.02) (HMI Only) | GMTCI | 1 | 152h | 100%
SRS Major baseline (sw21.21.145.04) | Mauro Lopez | 0 | 80h | 100%
EQA Workproduct Audit SRS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.03) | Mauro Lopez | 1 | 40h | 100%
SAD Major baseline (sw21.21.145.04) | Mauro Lopez | 0 | 80h | 100%
EQA Workproduct Audit SAD (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.03) | Mauro Lopez | 1 | 40h | 100%
Software Functional Specs Minor baseline (sw21.21.145.04) | Leonardo Iratagotia | 0 | 80h | 100%
Redmine Analysis Complete (sw21.21.145.03) | Leonardo Iratagotia | 1 | 40h | 100%
RC-1 Bootloader release to GMTCI (sw21.21.145.03) | Eliseo Flores | 0 | 0h | 100%
Architecture Design Major basline (sw21.21.145.02) | Eliseo Flores | 1 | 40h | 100%
Layer Design Major baseline (sw21.21.145.02) | Eliseo Flores | 1 | 40h | 100%
Unit Design Major baseline (sw21.21.145.02) | Eliseo Flores | 1 | 40h | 100%
EQA Workproduct Audit SW AD (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW DD (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Software Implementation (acc. To FROP)(sw21.21.145.02) | Eliseo Flores | 1 | 16h | 100%
Sanity Check (sw21.21.145.02) | Leonardo Iratagotia | 0.5 | 4h | 100%
Full Integration Testing(sw21.21.145.02) | Eliseo Flores | 1 | 16h | 100%
Software Integration Test Spec Major baseline(sw21.21.145.02) | Eliseo Flores | 1 | 16h | 100%
Internal SW release (sw21.21.145.02) | Eliseo Flores | 1 | 0h | 100%
Test Case Major baseline (sw21.21.145.02) | Oscar Espinosa | 1 | 16h | 100%
Test Case Major baseline (sw21.21.145.02) | Nikhil Gupta | 1 | 16h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.03) | Oscar Espinosa | 1 | 8h | 100%
Test Case Major baseline (sw21.21.145.02) | Victor Samson | 1 | 32h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.03) | Victor Samson | 1 | 80h | 100%
Test Case Major baseline (sw21.21.145.02) | Kalpana Dakshnamoorthy | 1 | 32h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.145.02) | Prabhu Kumar | 1 | 0h | 100%
Redmine Estimation (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 80h | 100%
CG4422 updated to GM (sw21.21.145.02) | Marco Sosa | 0 | 24h | 100%
FROP tentative (sw21.21.145.03) | Akhtar Abbas | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Eliseo Flores | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Leonardo Iratagotia | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Marco Sosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Mauro Lopez | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Oscar Espinosa | 1 | 0h | 100%
FROP tentative (sw21.21.145.03) | Prabhu Kumar | 1 | 0h | 100%
Create Production Study CALS (sw21.21.145.02) | Dennis Shinkonis | 1 | 4h | 100%
Software Functional Specs Major baseline (sw21.21.145.04) | Leonardo Iratagotia | 0 | 40h | 100%
EQA Workproduct Audit SWFS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.145.02) | Oscar Espinosa | 1 | 0h | 100%
SWE6 Verification Testing (sw21.21.145.02) | Oscar Espinosa | 1 | 16h | 100%
SWE6 Verification Test Report (sw21.21.145.02) | Oscar Espinosa | 1 | 0h | 100%
SWE6 Verification Test Report (sw21.21.145.02) | Jon Donegan | 1 | 0h | 100%
SWE6 Verification Test Report (sw21.21.145.02) | Nikhil Gupta | 1 | 0h | 100%
CG4879 Test Execution (sw21.21.145.02) | Oscar Espinosa | 0 | 24h | 100%
Redmine Estimation from FROP tentative (sw21.21.145.03) | Eliseo Flores | 0 | 80h | 100%
Test Execution (sw21.21.145.02) | Victor Samson | 1 | 16h | 100%
SYS Integration Test Report (sw21.21.145.02) | Victor Samson | 1 | 0h | 100%
Report review and approval (sw21.21.145.02) | Mauro Lopez | 1 | 0h | 100%
Report review and approval (sw21.21.145.02) | Gary Kempen | 1 | 0h | 100%
Test Execution (sw21.21.145.02) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
SYS Qualification Test Report (sw21.21.145.02) | Kalpana Dakshnamoorthy | 1 | 0h | 100%
Report review and approval (sw21.21.145.02) | Mauro Lopez | 1 | 0h | 100%
Report review and approval (sw21.21.145.02) | Gary Kempen | 1 | 0h | 100%
CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.02) | Eshwaran (HCL) | 0.10000000000000001 | 96h | 100%
CG3689 - Ethernet AVB Device Test (sw21.21.145.02) | Eshwaran (HCL) | 1 | 32h | 100%
CG3687 - Bootloader Flash Programming (sw21.21.145.02) | Eshwaran (HCL) | 0 | 60h | 100%
CG3926 - Arf Diff (sw21.21.145.02) | Naveen Gujjari | 1 | 24h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.02) | Eshwaran (HCL) | 0 | 40h | 100%
TCP Client (sw21.21.145.02) | John McShane | 0 | 120h | 100%
TCP Server (sw21.21.145.02) | John McShane | 0 | 120h | 100%
IPv4 (sw21.21.145.02) | John McShane | 0 | 120h | 100%
Software Release notes (sw21.21.145.02) | Eliseo Flores | 1 | 16h | 100%
Software Release notes (sw21.21.145.02) | Azad Mohammed | 1 | 16h | 100%
Software Release Assessment (sw21.21.145.02) | Akhtar Abbas | 1 | 0h | 100%
Share software packag (SW release) to GM (sw21.21.145.02) | Akhtar Abbas | 1 | 0h | 100%
CG2496 Test Report (sw21.21.145.02) | Pradeep Kumar | 0 | 80h | 100%
Unit Test report (sw21.21.145.02) | Neelima Gudem | 1 | 32h | 100%
SAA update (sw21.21.145.02) | Eliseo Flores | 1 | 32h | 100%
Integratoin Test report (sw21.21.145.02) | Neelima Gudem | 1 | 32h | 100%
Performance Paramters report (sw21.21.145.02) | Sachin Karkera | 1 | 32h | 100%
Stress Test Results (sw21.21.145.02) | Marco Sosa | 1 | 24h | 100%
Black box test results (sw21.21.145.02) | Marco Sosa | 1 | 24h | 100%
Black box test results (sw21.21.145.02) | Oscar Espinosa | 1 | 24h | 100%
FROP Final (sw21.21.145.03) | Akhtar Abbas | 1 | 0h | 100%
FROP Final (sw21.21.145.03) | Eliseo Flores | 1 | 0h | 100%
FROP Final (sw21.21.145.03) | Leonardo Iratagotia | 1 | 0h | 100%
FROP Final (sw21.21.145.03) | Marco Sosa | 1 | 0h | 100%
FROP Final (sw21.21.145.03) | Mauro Lopez | 1 | 0h | 100%
FROP Final (sw21.21.145.03) | Oscar Espinosa | 1 | 0h | 100%
Redmine 14914 root cause and implementation (sw21.21.145.03) | Grant Thomas | 1 | 80h | 100%
Redmine 15251 root cause and implementation (sw21.21.145.03) | Grant Thomas | 1 | 80h | 100%
Redmine 7942 root cause and implementation (sw21.21.145.03) | Hemangi Nehete | 1 | 80h | 100%
Architecture Design Major basline (sw21.21.145.03) | Sachin Karkera | 0 | 4h | 100%
Layer Design Major baseline (sw21.21.145.03) | Sachin Karkera | 0 | 4h | 100%
Unit Design Major baseline (sw21.21.145.03) | Sachin Karkera | 0 | 4h | 100%
EQA Workproduct Audit SW AD (sw21.21.145.03) | Prabhu Kumar | 0 | 4h | 100%
EQA Workproduct Audit SW DD (sw21.21.145.03) | Prabhu Kumar | 0 | 4h | 100%
EQA Workproduct Audit SW UD (sw21.21.145.03) | Prabhu Kumar | 0 | 4h | 100%
Integration Testing (sw21.21.145.03) | Grant Thomas | 0.69999999999999996 | 8h | 100%
Software Integration Test Spec Major baseline(sw21.21.145.03) | Sachin Karkera | 0 | 4h | 100%
Internal SW release (sw21.21.145.03) | Sachin Karkera | 1 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.145.03) | Prabhu Kumar | 0 | 4h | 100%
CG3923 Arf Diff (sw21.21.145.03) | Naveen Gujjari | 1 | 12h | 100%
Redmine impact analysis (sw21.21.145.03) | Oscar Espinosa | 1 | 16h | 100%
DTC Testing with sw21.21.145.01 | Oscar Espinosa | 0 | 24h | 100%
Test Case Major baseline (sw21.21.145.03) | Oscar Espinosa | 1 | 0h | 100%
Redmine testing (sw21.21.145.03) | Oscar Espinosa | 0.69999999999999996 | 8h | 100%
Test Summary Report (sw21.21.145.03) | Oscar Espinosa | 0.5 | 4h | 100%
CG4879 - partial testing (sw21.21.145.03) | Oscar Espinosa | 0 | 24h | 100%
Redmine impact analysis (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Test Case Major baseline (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 0h | 100%
Flashing Stress (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
FUSA testing (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Test Summary Report (sw21.21.145.03) | Kalpana Dakshnamoorthy | 0 | 4h | 100%
Test Summary Report (sw21.21.145.03) | Mauro Lopez | 0 | 4h | 100%
Redmine impact analysis (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
DTC Testing with sw21.21.145.01 | Kalpana Dakshnamoorthy | 0 | 24h | 100%
Test Case Major baseline (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 0h | 100%
Test Execution (sw21.21.145.03) | Kalpana Dakshnamoorthy | 1 | 16h | 100%
Test Summary Report (sw21.21.145.03) | Kalpana Dakshnamoorthy | 0 | 4h | 100%
Test Summary Report (sw21.21.145.03) | Mauro Lopez | 0 | 4h | 100%
Software Release notes (sw21.21.145.03) | Sachin Karkera | 1 | 16h | 100%
Software Release Assessment (sw21.21.145.03) | Azad Mohammed | 0 | 4h | 100%
Share software packag (SW release) to GM (sw21.21.145.03) | Azad Mohammed | 0 | 0h | 100%
Unit Test report (sw21.21.145.03) | Neelima Gudem | 0 | 24h | 100%
SAA update (sw21.21.145.03) | Neelima Gudem | 0 | 24h | 100%
Integratoin Test report (sw21.21.145.03) | Neelima Gudem | 0 | 24h | 100%
Performance Paramters report (sw21.21.145.03) | Sachin Karkera | 0 | 32h | 100%
Black box test results (sw21.21.145.03) | Oscar Espinosa | 0 | 24h | 100%
Black box test results (sw21.21.145.03) | Mauro Lopez | 0 | 24h | 100%
FROP Final (sw21.21.145.04) | Azad Mohammed | 0 | 40h | 100%
FROP Final (sw21.21.145.04) | Eliseo Flores | 0 | 40h | 100%
FROP Final (sw21.21.145.04) | Leonardo Iratagotia | 0 | 40h | 100%
FROP Final (sw21.21.145.04) | Marco Sosa | 0 | 40h | 100%
FROP Final (sw21.21.145.04) | Mauro Lopez | 0 | 40h | 100%
FROP Final (sw21.21.145.04) | Oscar Espinosa | 0 | 40h | 100%
sw21.21.145.04 cadence start | Eliseo Flores | 1 | 0h | 100%
sw21.21.145.04 cadence start | Leonardo Iratagotia | 1 | 0h | 100%
sw21.21.145.04 cadence start | Marco Sosa | 1 | 0h | 100%
sw21.21.145.04 cadence start | Mauro Lopez | 1 | 0h | 100%
sw21.21.145.04 cadence start | Oscar Espinosa | 1 | 0h | 100%
sw21.21.145.04 cadence start | Prabhu Kumar | 1 | 0h | 100%
sw21.21.145.04 cadence start | Azad Mohammed | 1 | 0h | 100%
Release Kick Off meeting (sw21.21.145.04) | Azad Mohammed | 0 | 8h | 100%
SRS Minor baseline (sw21.21.145.05) | Mauro Lopez | 0 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.05) | Mauro Lopez | 0 | 40h | 100%
SAD Minor baseline (sw21.21.145.05) | Mauro Lopez | 0 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.05) | Mauro Lopez | 0 | 40h | 100%
Redmine Analysis phase 1 (sw21.21.145.05) | Leonardo Iratagotia | 0 | 40h | 100%
A2L from GMTCI and Release Notes | Azad Mohammed | 0 | 80h | 100%
Architecture Design minor baselines / updates (sw21.21.145.04) | Eliseo Flores | 0 | 80h | 100%
Layer Design minor baseline / updates (sw21.21.145.04) | Eliseo Flores | 0 | 80h | 100%
Unit Design minor baseline / updates (sw21.21.145.04) | Eliseo Flores | 0 | 80h | 100%
Redmine Software Implementation (sw21.21.145.04) | Eliseo Flores | 0 | 80h | 100%
Test Case minor baseline / updates (sw21.21.145.04) | Oscar Espinosa | 0 | 0h | 100%
Test Case minor baseline /updates (sw21.21.145.04) | Victor Samson | 0 | 40h | 100%
Test Case minor baseline / updates (sw21.21.145.04) | Kalpana Dakshnamoorthy | 0 | 40h | 100%
FROP tentative (sw21.21.145.05) | Akhtar Abbas | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Eliseo Flores | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Leonardo Iratagotia | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Marco Sosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Mauro Lopez | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Oscar Espinosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Prabhu Kumar | 0 | 0h | 100%
RC2 App exchange (sw21.21.145.04) | GMTCI | 0 | 0h | 100%
SRS Major baseline (sw21.21.145.05) | Mauro Lopez | 0 | 80h | 100%
EQA Workproduct Audit SRS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.05) | Mauro Lopez | 0 | 80h | 100%
SAD Major baseline (sw21.21.145.04) | Mauro Lopez | 0 | 80h | 100%
EQA Workproduct Audit SAD (sw21.21.145.05) | Prabhu Kumar | 0 | 0h | 100%
Redmine Analysis phase 2 (sw21.21.145.05) | Mauro Lopez | 0 | 80h | 100%
Software Functional Specs Minor baseline (sw21.21.145.05) | Leonardo Iratagotia | 0 | 80h | 100%
Redmine Analysis Complete (sw21.21.145.05) | Leonardo Iratagotia | 0 | 80h | 100%
Architecture Design Major basline (sw21.21.145.04) | Eliseo Flores | 0 | 56h | 100%
Layer Design Major baseline (sw21.21.145.04) | Eliseo Flores | 0 | 56h | 100%
Unit Design Major baseline (sw21.21.145.04) | Eliseo Flores | 0 | 56h | 100%
EQA Workproduct Audit SW AD (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
EQA Workproduct Audit SW DD (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
EQA Workproduct Audit SW UD (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
EQA Workproduct Audit SW INT TS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Software Implementation (acc. To FROP)(sw21.21.145.04) | Eliseo Flores | 0 | 56h | 100%
Sanity Check (sw21.21.145.04) | Leonardo Iratagotia | 0 | 4h | 100%
Full Integration Testing(sw21.21.145.04) | Eliseo Flores | 0 | 16h | 100%
Software Integration Test Spec Major baseline(sw21.21.145.04) | Eliseo Flores | 0 | 8h | 100%
Internal SW release (sw21.21.145.04) | Eliseo Flores | 0 | 8h | 100%
RC-1 Bootloader release to GMTCI (sw21.21.145.05) | Eliseo Flores | 0 | 0h | 100%
Test Case Major baseline (sw21.21.145.04) | Oscar Espinosa | 0 | 80h | 100%
Test Case Major baseline (sw21.21.145.04) | Nikhil Gupta | 0 | 80h | 100%
EQA Workproduct Audit SW VAL TS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Estimation (sw21.21.145.05) | Oscar Espinosa | 0 | 80h | 100%
Test Case Major baseline (sw21.21.145.04) | Victor Samson | 0 | 80h | 100%
EQA Workproduct Audit SYS INT TS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Estimation (sw21.21.145.05) | Victor Samson | 0 | 80h | 100%
Test Case Major baseline (sw21.21.145.04) | Kalpana Dakshnamoorthy | 0 | 80h | 100%
EQA Workproduct Audit SYS QUAL TS (sw21.21.145.04) | Prabhu Kumar | 0 | 0h | 100%
Redmine Estimation (sw21.21.145.05) | Kalpana Dakshnamoorthy | 0 | 80h | 100%
CG4422 updated to GM (sw21.21.145.04) | Marco Sosa | 0 | 24h | 100%
FROP tentative (sw21.21.145.05) | Akhtar Abbas | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Eliseo Flores | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Leonardo Iratagotia | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Marco Sosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Mauro Lopez | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Oscar Espinosa | 0 | 0h | 100%
FROP tentative (sw21.21.145.05) | Prabhu Kumar | 0 | 0h | 100%
Create Production Study CALS (sw21.21.145.04) | Dennis Shinkonis | 0 | 24h | 100%
Software Functional Specs Major baseline (sw21.21.145.05) | Leonardo Iratagotia | 0 | 40h | 100%
EQA Workproduct Audit SWFS (sw21.21.145.05) | Prabhu Kumar | 0 | 0h | 100%
SW Validation Test Plan and Readiness Review (sw21.21.145.04) | Oscar Espinosa | 0 | 0h | 100%
SWE6 Verification Testing (sw21.21.145.04) | Oscar Espinosa | 0 | 36h | 100%
SWE6 Verification Test Report (sw21.21.145.04) | Oscar Espinosa | 0 | 4h | 100%
SWE6 Verification Test Report (sw21.21.145.04) | Jon Donegan | 0 | 4h | 100%
SWE6 Verification Test Report (sw21.21.145.04) | Nikhil Gupta | 0 | 4h | 100%
CG4879 Test Execution (sw21.21.145.04) | Oscar Espinosa | 0 | 24h | 100%
CG3926 - Arf Diff (sw21.21.145.04) | Naveen Gujjari | 0 | 24h | 100%
Redmine Estimation from FROP tentative (sw21.21.145.05) | Eliseo Flores | 0 | 80h | 100%
Test Execution (sw21.21.145.04) | Victor Samson | 0 | 36h | 100%
SYS Integration Test Report (sw21.21.145.04) | Victor Samson | 0 | 0h | 100%
Report review and approval (sw21.21.145.04) | Mauro Lopez | 0 | 4h | 100%
Report review and approval (sw21.21.145.04) | Gary Kempen | 0 | 4h | 100%
Test Execution (sw21.21.145.04) | Kalpana Dakshnamoorthy | 0 | 36h | 100%
SYS Qualification Test Report (sw21.21.145.04) | Kalpana Dakshnamoorthy | 0 | 0h | 100%
Report review and approval (sw21.21.145.04) | Mauro Lopez | 0 | 0.4h | 100%
Report review and approval (sw21.21.145.04) | Gary Kempen | 0 | 0.4h | 100%
CG3877 - CAN Physical and Protocol Layer Test (sw21.21.145.04) | Eshwaran (HCL) | 0 | 96h | 100%
CG3689 - Ethernet AVB Device Test (sw21.21.145.04) | Eshwaran (HCL) | 0 | 32h | 100%
CG3687 - Bootloader Flash Programming (sw21.21.145.04) | Eshwaran (HCL) | 0 | 60h | 100%
SAE J2602-2 - LIN Network for Vehicle Applications Conformance (sw21.21.145.04) | Eshwaran (HCL) | 0 | 40h | 100%
TCP Client (sw21.21.145.04) | John McShane | 0 | 120h | 100%
TCP Server (sw21.21.145.04) | John McShane | 0 | 120h | 100%
IPv4 (sw21.21.145.04) | John McShane | 0 | 120h | 100%
Software Release notes (sw21.21.145.04) | Eliseo Flores | 0 | 16h | 100%
Software Release notes (sw21.21.145.04) | Azad Mohammed | 0 | 16h | 100%
Software Release notes (sw21.21.145.04) | Akhtar Abbas | 0 | 16h | 100%
Software Release Assessment (sw21.21.145.04) | Azad Mohammed | 0 | 4h | 100%
Share software packag (SW release) to GM (sw21.21.145.04) | Azad Mohammed | 0 | 0h | 100%
CG2496 Test Report (sw21.21.145.04) | Pradeep Kumar | 0 | 80h | 100%
Unit Test report (sw21.21.145.04) | Neelima Gudem | 0 | 32h | 100%
SAA update (sw21.21.145.04) | Eliseo Flores | 0 | 32h | 100%
Integratoin Test report (sw21.21.145.04) | Neelima Gudem | 0 | 32h | 100%
Performance Paramters report (sw21.21.145.04) | Sachin Karkera | 0 | 32h | 100%
Stress Test Results (sw21.21.145.04) | Marco Sosa | 0 | 24h | 100%
Black box test results (sw21.21.145.04) | Marco Sosa | 0 | 24h | 100%
Black box test results (sw21.21.145.04) | Oscar Espinosa | 0 | 24h | 100%
FROP Final (sw21.21.145.03) | Akhtar Abbas | 0 | 0h | 100%
FROP Final (sw21.21.145.03) | Eliseo Flores | 0 | 0h | 100%
FROP Final (sw21.21.145.03) | Leonardo Iratagotia | 0 | 0h | 100%
FROP Final (sw21.21.145.03) | Marco Sosa | 0 | 0h | 100%
FROP Final (sw21.21.145.03) | Mauro Lopez | 0 | 0h | 100%
FROP Final (sw21.21.145.03) | Oscar Espinosa | 0 | 0h | 100%
IMDS | Marco Sosa | 0 | 80h | 100%
Create PFMEA | Kristine Hiott | 1 | 24h | 100%
PFMEA Review | Marco Sosa | 0 | 80h | 100%
PFMEA Review | Anshuman Mittal | 0 | 80h | 100%
PFMEA Review | Azad Mohammed | 0 | 80h | 100%
PFMEA Review | Mauro Lopez | 0 | 80h | 100%
PFMEA Review | Kristine Hiott | 0 | 80h | 100%
Share review with SHNS | Kristine Hiott | 0 | 8h | 100%
Update PFMEA | Kristine Hiott | 0 | 80h | 100%
PFMEA Review | Marco Sosa | 0 | 80h | 100%
PFMEA Review | Anshuman Mittal | 0 | 80h | 100%
PFMEA Review | Azad Mohammed | 0 | 80h | 100%
PFMEA Review | Mauro Lopez | 0 | 80h | 100%
PFMEA Review | Kristine Hiott | 0 | 80h | 100%
Create Control Plan | Kristine Hiott | 1 | 24h | 100%
Control Plan Review | Marco Sosa | 0 | 80h | 100%
Control Plan Review | Anshuman Mittal | 0 | 80h | 100%
Control Plan Review | Azad Mohammed | 0 | 80h | 100%
Control Plan Review | Mauro Lopez | 0 | 80h | 100%
Control Plan Review | Kristine Hiott | 0 | 80h | 100%
Share review with SHNS | Kristine Hiott | 0 | 8h | 100%
Update Control Plan | Kristine Hiott | 0 | 80h | 100%
Control Plan Review | Marco Sosa | 0 | 80h | 100%
Control Plan Review | Anshuman Mittal | 0 | 80h | 100%
Control Plan Review | Azad Mohammed | 0 | 80h | 100%
Control Plan Review | Mauro Lopez | 0 | 80h | 100%
Control Plan Review | Kristine Hiott | 0 | 80h | 100%
Create Process Flow | Kristine Hiott | 1 | 24h | 100%
Process Flow Review | Marco Sosa | 0 | 80h | 100%
Process Flow Review | Anshuman Mittal | 0 | 80h | 100%
Process Flow Review | Azad Mohammed | 0 | 80h | 100%
Process Flow Review | Mauro Lopez | 0 | 80h | 100%
Process Flow Review | Kristine Hiott | 0 | 80h | 100%
Share review with SHNS | Kristine Hiott | 0 | 8h | 100%
Update Process Flow | Kristine Hiott | 0 | 80h | 100%
Process Flow Review | Marco Sosa | 0 | 80h | 100%
Process Flow Review | Anshuman Mittal | 0 | 80h | 100%
Process Flow Review | Azad Mohammed | 0 | 80h | 100%
Process Flow Review | Mauro Lopez | 0 | 80h | 100%
Process Flow Review | Kristine Hiott | 0 | 80h | 100%
Tooling | Tooling Supplier | 1 | 464h | 100%
Tunning | Tooling Supplier | 0 | 144h | 100%
Graining | Tooling Supplier | 0 | 160h | 100%
Tooling | Tooling Supplier | 1 | 296h | 100%
Tunning | Tooling Supplier | 0 | 168h | 100%
Tooling | Tooling Supplier | 1 | 328h | 100%
Tunning | Tooling Supplier | 0 | 184h | 100%
Tooling | Tooling Supplier | 1 | 296h | 100%
Tunning | Tooling Supplier | 0 | 168h | 100%
Tooling | Tooling Supplier | 1 | 320h | 100%
Tunning | Tooling Supplier | 0 | 8h | 100%
Tooling | Tooling Supplier | 1 | 432h | 100%
Modifcation as per supplier request | Anshuman Mittal | 1 | 8h | 100%
Drawing / 3D release | Anshuman Mittal | 0 | 40h | 100%
Tunning | Tooling Supplier | 0.5 | 120h | 100%
Trial with modified tooling | Tooling Supplier | 0 | 40h | 100%
Deliver to SHNS | Tooling Supplier | 1 | 232h | 100%
Deliver to SHNS | Tooling Supplier | 0.5 | 832h | 100%
Shipping components | Huaping Ni | 0 | 40h | 100%
PV Parts Build | K.Umezawa | 0 | 40h | 100%
PV Parts Shipping | K.Umezawa | 0 | 40h | 100%
PV Testing | Sabina lab | 0 | 720h | 100%
Production 1 Meeting | Antonio Jimenez | 0 | 8h | 100%
Production 2 Meeting | Antonio Jimenez | 0 | 8h | 100%
Receive M1 PO from customer | Kristine Hiott | 0 | 0h | 100%
Sales issues PO to SHNS | Kristine Hiott | 0 | 56h | 100%
SHNS Deliver M1 parts to Customer | Kristine Hiott | 0 | 480h | 100%
SHNS provides measurement data per matching 1 requirements | Kristine Hiott | 0 | 480h | 100%
Matching 1 MRD | GM | 0 | 0h | 100%
Receive M2 PO from customer | Kristine Hiott | 0 | 8h | 100%
Sales issues PO to SHNS | Kristine Hiott | 0 | 8h | 100%
SHNS Deliver M2 parts to Customer | Kristine Hiott | 0 | 480h | 100%
SHNS provides measurement data per matching 2 requirements | Kristine Hiott | 0 | 480h | 100%
Matching 2 MRD | GM | 0 | 0h | 100%
Archival/Retention Request to NSI IT Team for E3 Project | Lawrence Buie | 0 | 0h | 100%
PPAP 1411 sub | Kristine Hiott | 0 | 0h | 100%
PPV - TWN Release for SW to plant | Marco Sosa | 0 | 0h | 100%
Obtain Customer Acceptance Note | Marco Sosa | 0 | 8h | 100%
Summarize Project Results and Lessons Learned | Marco Sosa | 0 | 8h | 100%
Review and Recognize Team Performance | Marco Sosa | 0 | 8h | 100%
Project Work Products move to Project Learning Database | Marco Sosa | 0 | 8h | 100%
Update the RAID Log and disposition any open items and Move it to Risk Database | Marco Sosa | 0 | 8h | 100%
Review and Reconcile Financial Performance | Marco Sosa | 0 | 8h | 100%
Update the PCE and disposition the unresolved changes | Marco Sosa | 0 | 8h | 100%
Close all the Action items raised in the Project | Marco Sosa | 0 | 8h | 100%
Close the Audit NCs and Observation | Marco Sosa | 0 | 8h | 100%
Archive all the Project Records (EQA Audit Reports, Review Reports , Test Reports, Analysis Reports, Work Product Audit Reports, Status Reports, Sub Contractor Status Report) | Marco Sosa | 0 | 8h | 100%
Renew / Close the Supplier contracts | Marco Sosa | 0 | 8h | 100%
Provide Subcontractor performance feedback | Marco Sosa | 0 | 8h | 100%
Close the Project Budget | Marco Sosa | 0 | 8h | 100%
Release the Resources for other project / activities | Marco Sosa | 0 | 8h | 100%
Conduct Closure Audit and ensure the audit issues are closed | Marco Sosa | 0 | 8h | 100%
Conduct the Project Closure Meeting | Marco Sosa | 0 | 8h | 100%
Styling Freeze (SF) | GM | 1 | 0h | 100%
IDR (Initial Data Release) | GM | 1 | 0h | 100%
Integration Bench MRD/P-Release | GM | 1 | 0h | 100%
Verified Data Release (VDR) | GM | 1 | 0h | 100%
Electrical A-Frame MRD | GM | 1 | 0h | 100%
IVER MRD | GM | 0 | 0h | 100%
65% Buyoff Ride | GM | 0 | 0h | 100%
80% Buyoff Ride | GM | 0 | 0h | 100%
100% Buyoff Ride | GM | 0 | 0h | 100%
Matching 1 MRD | GM | 0 | 0h | 100%
NCT / OTS GM MRD | GM | 0 | 0h | 100%
PPV MRD | GM | 0 | 0h | 100%
Matching 2 MRD | GM | 0 | 0h | 100%
PPAP NS | GM | 0 | 0h | 100%
MVB-NS MRD | GM | 0 | 0h | 100%
Validation Testing Complete (VTC MRD) | GM | 0 | 0h | 100%
PPAP Gate Final | GM | 0 | 0h | 100%
Validation Documentation Complete (VDC) | GM | 0 | 0h | 100%
MVB-S (ManVal Saleable) MRD | GM | 0 | 0h | 100%
SORP | GM | 0 | 0h | 100%
QG1 & QG2 - Concept Design Review | Akhtar Abbas | 1 | 8h | 100%
QG1 & QG2 - Concept Design Review | Anshuman Mittal | 1 | 8h | 100%
QG1 & QG2 - Concept Design Review | Antonio Jimenez | 1 | 8h | 100%
QG1 & QG2 - Concept Design Review | Mauro Lopez | 1 | 8h | 100%
QG1 & QG2 - Concept Design Review | Prabhu Kumar | 1 | 0h | 100%
QG3 - Prototype Design Review | Akhtar Abbas | 0 | 8h | 100%
QG3 - Prototype Design Review | Anshuman Mittal | 0 | 8h | 100%
QG3 - Prototype Design Review | Antonio Jimenez | 0 | 8h | 100%
QG3 - Prototype Design Review | Mauro Lopez | 0 | 8h | 100%
QG3 - Prototype Design Review | Prabhu Kumar | 0 | 0h | 100%
QG4 - DV Test Readiness Review | Akhtar Abbas | 0 | 8h | 100%
QG4 - DV Test Readiness Review | Anshuman Mittal | 0 | 8h | 100%
QG4 - DV Test Readiness Review | Antonio Jimenez | 0 | 8h | 100%
QG4 - DV Test Readiness Review | Mauro Lopez | 0 | 8h | 100%
QG4 - DV Test Readiness Review | Prabhu Kumar | 0 | 0h | 100%
QG5 - Production Design Review | Akhtar Abbas | 0 | 8h | 100%
QG5 - Production Design Review | Anshuman Mittal | 0 | 8h | 100%
QG5 - Production Design Review | Antonio Jimenez | 0 | 8h | 100%
QG5 - Production Design Review | Mauro Lopez | 0 | 8h | 100%
QG5 - Production Design Review | Prabhu Kumar | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Akhtar Abbas | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Anshuman Mittal | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Antonio Jimenez | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Mauro Lopez | 0 | 8h | 100%
QG6 - PV Test Readiness Review | Prabhu Kumar | 0 | 8h | 100%
QG7 - Production Launch Review | Akhtar Abbas | 0 | 8h | 100%
QG7 - Production Launch Review | Anshuman Mittal | 0 | 8h | 100%
QG7 - Production Launch Review | Antonio Jimenez | 0 | 8h | 100%
QG7 - Production Launch Review | Mauro Lopez | 0 | 8h | 100%
QG7 - Production Launch Review | Prabhu Kumar | 0 | 8h | 100%
Kick Off meeting | Marco Sosa | 1 | 0h | 100%
CG4090 - HSCAN Questionnaire | Marco Sosa | 0 | 80h | 100%
CG4090 - HSCAN Questionnaire | Akhtar Abbas | 0 | 80h | 100%
CG4090 - HSCAN Questionnaire | Eliseo Flores | 0 | 80h | 100%
CG4090 - HSCAN Questionnaire - GM Approval | GM | 0 | 160h | 100%
CG4080 - LIN Questionnaire | Marco Sosa | 0 | 80h | 100%
CG4080 - LIN Questionnaire | Akhtar Abbas | 0 | 80h | 100%
CG4080 - LIN Questionnaire | Eliseo Flores | 0 | 80h | 100%
CG4080 - LIN Questionnaire - GM Approval | GM | 0 | 160h | 100%
CG4077 - Ethernet Questionnaire | Marco Sosa | 0 | 80h | 100%
CG4077 - Ethernet Questionnaire | Akhtar Abbas | 0 | 80h | 100%
CG4077 - Ethernet Questionnaire | Eliseo Flores | 0 | 80h | 100%
CG4077 - Ethernet Questionnaire - GM Approval | GM | 0 | 160h | 100%
CG4073 - Global B Diagnostic validation Questionnaire | Marco Sosa | 0 | 80h | 100%
CG4073 - Global B Diagnostic validation Questionnaire | Akhtar Abbas | 0 | 80h | 100%
CG4073 - Global B Diagnostic validation Questionnaire | Eliseo Flores | 0 | 80h | 100%
CG4073 - Global B Diagnostic validation Questionnaire - GM Approval | GM | 0 | 160h | 100%
CG4748 - OTA Test Plan | Marco Sosa | 0 | 80h | 100%
CG4748 - OTA Test Plan | Akhtar Abbas | 0 | 80h | 100%
CG4748 - OTA Test Plan | Eliseo Flores | 0 | 80h | 100%
CG4748 - OTA Test Plan - GM Approval | GM | 0 | 160h | 100%
CG4879 - Test Plan | Marco Sosa | 0 | 80h | 100%
CG4879 - Test Plan | Akhtar Abbas | 0 | 80h | 100%
CG4879 - Test Plan | Eliseo Flores | 0 | 80h | 100%
CG4879 - Test Plan - GM Approval | GM | 0 | 160h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Marco Sosa | 0 | 80h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Akhtar Abbas | 0 | 80h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan | Eliseo Flores | 0 | 80h | 100%
CG4111 - Global B Serial Data and Diagnostics Test Plan - GM Approval | GM | 0 | 160h | 100%
GMW17219 Open Source Document Process (IVER) | Marco Sosa | 0 | 80h | 100%
GMW17219 Open Source Document Process (IVER) | Akhtar Abbas | 0 | 80h | 100%
GMW17219 Open Source Document Process (IVER) | Eliseo Flores | 0 | 80h | 100%
GMW17219 Open Source Document Process (VTC) | Marco Sosa | 0 | 80h | 100%
GMW17219 Open Source Document Process (VTC) | Akhtar Abbas | 0 | 80h | 100%
GMW17219 Open Source Document Process (VTC) | Eliseo Flores | 0 | 80h | 100%
Update SRS | Mauro Lopez | 0 | 80h | 100%
Release SRS | Mauro Lopez | 0 | 0h | 100%
Update SAD | Mauro Lopez | 0 | 80h | 100%
Release SAD | Mauro Lopez | 0 | 0h | 100%
Applique Deisng Freeze | GM | 0 | 0h | 100%
Applique Mechanical Review | Anshuman Mittal | 0 | 80h | 100%
Bench Sample Build | Yoshio Tanaka | 0 | 80h | 100%
Bench Sample Ship to GM | Yoshio Tanaka | 0 | 40h | 100%
Variation List | Anshuman Mittal | 0 | 8h | 100%
BOM | Anshuman Mittal | 0 | 8h | 100%
LED management sheet | Anshuman Mittal | 0 | 8h | 100%
Film& Drawing Preparation | Kristine Hiott | 0 | 80h | 100%
Screen preparation and printing | Krishnakumar Joshi | 0 | 80h | 100%
Forming and applique blank tooling lead time | Yoshio Tanaka | 0 | 200h | 100%
forming and punching | Anshuman Mittal | 0 | 80h | 100%
applique - shipping to OB supplier | Yoshio Tanaka | 0 | 24h | 100%
Applique shipping to NSII for LEG2 and LEG6 - no OB required | Yoshio Tanaka | 0 | 40h | 100%
22.22.xxx software development | Eliseo Flores | 0 | 160h | 100%
Internal Release | Eliseo Flores | 0 | 0h | 100%
Software Validation/Verification | Oscar Espinosa | 0 | 80h | 100%
Software Validation/Verification | Mauro Lopez | 0 | 80h | 100%
Release to GM | Akhtar Abbas | 0 | 0h | 100%
DIT | GM | 0 | 40h | 100%
TWN Request | Marco Sosa | 0 | 8h | 100%
TWN Release | Leonardo Iratagotia | 0 | 80h | 100%
IVER Samples Build | Yoshio Tanaka | 0 | 80h | 100%
IVER Samples Ship | Yoshio Tanaka | 0 | 24h | 100%
Verify VDC | Anshuman Mittal | 0 | 24h | 100%
Spec confirmation report to GM for approval | Anshuman Mittal | 0 | 80h | 100%
Material selection for production | Anshuman Mittal | 0 | 96h | 100%
Update VDC with GM feedback | Anshuman Mittal | 0 | 40h | 100%
Design Freeze | GM | 0 | 0h | 100%
Applique | Anshuman Mittal | 0 | 240h | 100%
Review with suppliers | Anshuman Mittal | 0 | 160h | 100%
OK to Tool Drawing release to GM | Anshuman Mittal | 0 | 40h | 100%
OK to Tool Drawing approval by GM | GM | 0 | 80h | 100%
Release Drawings to NS | Anshuman Mittal | 0 | 8h | 100%